## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 90813316 | 90430344 | 90385737 | 90857493 | 0 | 90669437 | 0.2644% | 100% | -462214 | -0.5111% | -427579 | -0.4708% | 2161 | 618 | 28.6% | 182 | 8.422% | 0 | 0% | 98 | 4.535% | 2259 | 4.535% | 3059 | 3075 | 2275 | 5.275% | 77.78%
| District Let | 30857922 | 30524477 | 31750355 | 31317118 | 0 | 31277126 | 2.466% | 83.33% | 971736 | 3.183% | 892433 | 2.892% | 1885 | 292 | 15.49% | 136 | 7.215% | 0 | 0% | 17 | 0.9019% | 1902 | 0.9019% | 2374 | 2390 | 1962 | 4.085% | 83.33%
| All Contracts | 121671238 | 120954821 | 122136092 | 122174611 | 0 | 121946563 | 0.8199% | 93.33% | 509522 | 0.4212% | 464854 | 0.3821% | 4046 | 910 | 22.49% | 318 | 7.86% | 0 | 0% | 115 | 2.842% | 4161 | 2.842% | 5433 | 5465 | 4237 | 4.721% | 80%
2 | Central Let | 108472548 | 107651602 | 113001931 | 112217364 | 0 | 111866035 | 3.915% | 90% | 4728402 | 4.392% | 4529386 | 4.176% | 3850 | 718 | 18.65% | 427 | 11.09% | 173 | 4.494% | 270 | 7.013% | 4293 | 11.51% | 5481 | 5458 | 4313 | 12.03% | 70%
| District Let | 17185643 | 16846853 | 17320695 | 16938601 | 0 | 16980900 | 0.7957% | 100% | 150963 | 0.8961% | 135052 | 0.7858% | 1732 | 108 | 6.236% | 135 | 7.794% | 14 | 0.8083% | 17 | 0.9815% | 1763 | 1.79% | 2006 | 1869 | 1626 | -6.12% | 100%
| All Contracts | 125658191 | 124498455 | 130322626 | 129155965 | 0 | 128846935 | 3.493% | 93.75% | 4879365 | 3.919% | 4664438 | 3.712% | 5582 | 826 | 14.8% | 562 | 10.07% | 187 | 3.35% | 287 | 5.142% | 6056 | 8.492% | 7487 | 7327 | 5939 | 6.396% | 81.25%
3 | Central Let | 42249404 | 41693216 | 43761780 | 44401210 | 0 | 45269991 | 8.579% | 72.73% | 1556399 | 3.733% | 1338752 | 3.169% | 2249 | 686 | 30.5% | 330 | 14.67% | 25 | 1.112% | 428 | 19.03% | 2702 | 20.14% | 3790 | 3735 | 2719 | 20.9% | 72.73%
| District Let | 50497086 | 49905085 | 57789915 | 59372060 | 235000 | 57139415 | 14.5% | 72.73% | 7358222 | 14.74% | 7292829 | 14.44% | 2594 | 1053 | 40.59% | 434 | 16.73% | 469 | 18.08% | 517 | 19.93% | 3580 | 38.01% | 5076 | 4905 | 3418 | 31.77% | 81.82%
| All Contracts | 92746490 | 91598301 | 101551695 | 103773270 | 235000 | 102409406 | 11.8% | 72.73% | 8914621 | 9.732% | 8631581 | 9.307% | 4843 | 1739 | 35.91% | 764 | 15.78% | 494 | 10.2% | 945 | 19.51% | 6282 | 29.71% | 8866 | 8640 | 6137 | 26.72% | 77.27%
4 | Central Let | 32719588 | 32285580 | 32364304 | 31770957 | 0 | 31998617 | -0.8888% | 83.33% | -142960 | -0.4428% | -355285 | -1.086% | 2175 | 281 | 12.92% | 148 | 6.805% | 0 | 0% | 17 | 0.7816% | 2192 | 0.7816% | 2621 | 2612 | 2183 | 0.3678% | 100%
| District Let | 110017396 | 109700426 | 118360843 | 118035985 | 1500000 | 119125329 | 8.591% | 100% | 8047992 | 7.336% | 8343448 | 7.584% | 2285 | 195 | 8.534% | 156 | 6.827% | 29 | 1.269% | 68 | 2.976% | 2382 | 4.245% | 2733 | 2594 | 2243 | -1.838% | 80%
| All Contracts | 142736984 | 141986006 | 150725147 | 149806942 | 1500000 | 151123946 | 6.436% | 90.91% | 7905032 | 5.567% | 7988163 | 5.596% | 4460 | 476 | 10.67% | 304 | 6.816% | 29 | 0.6502% | 85 | 1.906% | 4574 | 2.556% | 5354 | 5206 | 4426 | -0.7623% | 90.91%
5 | Central Let | 35178289 | 34681711 | 35459500 | 35503308 | 0 | 37419861 | 7.895% | 57.14% | 482744 | 1.392% | 281210 | 0.7994% | 1450 | 388 | 26.76% | 463 | 31.93% | 0 | 0% | 98 | 6.759% | 1548 | 6.759% | 2399 | 2397 | 1546 | 6.621% | 100%
| District Let | 11964270 | 11614646 | 12117678 | 11765801 | 0 | 11777646 | 1.403% | 87.5% | 246132 | 2.119% | 153409 | 1.282% | 1648 | 236 | 14.32% | 334 | 20.27% | 0 | 0% | 186 | 11.29% | 1834 | 11.29% | 2404 | 2312 | 1742 | 5.704% | 87.5%
| All Contracts | 47142559 | 46296357 | 47577178 | 47269109 | 0 | 49197507 | 6.266% | 73.33% | 728876 | 1.574% | 434619 | 0.9219% | 3098 | 624 | 20.14% | 797 | 25.73% | 0 | 0% | 284 | 9.167% | 3382 | 9.167% | 4803 | 4709 | 3288 | 6.133% | 93.33%
6 | Central Let | 68287384 | 68075975 | 73807298 | 74497658 | 4200000 | 74199059 | 8.994% | 100% | 5483510 | 8.055% | 5519914 | 8.083% | 1020 | 350 | 34.31% | 71 | 6.961% | 26 | 2.549% | 132 | 12.94% | 1178 | 15.49% | 1599 | 1464 | 1043 | 2.255% | 100%
| District Let | 58608149 | 58339978 | 64245775 | 64034619 | 0 | 63983179 | 9.673% | 80% | 5514862 | 9.453% | 5637626 | 9.619% | 1630 | 305 | 18.71% | 94 | 5.767% | 40 | 2.454% | 142 | 8.712% | 1812 | 11.17% | 2211 | 2111 | 1712 | 5.031% | 100%
| All Contracts | 126895533 | 126415953 | 138053073 | 138532277 | 4200000 | 138182238 | 9.308% | 87.5% | 10998372 | 8.7% | 11157540 | 8.793% | 2650 | 655 | 24.72% | 165 | 6.226% | 66 | 2.491% | 274 | 10.34% | 2990 | 12.83% | 3810 | 3575 | 2755 | 3.962% | 100%
7 | Central Let | 81661986 | 81050436 | 83276808 | 82776714 | 0 | 82832903 | 2.199% | 100% | 1568718 | 1.935% | 1614822 | 1.977% | 3049 | 344 | 11.28% | 247 | 8.101% | 0 | 0% | 50 | 1.64% | 3099 | 1.64% | 3774 | 3708 | 3117 | 2.23% | 100%
| District Let | 13322487 | 12991487 | 19979155 | 18094281 | 0 | 18133000 | 39.58% | 87.5% | 6657376 | 51.24% | 6656669 | 49.97% | 1884 | 116 | 6.157% | 219 | 11.62% | 78 | 4.14% | 28 | 1.486% | 1990 | 5.626% | 2406 | 2319 | 1984 | 5.308% | 100%
| All Contracts | 94984473 | 94041923 | 103255963 | 100870995 | 0 | 100965903 | 7.363% | 93.75% | 8226094 | 8.747% | 8271491 | 8.708% | 4933 | 460 | 9.325% | 466 | 9.447% | 78 | 1.581% | 78 | 1.581% | 5089 | 3.162% | 6180 | 6027 | 5101 | 3.406% | 100%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 4992370 | 4864209 | 4983506 | 4312252 | 0 | 4312712 | -11.34% | 100% | 5814 | 0.1195% | -8864 | -0.1776% | 463 | 69 | 14.9% | 41 | 8.855% | 7 | 1.512% | 0 | 0% | 470 | 1.512% | 580 | 568 | 458 | -1.08% | 93.75%
| All Contracts | 4992370 | 4864209 | 4983506 | 4312252 | 0 | 4312712 | -11.34% | 100% | 5814 | 0.1195% | -8864 | -0.1776% | 463 | 69 | 14.9% | 41 | 8.855% | 7 | 1.512% | 0 | 0% | 470 | 1.512% | 580 | 568 | 458 | -1.08% | 100%
Totals This Qtr | Central Let | 459382515 | 455868864 | 472057358 | 472024704 | 4200000 | 474255903 | 4.033% | 85.19% | 13214599 | 2.899% | 12501220 | 2.721% | 15954 | 3385 | 21.22% | 1868 | 11.71% | 224 | 1.404% | 1093 | 6.851% | 17271 | 8.255% | 22723 | 22449 | 17196 | 7.785% | 85.19%
| District Let | 297445323 | 294787161 | 326547922 | 323870717 | 1735000 | 322729307 | 9.479% | 86.27% | 28953097 | 9.822% | 29102602 | 9.784% | 14121 | 2374 | 16.81% | 1549 | 10.97% | 637 | 4.511% | 975 | 6.905% | 15733 | 11.42% | 19790 | 19068 | 15145 | 7.252% | 90.2%
| All Contracts | 756827838 | 750656025 | 798605280 | 795895421 | 5935000 | 796985210 | 6.172% | 85.71% | 42167696 | 5.617% | 41603822 | 5.497% | 30075 | 5759 | 19.15% | 3417 | 11.36% | 861 | 2.863% | 2068 | 6.876% | 33004 | 9.739% | 42513 | 41517 | 32341 | 7.534% | 87.62%
Totals Previous Quarter | Central Let | 372717568 | 370293410 | 384491837 | 384561460 | 4400000 | 384947851 | 3.958% | 85.29% | 12085633 | 3.264% | 11600646 | 3.112% | 11347 | 2053 | 18.09% | 1162 | 10.24% | 211 | 1.86% | 545 | 4.803% | 12103 | 6.663% | 15455 | 15293 | 12078 | 6.442% | 88.24%
| District Let | 246453328 | 244872932 | 274481222 | 273280287 | 1650000 | 271372101 | 10.82% | 88.46% | 27787936 | 11.35% | 28027896 | 11.37% | 8984 | 1475 | 16.42% | 966 | 10.75% | 587 | 6.534% | 696 | 7.747% | 10267 | 14.28% | 12717 | 12167 | 9726 | 8.259% | 92.31%
| All Contracts | 619170896 | 615166342 | 658973059 | 657841747 | 6050000 | 656319952 | 6.69% | 86.67% | 39873569 | 6.482% | 39628542 | 6.4% | 20331 | 3528 | 17.35% | 2128 | 10.47% | 798 | 3.925% | 1241 | 6.104% | 22370 | 10.03% | 28172 | 27460 | 21804 | 7.245% | 90%
Totals Fiscal Year 2022/2023 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1709 | 20103225201 | 2018-05-23 | QTR4 | 17/18 | 3 | 27 | 907 | 1313 | 1313 | 100% | 1 | 0 | 0 | 0 | 406 | 0 | 80840173 | 150000 | 80690173 | 80370929 | 81141842 | -44000 | 0 | -44000 | 81097842 | 80911304 | 100.3% | 1 | -90555 | -469244 | 327 | 79 | 0 | 0 | -1709315 | 0 | 0 | 0 | 1772025 | 38602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786283 | 79118 | 0 | 0 | 89346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1447449 | 0 | 0 | 0 | -509110 | 117720 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2022-09-16 | QTR1 | 22/23 |  | 2022-05-19 | QTR4 | 21/22 | 106 | 83257742.89 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 01 | T1745 | 43697915201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 199 | 285 | 281 | 97.99% | 1 | 4 | 0 | 0 | 86 | 0 | 2042506 | 50000 | 1992506 | 2042506 | 1941189 | 0 | 0 | 0 | 1941189 | 1938502 | 97.29% | 1 | -2688 | 0 | 64 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-11-02 | QTR2 | 22/23 |  | 2020-08-04 | QTR1 | 20/21 | 115 | 1951298.09
| 01 | T1763 | 44147515201 | 2019-07-31 | QTR1 | 19/20 | 1 | 0 | 200 | 215 | 183 | 84% | 1 | 32 | 0 | 0 | 15 | 0 | 1200000 | 0 | 1200000 | 1200000 | 1176976 | 0 | 0 | 0 | 1176976 | 1176787 | 98.07% | 1 | -190 | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-10-24 | QTR2 | 22/23 |  | 2020-06-30 | QTR4 | 19/20 | 118 | 950443.89
| 01 | T1771 | 44035615201 | 2021-08-25 | QTR1 | 21/22 | 1 | 2 | 110 | 191 | 191 | 150% | 0 | 0 | 0 | 0 | 26 | 55 | 879962 | 0 | 879962 | 906645 | 906645 | 0 | 0 | 0 | 906645 | 906645 | 103% | 1 | 0 | 26683 | 22 | 4 | 0 | 10 | 5787 | 5787 | 0 | 45 | 20896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 26683 | 5787 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-12 | QTR2 | 22/23 |  | 2022-07-26 | QTR1 | 22/23 | 108 | 847815.4 | B0 | ACC - LUMP SUM
| 01 | T1784 | 44210725201 | 2021-02-17 | QTR3 | 20/21 | 3 | 2 | 180 | 234 | 234 | 115% | 1 | 0 | 0 | 0 | 27 | 27 | 1091540 | 50000 | 1041540 | 1106522 | 1056999 | 0 | 0 | 0 | 1056999 | 1056999 | 101.5% | 1 | 43887 | 14982 | 8 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | -48834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 63816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 14982 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 |  | 2022-03-23 | QTR3 | 21/22 | 108 | 1402962.42
| 01 | T1791 | 44034715201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 80 | 227 | 280 | 166.2% | 0 | -53 | 53 | 0 | 98 | 49 | 610558 | 24380 | 586178 | 610558 | 610907 | -3490 | 0 | -3490 | 607417 | 607417 | 103.6% | 1 | 0 | 0 | 126 | 21 | 0 | 0 | 1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381 | 0 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 |  | 2022-03-07 | QTR3 | 21/22 | 108 | 735869.89 | B0 | ACC - LUMP SUM
| 01 | T1794 | 44477915201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 270 | 353 | 352 | 105.6% | 1 | 1 | 0 | 0 | 67 | 16 | 2947759 | 50000 | 2897759 | 2947759 | 2877401 | 0 | 0 | 0 | 2877401 | 2926249 | 101% | 1 | 48848 | 0 | 47 | 20 | 0 | 14 | 0 | 0 | 0 | 2 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 3850 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2022-05-18 | QTR4 | 21/22 | 108 | 2695046.26
| 01 | T1809 | 44624015201 | 2021-05-26 | QTR4 | 20/21 | 2 | 0 | 130 | 145 | 145 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 569569 | 27338 | 542231 | 569569 | 545539 | 0 | 0 | 0 | 545539 | 545539 | 100.6% | 1 | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 |  | 2022-06-18 | QTR4 | 21/22 | 113 | 560699.14
| 01 | T1823 | 44212415201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 85 | 96 | 96 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 631249 | 31254 | 599995 | 631249 | 599995 | 0 | 0 | 0 | 599995 | 599995 | 100% | 1 | 0 | 0 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-12 | QTR1 | 22/23 |  | 2022-04-12 | QTR4 | 21/22 | 118 | 604209.87 | B0 | ACC - LUMP SUM
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 9 | 14 | 31 | 2161 | 3059 | 3075 | 77.78% | 7 | -16 | 53 | 0 | 751 | 147 | 90813316 | 382972 | 90430344 | 90385737 | 90857493 | -47490 | 0 | -47490 | 90810003 | 90669437 | 100% | 9 | -698 | -427579 | 618 | 182 | 0 | 24 | -1702147 | 5787 | 0 | 47 | 1747937 | 38602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 850099 | 79118 | 0 | 0 | 89346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1447449 | 0 | 0 | 98 | -462214 | 123507
| 01 | E1R65 | 43084915201 | 2019-07-18 | QTR1 | 19/20 | 2 | 4 | 825 | 967 | 964 | 99.64% | 1 | 3 | 0 | 0 | 142 | 0 | 24334683 | 150000 | 24184683 | 24901396 | 24523563 | 0 | 0 | 0 | 24523563 | 24408360 | 100.9% | 1 | -115203 | 566713 | 87 | 55 | 0 | 0 | 220062 | 0 | 0 | 0 | 315298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87683 | 0 | 0 | 0 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627938 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2022-06-24 | QTR4 | 21/22 | 113 | 29026731.23
| 01 | E1T56 | 44022515201 | 2020-09-03 | QTR1 | 20/21 | 1 | 1 | 440 | 621 | 621 | 110% | 1 | 0 | 0 | 0 | 137 | 44 | 2201700 | 50000 | 2151700 | 2363829 | 2312290 | 0 | 0 | 0 | 2312290 | 2312290 | 107.5% | 1 | 27726 | 162129 | 98 | 39 | 0 | 0 | 165590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165590 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-10-12 | QTR2 | 22/23 |  | 2022-08-28 | QTR1 | 22/23 | 118 | 2100535.65 | A3 | ICC - DESIGN/BUILD - MINOR
| 01 | E1T69 | 43485915201 | 2021-02-18 | QTR3 | 20/21 | 1 | 3 | 200 | 291 | 290 | 99.5% | 1 | 1 | 0 | 0 | 91 | 0 | 2190000 | 50000 | 2140000 | 2305157 | 2299703 | 0 | 0 | 0 | 2299703 | 2299703 | 107.5% | 1 | 0 | 115157 | 72 | 19 | 0 | 0 | 115157 | 27632 | 0 | 0 | 9920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127938 | 27632 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-10-25 | QTR2 | 22/23 |  | 2022-08-03 | QTR1 | 22/23 | 115 | 1490902.95
| 01 | E1T70 | 44634815201 | 2021-02-18 | QTR3 | 20/21 | 1 | 1 | 100 | 146 | 168 | 139% | 0 | -22 | 22 | 0 | 29 | 17 | 135271 | 6781 | 128490 | 209621 | 221728 | -22990 | 0 | -22990 | 198738 | 198738 | 154.7% | 0 | 0 | 74350 | 21 | 8 | 0 | 0 | 0 | 0 | 0 | 17 | 74350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 74350 | 0 | F831207624 | AF USA CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2022-11-08 | QTR2 | 22/23 |  | 2021-12-21 | QTR2 | 21/22 | 115 | 152017.02
| 01 | E1U26 | 44488315201 | 2021-07-15 | QTR1 | 21/22 | 1 | 1 | 150 | 161 | 159 | 98.67% | 1 | 2 | 0 | 0 | 11 | 0 | 1247303 | 50000 | 1197303 | 1221387 | 1196429 | 0 | 0 | 0 | 1196429 | 1294630 | 108.1% | 1 | 98201 | -25916 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | -24080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24080 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 |  | 2022-07-15 | QTR1 | 22/23 | 118 | 1391481.98
| 01 | E1U27 | 44430815201 | 2021-08-19 | QTR1 | 21/22 | 1 | 0 | 170 | 188 | 188 | 100% | 1 | 0 | 0 | 0 | 18 | 0 | 748965 | 26664 | 722301 | 748965 | 763405 | 0 | 0 | 0 | 763405 | 763405 | 105.7% | 1 | 0 | 0 | 7 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-10-28 | QTR2 | 22/23 |  | 2022-07-01 | QTR1 | 22/23 | 115 | 748490.78
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 6 | 7 | 10 | 1885 | 2374 | 2390 | 83.33% | 5 | -16 | 22 | 0 | 428 | 61 | 30857922 | 333445 | 30524477 | 31750355 | 31317118 | -22990 | 0 | -22990 | 31294128 | 31277126 | 83.33% | 5 | 10724 | 892433 | 292 | 136 | 0 | 0 | 500809 | 27632 | 0 | 17 | 375488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87683 | 0 | 0 | 0 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 971736 | 27632
| District 01 Totals |  |  |  |  | 15 | 21 | 41 | 4046 | 5433 | 5465 | 80% | 12 | -32 | 75 | 0 | 1179 | 208 | 121671238 | 716417 | 120954821 | 122136092 | 122174611 | -70480 | 0 | -70480 | 122104131 | 121946563 | 93.33% | 14 | 10026 | 464854 | 910 | 318 | 0 | 24 | -1201338 | 33419 | 0 | 64 | 2123425 | 38602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 937782 | 79118 | 0 | 0 | 94241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1447449 | 0 | 0 | 115 | 509522 | 151139
| 02 | T2669 | 43544415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 9 | 1200 | 1479 | 1493 | 110.5% | 1 | -14 | 14 | 0 | 177 | 102 | 36475260 | 150000 | 36325260 | 37438271 | 37041923 | -100058 | 0 | -100058 | 36941865 | 37105576 | 102.1% | 1 | 163711 | 963012 | 81 | 86 | 0 | 9 | 653509 | 14083 | 0 | 9 | 75992 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 84 | 252326 | 4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102 | 981827 | 21137 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2022-08-03 | QTR1 | 22/23 |  | 2022-03-04 | QTR3 | 21/22 | 216 | 37281732.61
| 02 | T2732 | 21002455201 | 2019-02-27 | QTR3 | 18/19 | 2 | 5 | 700 | 1008 | 1008 | 123% | 0 | 0 | 0 | 0 | 195 | 113 | 23611052 | 160000 | 23451052 | 26613712 | 27048870 | 0 | 0 | 0 | 27048870 | 26998931 | 115.1% | 0 | -49939 | 3002661 | 79 | 68 | 16 | 106 | 2872785 | 1293012 | 0 | 7 | 194376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 113 | 3084932 | 1293012 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-25 | QTR1 | 22/23 |  | 2022-02-13 | QTR3 | 21/22 | 216 | 26976039.76
| 02 | T2733 | 43761315201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 150 | 226 | 266 | 146% | 0 | -40 | 40 | 0 | 54 | 22 | 1682750 | 50000 | 1632750 | 1682750 | 1542573 | -66600 | 0 | -66600 | 1475973 | 1522452 | 93.24% | 1 | 46478 | 0 | 25 | 22 | 0 | 22 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 22 | 2808 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-20 | QTR2 | 22/23 |  | 2020-03-19 | QTR3 | 19/20 | 209 | 1962691.97
| 02 | T2746 | 43761015201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 150 | 191 | 191 | 103.3% | 1 | 0 | 0 | 0 | 36 | 5 | 3853383 | 50000 | 3803383 | 3853383 | 3793632 | 0 | 0 | 0 | 3793632 | 3720865 | 97.83% | 1 | -72767 | 0 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-23 | QTR1 | 22/23 |  | 2020-05-22 | QTR4 | 19/20 | 209 | 4960764.49
| 02 | T2756 | 43461915201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 600 | 789 | 732 | 85.5% | 1 | 57 | 0 | 0 | 219 | -30 | 22598230 | 150000 | 22448230 | 22650960 | 22469154 | 0 | 0 | 0 | 22469154 | 22293734 | 99.31% | 1 | -175420 | 52730 | 133 | 86 | 0 | 0 | 120739 | 2419 | 0 | 0 | 15228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | -68367 | 0 | 0 | -30 | 67600 | 2419 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 |  | 2022-05-12 | QTR4 | 21/22 | 216 | 25503399.26
| 02 | T2771 | 43948415201 | 2020-04-29 | QTR4 | 19/20 | 1 | 5 | 340 | 623 | 598 | 100.3% | 1 | 25 | 0 | 0 | 257 | 26 | 6443949 | 59897 | 6384052 | 6682981 | 6771329 | 0 | 0 | 0 | 6771329 | 6801375 | 106.5% | 1 | 56442 | 239033 | 212 | 45 | 0 | 7 | 135060 | 36098 | 0 | 16 | 139779 | 8317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 19447 | 3717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 294287 | 48133 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-13 | QTR2 | 22/23 |  | 2022-04-20 | QTR4 | 21/22 | 208 | 5909474.87
| 02 | T2777 | 44126215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 180 | 245 | 242 | 108.9% | 1 | 3 | 0 | 0 | 63 | 2 | 3565965 | 50000 | 3515965 | 3565965 | 3516567 | 0 | 0 | 0 | 3516567 | 3467651 | 98.63% | 1 | -48916 | 0 | 24 | 22 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 |  | 2021-06-14 | QTR4 | 20/21 | 214 | 4228844.94
| 02 | T2782 | 43808425201 | 2021-03-31 | QTR3 | 20/21 | 2 | 0 | 200 | 272 | 272 | 112% | 1 | 0 | 0 | 0 | 48 | 24 | 737737 | 38937 | 698800 | 737737 | 693945 | 0 | 0 | 0 | 693945 | 694158 | 99.34% | 1 | 2007 | 0 | 8 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-11-03 | QTR2 | 22/23 |  | 2022-07-12 | QTR1 | 22/23 | 208 | 807642.54
| 02 | T2784 | 44133715201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 200 | 493 | 504 | 166% | 0 | -11 | 11 | 0 | 263 | 30 | 8801980 | 90457 | 8711523 | 9073930 | 8672744 | -41316 | 0 | -41316 | 8631428 | 8592793 | 98.64% | 1 | -38635 | 271950 | 134 | 38 | 0 | 0 | 0 | 0 | 91 | 30 | 271950 | 271950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 30 | 271950 | 271950 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-09 | QTR1 | 22/23 |  | 2022-03-03 | QTR3 | 21/22 | 209 | 9187133.29
| 02 | T2807 | 44117315201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 130 | 155 | 152 | 112.3% | 1 | 3 | 0 | 0 | 6 | 19 | 702242 | 21655 | 680587 | 702242 | 666627 | 0 | 0 | 0 | 666627 | 668500 | 98.22% | 1 | 2938 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-08-23 | QTR1 | 22/23 |  | 2022-06-03 | QTR4 | 21/22 | 208 | 504802.01
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 10 | 12 | 21 | 3850 | 5481 | 5458 | 70% | 7 | 23 | 65 | 0 | 1318 | 313 | 108472548 | 820946 | 107651602 | 113001931 | 112217364 | -207974 | 0 | -207974 | 112009390 | 111866035 | 90% | 9 | -114101 | 4529386 | 718 | 427 | 16 | 144 | 3784901 | 1345612 | 108 | 69 | 722323 | 282552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 87 | 271773 | 8486 | 0 | 0 | 17771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | -30 | -68367 | 0 | 173 | 270 | 4728402 | 1636651
| 02 | E20B4 | 43391115201 | 2020-09-16 | QTR1 | 20/21 | 1 | 1 | 522 | 567 | 497 | 86.59% | 1 | 70 | 0 | 0 | 45 | 0 | 3259226 | 50000 | 3209226 | 3394278 | 3308924 | 0 | 0 | 0 | 3308924 | 3308924 | 103.1% | 1 | 0 | 135052 | 3 | 42 | 0 | 0 | 776 | 0 | 0 | 0 | 135052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135829 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-12-01 | QTR2 | 22/23 |  | 2022-08-08 | QTR1 | 22/23 | 208 | 3309179.07
| 02 | E20C3 | 44120015201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 300 | 340 | 275 | 78.33% | 1 | 65 | 0 | 0 | 40 | 0 | 1044910 | 50000 | 994910 | 1044910 | 947808 | 0 | 0 | 0 | 947808 | 947808 | 95.27% | 1 | 0 | 0 | 9 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-07-21 | QTR1 | 22/23 |  | 2022-03-16 | QTR3 | 21/22 | 208 | 1524812.56
| 02 | E20C5 | 43317145201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 180 | 241 | 241 | 103.3% | 1 | 0 | 0 | 0 | 55 | 6 | 1735613 | 50000 | 1685613 | 1735613 | 1621490 | 0 | 0 | 0 | 1621490 | 1633712 | 96.92% | 1 | 12222 | 0 | 43 | 12 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-01 | QTR1 | 22/23 |  | 2022-05-05 | QTR4 | 21/22 | 214 | 2079687.2
| 02 | E20C6 | 44119815201 | 2021-03-17 | QTR3 | 20/21 | 1 | 0 | 210 | 242 | 240 | 103.3% | 1 | 2 | 0 | 0 | 23 | 9 | 982581 | 50000 | 932581 | 982581 | 924634 | 0 | 0 | 0 | 924634 | 924634 | 99.15% | 1 | 0 | 0 | 8 | 15 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-19 | QTR1 | 22/23 |  | 2022-05-12 | QTR4 | 21/22 | 208 | 1257557.66
| 02 | E20F6 | 43439815201 | 2021-07-21 | QTR1 | 21/22 | 1 | 0 | 120 | 143 | 143 | 111.7% | 1 | 0 | 0 | 0 | 23 | 0 | 763880 | 40335 | 723545 | 763880 | 682483 | 0 | 0 | 0 | 682483 | 682483 | 94.32% | 1 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 |  | 2022-06-16 | QTR4 | 21/22 | 208 | 820679.5
| 02 | E2X01 | 44031015201 | 2018-05-16 | QTR4 | 17/18 | 1 | 0 | 400 | 473 | 473 | 100.5% | 1 | 0 | 0 | 0 | 71 | 2 | 9399433 | 98455 | 9300978 | 9399433 | 9453262 | 0 | 0 | 0 | 9453262 | 9483339 | 102% | 1 | 30076 | 0 | 41 | 30 | 0 | 0 | 5627 | 0 | 0 | 2 | 9507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15134 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-20 | QTR2 | 22/23 |  | 2019-12-20 | QTR2 | 19/20 | 209 | 9867068.78
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 6 | 6 | 1 | 1732 | 2006 | 1869 | 100% | 6 | 137 | 0 | 0 | 257 | 17 | 17185643 | 338790 | 16846853 | 17320695 | 16938601 | 0 | 0 | 0 | 16938601 | 16980900 | 100% | 6 | 42298 | 135052 | 108 | 135 | 0 | 15 | 6403 | 0 | 14 | 2 | 144559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 17 | 150963 | 0
| District 02 Totals |  |  |  |  | 16 | 18 | 22 | 5582 | 7487 | 7327 | 81.25% | 13 | 160 | 65 | 0 | 1575 | 330 | 125658191 | 1159736 | 124498455 | 130322626 | 129155965 | -207974 | 0 | -207974 | 128947991 | 128846935 | 93.75% | 15 | -71803 | 4664438 | 826 | 562 | 16 | 159 | 3791304 | 1345612 | 122 | 71 | 866882 | 282552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 87 | 271773 | 8486 | 0 | 0 | 17771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | -30 | -68367 | 0 | 187 | 287 | 4879365 | 1636651
| 03 | 21585 | 22023925201 | 2002-06-19 | QTR4 | 01/02 | 1 | 0 | 270 | 368 | 426 | 157.8% | 0 | -58 | 58 | 0 | 0 | 0 | 943334 | 50000 | 893334 | 1116958 | 1163142 | 0 | 0 | 0 | 1163142 | 1088438 | 121.8% | 0 | -74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 32797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 123250 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-07-06 | QTR1 | 22/23 |  | 2022-01-14 | QTR3 | 21/22 | 313 | 0
| 03 | T3529 | 21787535201 | 2017-05-24 | QTR4 | 16/17 | 4 | 14 | 890 | 1701 | 1701 | 145.2% | 0 | 0 | 0 | 0 | 409 | 402 | 17153564 | 150000 | 17003564 | 18476146 | 18698461 | -35341 | 0 | -35341 | 18663120 | 18835408 | 110.8% | 0 | 236796 | 1322582 | 286 | 123 | 0 | 342 | 773266 | 678882 | 0 | 60 | 374405 | 182495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23100 | 0 | 0 | 0 | 202355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402 | 1390198 | 861377 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-11-30 | QTR2 | 22/23 |  | 2022-04-07 | QTR4 | 21/22 | 306 | 15223000
| 03 | T3665 | 43774715201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 120 | 322 | 311 | 90.83% | 1 | 11 | 0 | 0 | 202 | 0 | 3486000 | 50000 | 3436000 | 3486000 | 3372934 | 0 | 0 | 0 | 3372934 | 3425370 | 99.69% | 1 | 52435 | 0 | 150 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-05 | QTR2 | 22/23 |  | 2019-08-16 | QTR1 | 19/20 | 314 | 0 | B0 | ACC - LUMP SUM
| 03 | T3675 | 43774915201 | 2018-08-29 | QTR1 | 18/19 | 1 | 0 | 90 | 203 | 194 | 90% | 1 | 9 | 0 | 0 | 113 | 0 | 2642778 | 50000 | 2592778 | 2642778 | 2780919 | 0 | 0 | 0 | 2780919 | 2780919 | 107.3% | 1 | 0 | 0 | 46 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-05 | QTR2 | 22/23 |  | 2019-08-07 | QTR1 | 19/20 | 314 | 2368300
| 03 | T3707 | 43938615201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 119 | 168 | 168 | 121% | 0 | 0 | 0 | 0 | 49 | 0 | 698965 | 0 | 698965 | 713815 | 692942 | 0 | 0 | 0 | 692942 | 692942 | 99.14% | 1 | 0 | 14850 | 18 | 6 | 0 | 0 | 0 | 0 | 25 | 0 | 14850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 14850 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-06 | QTR2 | 22/23 |  | 2022-07-06 | QTR1 | 22/23 | 313 | 725593.3
| 03 | T3761 | 43776115201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 150 | 201 | 198 | 98% | 1 | 3 | 0 | 0 | 51 | 0 | 2870000 | 50000 | 2820000 | 2870000 | 2988110 | 0 | 0 | 0 | 2988110 | 3098877 | 109.9% | 1 | 110767 | 0 | 39 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 |  | 2021-10-29 | QTR2 | 21/22 | 321 | 3648686.57
| 03 | T3762 | 43972815201 | 2021-03-31 | QTR3 | 20/21 | 5 | 1 | 295 | 413 | 390 | 92.2% | 1 | 23 | 0 | 0 | 118 | 0 | 7546444 | 66513 | 7479931 | 7547764 | 7602863 | 0 | 0 | 0 | 7602863 | 8039182 | 107.5% | 1 | 455459 | 1320 | 86 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5820 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2022-12-29 | QTR2 | 22/23 |  | 2022-09-25 | QTR1 | 22/23 | 321 | 6787720.74
| 03 | T3778 | 44364315201 | 2021-10-27 | QTR2 | 21/22 | 1 | 0 | 150 | 186 | 185 | 99.33% | 1 | 1 | 0 | 0 | 36 | 0 | 5014999 | 58748 | 4956251 | 5014999 | 5263526 | 0 | 0 | 0 | 5263526 | 5470542 | 110.4% | 0 | 207016 | 0 | 28 | 8 | 0 | 0 | 4631 | 0 | 0 | 0 | 12960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17591 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-29 | QTR2 | 22/23 |  | 2022-07-06 | QTR1 | 22/23 | 321 | 5942459.32
| 03 | T3781 | 44403115201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 60 | 92 | 89 | 95% | 1 | 3 | 0 | 0 | 32 | 0 | 577089 | 26811 | 550278 | 577089 | 562865 | 0 | 0 | 0 | 562865 | 562865 | 102.3% | 1 | 0 | 0 | 10 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-08-04 | QTR1 | 22/23 |  | 2022-03-28 | QTR3 | 21/22 | 314 | 581614.59
| 03 | T3820 | 44364615201 | 2022-02-23 | QTR3 | 21/22 | 2 | 0 | 60 | 79 | 72 | 88.33% | 1 | 7 | 0 | 0 | 19 | 0 | 860079 | 32516 | 827563 | 860079 | 840896 | 0 | 0 | 0 | 840896 | 840896 | 101.6% | 1 | 0 | 0 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-17 | QTR2 | 22/23 |  | 2022-07-21 | QTR1 | 22/23 | 314 | 685675.54
| 03 | T9020 | 44531215215 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 45 | 57 | 1 | -24.44% | 1 | 56 | 0 | 0 | 12 | 0 | 456152 | 21600 | 434552 | 456152 | 434552 | 0 | 0 | 0 | 434552 | 434552 | 100% | 1 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2022-11-17 | QTR2 | 22/23 |  | 2020-04-20 | QTR4 | 19/20 | 306 | 457716.8
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 11 | 19 | 16 | 2249 | 3790 | 3735 | 72.73% | 8 | 55 | 58 | 0 | 1041 | 402 | 42249404 | 556188 | 41693216 | 43761780 | 44401210 | -35341 | 0 | -35341 | 44365869 | 45269991 | 72.73% | 8 | 987769 | 1338752 | 686 | 330 | 0 | 342 | 777897 | 678882 | 25 | 68 | 423975 | 182495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 0 | 0 | 18 | 235152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74704 | 0 | 0 | 0 | 17071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 428 | 1556399 | 861377
| 03 | E3O54 | 21860565201 | 2016-01-29 | QTR3 | 15/16 | 7 | 30 | 789 | 2118 | 2097 | 161.1% | 0 | 21 | 0 | 0 | 835 | 494 | 29137700 | 150000 | 28987700 | 36335019 | 36358268 | 0 | 150000 | 150000 | 36508268 | 37056965 | 127.8% | 0 | 724562 | 7197319 | 641 | 185 | 0 | 119 | 1770045 | 309387 | 9 | 3 | 686825 | 24327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 4298210 | 3702970 | 0 | 0 | 34680 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 211948 | 0 | 0 | 33 | 144197 | 144197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 494 | 7201002 | 4215560 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-07-07 | QTR1 | 22/23 |  | 2022-01-14 | QTR3 | 21/22 | 306 | 26259676.56 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 03 | E3R55 | 44147215201 | 2018-09-13 | QTR1 | 18/19 | 1 | 0 | 180 | 229 | 237 | 104.4% | 1 | -8 | 8 | 0 | 49 | 0 | 1397594 | 50000 | 1347594 | 1397594 | 1214442 | -13320 | 0 | -13320 | 1201122 | 1214442 | 90.12% | 1 | 13320 | 0 | 36 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2022-10-04 | QTR2 | 22/23 |  | 2019-09-21 | QTR1 | 19/20 | 313 | 1716536.28
| 03 | E3S63 | 4452481G201 | 2019-04-16 | QTR4 | 18/19 | 4 | 3 | 180 | 796 | 796 | 355.6% | 0 | 0 | 0 | 0 | 616 | 0 | 1463233 | 0 | 1463233 | 1553233 | 3732786 | 0 | 0 | 0 | 3732786 | 0 | 0% | 1 | -3732786 | 90000 | 98 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 90000 | 0 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2022-07-18 | QTR1 | 22/23 |  | 2021-10-12 | QTR2 | 21/22 | 321 | 1676149.95
| 03 | E3T33 | 40674255201 | 2021-08-12 | QTR1 | 21/22 | 1 | 0 | 180 | 199 | 92 | 42.22% | 1 | 107 | 0 | 0 | 16 | 3 | 671000 | 46442 | 624558 | 671000 | 620160 | 0 | 0 | 0 | 620160 | 620160 | 99.3% | 1 | 0 | 0 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 3 | 19087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 19087 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2022-08-09 | QTR1 | 22/23 |  | 2022-03-02 | QTR3 | 21/22 | 321 | 974400.82
| 03 | E3T37 | 44154715201 | 2020-12-17 | QTR2 | 20/21 | 4 | 0 | 150 | 219 | 228 | 120% | 1 | -9 | 9 | 0 | 57 | 12 | 1496843 | 58788 | 1438055 | 1496843 | 1510915 | -15210 | 0 | -15210 | 1495705 | 1559564 | 108.4% | 1 | 63859 | 0 | 31 | 17 | 0 | 9 | 9075 | 0 | 0 | 3 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20875 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-08-15 | QTR1 | 22/23 |  | 2021-12-16 | QTR2 | 21/22 | 321 | 2221301.11
| 03 | E3T54 | 44154415201 | 2021-06-10 | QTR4 | 20/21 | 1 | 0 | 210 | 278 | 288 | 104.8% | 1 | -10 | 10 | 0 | 68 | 0 | 3673382 | 50000 | 3623382 | 3673382 | 3504749 | -25790 | 0 | -25790 | 3478959 | 3661766 | 101.1% | 1 | 182807 | 0 | 50 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-02 | QTR2 | 22/23 |  | 2022-06-27 | QTR4 | 21/22 | 321 | 5542803.31
| 03 | E3T55 | 43974015201 | 2021-03-11 | QTR3 | 20/21 | 1 | 0 | 180 | 335 | 362 | 115% | 1 | -27 | 27 | 0 | 155 | 0 | 5227145 | 50000 | 5177145 | 5227145 | 5328540 | -101412 | 0 | -101412 | 5227128 | 5712178 | 110.3% | 0 | 485050 | 0 | 102 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-02 | QTR2 | 22/23 |  | 2022-05-31 | QTR4 | 21/22 | 314 | 4892771.41
| 03 | E3U03 | 43973915201 | 2020-12-17 | QTR2 | 20/21 | 1 | 1 | 335 | 433 | 433 | 101.8% | 1 | 0 | 0 | 0 | 92 | 6 | 3371488 | 50000 | 3321488 | 3376998 | 3480991 | 0 | 0 | 0 | 3480991 | 3693131 | 111.2% | 0 | 271808 | 5510 | 58 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 21671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 22488 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 |  | 2022-05-31 | QTR4 | 21/22 | 321 | 4444370.86
| 03 | E3U13 | 42357755201 | 2021-08-12 | QTR1 | 21/22 | 1 | 0 | 180 | 235 | 180 | 69.44% | 1 | 55 | 0 | 0 | 55 | 0 | 1172134 | 50000 | 1122134 | 1172134 | 929583 | 0 | 0 | 0 | 929583 | 929583 | 82.84% | 1 | 0 | 0 | 21 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 |  | 2022-05-02 | QTR4 | 21/22 | 314 | 2039783.8
| 03 | E3U33 | 44744415201 | 2021-12-09 | QTR2 | 21/22 | 1 | 0 | 90 | 94 | 52 | 53.33% | 1 | 42 | 0 | 0 | 4 | 0 | 680167 | 36771 | 643396 | 680167 | 561264 | 0 | 0 | 0 | 561264 | 561264 | 87.23% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-12-06 | QTR2 | 22/23 |  | 2022-06-13 | QTR4 | 21/22 | 313 | 773440.66
| 03 | E3U40 | 22253935201 | 2021-10-14 | QTR2 | 21/22 | 1 | 0 | 120 | 140 | 140 | 101.7% | 1 | 0 | 0 | 0 | 18 | 2 | 2206400 | 50000 | 2156400 | 2206400 | 2130362 | 0 | 85000 | 85000 | 2215362 | 2130362 | 98.79% | 1 | -85000 | 0 | 11 | 7 | 0 | 2 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4770 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-10-27 | QTR2 | 22/23 |  | 2022-07-08 | QTR1 | 22/23 | 321 | 2401773.5 | B10 | ACC - BONUS/INCENT/DISINCENT
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 11 | 23 | 34 | 2594 | 5076 | 4905 | 81.82% | 9 | 171 | 54 | 0 | 1965 | 517 | 50497086 | 592001 | 49905085 | 57789915 | 59372060 | -155732 | 235000 | 79268 | 59451328 | 57139415 | 72.73% | 8 | -2076380 | 7292829 | 1053 | 434 | 0 | 130 | 1783190 | 309387 | 9 | 9 | 820883 | 24327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 4306710 | 3702970 | 460 | 6 | 36197 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 211948 | 0 | 0 | 33 | 144197 | 144197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469 | 517 | 7358222 | 4215560
| District 03 Totals |  |  |  |  | 22 | 42 | 50 | 4843 | 8866 | 8640 | 77.27% | 17 | 226 | 112 | 0 | 3006 | 919 | 92746490 | 1148189 | 91598301 | 101551695 | 103773270 | -191073 | 235000 | 43927 | 103817197 | 102409406 | 72.73% | 16 | -1088611 | 8631581 | 1739 | 764 | 0 | 472 | 2561087 | 988269 | 34 | 77 | 1244858 | 206822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 0 | 0 | 357 | 4541862 | 3702970 | 460 | 6 | 36197 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 286652 | 0 | 0 | 33 | 161268 | 144197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494 | 945 | 8914621 | 5076937
| 04 | T4522 | 43631915201 | 2019-09-25 | QTR1 | 19/20 | 4 | 0 | 737 | 860 | 857 | 99.59% | 1 | 3 | 0 | 0 | 123 | 0 | 11069050 | 129285 | 10939766 | 11069050 | 10764445 | 0 | 0 | 0 | 10764445 | 10777804 | 98.52% | 1 | 13359 | 0 | 85 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 25517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30043 | 0 | 0 | 0 | 9396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64956 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 |  | 2022-05-11 | QTR4 | 21/22 | 412 | 13112789.31
| 04 | T4527 | 43689445201 | 2019-09-25 | QTR1 | 19/20 | 1 | 1 | 323 | 400 | 400 | 100% | 1 | 0 | 0 | 0 | 77 | 0 | 1334388 | 50000 | 1284388 | 1536888 | 1454286 | 0 | 0 | 0 | 1454286 | 1453044 | 113.1% | 0 | -1243 | 202500 | 52 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 4325 | 0 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206825 | 202500 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 |  | 2021-03-08 | QTR3 | 20/21 | 409 | 2037845.47
| 04 | T4544 | 43984715201 | 2020-05-20 | QTR4 | 19/20 | 3 | 3 | 450 | 534 | 531 | 103.1% | 1 | 3 | 0 | 0 | 67 | 17 | 7223964 | 83864 | 7140100 | 7285366 | 7104914 | 0 | 0 | 0 | 7104914 | 7178924 | 100.5% | 1 | 76645 | 61402 | 27 | 40 | 0 | 0 | 15957 | 0 | 0 | 0 | 68904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2326 | 0 | 0 | 17 | 28778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 115965 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 |  | 2022-05-03 | QTR4 | 21/22 | 408 | 8446703.33
| 04 | T4546 | 42751625201 | 2020-04-29 | QTR4 | 19/20 | 2 | 7 | 401 | 493 | 493 | 100% | 1 | 0 | 0 | 0 | 92 | 0 | 11887967 | 111049 | 11776919 | 11268781 | 11300160 | 0 | 0 | 0 | 11300160 | 11435187 | 97.1% | 1 | 192865 | -619187 | 66 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 64334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907 | 0 | 0 | 0 | 148223 | 60298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -762913 | 0 | 0 | 0 | -549449 | 60298 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2022-10-11 | QTR2 | 22/23 |  | 2022-05-11 | QTR4 | 21/22 | 409 | 11525995.08
| 04 | T4558 | 43975515201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 137 | 196 | 195 | 99.27% | 1 | 1 | 0 | 0 | 59 | 0 | 635419 | 33038 | 602381 | 635419 | 611152 | 0 | 0 | 0 | 611152 | 615668 | 102.2% | 1 | 8975 | 0 | 43 | 16 | 0 | 0 | 12282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12282 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-08-18 | QTR1 | 22/23 |  | 2022-05-18 | QTR4 | 21/22 | 409 | 656409.13
| 04 | T4569 | 44177415201 | 2021-07-28 | QTR1 | 21/22 | 2 | 0 | 127 | 138 | 136 | 98.43% | 1 | 2 | 0 | 0 | 11 | 0 | 568800 | 26773 | 542026 | 568800 | 536000 | 0 | 0 | 0 | 536000 | 537990 | 99.26% | 1 | 1990 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6461 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2022-06-10 | QTR4 | 21/22 | 412 | 559587.35
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 6 | 13 | 11 | 2175 | 2621 | 2612 | 100% | 6 | 9 | 0 | 0 | 429 | 17 | 32719588 | 434009 | 32285580 | 32364304 | 31770957 | 0 | 0 | 0 | 31770957 | 31998617 | 83.33% | 5 | 292591 | -355285 | 281 | 148 | 0 | 0 | 28239 | 0 | 0 | 0 | 168382 | 0 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33276 | 0 | 0 | 17 | 187556 | 60298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -762913 | 0 | 0 | 17 | -142960 | 262798
| 04 | E4R96 | 43310865201 | 2017-04-05 | QTR4 | 16/17 | 3 | 22 | 1500 | 1665 | 1573 | 93.87% | 1 | 92 | 0 | 0 | 165 | 0 | 102000000 | 150000 | 101850000 | 110058943 | 109950726 | 0 | 1500000 | 1500000 | 111450726 | 110900593 | 108.9% | 1 | -415056 | 8058943 | 68 | 97 | 0 | 0 | 4394429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707076 | 0 | 0 | 0 | 664098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7765602 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2021-10-29 | QTR2 | 21/22 | 412 | 111264427.38 | B1:B8:Y:B::Y | ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 04 | E4U45 | 44147415201 | 2021-05-07 | QTR4 | 20/21 | 1 | 3 | 194 | 358 | 352 | 134.5% | 0 | 6 | 0 | 0 | 106 | 58 | 1428608 | 34621 | 1393987 | 1539147 | 1506769 | 0 | 0 | 0 | 1506769 | 1507294 | 108.1% | 1 | 525 | 110539 | 71 | 20 | 15 | 58 | 110539 | 0 | 0 | 0 | 7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 58 | 117941 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2022-11-21 | QTR2 | 22/23 |  | 2022-09-16 | QTR1 | 22/23 | 412 | 786261.04
| 04 | E4U70 | 44147015201 | 2021-05-07 | QTR4 | 20/21 | 1 | 3 | 185 | 250 | 249 | 112.4% | 1 | 1 | 0 | 0 | 55 | 10 | 2377932 | 50000 | 2327932 | 2509209 | 2450657 | 0 | 0 | 0 | 2450657 | 2450657 | 105.3% | 1 | 0 | 131278 | 26 | 15 | 4 | 10 | 131278 | 39847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 10 | 131278 | 39847 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-10-03 | QTR2 | 22/23 |  | 2022-08-19 | QTR1 | 22/23 | 409 | 1774051.34
| 04 | E4U73 | 44163315201 | 2021-03-05 | QTR3 | 20/21 | 1 | 2 | 280 | 328 | 324 | 98.57% | 1 | 4 | 0 | 0 | 48 | 0 | 3534228 | 50000 | 3484228 | 3576916 | 3502409 | 0 | 0 | 0 | 3502409 | 3641361 | 104.5% | 1 | 138951 | 42688 | 27 | 21 | 0 | 0 | 17161 | 0 | 0 | 0 | 6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33171 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-07-07 | QTR1 | 22/23 |  | 2022-05-25 | QTR4 | 21/22 | 409 | 4315430.08
| 04 | E4V05 | 44531515215 | 2021-10-01 | QTR2 | 21/22 | 1 | 0 | 126 | 132 | 96 | 71.43% | 1 | 36 | 0 | 0 | 6 | 0 | 676628 | 32349 | 644279 | 676628 | 625424 | 0 | 0 | 0 | 625424 | 625424 | 97.07% | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 |  | 2022-06-10 | QTR4 | 21/22 | 408 | 664967.48
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 5 | 7 | 30 | 2285 | 2733 | 2594 | 80% | 4 | 139 | 0 | 0 | 380 | 68 | 110017396 | 316970 | 109700426 | 118360843 | 118035985 | 0 | 1500000 | 1500000 | 119535985 | 119125329 | 100% | 5 | -275580 | 8343448 | 195 | 156 | 19 | 68 | 4653407 | 39847 | 0 | 0 | 14391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2716098 | 0 | 0 | 0 | 664098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 68 | 8047992 | 39847
| District 04 Totals |  |  |  |  | 11 | 20 | 41 | 4460 | 5354 | 5206 | 90.91% | 10 | 148 | 0 | 0 | 809 | 85 | 142736984 | 750979 | 141986006 | 150725147 | 149806942 | 0 | 1500000 | 1500000 | 151306942 | 151123946 | 90.91% | 10 | 17011 | 7988163 | 476 | 304 | 19 | 68 | 4681646 | 39847 | 0 | 0 | 182773 | 0 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2749374 | 0 | 0 | 17 | 851654 | 60298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | -762913 | 0 | 29 | 85 | 7905032 | 302645
| 05 | T5688 | 44103615201 | 2021-01-27 | QTR3 | 20/21 | 2 | 3 | 140 | 300 | 300 | 113.6% | 1 | 0 | 0 | 0 | 141 | 19 | 4662267 | 53000 | 4609267 | 4737267 | 4423238 | 0 | 0 | 0 | 4423238 | 4604586 | 99.9% | 1 | 211340 | 75000 | 63 | 78 | 0 | 19 | 61462 | 0 | 0 | 0 | 13201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 74663 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-11-01 | QTR2 | 22/23 |  | 2022-05-23 | QTR4 | 21/22 | 509 | 5545150.49
| 05 | T5700 | 44293215201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 170 | 350 | 350 | 117.1% | 1 | 0 | 0 | 0 | 151 | 29 | 1579513 | 50000 | 1529513 | 1579513 | 1554158 | 0 | 0 | 0 | 1554158 | 1562899 | 102.2% | 1 | 19785 | 0 | 33 | 118 | 0 | 0 | 0 | 0 | 0 | 29 | 7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 7602 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 |  | 2022-07-08 | QTR1 | 22/23 | 513 | 1579888.21
| 05 | T5704 | 44113315201 | 2020-11-18 | QTR2 | 20/21 | 1 | 5 | 300 | 515 | 515 | 108% | 1 | 0 | 0 | 0 | 191 | 24 | 10173619 | 124196 | 10049423 | 10199686 | 10343682 | 0 | 0 | 0 | 10343682 | 11087533 | 110.3% | 0 | 761044 | 26067 | 104 | 87 | 0 | 0 | 6721 | 0 | 0 | 24 | 50276 | 8139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20322 | 0 | 0 | 0 | 7261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 84580 | 8139 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-10-13 | QTR2 | 22/23 |  | 2022-08-11 | QTR1 | 22/23 | 513 | 12810546.48
| 05 | T5708 | 44101415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 210 | 349 | 348 | 104.3% | 1 | 1 | 0 | 0 | 129 | 10 | 6490691 | 84382 | 6406309 | 6568600 | 6865453 | 0 | 0 | 0 | 6865453 | 7282431 | 113.7% | 0 | 416979 | 77909 | 53 | 76 | 0 | 10 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 92162 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-07-19 | QTR1 | 22/23 |  | 2022-03-18 | QTR3 | 21/22 | 515 | 8517614.92
| 05 | T5709 | 44113525201 | 2021-01-27 | QTR3 | 20/21 | 2 | 0 | 280 | 431 | 431 | 105.7% | 1 | 0 | 0 | 0 | 135 | 16 | 8389168 | 85000 | 8304168 | 8389168 | 8382005 | 0 | 0 | 0 | 8382005 | 8827365 | 106.3% | 1 | 485238 | 0 | 98 | 37 | 0 | 4 | 20466 | 0 | 0 | 11 | 55149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 82960 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-09-09 | QTR1 | 22/23 |  | 2022-07-06 | QTR1 | 22/23 | 515 | 8661613.49
| 05 | T5716 | 43745115201 | 2021-04-28 | QTR4 | 20/21 | 1 | 2 | 200 | 246 | 245 | 99.5% | 1 | 1 | 0 | 0 | 46 | 0 | 2263271 | 50000 | 2213271 | 2365506 | 2356172 | 0 | 0 | 0 | 2356172 | 2456514 | 111% | 0 | 130713 | 102234 | 29 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 129138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129138 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2022-09-02 | QTR1 | 22/23 |  | 2022-06-30 | QTR4 | 21/22 | 509 | 2040645.74
| 05 | T5722 | 44350715201 | 2021-07-28 | QTR1 | 21/22 | 1 | 0 | 150 | 208 | 208 | 100% | 1 | 0 | 0 | 0 | 58 | 0 | 1619760 | 50000 | 1569760 | 1619760 | 1578600 | 0 | 0 | 0 | 1578600 | 1598533 | 101.8% | 1 | 19933 | 0 | 8 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 6173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11639 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2022-09-02 | QTR1 | 22/23 |  | 2022-07-11 | QTR1 | 22/23 | 515 | 1216963.81
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 7 | 9 | 11 | 1450 | 2399 | 2397 | 100% | 7 | 2 | 0 | 0 | 851 | 98 | 35178289 | 496578 | 34681711 | 35459500 | 35503308 | 0 | 0 | 0 | 35503308 | 37419861 | 57.14% | 4 | 2045032 | 281210 | 388 | 463 | 0 | 33 | 166558 | 0 | 0 | 64 | 261539 | 8139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25788 | 0 | 0 | 1 | 28858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 482744 | 8139
| 05 | E52A7 | 44194515201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 130 | 215 | 215 | 100% | 1 | 0 | 0 | 0 | 85 | 0 | 1902006 | 50000 | 1852006 | 1902006 | 1790542 | 0 | 0 | 0 | 1790542 | 1806715 | 97.55% | 1 | 16173 | 0 | 44 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 7806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14123 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-07-22 | QTR1 | 22/23 |  | 2022-04-08 | QTR4 | 21/22 | 514 | 1695842.63
| 05 | E53A5 | 44113915201 | 2020-12-15 | QTR2 | 20/21 | 1 | 3 | 300 | 373 | 373 | 100% | 1 | 0 | 0 | 0 | 73 | 0 | 1298860 | 50000 | 1248860 | 1434756 | 1399753 | 0 | 0 | 0 | 1399753 | 1404115 | 112.4% | 0 | 7240 | 135896 | 14 | 59 | 0 | 0 | 25354 | 0 | 0 | 0 | 4140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142824 | 0 | F813590186 | P&S PAVING & FLORIDA INDUSTRIAL | N/A | N/A | N/A | N/A | 2022-09-19 | QTR1 | 22/23 |  | 2022-04-02 | QTR4 | 21/22 | 513 | 1281104.01
| 05 | E53A8 | 43632525201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 310 | 383 | 382 | 99.68% | 1 | 1 | 0 | 0 | 73 | 0 | 1713111 | 50000 | 1663111 | 1713111 | 1658956 | 0 | 0 | 0 | 1658956 | 1658958 | 99.75% | 1 | 33039 | 0 | 24 | 49 | 0 | 0 | 24573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24573 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-08 | QTR1 | 22/23 |  | 2022-06-17 | QTR4 | 21/22 | 513 | 1970561.3
| 05 | E54A1 | 44326315201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 120 | 222 | 214 | 93.33% | 1 | 8 | 0 | 0 | 102 | 0 | 985800 | 50000 | 935800 | 985800 | 930200 | 0 | 0 | 0 | 930200 | 930222 | 99.4% | 1 | 22 | 0 | 42 | 60 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2022-11-08 | QTR2 | 22/23 |  | 2022-06-01 | QTR4 | 21/22 | 514 | 1158387
| 05 | E56A2 | 44113415201 | 2021-07-07 | QTR1 | 21/22 | 1 | 1 | 110 | 173 | 173 | 118.2% | 1 | 0 | 0 | 0 | 43 | 20 | 1492986 | 50000 | 1442986 | 1574717 | 1530292 | 0 | 0 | 0 | 1530292 | 1569043 | 108.7% | 1 | 38751 | 81732 | 12 | 31 | 0 | 20 | 81732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 81732 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 |  | 2022-05-23 | QTR4 | 21/22 | 513 | 1629586.92
| 05 | E57A6 | 44713915201 | 2021-10-05 | QTR2 | 21/22 | 1 | 1 | 88 | 134 | 134 | 113.6% | 1 | 0 | 0 | 0 | 34 | 12 | 412340 | 20172 | 392168 | 412340 | 370378 | 0 | 0 | 0 | 370378 | 370378 | 94.44% | 1 | 0 | 0 | 17 | 17 | 0 | 12 | 19486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 19486 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-11-09 | QTR2 | 22/23 |  | 2022-07-10 | QTR1 | 22/23 | 509 | 433630.5
| 05 | E58A6 | 44845415201 | 2021-12-07 | QTR2 | 21/22 | 1 | 0 | 230 | 234 | 120 | 50.43% | 1 | 114 | 0 | 0 | 4 | 0 | 710278 | 29452 | 680826 | 710278 | 702088 | 0 | 0 | 0 | 702088 | 702088 | 103.1% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-09-22 | QTR1 | 22/23 |  | 2022-08-15 | QTR1 | 22/23 | 514 | 626464
| 05 | E5Z92 | 43913815201 | 2019-11-05 | QTR2 | 19/20 | 1 | 2 | 360 | 670 | 701 | 151.4% | 0 | -31 | 31 | 0 | 156 | 154 | 3448889 | 50000 | 3398889 | 3384670 | 3383592 | -477312 | 0 | -477312 | 2906280 | 3336127 | 98.15% | 1 | 429848 | -64219 | 83 | 73 | 0 | 3 | 7050 | 0 | 0 | 6 | 25464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | -71121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | -38606 | 0 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2022-09-09 | QTR1 | 22/23 |  | 2022-02-08 | QTR3 | 21/22 | 515 | 3664930.24
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 8 | 8 | 7 | 1648 | 2404 | 2312 | 87.5% | 7 | 92 | 31 | 0 | 570 | 186 | 11964270 | 349624 | 11614646 | 12117678 | 11765801 | -477312 | 0 | -477312 | 11288489 | 11777646 | 87.5% | 7 | 525073 | 153409 | 236 | 334 | 0 | 35 | 160195 | 0 | 0 | 6 | 37410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 48526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 246132 | 0
| District 05 Totals |  |  |  |  | 15 | 17 | 18 | 3098 | 4803 | 4709 | 93.33% | 14 | 94 | 31 | 0 | 1421 | 284 | 47142559 | 846202 | 46296357 | 47577178 | 47269109 | -477312 | 0 | -477312 | 46791797 | 49197507 | 73.33% | 11 | 2570105 | 434619 | 624 | 797 | 0 | 68 | 326753 | 0 | 0 | 70 | 298949 | 8139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 74314 | 0 | 0 | 1 | 28858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284 | 728876 | 8139
| 06 | T6433 | 42440715201 | 2018-06-13 | QTR4 | 17/18 | 3 | 15 | 700 | 1063 | 940 | 101.3% | 1 | 123 | 0 | 0 | 231 | 132 | 67230501 | 151730 | 67078771 | 72750415 | 73542354 | 0 | 4200000 | 4200000 | 77742354 | 73243755 | 109.2% | 1 | -4309470 | 5519914 | 198 | 33 | 0 | 0 | 557153 | 37295 | 0 | 132 | 4723947 | 3063646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450249 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -309497 | 0 | 0 | 132 | 5471149 | 3100941 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2022-08-19 | QTR1 | 22/23 |  | 2021-12-16 | QTR2 | 21/22 | 606 | 76112026.4 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 06 | T6480 | 44018215201 | 2021-02-17 | QTR3 | 20/21 | 2 | 0 | 170 | 277 | 267 | 94.12% | 1 | 10 | 0 | 0 | 107 | 0 | 515515 | 29915 | 485600 | 515515 | 456395 | 0 | 0 | 0 | 456395 | 456395 | 93.99% | 1 | 0 | 0 | 87 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-09-30 | QTR1 | 22/23 |  | 2022-06-27 | QTR4 | 21/22 | 636 | 619720.15
| 06 | T6497 | 44516815201 | 2020-11-18 | QTR2 | 20/21 | 3 | 0 | 150 | 259 | 257 | 116% | 1 | 2 | 0 | 0 | 109 | 0 | 541368 | 29764 | 511604 | 541368 | 498909 | 0 | 0 | 0 | 498909 | 498909 | 97.52% | 1 | 0 | 0 | 65 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 4133 | 0 | 0 | 0 | 8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 12361 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-25 | QTR1 | 22/23 |  | 2022-05-23 | QTR4 | 21/22 | 613 | 585940.8
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 3 | 8 | 15 | 1020 | 1599 | 1464 | 100% | 3 | 135 | 0 | 0 | 447 | 132 | 68287384 | 211409 | 68075975 | 73807298 | 74497658 | 0 | 4200000 | 4200000 | 78697658 | 74199059 | 100% | 3 | -4309470 | 5519914 | 350 | 71 | 0 | 0 | 557153 | 37295 | 0 | 132 | 4723947 | 3063646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 454382 | 0 | 0 | 0 | 22961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -309497 | 0 | 26 | 132 | 5483510 | 3100941
| 06 | E6L38 | 25168465201 | 2018-05-02 | QTR4 | 17/18 | 2 | 6 | 1000 | 1287 | 1259 | 109% | 1 | 28 | 0 | 0 | 169 | 118 | 56331262 | 150000 | 56181262 | 61782326 | 61740658 | 0 | 0 | 0 | 61740658 | 61689883 | 109.8% | 1 | -2495 | 5451064 | 115 | 54 | 0 | 0 | 408613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 4906149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76933 | 0 | 0 | 118 | 5342031 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-08-10 | QTR1 | 22/23 |  | 2022-02-11 | QTR3 | 21/22 | 606 | 56289000 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
| 06 | E6M02 | 43952215201 | 2021-05-27 | QTR4 | 20/21 | 1 | 0 | 120 | 134 | 97 | 69.17% | 1 | 37 | 0 | 0 | 14 | 0 | 284704 | 15025 | 269679 | 284704 | 265754 | 0 | 0 | 0 | 265754 | 265754 | 98.54% | 1 | 0 | 0 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-11-22 | QTR2 | 22/23 |  | 2022-09-27 | QTR1 | 22/23 | 613 | 309692.5
| 06 | E6M50 | 44196715201 | 2020-11-19 | QTR2 | 20/21 | 1 | 2 | 240 | 412 | 412 | 118.8% | 1 | 0 | 0 | 0 | 148 | 24 | 873331 | 43833 | 829498 | 1042774 | 969094 | 0 | 0 | 0 | 969094 | 969094 | 116.8% | 0 | 0 | 169443 | 104 | 23 | 20 | 24 | 162091 | 0 | 1 | 0 | 6118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24 | 168208 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2022-11-18 | QTR2 | 22/23 |  | 2022-08-30 | QTR1 | 22/23 | 613 | 905939.9
| 06 | E6M84 | 44253915201 | 2020-08-27 | QTR1 | 20/21 | 2 | 1 | 150 | 220 | 220 | 112.7% | 1 | 0 | 0 | 0 | 70 | 0 | 608490 | 30869 | 577621 | 625609 | 579687 | 0 | 0 | 0 | 579687 | 585088 | 101.3% | 1 | 5401 | 17119 | 40 | 11 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 1768 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 |  | 2022-05-25 | QTR4 | 21/22 | 613 | 624645.65
| 06 | E6N00 | 44394015201 | 2022-02-24 | QTR3 | 21/22 | 1 | 0 | 120 | 158 | 123 | 70.83% | 1 | 35 | 0 | 0 | 38 | 0 | 510362 | 28444 | 481918 | 510362 | 479426 | 0 | 0 | 0 | 479426 | 473360 | 98.22% | 1 | -6066 | 0 | 33 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2022-12-08 | QTR2 | 22/23 |  | 2022-10-10 | QTR2 | 22/23 | 613 | 600250.3
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 5 | 7 | 9 | 1630 | 2211 | 2111 | 100% | 5 | 100 | 0 | 0 | 439 | 142 | 58608149 | 268171 | 58339978 | 64245775 | 64034619 | 0 | 0 | 0 | 64034619 | 63983179 | 80% | 4 | -3160 | 5637626 | 305 | 94 | 39 | 24 | 570704 | 0 | 1 | 0 | 7931 | 0 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 4908959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76933 | 0 | 40 | 142 | 5514862 | 0
| District 06 Totals |  |  |  |  | 8 | 15 | 24 | 2650 | 3810 | 3575 | 100% | 8 | 235 | 0 | 0 | 886 | 274 | 126895533 | 479580 | 126415953 | 138053073 | 138532277 | 0 | 4200000 | 4200000 | 142732277 | 138182238 | 87.5% | 7 | -4312630 | 11157540 | 655 | 165 | 39 | 24 | 1127857 | 37295 | 1 | 132 | 4731878 | 3063646 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 118 | 5363341 | 0 | 0 | 0 | 22961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -386430 | 0 | 66 | 274 | 10998372 | 3100941
| 07 | T7408 | 42895315201 | 2018-06-13 | QTR4 | 17/18 | 4 | 25 | 1115 | 1267 | 1253 | 98.74% | 1 | 14 | 0 | 0 | 152 | 0 | 52309860 | 150000 | 52159860 | 53697121 | 53886362 | 0 | 0 | 0 | 53886362 | 53722937 | 103% | 1 | -163425 | 1387261 | 66 | 86 | 0 | 0 | 630838 | 47733 | 0 | 0 | 729633 | 81715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117242 | 0 | 0 | 0 | 35355 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -227170 | 0 | 0 | 0 | 1315397 | 162073 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-07-15 | QTR1 | 22/23 |  | 2022-02-18 | QTR3 | 21/22 | 714 | 61751000
| 07 | T7434 | 43734915201 | 2019-06-12 | QTR4 | 18/19 | 1 | 1 | 441 | 514 | 514 | 100% | 1 | 0 | 0 | 0 | 73 | 0 | 5555515 | 50000 | 5505515 | 5352409 | 5279909 | 0 | 0 | 0 | 5279909 | 5286766 | 96.03% | 1 | 6857 | -203106 | 35 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -203106 | 0 | 0 | 0 | -203106 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2022-10-24 | QTR2 | 22/23 |  | 2022-03-02 | QTR3 | 21/22 | 798 | 5564432.46
| 07 | T7444 | 44108325201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 443 | 585 | 581 | 110.4% | 1 | 4 | 0 | 0 | 92 | 50 | 10034121 | 129550 | 9904571 | 10350046 | 9810424 | 0 | 0 | 0 | 9810424 | 9853179 | 99.48% | 1 | 103829 | 315925 | 59 | 33 | 0 | 0 | 0 | 0 | 0 | 50 | 344704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 411706 | 0 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 |  | 2022-05-31 | QTR4 | 21/22 | 714 | 12990036.6
| 07 | T7446 | 43005125201 | 2020-02-26 | QTR3 | 19/20 | 2 | 1 | 240 | 272 | 272 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 4532943 | 100000 | 4432943 | 4557685 | 4389265 | 0 | 0 | 0 | 4389265 | 4384901 | 98.92% | 1 | -4365 | 24742 | 15 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 22996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29305 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-12-07 | QTR2 | 22/23 |  | 2021-05-11 | QTR4 | 20/21 | 798 | 4923200
| 07 | T7459 | 44550725201 | 2021-02-17 | QTR3 | 20/21 | 2 | 0 | 210 | 355 | 354 | 110.5% | 1 | 1 | 0 | 0 | 145 | 0 | 1887858 | 50000 | 1837858 | 1887858 | 1854136 | 0 | 0 | 0 | 1854136 | 1854136 | 100.9% | 1 | 38612 | 0 | 100 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-09-12 | QTR1 | 22/23 |  | 2022-07-07 | QTR1 | 22/23 | 799 | 2521800
| 07 | T7463 | 43762415201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 200 | 271 | 271 | 111.5% | 1 | 0 | 0 | 0 | 50 | 21 | 5399019 | 50000 | 5349019 | 5449019 | 5598998 | 0 | 0 | 0 | 5598998 | 5769676 | 107.9% | 1 | 201519 | 50000 | 30 | 18 | 0 | 0 | 15416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15416 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-08-02 | QTR1 | 22/23 |  | 2022-04-08 | QTR4 | 21/22 | 799 | 5600000
| 07 | T7465 | 44110415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 200 | 288 | 288 | 119% | 1 | 0 | 0 | 0 | 50 | 38 | 1187466 | 40000 | 1147466 | 1227466 | 1221695 | 0 | 0 | 0 | 1221695 | 1225383 | 106.8% | 1 | 3688 | 40000 | 33 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-26 | QTR2 | 22/23 |  | 2022-04-25 | QTR4 | 21/22 | 798 | 941000
| 07 | T7474 | 44555415201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 200 | 222 | 175 | 76.5% | 1 | 47 | 0 | 0 | 22 | 0 | 755204 | 42000 | 713204 | 755204 | 735925 | 0 | 0 | 0 | 735925 | 735925 | 103.2% | 1 | 40677 | 0 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 |  | 2022-05-06 | QTR4 | 21/22 | 796 | 918700
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 8 | 14 | 31 | 3049 | 3774 | 3708 | 100% | 8 | 66 | 0 | 0 | 616 | 109 | 81661986 | 611550 | 81050436 | 83276808 | 82776714 | 0 | 0 | 0 | 82776714 | 82832903 | 100% | 8 | 227392 | 1614822 | 344 | 247 | 0 | 0 | 646254 | 47733 | 0 | 50 | 1097333 | 81715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184244 | 0 | 0 | 0 | 35355 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 35809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -430276 | 0 | 0 | 50 | 1568718 | 162073
| 07 | E7L92 | 43669715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 11 | 675 | 1004 | 1004 | 115.7% | 1 | 0 | 0 | 0 | 301 | 28 | 4257317 | 50000 | 4207317 | 10851592 | 9627641 | 0 | 0 | 0 | 9627641 | 9622285 | 228.7% | 0 | -5356 | 6594276 | 66 | 157 | 32 | 0 | 8007524 | 0 | 0 | 0 | 265662 | 8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28 | 365894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2044097 | 0 | 78 | 28 | 6594983 | 8995 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-08 | QTR1 | 22/23 |  | 2022-01-26 | QTR3 | 21/22 | 799 | 4476953.25
| 07 | E7N30 | 43473625201 | 2021-08-11 | QTR1 | 21/22 | 1 | 0 | 188 | 216 | 215 | 100.5% | 1 | 1 | 0 | 0 | 26 | 0 | 1297005 | 50000 | 1247005 | 1297005 | 1237378 | 0 | 0 | 0 | 1237378 | 1237963 | 99.27% | 1 | 585 | 0 | 10 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2022-12-12 | QTR2 | 22/23 |  | 2022-08-05 | QTR1 | 22/23 | 796 | 1230300
| 07 | E7N54 | 43480735201 | 2021-01-29 | QTR3 | 20/21 | 1 | 1 | 150 | 255 | 190 | 109.3% | 1 | 65 | 0 | 0 | 26 | 79 | 1422150 | 50000 | 1372150 | 1360924 | 1310034 | 0 | 0 | 0 | 1310034 | 1310789 | 95.53% | 1 | 755 | -61226 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61226 | 0 | 0 | 0 | -61226 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-10-17 | QTR2 | 22/23 |  | 2022-02-21 | QTR3 | 21/22 | 799 | 1400000
| 07 | E7N99 | 44025425201 | 2021-07-14 | QTR1 | 21/22 | 3 | 1 | 140 | 155 | 155 | 100% | 1 | 0 | 0 | 0 | 15 | 0 | 1595242 | 50000 | 1545242 | 1718861 | 1294242 | 0 | 0 | 0 | 1294242 | 1316286 | 85.18% | 1 | 22044 | 123619 | 4 | 11 | 0 | 0 | 123619 | 113968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123619 | 113968 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-11-08 | QTR2 | 22/23 |  | 2022-05-09 | QTR4 | 21/22 | 799 | 1647300
| 07 | E7O21 | 44366415201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 60 | 60 | 44 | 73.33% | 1 | 16 | 0 | 0 | 0 | 0 | 397254 | 14000 | 383254 | 397254 | 370201 | 0 | 0 | 0 | 370201 | 370201 | 96.59% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-11 | QTR1 | 22/23 |  | 2022-04-26 | QTR4 | 21/22 | 796 | 296700
| 07 | E7P10 | 44948515201 | 2022-03-09 | QTR3 | 21/22 | 1 | 0 | 40 | 46 | 46 | 100% | 1 | 0 | 0 | 0 | 6 | 0 | 403261 | 17000 | 386261 | 403261 | 392075 | 0 | 0 | 0 | 392075 | 392075 | 101.5% | 1 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-11-28 | QTR2 | 22/23 |  | 2022-08-30 | QTR1 | 22/23 | 796 | 420300
| 07 | E7R28 | 44769615201 | 2021-05-10 | QTR4 | 20/21 | 1 | 0 | 310 | 341 | 341 | 100% | 1 | 0 | 0 | 0 | 31 | 0 | 2063258 | 50000 | 2013258 | 2063258 | 2025710 | 0 | 0 | 0 | 2025710 | 2046401 | 101.6% | 1 | 20691 | 0 | 17 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 |  | 2022-06-17 | QTR4 | 21/22 | 796 | 1523991.28 | LBDB | LOW BID DESIGN BUILD
| 07 | E7R29 | 43982995201 | 2021-05-17 | QTR4 | 20/21 | 2 | 0 | 321 | 329 | 324 | 98.44% | 1 | 5 | 0 | 0 | 8 | 0 | 1887000 | 50000 | 1837000 | 1887000 | 1837000 | 0 | 0 | 0 | 1837000 | 1837000 | 100% | 1 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-08-01 | QTR1 | 22/23 |  | 2022-06-03 | QTR4 | 21/22 | 796 | 2845446.28 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 8 | 12 | 13 | 1884 | 2406 | 2319 | 100% | 8 | 87 | 0 | 0 | 413 | 107 | 13322487 | 331000 | 12991487 | 19979155 | 18094281 | 0 | 0 | 0 | 18094281 | 18133000 | 87.5% | 7 | 38719 | 6656669 | 116 | 219 | 32 | 0 | 8131143 | 113968 | 0 | 0 | 265662 | 8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28 | 365894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2105323 | 0 | 78 | 28 | 6657376 | 122963
| District 07 Totals |  |  |  |  | 16 | 26 | 44 | 4933 | 6180 | 6027 | 100% | 16 | 153 | 0 | 0 | 1029 | 216 | 94984473 | 942550 | 94041923 | 103255963 | 100870995 | 0 | 0 | 0 | 100870995 | 100965903 | 93.75% | 15 | 266111 | 8271491 | 460 | 466 | 32 | 0 | 8777397 | 161701 | 0 | 50 | 1362995 | 90710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28 | 550138 | 0 | 0 | 0 | 35355 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 35809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2535599 | 0 | 78 | 78 | 8226094 | 285036
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8S34 | 43798655201 | 2021-03-09 | QTR3 | 20/21 | 1 | 1 | 160 | 200 | 190 | 93.75% | 1 | 10 | 0 | 0 | 40 | 0 | 878913 | 50000 | 828913 | 870049 | 822741 | 0 | 0 | 0 | 822741 | 823180 | 99.31% | 1 | 7889 | -8864 | 24 | 16 | 0 | 0 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8864 | 0 | 0 | 0 | -5345 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-07-06 | QTR1 | 22/23 |  | 2022-05-06 | QTR4 | 21/22 | 854 | 1113411.37
| 08 | E8S70 | 44262215201 | 2020-11-17 | QTR2 | 20/21 | 5 | 0 | 303 | 380 | 378 | 101.7% | 1 | 2 | 0 | 0 | 77 | 0 | 4113457 | 78161 | 4035296 | 4113457 | 3489511 | 0 | 0 | 0 | 3489511 | 3489532 | 86.48% | 1 | 21 | 0 | 45 | 25 | 0 | 0 | 11159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 11159 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-08-19 | QTR1 | 22/23 |  | 2022-06-13 | QTR4 | 21/22 | 854 | 7220597.77
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 2 | 6 | 1 | 463 | 580 | 568 | 100% | 2 | 12 | 0 | 0 | 117 | 0 | 4992370 | 128161 | 4864209 | 4983506 | 4312252 | 0 | 0 | 0 | 4312252 | 4312712 | 100% | 2 | 7910 | -8864 | 69 | 41 | 0 | 0 | 14678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8864 | 0 | 7 | 0 | 5814 | 0
| District 08 Totals |  |  |  |  | 2 | 6 | 1 | 463 | 580 | 568 | 100% | 2 | 12 | 0 | 0 | 117 | 0 | 4992370 | 128161 | 4864209 | 4983506 | 4312252 | 0 | 0 | 0 | 4312252 | 4312712 | 100% | 2 | 7910 | -8864 | 69 | 41 | 0 | 0 | 14678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8864 | 0 | 7 | 0 | 5814 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 54 | 89 | 136 | 15954 | 22723 | 22449 | 85.19% | 46 | 274 | 176 | 0 | 5453 | 1218 | 459382515 | 3513652 | 455868864 | 472057358 | 472024704 | -290805 | 4200000 | 3909195 | 475933899 | 474255903 | 85.19% | 46 | -871485 | 12501220 | 3385 | 1868 | 16 | 543 | 4258855 | 2115309 | 133 | 430 | 9145436 | 3657149 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 0 | 36 | 132 | 2054714 | 87604 | 0 | 18 | 381847 | 92924 | 0 | 0 | 0 | 0 | 0 | 0 | 35809 | 0 | 0 | 0 | 114704 | 40000 | 7 | 0 | 51634 | 0 | 32 | 0 | 0 | 0 | 0 | -30 | -3018502 | 0 | 224 | 1093 | 13214599 | 6155486
| Statewide District Let Contracts SubTotal |  |  |  |  | 51 | 76 | 105 | 14121 | 19790 | 19068 | 90.2% | 46 | 722 | 107 | 0 | 4569 | 1098 | 297445323 | 2658162 | 294787161 | 326547922 | 323870717 | -656034 | 1735000 | 1078966 | 324949683 | 322729307 | 86.27% | 44 | -1730396 | 29102602 | 2374 | 1549 | 90 | 272 | 15820529 | 490834 | 24 | 34 | 1666324 | 33322 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 630 | 12433870 | 3702970 | 460 | 6 | 705190 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 57960 | 0 | 0 | 0 | 211948 | 0 | 0 | 33 | 144197 | 144197 | 10 | 0 | 0 | 0 | 0 | 0 | -2191120 | 0 | 637 | 975 | 28953097 | 4406002
| Statewide Totals |  |  |  |  | 105 | 165 | 241 | 30075 | 42513 | 41517 | 87.62% | 92 | 996 | 283 | 0 | 10022 | 2316 | 756827838 | 6171814 | 750656025 | 798605280 | 795895421 | -946839 | 5935000 | 4988161 | 800883582 | 796985210 | 85.71% | 90 | -2601881 | 41603822 | 5759 | 3417 | 106 | 815 | 20079384 | 2606143 | 157 | 464 | 10811760 | 3690471 | 0 | 0 | 266702 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 0 | 89 | 762 | 14488584 | 3790574 | 460 | 24 | 1087037 | 127604 | 0 | 0 | 0 | 0 | 0 | 0 | 93769 | 0 | 0 | 0 | 326652 | 40000 | 7 | 33 | 195831 | 144197 | 42 | 0 | 0 | 0 | 0 | -30 | -5209622 | 0 | 861 | 2068 | 42167696 | 10561488

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1R65 | 43084915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2019-07-18 | 24334683 | 24901396 | 24523563 | 566712.9 | 0 | 24408360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24523563 | 24408360 | -115203 | 29026731
1 | E1T56 | 44022515201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2020-09-03 | 2201700 | 2363829 | 2340016 | 162129.2 | 0 | 2340016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340016 | 2340016 | 0 | 2100536 | A3 | ICC - DESIGN/BUILD - MINOR
1 | E1T69 | 43485915201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-02-18 | 2190000 | 2305157 | 2299703 | 115157.45 | 0 | 2299703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2299703 | 2299703 | 0 | 1490903
1 | E1T70 | 44634815201 | F831207624 | AF USA CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2021-02-18 | 135271 | 209621 | 221728 | 74349.65 | -22990 | 198738 | -22990 | 0 | 0 | 0 | 0 | 0 | -22990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22990 | 198738 | 198738 | 0 | 152017
1 | E1U26 | 44488315201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-07-15 | 1247303 | 1221387 | 1196429 | -25916 | 0 | 1294630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196429 | 1294630 | 98201 | 1391482
1 | E1U27 | 44430815201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-08-19 | 748965 | 748965 | 763405 | 0 | 0 | 763405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763405 | 763405 | 0 | 748491
1 | T1709 | 20103225201 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2018-05-23 | 80840173 | 80370929 | 81141842 | -469243.92 | -44000 | 81007287 | 0 | 0 | 0 | 0 | 0 | -44000 | -44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44000 | 81097842 | 81007287 | -90555 | 83257743 | B5 | ACC - INCENTIVE/DISINCENTIVE
1 | T1745 | 43697915201 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2019-04-24 | 2042506 | 2042506 | 1941189 | 0 | 0 | 1938502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1941189 | 1938502 | -2688 | 1951298
1 | T1763 | 44147515201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-07-31 | 1200000 | 1200000 | 1176976 | 0 | 0 | 1176787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1176976 | 1176787 | -190 | 950444
1 | T1771 | 44035615201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-08-25 | 879962 | 906645 | 906645 | 26683 | 0 | 906645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 906645 | 906645 | 0 | 847815 | B0 | ACC - LUMP SUM
1 | T1784 | 44210725201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 1091540 | 1106522 | 1100887 | 14982.17 | 0 | 1100887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100887 | 1100887 | 0 | 1402962
1 | T1791 | 44034715201 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2021-01-27 | 610558 | 610558 | 610907 | 0 | -3490 | 607417 | -3490 | 0 | 0 | 0 | 0 | 0 | -3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3490 | 607417 | 607417 | 0 | 735870 | B0 | ACC - LUMP SUM
1 | T1794 | 44477915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-27 | 2947759 | 2947759 | 2877401 | 0 | 0 | 2926249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2877401 | 2926249 | 48848 | 2695046
1 | T1809 | 44624015201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 569569 | 569569 | 545539 | 0 | 0 | 545539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545539 | 545539 | 0 | 560699
1 | T1823 | 44212415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-09-29 | 631249 | 631249 | 599995 | 0 | 0 | 599995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599995 | 599995 | 0 | 604210 | B0 | ACC - LUMP SUM
2 | E20B4 | 43391115201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-09-16 | 3259226 | 3394278 | 3308924 | 135052.25 | 0 | 3308924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3308924 | 3308924 | 0 | 3309179
2 | E20C3 | 44120015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2020-12-16 | 1044910 | 1044910 | 947808 | 0 | 0 | 947808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 947808 | 947808 | 0 | 1524813
2 | E20C5 | 43317145201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 1735613 | 1735613 | 1621490 | 0 | 0 | 1633712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1621490 | 1633712 | 12222 | 2079687
2 | E20C6 | 44119815201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-03-17 | 982581 | 982581 | 924634 | 0 | 0 | 924634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924634 | 924634 | 0 | 1257558
2 | E20F6 | 43439815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-07-21 | 763880 | 763880 | 682483 | 0 | 0 | 682483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682483 | 682483 | 0 | 820680
2 | E2X01 | 44031015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-16 | 9399433 | 9399433 | 9453262 | 0 | 0 | 9483339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9453262 | 9483339 | 30076 | 9867069
2 | T2669 | 43544415201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2017-10-25 | 36475260 | 37438271 | 37041923 | 963011.63 | -100058 | 37105576 | -100058 | 0 | 0 | 0 | 0 | 0 | -100058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100058 | 36941865 | 37105576 | 163711 | 37281733
2 | T2732 | 21002455201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 23611052 | 26613712 | 27048870 | 3002660.63 | 0 | 26998931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27048870 | 26998931 | -49939 | 26976040
2 | T2733 | 43761315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 1682750 | 1682750 | 1542573 | 0 | -66600 | 1522452 | -66600 | 0 | 0 | 0 | 0 | 0 | -66600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66600 | 1475973 | 1522452 | 46478 | 1962692
2 | T2746 | 43761015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-08-28 | 3853383 | 3853383 | 3793632 | 0 | 0 | 3720865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3793632 | 3720865 | -72767 | 4960764
2 | T2756 | 43461915201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2020-01-29 | 22598230 | 22650960 | 22469154 | 52729.99 | 0 | 22293734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22469154 | 22293734 | -175420 | 25503399
2 | T2771 | 43948415201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 6443949 | 6682981 | 6797724 | 239032.6 | 0 | 6827771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6797724 | 6827771 | 30046 | 5909475
2 | T2777 | 44126215201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 3565965 | 3565965 | 3516567 | 0 | 0 | 3519561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3516567 | 3519561 | 2994 | 4228845
2 | T2782 | 43808425201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-03-31 | 737737 | 737737 | 695739 | 0 | 0 | 695952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695739 | 695952 | 213 | 807643
2 | T2784 | 44133715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 8801980 | 9073930 | 8672744 | 271949.84 | -41316 | 8592793 | -41316 | 0 | 0 | 0 | 0 | 0 | -41316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41316 | 8631428 | 8592793 | -38635 | 9187133
2 | T2807 | 44117315201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-03-31 | 702242 | 702242 | 667693 | 0 | 0 | 669566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667693 | 669566 | 1873 | 504802
3 | 21585 | 22023925201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2002-06-19 | 943334 | 1116958 | 1163142 | 0 | 0 | 1088438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163142 | 1088438 | -74704 | 0
3 | E3O54 | 21860565201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2016-01-29 | 29137700 | 36335019 | 36358268 | 7197319.1 | 150000 | 37232830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 36508268 | 37232830 | 724562 | 26259677 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
3 | E3R55 | 44147215201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2018-09-13 | 1397594 | 1397594 | 1214442 | 0 | -13320 | 1214442 | -13320 | 0 | 0 | 0 | 0 | 0 | -13320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13320 | 1201122 | 1214442 | 13320 | 1716536
3 | E3S63 | 4452481G201 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2019-04-16 | 1463233 | 1553233 | 3732786 | 89999.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3732786 | 0 | -3732786 | 1676150
3 | E3T33 | 40674255201 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2021-08-12 | 671000 | 671000 | 620160 | 0 | 0 | 620160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620160 | 620160 | 0 | 974401
3 | E3T37 | 44154715201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-12-17 | 1496843 | 1496843 | 1510915 | 0 | -15210 | 1559564 | -15210 | 0 | 0 | 0 | 0 | 0 | -15210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15210 | 1495705 | 1559564 | 63859 | 2221301
3 | E3T54 | 44154415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-10 | 3673382 | 3673382 | 3504749 | 0 | -25790 | 3661766 | -25790 | 0 | 0 | 0 | 0 | 0 | -25790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25790 | 3478959 | 3661766 | 182807 | 5542803
3 | E3T55 | 43974015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-03-11 | 5227145 | 5227145 | 5328540 | 0 | -101412 | 5712178 | -101412 | 0 | 0 | 0 | 0 | 0 | -101412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101412 | 5227128 | 5712178 | 485050 | 4892771
3 | E3U03 | 43973915201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-12-17 | 3371488 | 3376998 | 3540659 | 5510 | 0 | 3752799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3540659 | 3752799 | 212140 | 4444371
3 | E3U13 | 42357755201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2021-08-12 | 1172134 | 1172134 | 929583 | 0 | 0 | 929583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929583 | 929583 | 0 | 2039784
3 | E3U33 | 44744415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-12-09 | 680167 | 680167 | 561264 | 0 | 0 | 561264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561264 | 561264 | 0 | 773441
3 | E3U40 | 22253935201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-10-14 | 2206400 | 2206400 | 2130362 | 0 | 85000 | 2130362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 85000 | 2215362 | 2130362 | -85000 | 2401774 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | T3529 | 21787535201 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2017-05-24 | 17153564 | 18476146 | 18698461 | 1322581.74 | -35341 | 18923171 | 0 | 0 | 0 | 0 | -35341 | 0 | -35341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35341 | 18663120 | 18923171 | 260051 | 15223000
3 | T3665 | 43774715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-07-25 | 3486000 | 3486000 | 3372934 | 0 | 0 | 3425370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3372934 | 3425370 | 52435 | 0 | B0 | ACC - LUMP SUM
3 | T3675 | 43774915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-08-29 | 2642778 | 2642778 | 2780919 | 0 | 0 | 2780919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780919 | 2780919 | 0 | 2368300
3 | T3707 | 43938615201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 698965 | 713815 | 692942 | 14850 | 0 | 692942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 692942 | 692942 | 0 | 725593
3 | T3761 | 43776115201 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 2870000 | 2870000 | 2988110 | 0 | 0 | 3098877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2988110 | 3098877 | 110767 | 3648687
3 | T3762 | 43972815201 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2021-03-31 | 7546444 | 7547764 | 7622003 | 1320 | 0 | 8058321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7622003 | 8058321 | 436319 | 6787721
3 | T3778 | 44364315201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 5014999 | 5014999 | 5263526 | 0 | 0 | 5470542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5263526 | 5470542 | 207016 | 5942459
3 | T3781 | 44403115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 577089 | 577089 | 562865 | 0 | 0 | 562865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562865 | 562865 | 0 | 581615
3 | T3820 | 44364615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 860079 | 860079 | 840896 | 0 | 0 | 840896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840896 | 840896 | 0 | 685676
3 | T9020 | 44531215215 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2019-10-30 | 456152 | 456152 | 434552 | 0 | 0 | 434552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434552 | 434552 | 0 | 457717
4 | E4R96 | 43310865201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2017-04-05 | 102000000 | 110058943 | 109950726 | 8058942.97 | 1500000 | 111035670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 111450726 | 111035670 | -415056 | 111264427 | B1:B8:Y:B::Y | ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
4 | E4U45 | 44147415201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2021-05-07 | 1428608 | 1539147 | 1506769 | 110538.52 | 0 | 1507294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506769 | 1507294 | 525 | 786261
4 | E4U70 | 44147015201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2021-05-07 | 2377932 | 2509209 | 2450657 | 131277.8 | 0 | 2450657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450657 | 2450657 | 0 | 1774051
4 | E4U73 | 44163315201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-03-05 | 3534228 | 3576916 | 3502409 | 42688.46 | 0 | 3641361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3502409 | 3641361 | 138951 | 4315430
4 | E4V05 | 44531515215 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2021-10-01 | 676628 | 676628 | 625424 | 0 | 0 | 625424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625424 | 625424 | 0 | 664967
4 | T4522 | 43631915201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 11069050 | 11069050 | 10764445 | 0 | 0 | 10777804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10764445 | 10777804 | 13359 | 13112789
4 | T4527 | 43689445201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 1334388 | 1536888 | 1454286 | 202500 | 0 | 1453044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454286 | 1453044 | -1243 | 2037845
4 | T4544 | 43984715201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 7223964 | 7285366 | 7107549 | 61402.36 | 0 | 7181559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7107549 | 7181559 | 74010 | 8446703
4 | T4546 | 42751625201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 11887967 | 11268781 | 11357998 | -619186.62 | 0 | 11493025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11357998 | 11493025 | 135027 | 11525995
4 | T4558 | 43975515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 635419 | 635419 | 615611 | 0 | 0 | 620127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615611 | 620127 | 4516 | 656409
4 | T4569 | 44177415201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-07-28 | 568800 | 568800 | 536000 | 0 | 0 | 537990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536000 | 537990 | 1990 | 559587
5 | E52A7 | 44194515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-02-02 | 1902006 | 1902006 | 1790542 | 0 | 0 | 1806715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1790542 | 1806715 | 16173 | 1695843
5 | E53A5 | 44113915201 | F813590186 | P&S PAVING & FLORIDA INDUSTRIAL | N/A | N/A | N/A | N/A | 2020-12-15 | 1298860 | 1434756 | 1402631 | 135895.79 | 0 | 1406993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1402631 | 1406993 | 4362 | 1281104
5 | E53A8 | 43632525201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 1713111 | 1713111 | 1691993 | 0 | 0 | 1691994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1691993 | 1691994 | 2 | 1970561
5 | E54A1 | 44326315201 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2021-01-05 | 985800 | 985800 | 930200 | 0 | 0 | 930222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930200 | 930222 | 22 | 1158387
5 | E56A2 | 44113415201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-07-07 | 1492986 | 1574717 | 1530292 | 81731.55 | 0 | 1583974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530292 | 1583974 | 53682 | 1629587
5 | E57A6 | 44713915201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2021-10-05 | 412340 | 412340 | 370378 | 0 | 0 | 370378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370378 | 370378 | 0 | 433631
5 | E58A6 | 44845415201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2021-12-07 | 710278 | 710278 | 702088 | 0 | 0 | 702088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702088 | 702088 | 0 | 626464
5 | E5Z92 | 43913815201 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2019-11-05 | 3448889 | 3384670 | 3383592 | -64219.29 | -477312 | 3336127 | -477312 | 0 | 0 | 0 | 0 | 0 | -477312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -477312 | 2906280 | 3336127 | 429848 | 3664930
5 | T5688 | 44103615201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-01-27 | 4662267 | 4737267 | 4453230 | 75000 | 0 | 4634578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4453230 | 4634578 | 181348 | 5545150
5 | T5700 | 44293215201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 1579513 | 1579513 | 1565201 | 0 | 0 | 1573943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565201 | 1573943 | 8741 | 1579888
5 | T5704 | 44113315201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 10173619 | 10199686 | 10360875 | 26067.2 | 0 | 11104726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10360875 | 11104726 | 743851 | 12810546
5 | T5708 | 44101415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 6490691 | 6568600 | 6865453 | 77909.15 | 0 | 7282431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6865453 | 7282431 | 416979 | 8517615
5 | T5709 | 44113525201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 8389168 | 8389168 | 8421882 | 0 | 0 | 8867242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8421882 | 8867242 | 445360 | 8661613
5 | T5716 | 43745115201 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2021-04-28 | 2263271 | 2365506 | 2386543 | 102234.42 | 0 | 2486885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2386543 | 2486885 | 100342 | 2040646
5 | T5722 | 44350715201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2021-07-28 | 1619760 | 1619760 | 1578600 | 0 | 0 | 1598533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1578600 | 1598533 | 19933 | 1216964
6 | E6L38 | 25168465201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2018-05-02 | 56331262 | 61782326 | 61740658 | 5451064.21 | 0 | 61738163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61740658 | 61738163 | -2495 | 56289000 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT
6 | E6M02 | 43952215201 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2021-05-27 | 284704 | 284704 | 265754 | 0 | 0 | 265754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265754 | 265754 | 0 | 309693
6 | E6M50 | 44196715201 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2020-11-19 | 873331 | 1042774 | 969094 | 169443.01 | 0 | 969094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969094 | 969094 | 0 | 905940
6 | E6M84 | 44253915201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-08-27 | 608490 | 625609 | 579687 | 17119 | 0 | 585088 | -3380 | 0 | 0 | 0 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579687 | 585088 | 5401 | 624646
6 | E6N00 | 44394015201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2022-02-24 | 510362 | 510362 | 479426 | 0 | 0 | 473360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479426 | 473360 | -6066 | 600250
6 | T6433 | 42440715201 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2018-06-13 | 67230501 | 72750415 | 73542354 | 5519913.82 | 4200000 | 73447058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 200000 | 0 | 4200000 | 4200000 | 77742354 | 73447058 | -4295296 | 76112026 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
6 | T6480 | 44018215201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-02-17 | 515515 | 515515 | 456395 | 0 | 0 | 456395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456395 | 456395 | 0 | 619720
6 | T6497 | 44516815201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 541368 | 541368 | 498909 | 0 | 0 | 498909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498909 | 498909 | 0 | 585941
7 | E7L92 | 43669715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 4257317 | 10851592 | 9627641 | 6594275.62 | 0 | 9622285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9627641 | 9622285 | -5356 | 4476953
7 | E7N30 | 43473625201 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2021-08-11 | 1297005 | 1297005 | 1237378 | 0 | 0 | 1237963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1237378 | 1237963 | 585 | 1230300
7 | E7N54 | 43480735201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-01-29 | 1422150 | 1360924 | 1310034 | -61225.94 | 0 | 1310789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1310034 | 1310789 | 755 | 1400000
7 | E7N99 | 44025425201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-07-14 | 1595242 | 1718861 | 1294242 | 123618.62 | 0 | 1316286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1294242 | 1316286 | 22044 | 1647300
7 | E7O21 | 44366415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-12-08 | 397254 | 397254 | 370201 | 0 | 0 | 370201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370201 | 370201 | 0 | 296700
7 | E7P10 | 44948515201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-03-09 | 403261 | 403261 | 392075 | 0 | 0 | 392075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392075 | 392075 | 0 | 420300
7 | E7R28 | 44769615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-05-10 | 2063258 | 2063258 | 2025710 | 0 | 0 | 2046401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025710 | 2046401 | 20691 | 1523991 | LBDB | LOW BID DESIGN BUILD
7 | E7R29 | 43982995201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-05-17 | 1887000 | 1887000 | 1837000 | 0 | 0 | 1837000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1837000 | 1837000 | 0 | 2845446 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR
7 | T7408 | 42895315201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-06-13 | 52309860 | 53697121 | 53886362 | 1387260.64 | 0 | 53722937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53886362 | 53722937 | -163425 | 61751000
7 | T7434 | 43734915201 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2019-06-12 | 5555515 | 5352409 | 5279909 | -203106.34 | 0 | 5286766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5279909 | 5286766 | 6857 | 5564432
7 | T7444 | 44108325201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 10034121 | 10350046 | 9871498 | 315924.97 | 0 | 9914253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9871498 | 9914253 | 42755 | 12990037
7 | T7446 | 43005125201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 4532943 | 4557685 | 4389265 | 24742.06 | 0 | 4384901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389265 | 4384901 | -4365 | 4923200
7 | T7459 | 44550725201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-02-17 | 1887858 | 1887858 | 1892749 | 0 | 0 | 1892749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1892749 | 1892749 | 0 | 2521800
7 | T7463 | 43762415201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 5399019 | 5449019 | 5629840 | 50000 | 0 | 5800518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5629840 | 5800518 | 170678 | 5600000
7 | T7465 | 44110415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 1187466 | 1227466 | 1221695 | 40000 | 0 | 1225383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221695 | 1225383 | 3688 | 941000
7 | T7474 | 44555415201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 755204 | 755204 | 776603 | 0 | 0 | 776603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776603 | 776603 | 0 | 918700
8 | E8S34 | 43798655201 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-03-09 | 878913 | 870049 | 830191 | -8863.5 | 0 | 830630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830191 | 830630 | 439 | 1113411
8 | E8S70 | 44262215201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-11-17 | 4113457 | 4113457 | 3489511 | 0 | 0 | 3489532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3489511 | 3489532 | 21 | 7220598

## Performance Measures
Sum of Work Order Preminum Cost | Responsible Party | [8 empty] | Total Original Amount | % of Original | Total Avoidable Premium Cost
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total
01 |  | 40233.96 |  | 9396.46 | 5787.13 | 108345.75 | -199979.96 | -36216.66 |  | 121671238 | 0.04555% | 55417.55
02 |  | 16367.99 |  | 271949.84 | 11487.16 | 1355835.41 | -399959.92 | 1255680.48 |  | 125658191 | 0.2386% | 299804.99
03 |  | 2970 | 0 | 3856887.11 | 1071085.57 | 248733.74 |  | 5179676.42 |  | 92746490 | 5.317% | 4930942.68
04 |  | 944.04 |  |  | 80819.93 | 318568.95 |  | 400332.92 |  | 142736984 | 0.05728% | 81763.97
05 |  | 9945.82 |  | 3562.9 | 2148.4 | 5554.98 |  | 21212.1 |  | 47142559 | 0.03321% | 15657.12
06 |  | 70087.7 |  | 0 | 3030853.3 | 0 |  | 3100941 |  | 126895533 | 2.444% | 3100941
07 |  | 140760.37 |  | 8481.99 | 154926.56 | 0 | -599939.88 | -295770.96 |  | 94984473 | 0.3202% | 304168.92
08 | [5 empty] | 0 |  | 0 |  | 4992370 | 0% | 0
Grand Total |  | 281309.88 | 0 | 4150278.3 | 4357108.05 | 2037038.83 | -1199879.76 | 9625855.3 |  | 756827838 | 1.161% | 8788696.23
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | (blank) | Grand Total |  | Total Avoidable Days SA
01 |  | 2 |  | 47 | 25 | 134 | 0 | 208 |  | 74
02 |  | 24 |  | 30 | 0 | 233 | 0 | 287 |  | 54
03 |  | 11 | 2 | 384 | 488 | 60 |  | 945 |  | 885
04 |  | 0 |  |  | 27 | 58 |  | 85 |  | 27
05 |  | 24 |  | 0 | 0 | 260 |  | 284 |  | 24
06 |  | 0 |  | 0 | 132 | 142 |  | 274 |  | 132
07 |  | 0 |  | 0 | 0 | 78 | 0 | 78 |  | 0
08 | [5 empty] | 0 |  | 0 |  | 0
Grand Total |  | 61 | 2 | 461 | 672 | 965 | 0 | 2161 |  | 1196
Sum of Days Added | Responsible Party
District | Avoidable, CEI Consultant | Avoidable, Design Consultant | Avoidable, In-House CEI | Avoidable, In-House Designer | Avoidable, Third Party | Unavoidable, No Remedial Action Required | Grand Total |  | Total Avoidable Days TE | Total Avoidable Days SA and TE | Total Original Days | % Avoidable Days
01 | [5 empty] | 157 | 157 |  | 0 | 74 | 4046 | 1.829%
02 |  |  |  | 91 |  | 160 | 251 |  | 91 | 145 | 5582 | 2.598%
03 |  | 163 |  |  |  | 404 | 567 |  | 163 | 1048 | 4843 | 21.64%
04 | [5 empty] | 67 | 67 |  | 0 | 27 | 4460 | 0.6054%
05 | [8 empty] | 0 | 24 | 3098 | 0.7747%
06 | [5 empty] | 66 | 66 |  | 0 | 132 | 2650 | 4.981%
07 | [5 empty] | 133 | 133 |  | 0 | 0 | 4933 | 0%
08 | [5 empty] | 26 | 26 |  | 0 | 0 | 463 | 0%
Grand Total |  | 163 |  | 91 |  | 1013 | 1267 |  | 254 | 1450 | 30075 | 4.821%

## Card 2 SA Data
District | Contract | Lead Fin Proj ID | SA Number | Card Type | Contingency SA? | Work Order | SA Code | Work Order Amount | Work Order Preminum Cost | Avoidable Code | Cost Recovery Code | Claim/Extend | Days Added | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1R65 | 43084915201 | 002 | 2 |  | 1 | 004 | 127200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | [13 empty] | Avoidable, CEI Consultant
01 | E1R65 | 43084915201 | 014 | 2 |  | 1 | 101 | 20409.25 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 | 014 | 2 |  | 2 | 115 | 38777.2 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Drainage Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 | 014 | 2 |  | 3 | 112 | 55111.96 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1R65 | 43084915201 | 014 | 2 |  | 4 | 503 | 86877.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R65 | 43084915201 | 014 | 2 |  | 5 | 012 | 31902.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1R65 | 43084915201 | 022 | 2 |  | 1 | 003 | 55876.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | E1R65 | 43084915201 | 022 | 2 |  | 2 | 503 | 558 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R65 | 43084915201 | 025 | 2 |  | 1 | 107 | 150000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1T56 | 44022515201 | 019 | 2 |  | 1 | 924 | 0 | 0 | 0 |  | N | 44 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1T56 | 44022515201 | 019 | 2 |  | 2 | 012 | 162129.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1T69 | 43485915201 | 006 | 2 |  | 1 | 012 | 72088.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1T69 | 43485915201 | 008 | 2 |  | 1 | 004 | 27632.35 | 27632.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
01 | E1T69 | 43485915201 | 008 | 2 |  | 2 | 001 | 6609.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1T69 | 43485915201 | 013 | 2 |  | 1 | 001 | 8827.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1T70 | 44634815201 | 005 | 2 |  | 1 | 106 | 67506.91 | 0 | 5 |  | N | 15 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | E1T70 | 44634815201 | 005 | 2 |  | 2 | 122 | 6842.74 | 0 | 2 |  | N | 2 | Avoidable, In-House Designer | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
01 | E1U26 | 44488315201 | 001 | 2 |  | 1 | 107 | -25916 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 004 | 2 |  | 1 | 003 | -1772543.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1709 | 20103225201 | 007 | 2 |  | 1 | 115 | 3897 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 008 | 2 |  | 1 | 305 | -557029.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 010 | 2 |  | 1 | 305 | -152551.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 011 | 2 |  | 1 | 305 | -737868.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 014 | 2 |  | 1 | 503 | 786282.89 | 79117.52 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1709 | 20103225201 | 018 | 2 | 850 | 1 | 105 | 6810.93 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 2 | 105 | 43240.26 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 3 | 024 | 15138.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 4 | 105 | 25394.3 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 5 | 105 | 18021.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 6 | 105 | 4026.12 | 4026.12 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 7 | 118 | 8902.23 | 8902.23 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1709 | 20103225201 | 018 | 2 | 850 | 8 | 007 | 1.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 018 | 2 | 850 | 9 | 024 | 8465.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 036 | 2 |  | 1 | 923 | 55001.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 039 | 2 |  | 1 | 106 | -116158.65 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1709 | 20103225201 | 042 | 2 |  | 1 | 924 | 6820 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
01 | T1709 | 20103225201 | 043 | 2 |  | 1 | 105 | 182000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 049 | 2 |  | 1 | 128 | 715754.35 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1709 | 20103225201 | 049 | 2 |  | 2 | 126 | 138841.1 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1709 | 20103225201 | 049 | 2 |  | 3 | 105 | 42788.61 | 2167.64 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 057 | 2 |  | 1 | 126 | 309944.66 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
01 | T1709 | 20103225201 | 058 | 2 |  | 1 | 107 | -2.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 059 | 2 |  | 1 | 928 | 40981.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 1 | 007 | 5323.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 060 | 2 | 850 | 2 | 001 | 11398.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1709 | 20103225201 | 060 | 2 | 850 | 3 | 107 | 16232.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 4 | 105 | 8067.69 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 5 | 105 | 4225.87 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 6 | 107 | 16233 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 7 | 001 | 5071.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1709 | 20103225201 | 060 | 2 | 850 | 8 | 107 | 6252.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 9 | 107 | 616 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 10 | 105 | 1595.88 | 1595.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 11 | 105 | 24203 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 060 | 2 | 850 | 12 | 107 | 780.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 064 | 2 |  | 1 | 012 | 8273.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1709 | 20103225201 | 067 | 2 | 850 | 1 | 001 | 32936.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | T1709 | 20103225201 | 070 | 2 |  | 1 | 105 | 25959 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 | 070 | 2 |  | 2 | 101 | 10551.45 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1709 | 20103225201 | 074 | 2 |  | 1 | 007 | -20743.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
01 | T1709 | 20103225201 | 081 | 2 |  | 3 | 115 | 4952.76 | 4952.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
01 | T1709 | 20103225201 | 082 | 2 |  | 1 | 118 | 45957.5 | 16957.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
01 | T1709 | 20103225201 | 087 | 2 |  | 1 | 128 | 113905.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1709 | 20103225201 | 092 | 2 |  | 1 | 022 | 51320.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1709 | 20103225201 | 092 | 2 |  | 2 | 024 | 14422.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1771 | 44035615201 | 004 | 2 |  | 1 | 128 | 20895.87 | 0 | 2 |  | N | 45 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | T1771 | 44035615201 | 009 | 2 |  | 1 | 015 | 5787.13 | 5787.13 | 5 |  | N | 10 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
01 | T1784 | 44210725201 | 001 | 2 |  | 1 | 112 | -48833.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
01 | T1784 | 44210725201 | 013 | 2 |  | 1 | 503 | 63815.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | E20B4 | 43391115201 | 013 | 2 |  | 1 | 119 | 135052.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Major Sturctural Component Changes | Plan Modifications | 2
02 | T2669 | 43544415201 | 005 | 2 |  | 1 | 001 | 1647.6 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 013 | 2 |  | 1 | 009 | 14584.48 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
02 | T2669 | 43544415201 | 020 | 2 |  | 1 | 001 | 47635.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 021 | 2 |  | 1 | 503 | 247556.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 | 025 | 2 | 850 | 1 | 503 | 0 | 4769.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 | 025 | 2 | 850 | 2 | 003 | 6765.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 | 025 | 2 | 850 | 3 | 003 | 3517.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 | 025 | 2 | 850 | 4 | 112 | 2285.4 | 2285.4 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2669 | 43544415201 | 025 | 2 | 850 | 5 | 003 | 14082.59 | 14082.59 | 1 |  | N | 0 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 | 025 | 2 | 850 | 6 | 001 | 18484.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 027 | 2 |  | 1 | 001 | 325407.99 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 033 | 2 |  | 1 | 001 | 29000 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2669 | 43544415201 | 036 | 2 |  | 1 | 012 | 147179.66 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2669 | 43544415201 | 050 | 2 |  | 1 | 503 | 0 | 0 | 0 |  | N | 84 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2732 | 21002455201 | 020 | 2 |  | 1 | 003 | 371906.87 | 0 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 1 | 001 | 40218.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 2 | 001 | 11423.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 3 | 023 | 17770.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 4 | 003 | 18283.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 5 | 001 | 4012.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 6 | 003 | 1521.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 021 | 2 | 850 | 8 | 101 | 11846.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2732 | 21002455201 | 021 | 2 | 850 | 9 | 003 | 7835.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 031 | 2 |  | 1 | 001 | 96454.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 | 033 | 2 |  | 1 | 112 | 97807.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2732 | 21002455201 | 034 | 2 |  | 1 | 012 | 2286491.33 | 1293012.1 | 0 |  | N | 53 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2756 | 43461915201 | 006 | 2 |  | 1 | 305 | -68366.53 | 0 | 0 |  | N | -30 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2756 | 43461915201 | 006 | 2 |  | 2 | 101 | 15228 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2756 | 43461915201 | 006 | 2 |  | 3 | 004 | 105868.52 | 2418.88 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2771 | 43948415201 | 004 | 2 | 850 | 1 | 001 | 13393 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 | 004 | 2 | 850 | 2 | 107 | 1650 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2771 | 43948415201 | 004 | 2 | 850 | 3 | 115 | 25144 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2771 | 43948415201 | 004 | 2 | 850 | 4 | 001 | 5668.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 | 004 | 2 | 850 | 5 | 001 | 15730.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 | 004 | 2 | 850 | 6 | 001 | 2852.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 | 012 | 2 |  | 1 | 101 | 2715.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2771 | 43948415201 | 017 | 2 | 850 | 1 | 001 | 37818.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 | 017 | 2 | 850 | 2 | 115 | 0.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2771 | 43948415201 | 017 | 2 | 850 | 3 | 001 | 2893.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 | 017 | 2 | 850 | 7 | 107 | 1298.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2771 | 43948415201 | 017 | 2 | 850 | 8 | 118 | 3129.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2771 | 43948415201 | 017 | 2 | 850 | 9 | 118 | 309.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2771 | 43948415201 | 017 | 2 | 850 | 10 | 118 | 6285.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
02 | T2771 | 43948415201 | 017 | 2 | 850 | 13 | 112 | 11871 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2771 | 43948415201 | 025 | 2 | 850 | 1 | 115 | 15852.94 | 8317.28 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2771 | 43948415201 | 025 | 2 | 850 | 2 | 105 | 6479.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2771 | 43948415201 | 025 | 2 | 850 | 3 | 115 | 2609.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2771 | 43948415201 | 025 | 2 | 850 | 4 | 001 | 660 | 660 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 | 025 | 2 | 850 | 5 | 003 | 9497.27 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2771 | 43948415201 | 025 | 2 | 850 | 6 | 101 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2771 | 43948415201 | 025 | 2 | 850 | 7 | 503 | 19447.42 | 3717 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2771 | 43948415201 | 025 | 2 | 850 | 8 | 001 | 3614.31 | 3614.31 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 | 040 | 2 | 850 | 1 | 001 | 42931.92 | 31824 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2784 | 44133715201 | 009 | 2 |  | 1 | 113 | 271949.84 | 271949.84 | 2 |  | N | 30 | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 012 | 2 |  | 1 | 003 | 392550 | 0 | 5 |  | N | 110 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860565201 | 015 | 2 |  | 1 | 503 | 10043.17 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 017 | 2 |  | 1 | 105 | 68404.65 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 1 | 007 | 2012.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 2 | 107 | 2660 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 3 | 008 | 984 | 984 | 5 |  | N | 0 | Avoidable, Third Party | R/W Requested Change | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 4 | 007 | -2012.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 5 | 007 | 2012.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 6 | 107 | -2660 | 0 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 7 | 107 | 2660 | 0 | 5 |  | N | 0 | Avoidable, Third Party | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 8 | 008 | -984 | 0 | 5 |  | N | 0 | Avoidable, Third Party | R/W Requested Change | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 9 | 008 | 984 | 0 | 5 |  | N | 0 | Avoidable, Third Party | R/W Requested Change | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 10 | 107 | 15041.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 11 | 107 | 50.65 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 13 | 107 | 3762 | 408.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 14 | 503 | 5260.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 15 | 107 | 401.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 16 | 107 | 33.5 | 33.5 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 17 | 009 | 13036.83 | 13036.83 | 2 |  | N | 0 | Avoidable, In-House Designer | Permit Related Issue | Changed Conditions | 1
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 18 | 107 | 42575.87 | 1107.16 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 031 | 2 | 850 | 19 | 003 | 2949.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860565201 | 032 | 2 |  | 1 | 503 | 177019 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 038 | 2 |  | 1 | 010 | 33964.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3O54 | 21860565201 | 040 | 2 |  | 1 | 503 | 101189.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 041 | 2 |  | 1 | 503 | 1518.3 | 1518.3 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 042 | 2 |  | 1 | 503 | 16377.44 | 16377.44 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 045 | 2 |  | 1 | 503 | 90746.27 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 045 | 2 |  | 2 | 503 | 34514.49 | 34514.49 | 5 |  | N | 3 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 045 | 2 |  | 3 | 116 | 10761.88 | 10761.88 | 2 |  | N | 0 | Avoidable, In-House Designer | Inadequate R/W Provided for Construction | Plan Modifications | 2
03 | E3O54 | 21860565201 | 049 | 2 |  | 1 | 919 | 59336.24 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Inadequate R/W Provided for Construction | Plan Modifications | 2
03 | E3O54 | 21860565201 | 062 | 2 |  | 1 | 861 | 76560 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
03 | E3O54 | 21860565201 | 063 | 2 |  | 1 | 861 | 135387.5 | 0 | 1 |  | C | 0 | Avoidable, Design Consultant | Claim Settlement | Claim Settlement | 10
03 | E3O54 | 21860565201 | 068 | 2 |  | 1 | 503 | 959832 | 955929.65 | 2 |  | C | 190 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 073 | 2 |  | 1 | 922 | 45777.6 | 45777.6 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 074 | 2 |  | 1 | 008 | 87736.2 | 87736.2 | 5 |  | C | 7 | Avoidable, Third Party | R/W Requested Change | Changed Conditions | 1
03 | E3O54 | 21860565201 | 075 | 2 |  | 1 | 503 | 1272867.56 | 1272867.56 | 2 |  | N | 135 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 075 | 2 |  | 2 | 503 | 81762.51 | 81762.51 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 077 | 2 |  | 1 | 503 | 1340000 | 1340000 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 | 085 | 2 |  | 1 | 005 | 131654.65 | 131654.65 | 5 |  | N | 31 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | E3O54 | 21860565201 | 086 | 2 |  | 1 | 005 | 5940.91 | 5940.91 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | E3O54 | 21860565201 | 087 | 2 |  | 1 | 005 | 6600.94 | 6600.94 | 5 |  | C | 1 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | E3O54 | 21860565201 | 096 | 2 |  | 1 | 001 | 1126139.26 | 176259.9 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3O54 | 21860565201 | 101 | 2 |  | 1 | 009 | 31370.15 | 31370.15 | 5 |  | C | 0 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
03 | E3O54 | 21860565201 | 110 | 2 |  | 1 | 117 | 12015.75 | 12015.75 | 5 |  | N | 0 | Avoidable, Third Party | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | E3O54 | 21860565201 | 113 | 2 | 850 | 1 | 107 | 116.3 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 117 | 2 |  | 1 | 010 | 21134.58 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
03 | E3O54 | 21860565201 | 128 | 2 |  | 1 | 113 | 522000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 129 | 2 |  | 1 | 927 | 130087.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 138 | 2 |  | 1 | 003 | 29347.88 | 0 | 4 |  | E | 2 | Avoidable, In-House CEI | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860565201 | 154 | 2 |  | 1 | 022 | 34679.65 | 34679.65 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3S63 | 4452481G201 | 012 | 2 |  | 1 | 101 | 89999.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3U03 | 43973915201 | 004 | 2 |  | 1 | 115 | 5510 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3529 | 21787535201 | 004 | 2 |  | 1 | 503 | 163156.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3529 | 21787535201 | 009 | 2 |  | 1 | 919 | 4874.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3529 | 21787535201 | 012 | 2 |  | 1 | 003 | 32185.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3529 | 21787535201 | 012 | 2 |  | 2 | 503 | -13248.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3529 | 21787535201 | 017 | 2 |  | 1 | 117 | 34515.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Access Management Issues Not Properly Addressed | Plan Modifications | 2
03 | T3529 | 21787535201 | 029 | 2 |  | 1 | 106 | 182495.18 | 182495.18 | 2 |  | N | 59 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3529 | 21787535201 | 030 | 2 |  | 1 | 922 | 59633.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
03 | T3529 | 21787535201 | 034 | 2 |  | 1 | 015 | 298035.45 | 298035.45 | 5 |  | N | 88 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | T3529 | 21787535201 | 041 | 2 |  | 1 | 012 | 73639 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
03 | T3529 | 21787535201 | 046 | 2 |  | 1 | 122 | 15563.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
03 | T3529 | 21787535201 | 057 | 2 |  | 1 | 015 | 380846.83 | 380846.83 | 5 |  | N | 247 | Avoidable, Third Party | Joint Project Agreement Utility Conflict | Changed Conditions | 1
03 | T3529 | 21787535201 | 065 | 2 |  | 1 | 107 | 50361.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3529 | 21787535201 | 066 | 2 |  | 1 | 107 | 53851 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3529 | 21787535201 | 087 | 2 |  | 1 | 107 | 6000 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | T3529 | 21787535201 | 096 | 2 |  | 1 | 007 | -19327.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | T3707 | 43938615201 | 003 | 2 |  | 1 | 101 | 14850 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | T3762 | 43972815201 | 002 | 2 |  | 1 | 101 | 1320 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4R96 | 43310865201 | 006 | 2 |  | 1 | 004 | 117825.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 016 | 2 |  | 1 | 004 | 239615.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 033 | 2 |  | 1 | 004 | 304975.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 040 | 2 | 850 | 1 | 023 | 13430.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 040 | 2 | 850 | 2 | 023 | 25303.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 060 | 2 |  | 1 | 503 | 276902.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 061 | 2 |  | 1 | 004 | 2792006.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 062 | 2 |  | 1 | 503 | 80121.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 062 | 2 |  | 2 | 003 | 210513.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 062 | 2 |  | 3 | 023 | 129933.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 062 | 2 |  | 4 | 004 | -381537.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 065 | 2 |  | 1 | 503 | 1359809.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 075 | 2 |  | 1 | 503 | 209339.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 077 | 2 |  | 1 | 004 | 229772.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 080 | 2 |  | 1 | 503 | 771170.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 083 | 2 |  | 1 | 923 | 107912.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 084 | 2 |  | 1 | 926 | 27163.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 085 | 2 |  | 1 | 004 | 91860 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 086 | 2 |  | 1 | 003 | 159093.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 092 | 2 |  | 1 | 004 | 79918.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
04 | E4R96 | 43310865201 | 094 | 2 |  | 1 | 503 | 9732.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 095 | 2 |  | 1 | 023 | 189959.39 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | E4R96 | 43310865201 | 097 | 2 |  | 1 | 003 | 468984.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 098 | 2 |  | 1 | 003 | 81400.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4R96 | 43310865201 | 099 | 2 |  | 1 | 023 | 202469.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4U45 | 44147415201 | 011 | 2 |  | 1 | 001 | 42936.13 | 0 | 0 |  | N | 30 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4U45 | 44147415201 | 024 | 2 |  | 1 | 001 | 67602.39 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4U70 | 44147015201 | 003 | 2 |  | 1 | 003 | 91430.61 | 0 | 5 |  | N | 10 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | E4U70 | 44147015201 | 017 | 2 |  | 1 | 001 | 39847.19 | 39847.19 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | E4U73 | 44163315201 | 014 | 2 | 850 | 1 | 850 | 35000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
04 | E4U73 | 44163315201 | 016 | 2 |  | 1 | 003 | 7688.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4527 | 43689445201 | 026 | 2 |  | 1 | 208 | 162500 | 162500 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
04 | T4527 | 43689445201 | 026 | 2 |  | 2 | 860 | 40000 | 40000 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Claim Settlement | Claim Settlement | 10
04 | T4544 | 43984715201 | 010 | 2 |  | 1 | 001 | 8502.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 | 013 | 2 |  | 1 | 101 | 49280 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4544 | 43984715201 | 016 | 2 |  | 1 | 101 | 3620 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4546 | 42751625201 | 006 | 2 |  | 1 | 305 | -4720.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4546 | 42751625201 | 007 | 2 |  | 1 | 305 | -142472.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4546 | 42751625201 | 007 | 2 |  | 2 | 107 | 57794 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4546 | 42751625201 | 012 | 2 |  | 1 | 024 | 3903.28 | 3903.28 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4546 | 42751625201 | 017 | 2 |  | 1 | 024 | 5511.97 | 5511.97 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4546 | 42751625201 | 029 | 2 |  | 1 | 305 | -615719.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
04 | T4546 | 42751625201 | 031 | 2 |  | 1 | 700 | 25633.94 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
04 | T4546 | 42751625201 | 034 | 2 |  | 1 | 022 | 50882.93 | 50882.93 | 5 |  | C | 0 | Avoidable, Third Party | Minor Changes | Minor Changes | 7
05 | E53A5 | 44113915201 | 002 | 2 |  | 1 | 101 | 4140 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | E53A5 | 44113915201 | 007 | 2 |  | 1 | 003 | 25353.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E53A5 | 44113915201 | 015 | 2 |  | 1 | 503 | 106401.92 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E56A2 | 44113415201 | 006 | 2 |  | 1 | 003 | 81731.55 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Z92 | 43913815201 | 028 | 2 |  | 1 | 105 | 6901.4 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E5Z92 | 43913815201 | 037 | 2 |  | 1 | 503 | -71120.69 | 0 | 0 |  | N | 145 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5688 | 44103615201 | 006 | 2 | 850 | 1 | 001 | 25000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5688 | 44103615201 | 012 | 2 | 850 | 1 | 001 | 0.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5688 | 44103615201 | 012 | 2 | 850 | 2 | 001 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5688 | 44103615201 | 012 | 2 | 850 | 3 | 001 | 10911.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5688 | 44103615201 | 012 | 2 | 850 | 4 | 107 | 1064.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5688 | 44103615201 | 012 | 2 | 850 | 5 | 112 | 2864.89 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5688 | 44103615201 | 012 | 2 | 850 | 6 | 001 | 4630.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5688 | 44103615201 | 012 | 2 | 850 | 7 | 001 | 2110.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5704 | 44113315201 | 006 | 2 |  | 1 | 128 | 8138.89 | 8138.89 | 1 |  | N | 24 | Avoidable, Design Consultant | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5704 | 44113315201 | 007 | 2 |  | 1 | 101 | 4509.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5704 | 44113315201 | 029 | 2 |  | 1 | 503 | 13419.16 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5708 | 44101415201 | 012 | 2 |  | 1 | 001 | 77909.15 | 0 | 0 |  | N | 10 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5716 | 43745115201 | 005 | 2 | 850 | 1 | 107 | 15712.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5716 | 43745115201 | 005 | 2 | 850 | 2 | 112 | 9844.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5716 | 43745115201 | 005 | 2 | 850 | 3 | 118 | 346.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5716 | 43745115201 | 011 | 2 |  | 1 | 106 | 18998.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5716 | 43745115201 | 011 | 2 |  | 2 | 108 | 1051.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | T5716 | 43745115201 | 011 | 2 |  | 3 | 101 | 479.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5716 | 43745115201 | 011 | 2 |  | 4 | 112 | 32705.52 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | E6L38 | 25168465201 | 001 | 2 |  | 1 | 503 | 4636415 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 | 010 | 2 |  | 1 | 208 | 104202.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
06 | E6L38 | 25168465201 | 022 | 2 |  | 1 | 923 | 48279.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
06 | E6L38 | 25168465201 | 036 | 2 |  | 1 | 305 | -76932.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | No Specification Provided for Work | Specification Modification | 3
06 | E6L38 | 25168465201 | 047 | 2 |  | 1 | 009 | 389135.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | E6L38 | 25168465201 | 056 | 2 |  | 1 | 503 | 5640.17 | 0 | 0 |  | C | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 | 056 | 2 |  | 2 | 503 | 162000 | 0 | 0 |  | C | 118 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 | 056 | 2 |  | 3 | 924 | 182323.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M50 | 44196715201 | 005 | 2 | 850 | 1 | 001 | 17322.72 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M50 | 44196715201 | 006 | 2 |  | 1 | 001 | 125777.01 | 0 | 0 |  | N | 24 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M84 | 44253915201 | 015 | 2 | 850 | 1 | 503 | 1768.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 001 | 2 |  | 1 | 305 | -309497 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 007 | 2 |  | 1 | 126 | 325063.43 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
06 | T6433 | 42440715201 | 010 | 2 | 850 | 1 | 108 | 48000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 | 010 | 2 | 850 | 2 | 107 | 58988.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 010 | 2 | 850 | 3 | 108 | 42973.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 | 010 | 2 | 850 | 4 | 103 | 37.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6433 | 42440715201 | 016 | 2 |  | 1 | 923 | 189128.97 | 0 | 0 |  | E | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 1 | 001 | 19567.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6433 | 42440715201 | 019 | 2 | 850 | 2 | 126 | 69654.03 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Computation Error | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 3 | 107 | 8962.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 4 | 103 | 20834.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 5 | 108 | 30074 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 | 019 | 2 | 850 | 6 | 007 | 907.65 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 022 | 2 | 850 | 1 | 105 | 136059.98 | 36093.57 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 022 | 2 | 850 | 2 | 007 | 13940.02 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 024 | 2 |  | 1 | 106 | 2924729.56 | 2924729.56 | 5 |  | N | 132 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6433 | 42440715201 | 028 | 2 | 850 | 1 | 105 | 64285.13 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 028 | 2 | 850 | 2 | 007 | 47074.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 028 | 2 | 850 | 3 | 005 | 34563.3 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
06 | T6433 | 42440715201 | 028 | 2 | 850 | 4 | 023 | 4076.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
06 | T6433 | 42440715201 | 039 | 2 |  | 1 | 112 | 215308.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 1 | 115 | 6899.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 2 | 023 | 975.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 3 | 007 | 4620 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 040 | 2 | 850 | 4 | 101 | 9349.84 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 5 | 115 | 22254.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 6 | 105 | 12823.17 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 7 | 007 | 75140.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 040 | 2 | 850 | 8 | 115 | 10885.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 9 | 112 | 2074.82 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 040 | 2 | 850 | 10 | 503 | 4976.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 044 | 2 | 850 | 1 | 503 | 130434.28 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 044 | 2 | 850 | 2 | 112 | 11708.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 044 | 2 | 850 | 3 | 017 | 7857.54 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 046 | 2 | 850 | 1 | 007 | 141260.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 046 | 2 | 850 | 2 | 115 | 8739.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 1 | 115 | 791.16 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 2 | 503 | 59464.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 048 | 2 | 850 | 3 | 105 | 25113.42 | 23950.92 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 4 | 123 | 36173.17 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Landscaping Changes | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 5 | 107 | 4716.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 6 | 107 | 11997.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 048 | 2 | 850 | 7 | 119 | 9964.98 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Major Sturctural Component Changes | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 1 | 115 | 16803.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 2 | 115 | 3611.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 3 | 009 | 34944.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 4 | 118 | 13730.42 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 5 | 107 | 11256.07 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 6 | 118 | 9625.76 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 7 | 105 | 10043.21 | 10043.21 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 8 | 131 | 14762.31 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Architectural Feature Related Issue | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 9 | 115 | 76552.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 10 | 503 | 10127.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 049 | 2 |  | 11 | 019 | 5235.11 | 5235.11 | 5 |  | N | 0 | Avoidable, Third Party | Conflict With Other Contractors | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 12 | 106 | 68828.57 | 68828.57 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 13 | 009 | 89292.29 | 2668.06 | 5 |  | N | 0 | Avoidable, Third Party | Permit Related Issue | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 14 | 001 | 95778.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 15 | 503 | 7920 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 049 | 2 |  | 16 | 112 | 125691.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
06 | T6433 | 42440715201 | 049 | 2 |  | 17 | 503 | 68425.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 049 | 2 |  | 18 | 503 | 155516.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 | 049 | 2 |  | 19 | 007 | 29392 | 29392 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
06 | T6433 | 42440715201 | 049 | 2 |  | 20 | 106 | 127644.23 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | E7L92 | 43669715201 | 001 | 2 |  | 1 | 007 | 7646917.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 | 007 | 2 |  | 1 | 305 | -4554.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 | 007 | 2 |  | 2 | 305 | -2039541.73 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 | 009 | 2 |  | 1 | 012 | 191560.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L92 | 43669715201 | 032 | 2 | 850 | 1 | 115 | 8994.73 | 8994.73 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 | 032 | 2 | 850 | 2 | 108 | 8250 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | E7L92 | 43669715201 | 032 | 2 | 850 | 3 | 112 | 6983.92 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | E7L92 | 43669715201 | 037 | 2 |  | 1 | 118 | 133624.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7L92 | 43669715201 | 037 | 2 |  | 2 | 118 | 47128.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7L92 | 43669715201 | 037 | 2 |  | 3 | 012 | 83187 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L92 | 43669715201 | 037 | 2 |  | 4 | 503 | 169393.4 | 0 | 0 |  | N | 28 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 047 | 2 |  | 1 | 850 | 21546.76 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | E7L92 | 43669715201 | 049 | 2 |  | 1 | 012 | 85058.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7L92 | 43669715201 | 052 | 2 |  | 1 | 503 | 180872.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 053 | 2 |  | 1 | 108 | 22808.88 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | E7L92 | 43669715201 | 059 | 2 |  | 1 | 118 | 5474.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | E7L92 | 43669715201 | 059 | 2 |  | 2 | 012 | 800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7N54 | 43480735201 | 001 | 2 |  | 1 | 305 | -61225.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | E7N99 | 44025425201 | 005 | 2 |  | 1 | 007 | 113967.76 | 113967.76 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | E7N99 | 44025425201 | 005 | 2 |  | 2 | 007 | 9650.86 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7408 | 42895315201 | 009 | 2 |  | 2 | 101 | 18400 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 013 | 2 |  | 1 | 101 | 1049.58 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 016 | 2 |  | 1 | 305 | -227169.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 1 | 105 | 14023.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 2 | 107 | 2293.06 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 3 | 105 | 8200 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 4 | 001 | 3648.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 | 029 | 2 | 850 | 5 | 503 | 2142.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 029 | 2 | 850 | 6 | 023 | 100.8 | 100.8 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 029 | 2 | 850 | 7 | 105 | 3708.41 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 8 | 115 | 5000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 9 | 107 | 8432.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 10 | 503 | 2200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 029 | 2 | 850 | 11 | 107 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 029 | 2 | 850 | 12 | 105 | 19501.01 | 19501.01 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 030 | 2 | 850 | 1 | 105 | 28713.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 030 | 2 | 850 | 2 | 115 | 2109.32 | 2109.32 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 030 | 2 | 850 | 3 | 105 | 677.33 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 031 | 2 |  | 1 | 105 | 3000 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 031 | 2 |  | 2 | 101 | -2909 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 031 | 2 |  | 3 | 106 | 4210 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7408 | 42895315201 | 031 | 2 |  | 4 | 004 | -9761.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 | 031 | 2 |  | 5 | 105 | 780 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 2 | 112 | 32617.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 3 | 128 | 9689.61 | 6198.23 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 4 | 128 | 7136.64 | 2283.76 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 5 | 108 | 22000.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 6 | 105 | 5000 | 5000 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 7 | 923 | 77575.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 8 | 105 | 3486.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 032 | 2 |  | 9 | 010 | 17000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7408 | 42895315201 | 032 | 2 |  | 10 | 128 | 9543.22 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7408 | 42895315201 | 036 | 2 |  | 1 | 503 | 2667 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 040 | 2 | 850 | 1 | 503 | 2919 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 040 | 2 | 850 | 2 | 012 | 1472.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7408 | 42895315201 | 040 | 2 | 850 | 3 | 107 | 5390.18 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 040 | 2 | 850 | 4 | 107 | 4283.97 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 040 | 2 | 850 | 5 | 105 | 682.08 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 040 | 2 | 850 | 6 | 503 | 4000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 040 | 2 | 850 | 7 | 118 | 5341.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7408 | 42895315201 | 043 | 2 | 850 | 1 | 850 | 1500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7408 | 42895315201 | 044 | 2 | 850 | 1 | 105 | 1980 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 2 | 115 | 2229.5 | 2229.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 3 | 115 | 138.12 | 138.12 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 4 | 107 | 7237.65 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 5 | 105 | 783.24 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 6 | 012 | 1183.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7408 | 42895315201 | 044 | 2 | 850 | 7 | 503 | 1882.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 044 | 2 | 850 | 8 | 010 | 12500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7408 | 42895315201 | 044 | 2 | 850 | 9 | 118 | 7461.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 12 | 115 | 8756.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 13 | 115 | -8756.55 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 044 | 2 | 850 | 14 | 115 | 8756.55 | 1953.46 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 051 | 2 |  | 1 | 108 | 112000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7408 | 42895315201 | 054 | 2 |  | 1 | 128 | 92000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7408 | 42895315201 | 057 | 2 | 850 | 1 | 105 | 1558.76 | 1558.76 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 057 | 2 | 850 | 2 | 122 | 7700 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | T7408 | 42895315201 | 057 | 2 | 850 | 3 | 009 | 47732.85 | 47732.85 | 1 |  | N | 0 | Avoidable, Design Consultant | Permit Related Issue | Changed Conditions | 1
07 | T7408 | 42895315201 | 057 | 2 | 850 | 4 | 118 | 4197.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7408 | 42895315201 | 057 | 2 | 850 | 5 | 115 | 10811.26 | 1953.46 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 058 | 2 | 850 | 1 | 850 | 31500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7408 | 42895315201 | 064 | 2 | 850 | 1 | 115 | 13432.19 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | T7408 | 42895315201 | 069 | 2 |  | 1 | 105 | 28265.29 | 28265.29 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 069 | 2 |  | 2 | 022 | 32524.9 | 32524.9 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 069 | 2 |  | 3 | 105 | 67073.39 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 | 069 | 2 |  | 4 | 503 | 23336.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 | 073 | 2 | 850 | 1 | 850 | 45000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
07 | T7408 | 42895315201 | 076 | 2 |  | 1 | 101 | 17745.74 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7408 | 42895315201 | 078 | 2 |  | 1 | 007 | 30989.14 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
07 | T7408 | 42895315201 | 078 | 2 |  | 2 | 112 | 10523.85 | 10523.85 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 | 078 | 2 |  | 3 | 112 | 47377.02 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 | 078 | 2 |  | 4 | 012 | 14109.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
07 | T7408 | 42895315201 | 079 | 2 |  | 1 | 001 | 56000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 | 079 | 2 |  | 2 | 928 | 29000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 | 080 | 2 |  | 1 | 009 | 450000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7434 | 43734915201 | 021 | 2 |  | 1 | 305 | -203106.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Permit Related Issue | Changed Conditions | 1
07 | T7444 | 44108325201 | 020 | 2 |  | 1 | 503 | 67002.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7444 | 44108325201 | 020 | 2 |  | 2 | 131 | 221716.08 | 0 | 0 |  | N | 50 | Unavoidable, No Remedial Action Required | Architectural Feature Related Issue | Plan Modifications | 2
07 | T7444 | 44108325201 | 020 | 2 |  | 3 | 108 | 27206.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7446 | 43005125201 | 009 | 2 |  | 1 | 128 | 4547.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
07 | T7446 | 43005125201 | 009 | 2 |  | 2 | 101 | 1243.4 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
07 | T7446 | 43005125201 | 009 | 2 |  | 3 | 115 | 12642.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | T7446 | 43005125201 | 009 | 2 |  | 4 | 010 | 6308.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
07 | T7465 | 44110415201 | 010 | 2 | 850 | 1 | 850 | 40000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
08 | E8S34 | 43798655201 | 002 | 2 |  | 1 | 305 | -8863.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Contingency Supplemental Agreement | Contingency | 13
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 001 | 5083.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 101 | 685.02 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 924 | 6200 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 107 | 14093.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 107 | 10663.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 128 | 7762.21 | 7762.21 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 503 | 247.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 105 | 4076.9 | 655.65 | 2 |  | N | 0 | Avoidable, In-House Designer | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 2 | 101 | 9786.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 101 | -9786.6 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 2 | 101 | 1565.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 3 | 115 | 12739.88 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 4 | 024 | 4895.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 1 | 101 | -1565.76 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1R65 | 43084915201 |  | 2 | CPI | 2 | 101 | 978.6 | 978.6 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
01 | E1T56 | 44022515201 |  | 2 | CPI | 1 | 012 | 3461.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | E1T69 | 43485915201 |  | 2 | CPI | 1 | 105 | 2756.99 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | E1T69 | 43485915201 |  | 2 | CPI | 2 | 112 | 7163 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
01 | E1T69 | 43485915201 |  | 2 | CPI | 1 | 010 | 2860.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Additional Work Due To Weather Damage | Weather Related Damage | 9
01 | E1T69 | 43485915201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
01 | E1T69 | 43485915201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
01 | E1U26 | 44488315201 |  | 2 | CPI | 1 | 101 | 1835.54 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 107 | 71706.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 107 | 25337.93 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 105 | 1594.37 | 1594.37 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 019 | 1300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict With Other Contractors | Changed Conditions | 1
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 107 | 2957.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 107 | 513.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 013 | 2057 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Test Projects | Changed Conditions | 1
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 105 | 1633.34 | 1633.34 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 012 | 17611.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1709 | 20103225201 |  | 2 | CPI | 1 | 105 | 5288.07 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
01 | T1784 | 44210725201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 27 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
01 | T1791 | 44034715201 |  | 2 | CPI | 1 | 012 | 1380.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1791 | 44034715201 |  | 2 | CPI | 1 | 924 | 0 | 0 | 0 |  | N | 49 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
01 | T1794 | 44477915201 |  | 2 | CPI | 1 | 108 | 3850 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
01 | T1794 | 44477915201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 14 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
01 | T1794 | 44477915201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 1 |  | N | 2 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | E20B4 | 43391115201 |  | 2 | CPI | 1 | 001 | 776.47 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C5 | 43317145201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C5 | 43317145201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C5 | 43317145201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C5 | 43317145201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C6 | 44119815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E20C6 | 44119815201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E20C6 | 44119815201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | E2X01 | 44031015201 |  | 2 | CPI | 1 | 001 | 5627.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | E2X01 | 44031015201 |  | 2 | CPI | 1 | 115 | 5600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2X01 | 44031015201 |  | 2 | CPI | 1 | 115 | 827.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2X01 | 44031015201 |  | 2 | CPI | 1 | 115 | 3080 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | E2X01 | 44031015201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 101 | 880 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 003 | 3206.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 107 | 38029.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 923 | 22148.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 923 | 2116.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 2 | 503 | 4769.35 | 4769.35 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 115 | 2198.36 | 2198.36 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 101 | 3375.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 101 | 3840.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 923 | 2055.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 108 | 10907.69 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 2 | 003 | 7260 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 003 | 31139.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 2 | 105 | 14476.16 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 3 | 004 | 3597.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 9 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2669 | 43544415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 1 |  | N | 6 | Avoidable, Design Consultant | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 107 | 21680 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 001 | 12188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 2 | 923 | 27018.82 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 923 | 3622.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 3900 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 001 | 12188 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 57041.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 2100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 2100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 004 | 4146.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 2 | 115 | -2100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 001 | 2363.06 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 003 | 3751.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2733 | 43761315201 |  | 2 | CPI | 1 | 012 | 2808.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2733 | 43761315201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
02 | T2733 | 43761315201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 20 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
02 | T2746 | 43761015201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 924 | 17157.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 924 | 4228 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 924 | 17157.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 924 | 17157.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 001 | 3383.13 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2756 | 43461915201 |  | 2 | CPI | 1 | 007 | 11487.16 | 11487.16 | 5 |  | N | 0 | Avoidable, Third Party | Local Government Agreement Modification | Changed Conditions | 1
02 | T2771 | 43948415201 |  | 2 | CPI | 1 | 112 | 36721.71 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2771 | 43948415201 |  | 2 | CPI | 1 | 112 | 22412.02 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2771 | 43948415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 6 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2771 | 43948415201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
02 | T2771 | 43948415201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
02 | T2771 | 43948415201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
02 | T2771 | 43948415201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 101 | 5390.05 | 534.78 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 105 | 19607.76 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
02 | T2777 | 44126215201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
02 | T2782 | 43808425201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
02 | T2807 | 44117315201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
02 | T2807 | 44117315201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
02 | T2807 | 44117315201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
03 | 21585 | 22023925201 |  | 2 | CPI | 1 | 503 | 1945.67 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | 21585 | 22023925201 |  | 2 | CPI | 2 | 503 | 25548.8 | 0 | 0 |  | N | 15 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | 21585 | 22023925201 |  | 2 | CPI | 3 | 107 | 6979.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | 21585 | 22023925201 |  | 2 | CPI | 4 | 105 | 5800 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | 21585 | 22023925201 |  | 2 | CPI | 6 | 503 | 198 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | 21585 | 22023925201 |  | 2 | CPI | 7 | 503 | 5104.08 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | 21585 | 22023925201 |  | 2 | CPI | 8 | 112 | 495 | 495 | 1 |  | N | 4 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | 21585 | 22023925201 |  | 2 | CPI | 9 | 112 | 2475 | 2475 | 1 |  | N | 4 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 503 | 600 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 107 | 100 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 503 | 11784.7 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 107 | 760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 001 | 74844 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | E3O54 | 21860565201 |  | 2 | CPI | 2 | 503 | 21633.46 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 007 | 5037.84 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 003 | 4037.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 503 | 760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860575201 |  | 2 | CPI | 2 | 003 | 4037.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 503 | -760 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860575201 |  | 2 | CPI | 2 | 003 | -4037.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 107 | 7520.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 503 | 23061.17 | 23061.17 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3O54 | 21860575201 |  | 2 | CPI | 2 | 107 | 619.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860575201 |  | 2 | CPI | 1 | 107 | 0.95 | 0.95 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 |  | 2 | CPI | 1 | 503 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T33 | 40674255201 |  | 2 | CPI | 1 | 101 | 19086.72 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3T33 | 40674255201 |  | 2 | CPI | 1 | 101 | 0 | 0 | 1 |  | N | 3 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 003 | 9075 | 3151.33 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 115 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 503 | 8500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 9 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | E3T37 | 44154715201 |  | 2 | CPI | 1 | 115 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | E3U03 | 43973915201 |  | 2 | CPI | 1 | 101 | 4042 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
03 | E3U03 | 43973915201 |  | 2 | CPI | 1 | 105 | 12119.48 | 12119.48 | 5 |  | N | 0 | Avoidable, Third Party | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3U03 | 43973915201 |  | 2 | CPI | 1 | 023 | 816.74 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3U03 | 43973915201 |  | 2 | CPI | 1 | 023 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
03 | E3U40 | 22253935201 |  | 2 | CPI | 1 | 004 | 4070 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | E3U40 | 22253935201 |  | 2 | CPI | 1 | 022 | 700 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | E3U40 | 22253935201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 503 | 8993.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 503 | 7560 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 503 | 7560 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3529 | 21787535201 |  | 2 | CPI | 2 | 112 | 19478.85 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 115 | 1977.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 115 | 5080.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 001 | 2901 | 2901 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 115 | 5080.9 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 503 | 25500 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 350 | -3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 005 | 8535.58 | 8535.58 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | T3529 | 21787535201 |  | 2 | CPI | 2 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 005 | 8535.58 | 1472.02 | 5 |  | N | 0 | Avoidable, Third Party | Utility Adjustments | Utility Delays | 11
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 350 | 3300 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 503 | 2833.6 | 0 | 5 |  | N | 0 | Avoidable, Third Party | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 003 | 4986.01 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3529 | 21787535201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 7 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3761 | 43776115201 |  | 2 | CPI | 1 | 115 | 4689.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3762 | 43972815201 |  | 2 | CPI | 1 | 350 | 4500 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Partnering | Partnering | 5
03 | T3778 | 44364315201 |  | 2 | CPI | 1 | 115 | 12960.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
03 | T3778 | 44364315201 |  | 2 | CPI | 2 | 003 | 2882 | 2750 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
03 | T3778 | 44364315201 |  | 2 | CPI | 3 | 012 | 1749 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | 1122 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 2 | 023 | 12651.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | -1122 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 2 | 023 | -12651.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | 12741.09 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 2 | 023 | 2750 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310945201 |  | 2 | CPI | 1 | 023 | 25482.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310945201 |  | 2 | CPI | 2 | 023 | 16140 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310945201 |  | 2 | CPI | 1 | 023 | 5879.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | 14187.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 2 | 023 | 23366.21 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4R96 | 43310865201 |  | 2 | CPI | 1 | 023 | 2455.49 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | E4U45 | 44147415201 |  | 2 | CPI | 1 | 105 | 7402.62 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | E4U73 | 44163315201 |  | 2 | CPI | 1 | 007 | 7624.56 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U73 | 44163315201 |  | 2 | CPI | 1 | 106 | 2310 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | E4U73 | 44163315201 |  | 2 | CPI | 1 | 007 | 1848.38 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
04 | E4U73 | 44163315201 |  | 2 | CPI | 2 | 122 | 4677.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | E4U73 | 44163315201 |  | 2 | CPI | 1 | 502 | 9022.05 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inaccurate Directions Given | CEI Actions/Inactions | 6
04 | T4522 | 43631915201 |  | 2 | CPI | 1 | 503 | 3775.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4522 | 43631915201 |  | 2 | CPI | 1 | 106 | 12615.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4522 | 43631915201 |  | 2 | CPI | 1 | 503 | 26267.66 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4522 | 43631915201 |  | 2 | CPI | 1 | 106 | 12901.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4522 | 43631915201 |  | 2 | CPI | 2 | 024 | 9396.42 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
04 | T4527 | 43689445201 |  | 2 | CPI | 1 | 105 | 3663 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
04 | T4527 | 43689445201 |  | 2 | CPI | 2 | 115 | 661.63 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 101 | 676.11 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 503 | 2325.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 108 | 2695 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 2 | 101 | 10427.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Necessary Pay Item Not Included | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 001 | 4565.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 001 | 578.98 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 023 | 5386.16 | 5386.16 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 022 | 9696 | 9696 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 2 | 003 | 2310 | 2310 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 122 | 2205.73 | 2205.73 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 024 | 6926.99 | 6926.99 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 2 | 024 | 6768.5 | 6768.5 | 5 |  | N | 0 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4544 | 43984715201 |  | 2 | CPI | 1 | 024 | 0 | 0 | 5 |  | N | 17 | Avoidable, Third Party | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
04 | T4546 | 42751625201 |  | 2 | CPI | 1 | 503 | 907.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4546 | 42751625201 |  | 2 | CPI | 1 | 023 | 968.93 | 968.93 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4546 | 42751625201 |  | 2 | CPI | 1 | 022 | 25536.68 | 25536.68 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
04 | T4546 | 42751625201 |  | 2 | CPI | 2 | 108 | 6539.86 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4546 | 42751625201 |  | 2 | CPI | 1 | 022 | 27021.28 | 27021.28 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4546 | 42751625202 |  | 2 | CPI | 1 | 022 | 894.59 | 894.59 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4546 | 42751625202 |  | 2 | CPI | 2 | 022 | 7869.3 | 7869.3 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4558 | 43975515201 |  | 2 | CPI | 1 | 001 | 8979.14 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4558 | 43975515201 |  | 2 | CPI | 2 | 012 | 2890.37 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Non Weather Related Damages | Changed Conditions | 1
04 | T4558 | 43975515201 |  | 2 | CPI | 1 | 012 | 412.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
04 | T4569 | 44177415201 |  | 2 | CPI | 1 | 108 | 944.04 | 944.04 | 1 |  | N | 0 | Avoidable, Design Consultant | Scope of Work Not Clearly Defined | Plan Modifications | 2
04 | T4569 | 44179615201 |  | 2 | CPI | 1 | 112 | 4357.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
04 | T4569 | 44179615201 |  | 2 | CPI | 2 | 023 | 1159.35 | 1159.35 | 5 |  | N | 0 | Avoidable, Third Party | Project Phasing Not Constructible | Plan Modifications | 2
05 | E52A7 | 44194515201 |  | 2 | CPI | 1 | 503 | 6316.67 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E52A7 | 44194515201 |  | 2 | CPI | 2 | 112 | 1624.6 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E52A7 | 44194515201 |  | 2 | CPI | 3 | 105 | 4713.25 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
05 | E52A7 | 44194515201 |  | 2 | CPI | 4 | 112 | 1468.09 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | E53A5 | 44113915201 |  | 2 | CPI | 1 | 503 | 1373.28 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E53A5 | 44113915201 |  | 2 | CPI | 1 | 503 | 5554.98 | 5554.98 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | E53A8 | 43632525201 |  | 2 | CPI | 1 | 003 | 626.31 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E53A8 | 43632525201 |  | 2 | CPI | 2 | 003 | 21797.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E53A8 | 43632525201 |  | 2 | CPI | 1 | 003 | 2148.4 | 2148.4 | 5 |  | N | 0 | Avoidable, Third Party | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E54A1 | 44326315201 |  | 2 | CPI | 1 | 012 | 2000 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | E57A6 | 44713915201 |  | 2 | CPI | 1 | 001 | 19485.75 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E57A6 | 44713915201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 12 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | E5Z92 | 43913815201 |  | 2 | CPI | 1 | 108 | 18563.04 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z92 | 43913815201 |  | 2 | CPI | 1 | 004 | 3887.44 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
05 | E5Z92 | 43913815201 |  | 2 | CPI | 2 | 003 | 3162.99 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | E5Z92 | 43913815201 |  | 2 | CPI | 1 | 108 | 0 | 0 | 0 |  | N | 2 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
05 | E5Z92 | 43913815201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 3 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
05 | T5688 | 44103615201 |  | 2 | CPI | 1 | 107 | 2518.32 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5688 | 44103615201 |  | 2 | CPI | 2 | 106 | 6752.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5688 | 44103615201 |  | 2 | CPI | 1 | 001 | 15727.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5688 | 44103615201 |  | 2 | CPI | 1 | 001 | 1 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5688 | 44103615201 |  | 2 | CPI | 1 | 001 | 0 | 0 | 0 |  | N | 19 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5700 | 44293215201 |  | 2 | CPI | 1 | 106 | 5795.45 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
05 | T5700 | 44293215201 |  | 2 | CPI | 1 | 112 | 1806.93 | 1806.93 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5700 | 44293215201 |  | 2 | CPI | 1 | 112 | 0 | 0 | 0 |  | N | 29 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5704 | 44113315201 |  | 2 | CPI | 1 | 101 | 14000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5704 | 44113315201 |  | 2 | CPI | 1 | 503 | 6902.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5704 | 44113315201 |  | 2 | CPI | 1 | 101 | 14000 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5704 | 44113315201 |  | 2 | CPI | 1 | 023 | 7260.79 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5704 | 44113315201 |  | 2 | CPI | 1 | 001 | 2472.91 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5704 | 44113315201 |  | 2 | CPI | 1 | 128 | 3562.9 | 3562.9 | 2 |  | N | 0 | Avoidable, In-House Designer | Inaccurate/Inadequate Survey Information | Plan Modifications | 2
05 | T5704 | 44113315201 |  | 2 | CPI | 1 | 118 | 3823 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5704 | 44113315201 |  | 2 | CPI | 1 | 101 | 2242 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
05 | T5704 | 44113315201 |  | 2 | CPI | 2 | 001 | 4248.5 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5708 | 44101415201 |  | 2 | CPI | 1 | 024 | 5384.29 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5708 | 44101415201 |  | 2 | CPI | 2 | 024 | 2050.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5708 | 44101415201 |  | 2 | CPI | 3 | 024 | 6818.3 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5709 | 44113515201 |  | 2 | CPI | 1 | 021 | 7344.48 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
05 | T5709 | 44113515201 |  | 2 | CPI | 1 | 115 | 2586.64 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5709 | 44113515201 |  | 2 | CPI | 2 | 115 | 4517.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
05 | T5709 | 44113515201 |  | 2 | CPI | 1 | 113 | 17013.33 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5709 | 44113515201 |  | 2 | CPI | 2 | 012 | 20466.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 118 | 31031.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 021 | 0 | 0 | 0 |  | N | 1 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 012 | 0 | 0 | 0 |  | N | 4 | Unavoidable, No Remedial Action Required | Non Weather Related Damages | Changed Conditions | 1
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 113 | 0 | 0 | 0 |  | N | 5 | Unavoidable, No Remedial Action Required | Pavement Design Modification | Plan Modifications | 2
05 | T5709 | 44113525201 |  | 2 | CPI | 1 | 118 | 0 | 0 | 0 |  | N | 6 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5716 | 43745115201 |  | 2 | CPI | 1 | 107 | 41083.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
05 | T5716 | 43745115201 |  | 2 | CPI | 1 | 112 | 4972.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
05 | T5716 | 43745115201 |  | 2 | CPI | 2 | 118 | 3943.78 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
05 | T5722 | 44350715201 |  | 2 | CPI | 1 | 503 | 5466.25 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
05 | T5722 | 44350715201 |  | 2 | CPI | 2 | 115 | 6173.24 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 007 | 4869.19 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 007 | 14607.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 503 | 41951 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 503 | 8258.12 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 926 | 5520.93 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 |  | 2 | CPI | 1 | 503 | 35897.34 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6L38 | 25168465201 |  | 2 | CPI | 2 | 503 | 15987.2 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | E6M02 | 43952215201 |  | 2 | CPI | 1 | 101 | 1812.89 | 0 | 2 |  | N | 0 | Avoidable, In-House Designer | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6M50 | 44196715201 |  | 2 | CPI | 1 | 001 | 1668.57 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M50 | 44196715201 |  | 2 | CPI | 1 | 001 | 8661.36 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M50 | 44196715201 |  | 2 | CPI | 1 | 001 | 3401 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M50 | 44196715201 |  | 2 | CPI | 2 | 001 | 5259.96 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M50 | 44196715201 |  | 2 | CPI | 1 | 101 | 6117.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6N00 | 44394015201 |  | 2 | CPI | 1 | 503 | 1042.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 |  | 2 | CPI | 1 | 107 | 33607.85 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 2 | 105 | 6183.68 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 3 | 108 | 3102 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 4 | 503 | 13385 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6433 | 42440715201 |  | 2 | CPI | 1 | 108 | 47546.81 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 2 | 107 | 31330.03 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 1 | 023 | 9680.37 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
06 | T6433 | 42440715201 |  | 2 | CPI | 1 | 103 | 5164.26 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6497 | 44516715201 |  | 2 | CPI | 1 | 023 | 5142.35 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Incorrect/Insufficient Subsoil Information | Plan Modifications | 2
06 | T6497 | 44516815201 |  | 2 | CPI | 1 | 503 | 4133 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
06 | T6497 | 44516815201 |  | 2 | CPI | 1 | 023 | 3085.41 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 924 | 1975 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 115 | 6262.43 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 007 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 115 | 17788.22 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 2 | 503 | 15628.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 115 | 3946.24 | 3946.24 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 2 | 115 | 8994.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 115 | -8994.73 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Drainage Modification | Plan Modifications | 2
07 | E7L92 | 43669715201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7L92 | 43669715201 |  | 2 | CPI | 2 | 122 | 4400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Bike, Pedestrian, ADA or Public Transit Changes | Plan Modifications | 2
07 | E7N54 | 43480735201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | E7N54 | 43480735201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
07 | E7N54 | 43480735201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
07 | E7N54 | 43480735201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 007 | 1300.94 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 105 | 5473.57 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 106 | 5503.28 | 5503.28 | 5 |  | N | 0 | Avoidable, Third Party | Existing/Proposed Utility Conflict | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 503 | 32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 112 | 1622.5 | 1622.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 001 | 23520.6 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 112 | -1622.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 112 | 1622.5 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 924 | 2530 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Project Phasing Not Constructible | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 3 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 4 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 5 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 6 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 7 | 004 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Design Std/Spec Change after Letting | Changed Conditions | 1
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 108 | 10550.67 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 001 | 10640.87 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 023 | 2729.02 | 2729.02 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895315201 |  | 2 | CPI | 2 | 023 | 100.8 | 100.8 | 5 |  | N | 0 | Avoidable, Third Party | Subsurface Conditions | Changed Conditions | 1
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 105 | 6410.64 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 105 | 685.5 | 685.5 | 1 |  | N | 0 | Avoidable, Design Consultant | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895615201 |  | 2 | CPI | 2 | 105 | 7039.83 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 107 | 9519.44 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 023 | -100.8 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 43473825201 |  | 2 | CPI | 1 | 503 | 1167 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 503 | 7581 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 107 | 15136.21 | 0 | 1 |  | N | 0 | Avoidable, Design Consultant | MOT Plan Modification | Plan Modifications | 2
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 503 | 4545.78 | 4545.78 | 1 |  | N | 0 | Avoidable, Design Consultant | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 41548935201 |  | 2 | CPI | 2 | 503 | 32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 503 | 32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 503 | -32400 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895315201 |  | 2 | CPI | 1 | 305 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895515201 |  | 2 | CPI | 1 | 305 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895515201 |  | 2 | CPI | 2 | 305 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7408 | 42895615201 |  | 2 | CPI | 1 | 105 | 1310.15 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7408 | 42895615201 |  | 2 | CPI | 2 | 107 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | MOT Plan Modification | Plan Modifications | 2
07 | T7434 | 43734915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7434 | 43734915201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7444 | 44108325201 |  | 2 | CPI | 1 | 108 | 1013.53 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7444 | 44108325201 |  | 2 | CPI | 1 | 108 | 14338.77 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Scope of Work Not Clearly Defined | Plan Modifications | 2
07 | T7444 | 44108325201 |  | 2 | CPI | 1 | 105 | 40214 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7444 | 44108325201 |  | 2 | CPI | 1 | 105 | 40215.11 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Conflict Between Pay Item & Pay Item Note | Plan Modifications | 2
07 | T7446 | 43005125201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7446 | 43005125201 |  | 2 | CPI | 1 | 118 | 4562.61 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Inadequate/Improper Signalization/Markings | Plan Modifications | 2
07 | T7463 | 43762415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 1 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 2 | 016 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 1 | 001 | 1476.68 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 1 | 001 | 13939.18 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
07 | T7463 | 43762415201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
07 | T7465 | 44110415201 |  | 2 | CPI | 1 | 003 | 0 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
07 | T7465 | 44110415201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
07 | T7465 | 44110415201 |  | 2 | CPI | 0 |  | 0 | -99989.98 |  |  |  | 0
08 | E8S34 | 43798655201 |  | 2 | CPI | 1 | 003 | 3519 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
08 | E8S70 | 44262215201 |  | 2 | CPI | 1 | 001 | 1404.55 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
08 | E8S70 | 44262235201 |  | 2 | CPI | 1 | 001 | 9753.97 | 0 | 0 |  | N | 0 | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1

## Card 2 TE Data
District | Contract ID | Lead Fin Proj ID | Reason Code | Old Reason Code | Days Added | TE Number | TE Seq No. | Avoidable Code | Claim/Extend | Responsible Party | Reason Description | Reason Group | Sort Code
01 | E1T56 | 44022515201 | 924 |  | 90 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required
05 | [9 empty] | Avoidable, Third Party
01 | [9 empty] | Avoidable, Third Party
01 | [9 empty] | Avoidable, In-House CEI
01 | [9 empty] | Avoidable, CEI Consultant
01 | E1T69 | 43485915201 | 924 |  | 33 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required
01 | E1T69 | 43485915201 | 924 |  | 34 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required
02 | E20F6 | 43439815201 | 106 |  | 14 | 005 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Existing/Proposed Utility Conflict | Plan Modifications | 2
02 | T2669 | 43544415201 | 503 |  | 10 | 042 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2669 | 43544415201 | 924 |  | 11 | 048 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
02 | T2732 | 21002455201 | 401 |  | 27 | 038 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
02 | T2732 | 21002455201 | 003 |  | 16 | 047 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2732 | 21002455201 | 405 |  | 5 | 050 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Harmonize Project With Adjacent Project | Changed Conditions | 1
02 | T2733 | 43761315201 | 005 |  | 7 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2771 | 43948415201 | 924 |  | 53 | 037 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Utility Adjustments | Utility Delays | 11
02 | T2777 | 44126215201 | 126 |  | 17 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Computation Error | Plan Modifications | 2
02 | T2784 | 44133715201 | 113 |  | 91 | 018 | 1 | 2 | N | Avoidable, In-House Designer | Pavement Design Modification | Plan Modifications | 2
03 | E3O54 | 21860565201 | 130 |  | 9 | 013 | 1 | 1 | N | Avoidable, Design Consultant | Indecision/Delayed Response | Plan Modifications | 2
03 | E3O54 | 21860565201 | 924 |  | 8 | 144 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Indecision/Delayed Response | Plan Modifications | 2
03 | E3S63 | 4452481G201 | 700 |  | 154 | 009 | 1 | 1 | N | Avoidable, Design Consultant | Minor Changes | Minor Changes | 7
03 | E3S63 | 4452481G201 | 924 |  | 14 | 022 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | E3S63 | 4452481G201 | 700 |  | 106 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | E3S63 | 4452481G201 | 700 |  | 200 | 033 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | E3T37 | 44154715201 | 924 |  | 9 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | E3T55 | 43974015201 | 924 |  | 42 | 018 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Minor Changes | Minor Changes | 7
03 | T3707 | 43938615201 | 101 |  | 25 | 007 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
04 | E4U45 | 44147415201 | 016 |  | 15 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Material/Suppliers No Longer Available | Changed Conditions | 1
04 | E4U70 | 44147015201 | 401 |  | 10 | 013 | 1 | 0 | C | Unavoidable, No Remedial Action Required | Material Shortage | Material Shortage | 12
04 | E4U70 | 44147015201 | 001 |  | 4 | 013 | 2 | 0 | C | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4527 | 43689445201 | 924 |  | 20 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4558 | 43975515201 | 924 |  | 13 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
04 | T4558 | 43975515201 | 924 |  | 5 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M50 | 44196715201 | 101 |  | 1 | 020 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Necessary Pay Item Not Included | Plan Modifications | 2
06 | E6M50 | 44196715201 | 001 |  | 20 | 024 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Subsurface Conditions | Changed Conditions | 1
06 | E6M84 | 44253915201 | 007 |  | 19 | 014 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
06 | T6497 | 44516815201 | 503 |  | 26 | 015 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 007 |  | 32 | 040 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Local Government Agreement Modification | Changed Conditions | 1
07 | E7L92 | 43669715201 | 503 |  | 46 | 048 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | E7L92 | 43669715201 | 924 |  | 26 | 054 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
07 | T7459 | 44550725201 | 924 |  | 29 | 012 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S70 | 44262215201 | 503 |  | 7 | 011 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6
08 | E8S70 | 44262215201 | 924 |  | 19 | 016 | 1 | 0 | N | Unavoidable, No Remedial Action Required | Change Resulting from an Engineering Decision | CEI Actions/Inactions | 6

## Detailed Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 SA Data - PPP
Note: There were no PPP projects passed in this quarter.

## Card 2 TE Data - PPP
Note: There were no PPP projects passed in this quarter.

## Sheet1 (hidden)
01CO | 01 | T1709 | 20103225201 | 2018-05-23 | QTR4 | 17/18 | 3 | 27 | 907 | 1313 | 1313 | 0 | 0 | 0 | 406 | 0 | 80840173 | 150000 | 80690173 | 80370929 | 81141842 | -44000 | 0 | -44000 | 81097842 | 80911304 | -90555 | -469244 | 327 | 0 | 0 | -1709315 | 0 | 0 | 0 | 1772025 | 38602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786283 | 79118 | 0 | 0 | 89346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -509110 | 117720 | F981255690 | SACYR CONSTRUCCION SA | N/A | N/A | N/A | N/A | 2022-09-16 | QTR1 | 22/23 | 2022-05-19 | QTR4 | 21/22 | 106 | 83257742.89 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 79 | 0 | 0 | -1447449 | 0 |  | CO | 9 | 01co | 1 | 9
01CO | 01 | T1745 | 43697915201 | 2019-04-24 | QTR4 | 18/19 | 1 | 0 | 199 | 285 | 281 | 4 | 0 | 0 | 86 | 0 | 2042506 | 50000 | 1992506 | 2042506 | 1941189 | 0 | 0 | 0 | 1941189 | 1938502 | -2688 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F571191566 | FLORIDA SAFETY CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-11-02 | QTR2 | 22/23 | 2020-08-04 | QTR1 | 20/21 | 115 | 1951298.09 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 6 | 01do | 10 | 15
01CO | 01 | T1763 | 44147515201 | 2019-07-31 | QTR1 | 19/20 | 1 | 0 | 200 | 215 | 183 | 32 | 0 | 0 | 15 | 0 | 1200000 | 0 | 1200000 | 1200000 | 1176976 | 0 | 0 | 0 | 1176976 | 1176787 | -190 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-10-24 | QTR2 | 22/23 | 2020-06-30 | QTR4 | 19/20 | 118 | 950443.89 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO | 10 | 02co | 16 | 25
01CO | 01 | T1771 | 44035615201 | 2021-08-25 | QTR1 | 21/22 | 1 | 2 | 110 | 191 | 191 | 0 | 0 | 0 | 26 | 55 | 879962 | 0 | 879962 | 906645 | 906645 | 0 | 0 | 0 | 906645 | 906645 | 0 | 26683 | 22 | 0 | 10 | 5787 | 5787 | 0 | 45 | 20896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 26683 | 5787 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-12 | QTR2 | 22/23 | 2022-07-26 | QTR1 | 22/23 | 108 | 847815.4 | B0 | ACC - LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0 |  | CO | 6 | 02do | 26 | 31
01CO | 01 | T1784 | 44210725201 | 2021-02-17 | QTR3 | 20/21 | 3 | 2 | 180 | 234 | 234 | 0 | 0 | 0 | 27 | 27 | 1091540 | 50000 | 1041540 | 1106522 | 1056999 | 0 | 0 | 0 | 1056999 | 1056999 | 43887 | 14982 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | -48834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 63816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 14982 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 | 2022-03-23 | QTR3 | 21/22 | 108 | 1402962.42 |  |  | 27 | 19 | 0 | 0 | 0 | 0 |  | CO | 11 | 03co | 32 | 42
01CO | 01 | T1791 | 44034715201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 80 | 227 | 280 | -53 | 53 | 0 | 98 | 49 | 610558 | 24380 | 586178 | 610558 | 610907 | -3490 | 0 | -3490 | 607417 | 607417 | 0 | 0 | 126 | 0 | 0 | 1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381 | 0 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 | 2022-03-07 | QTR3 | 21/22 | 108 | 735869.89 | B0 | ACC - LUMP SUM | 49 | 21 | 0 | 0 | 0 | 0 |  | CO | 11 | 03do | 43 | 53
01CO | 01 | T1794 | 44477915201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 270 | 353 | 352 | 1 | 0 | 0 | 67 | 16 | 2947759 | 50000 | 2897759 | 2947759 | 2877401 | 0 | 0 | 0 | 2877401 | 2926249 | 48848 | 0 | 47 | 0 | 14 | 0 | 0 | 0 | 2 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 3850 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2022-05-18 | QTR4 | 21/22 | 108 | 2695046.26 |  |  | 16 | 20 | 0 | 0 | 0 | 0 |  | CO | 6 | 04co | 54 | 59
01CO | 01 | T1809 | 44624015201 | 2021-05-26 | QTR4 | 20/21 | 2 | 0 | 130 | 145 | 145 | 0 | 0 | 0 | 15 | 0 | 569569 | 27338 | 542231 | 569569 | 545539 | 0 | 0 | 0 | 545539 | 545539 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 | 2022-06-18 | QTR4 | 21/22 | 113 | 560699.14 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO | 5 | 04do | 60 | 64
01CO | 01 | T1823 | 44212415201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 85 | 96 | 96 | 0 | 0 | 0 | 11 | 0 | 631249 | 31254 | 599995 | 631249 | 599995 | 0 | 0 | 0 | 599995 | 599995 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-12 | QTR1 | 22/23 | 2022-04-12 | QTR4 | 21/22 | 118 | 604209.87 | B0 | ACC - LUMP SUM | 0 | 7 | 0 | 0 | 0 | 0 |  | CO | 7 | 05co | 65 | 71
01DO | 01 | E1R65 | 43084915201 | 2019-07-18 | QTR1 | 19/20 | 2 | 4 | 825 | 967 | 964 | 3 | 0 | 0 | 142 | 0 | 24334683 | 150000 | 24184683 | 24901396 | 24523563 | 0 | 0 | 0 | 24523563 | 24408360 | -115203 | 566713 | 87 | 0 | 0 | 220062 | 0 | 0 | 0 | 315298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87683 | 0 | 0 | 0 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627938 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2022-06-24 | QTR4 | 21/22 | 113 | 29026731.23 |  |  | 0 | 55 | 0 | 0 | 0 | 0 | T | DO | 8 | 05do | 72 | 79
01DO | 01 | E1T56 | 44022515201 | 2020-09-03 | QTR1 | 20/21 | 1 | 1 | 440 | 621 | 621 | 0 | 0 | 0 | 137 | 44 | 2201700 | 50000 | 2151700 | 2363829 | 2312290 | 0 | 0 | 0 | 2312290 | 2312290 | 27726 | 162129 | 98 | 0 | 0 | 165590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165590 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-10-12 | QTR2 | 22/23 | 2022-08-28 | QTR1 | 22/23 | 118 | 2100535.65 | A3 | ICC - DESIGN/BUILD - MINOR | 0 | 39 | 0 | 0 | 0 | 0 |  | DO | 3 | 06co | 80 | 82
01DO | 01 | E1T69 | 43485915201 | 2021-02-18 | QTR3 | 20/21 | 1 | 3 | 200 | 291 | 290 | 1 | 0 | 0 | 91 | 0 | 2190000 | 50000 | 2140000 | 2305157 | 2299703 | 0 | 0 | 0 | 2299703 | 2299703 | 0 | 115157 | 72 | 0 | 0 | 115157 | 27632 | 0 | 0 | 9920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127938 | 27632 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-10-25 | QTR2 | 22/23 | 2022-08-03 | QTR1 | 22/23 | 115 | 1490902.95 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO | 5 | 06do | 83 | 87
01DO | 01 | E1T70 | 44634815201 | 2021-02-18 | QTR3 | 20/21 | 1 | 1 | 100 | 146 | 168 | -22 | 22 | 0 | 29 | 17 | 135271 | 6781 | 128490 | 209621 | 221728 | -22990 | 0 | -22990 | 198738 | 198738 | 0 | 74350 | 21 | 0 | 0 | 0 | 0 | 0 | 17 | 74350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 74350 | 0 | F831207624 | AF USA CONSTRUCTION CORP | N/A | N/A | N/A | N/A | 2022-11-08 | QTR2 | 22/23 | 2021-12-21 | QTR2 | 21/22 | 115 | 152017.02 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | DO | 8 | 07co | 88 | 95
01DO | 01 | E1U26 | 44488315201 | 2021-07-15 | QTR1 | 21/22 | 1 | 1 | 150 | 161 | 159 | 2 | 0 | 0 | 11 | 0 | 1247303 | 50000 | 1197303 | 1221387 | 1196429 | 0 | 0 | 0 | 1196429 | 1294630 | 98201 | -25916 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | -24080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24080 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-09-06 | QTR1 | 22/23 | 2022-07-15 | QTR1 | 22/23 | 118 | 1391481.98 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO | 8 | 07do | 96 | 103
01DO | 01 | E1U27 | 44430815201 | 2021-08-19 | QTR1 | 21/22 | 1 | 0 | 170 | 188 | 188 | 0 | 0 | 0 | 18 | 0 | 748965 | 26664 | 722301 | 748965 | 763405 | 0 | 0 | 0 | 763405 | 763405 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-10-28 | QTR2 | 22/23 | 2022-07-01 | QTR1 | 22/23 | 115 | 748490.78 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 104 | 103
02CO | 02 | T2669 | 43544415201 | 2017-10-25 | QTR2 | 17/18 | 1 | 9 | 1200 | 1479 | 1493 | -14 | 14 | 0 | 177 | 102 | 36475260 | 150000 | 36325260 | 37438271 | 37041923 | -100058 | 0 | -100058 | 36941865 | 37105576 | 163711 | 963012 | 81 | 0 | 9 | 653509 | 14083 | 0 | 9 | 75992 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 84 | 252326 | 4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 102 | 981827 | 21137 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2022-08-03 | QTR1 | 22/23 | 2022-03-04 | QTR3 | 21/22 | 216 | 37281732.61 |  |  | 15 | 86 | 0 | 0 | 0 | 0 |  | CO | 2 | 08do | 104 | 105
02CO | 02 | T2732 | 21002455201 | 2019-02-27 | QTR3 | 18/19 | 2 | 5 | 700 | 1008 | 1008 | 0 | 0 | 0 | 195 | 113 | 23611052 | 160000 | 23451052 | 26613712 | 27048870 | 0 | 0 | 0 | 27048870 | 26998931 | -49939 | 3002661 | 79 | 16 | 106 | 2872785 | 1293012 | 0 | 7 | 194376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 48 | 113 | 3084932 | 1293012 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-25 | QTR1 | 22/23 | 2022-02-13 | QTR3 | 21/22 | 216 | 26976039.76 |  |  | 7 | 68 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2733 | 43761315201 | 2019-03-27 | QTR3 | 18/19 | 1 | 0 | 150 | 226 | 266 | -40 | 40 | 0 | 54 | 22 | 1682750 | 50000 | 1632750 | 1682750 | 1542573 | -66600 | 0 | -66600 | 1475973 | 1522452 | 46478 | 0 | 25 | 0 | 22 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 22 | 2808 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-20 | QTR2 | 22/23 | 2020-03-19 | QTR3 | 19/20 | 209 | 1962691.97 |  |  | 22 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2746 | 43761015201 | 2019-08-28 | QTR1 | 19/20 | 1 | 0 | 150 | 191 | 191 | 0 | 0 | 0 | 36 | 5 | 3853383 | 50000 | 3803383 | 3853383 | 3793632 | 0 | 0 | 0 | 3793632 | 3720865 | -72767 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-23 | QTR1 | 22/23 | 2020-05-22 | QTR4 | 19/20 | 209 | 4960764.49 |  |  | 5 | 17 | 0 | 0 | 0 | 0 |  | CO |  | 0
02CO | 02 | T2756 | 43461915201 | 2020-01-29 | QTR3 | 19/20 | 1 | 1 | 600 | 789 | 732 | 57 | 0 | 0 | 219 | -30 | 22598230 | 150000 | 22448230 | 22650960 | 22469154 | 0 | 0 | 0 | 22469154 | 22293734 | -175420 | 52730 | 133 | 0 | 0 | 120739 | 2419 | 0 | 0 | 15228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | 67600 | 2419 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 | 2022-05-12 | QTR4 | 21/22 | 216 | 25503399.26 |  |  | 0 | 86 | 0 | -30 | -68367 | 0 |  | CO
02CO | 02 | T2771 | 43948415201 | 2020-04-29 | QTR4 | 19/20 | 1 | 5 | 340 | 623 | 598 | 25 | 0 | 0 | 257 | 26 | 6443949 | 59897 | 6384052 | 6682981 | 6771329 | 0 | 0 | 0 | 6771329 | 6801375 | 56442 | 239033 | 212 | 0 | 7 | 135060 | 36098 | 0 | 16 | 139779 | 8317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 19447 | 3717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 294287 | 48133 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-13 | QTR2 | 22/23 | 2022-04-20 | QTR4 | 21/22 | 208 | 5909474.87 |  |  | 26 | 45 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2777 | 44126215201 | 2020-07-29 | QTR1 | 20/21 | 1 | 0 | 180 | 245 | 242 | 3 | 0 | 0 | 63 | 2 | 3565965 | 50000 | 3515965 | 3565965 | 3516567 | 0 | 0 | 0 | 3516567 | 3467651 | -48916 | 0 | 24 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2 | 24998 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 | 2021-06-14 | QTR4 | 20/21 | 214 | 4228844.94 |  |  | 2 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2782 | 43808425201 | 2021-03-31 | QTR3 | 20/21 | 2 | 0 | 200 | 272 | 272 | 0 | 0 | 0 | 48 | 24 | 737737 | 38937 | 698800 | 737737 | 693945 | 0 | 0 | 0 | 693945 | 694158 | 2007 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-11-03 | QTR2 | 22/23 | 2022-07-12 | QTR1 | 22/23 | 208 | 807642.54 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2784 | 44133715201 | 2020-07-29 | QTR1 | 20/21 | 1 | 1 | 200 | 493 | 504 | -11 | 11 | 0 | 263 | 30 | 8801980 | 90457 | 8711523 | 9073930 | 8672744 | -41316 | 0 | -41316 | 8631428 | 8592793 | -38635 | 271950 | 134 | 0 | 0 | 0 | 0 | 91 | 30 | 271950 | 271950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 30 | 271950 | 271950 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-09 | QTR1 | 22/23 | 2022-03-03 | QTR3 | 21/22 | 209 | 9187133.29 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2807 | 44117315201 | 2021-03-31 | QTR3 | 20/21 | 1 | 0 | 130 | 155 | 152 | 3 | 0 | 0 | 6 | 19 | 702242 | 21655 | 680587 | 702242 | 666627 | 0 | 0 | 0 | 666627 | 668500 | 2938 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-08-23 | QTR1 | 22/23 | 2022-06-03 | QTR4 | 21/22 | 208 | 504802.01 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E20B4 | 43391115201 | 2020-09-16 | QTR1 | 20/21 | 1 | 1 | 522 | 567 | 497 | 70 | 0 | 0 | 45 | 0 | 3259226 | 50000 | 3209226 | 3394278 | 3308924 | 0 | 0 | 0 | 3308924 | 3308924 | 0 | 135052 | 3 | 0 | 0 | 776 | 0 | 0 | 0 | 135052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135829 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-12-01 | QTR2 | 22/23 | 2022-08-08 | QTR1 | 22/23 | 208 | 3309179.07 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20C3 | 44120015201 | 2020-12-16 | QTR2 | 20/21 | 1 | 0 | 300 | 340 | 275 | 65 | 0 | 0 | 40 | 0 | 1044910 | 50000 | 994910 | 1044910 | 947808 | 0 | 0 | 0 | 947808 | 947808 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-07-21 | QTR1 | 22/23 | 2022-03-16 | QTR3 | 21/22 | 208 | 1524812.56 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20C5 | 43317145201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 180 | 241 | 241 | 0 | 0 | 0 | 55 | 6 | 1735613 | 50000 | 1685613 | 1735613 | 1621490 | 0 | 0 | 0 | 1621490 | 1633712 | 12222 | 0 | 43 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-01 | QTR1 | 22/23 | 2022-05-05 | QTR4 | 21/22 | 214 | 2079687.2 |  |  | 6 | 12 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20C6 | 44119815201 | 2021-03-17 | QTR3 | 20/21 | 1 | 0 | 210 | 242 | 240 | 2 | 0 | 0 | 23 | 9 | 982581 | 50000 | 932581 | 982581 | 924634 | 0 | 0 | 0 | 924634 | 924634 | 0 | 0 | 8 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-19 | QTR1 | 22/23 | 2022-05-12 | QTR4 | 21/22 | 208 | 1257557.66 |  |  | 9 | 15 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20F6 | 43439815201 | 2021-07-21 | QTR1 | 21/22 | 1 | 0 | 120 | 143 | 143 | 0 | 0 | 0 | 23 | 0 | 763880 | 40335 | 723545 | 763880 | 682483 | 0 | 0 | 0 | 682483 | 682483 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 | 2022-06-16 | QTR4 | 21/22 | 208 | 820679.5 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2X01 | 44031015201 | 2018-05-16 | QTR4 | 17/18 | 1 | 0 | 400 | 473 | 473 | 0 | 0 | 0 | 71 | 2 | 9399433 | 98455 | 9300978 | 9399433 | 9453262 | 0 | 0 | 0 | 9453262 | 9483339 | 30076 | 0 | 41 | 0 | 0 | 5627 | 0 | 0 | 2 | 9507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15134 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-12-20 | QTR2 | 22/23 | 2019-12-20 | QTR2 | 19/20 | 209 | 9867068.78 |  |  | 2 | 30 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | 21585 | 22023925201 | 2002-06-19 | QTR4 | 01/02 | 1 | 0 | 270 | 368 | 426 | -58 | 58 | 0 | 0 | 0 | 943334 | 50000 | 893334 | 1116958 | 1163142 | 0 | 0 | 0 | 1163142 | 1088438 | -74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 32797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 123250 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-07-06 | QTR1 | 22/23 | 2022-01-14 | QTR3 | 21/22 | 313 | 0 |  |  | 26 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3529 | 21787535201 | 2017-05-24 | QTR4 | 16/17 | 4 | 14 | 890 | 1701 | 1701 | 0 | 0 | 0 | 409 | 402 | 17153564 | 150000 | 17003564 | 18476146 | 18698461 | -35341 | 0 | -35341 | 18663120 | 18835408 | 236796 | 1322582 | 286 | 0 | 342 | 773266 | 678882 | 0 | 60 | 374405 | 182495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23100 | 0 | 0 | 0 | 202355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17071 | 0 | 0 | 0 | 0 | 0 | 0 | 402 | 1390198 | 861377 | F592247483 | PHOENIX CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-11-30 | QTR2 | 22/23 | 2022-04-07 | QTR4 | 21/22 | 306 | 15223000 |  |  | 7 | 123 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3665 | 43774715201 | 2018-07-25 | QTR1 | 18/19 | 1 | 0 | 120 | 322 | 311 | 11 | 0 | 0 | 202 | 0 | 3486000 | 50000 | 3436000 | 3486000 | 3372934 | 0 | 0 | 0 | 3372934 | 3425370 | 52435 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-05 | QTR2 | 22/23 | 2019-08-16 | QTR1 | 19/20 | 314 | 0 | B0 | ACC - LUMP SUM | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3675 | 43774915201 | 2018-08-29 | QTR1 | 18/19 | 1 | 0 | 90 | 203 | 194 | 9 | 0 | 0 | 113 | 0 | 2642778 | 50000 | 2592778 | 2642778 | 2780919 | 0 | 0 | 0 | 2780919 | 2780919 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-05 | QTR2 | 22/23 | 2019-08-07 | QTR1 | 19/20 | 314 | 2368300 |  |  | 0 | 67 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3707 | 43938615201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 119 | 168 | 168 | 0 | 0 | 0 | 49 | 0 | 698965 | 0 | 698965 | 713815 | 692942 | 0 | 0 | 0 | 692942 | 692942 | 0 | 14850 | 18 | 0 | 0 | 0 | 0 | 25 | 0 | 14850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 14850 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-06 | QTR2 | 22/23 | 2022-07-06 | QTR1 | 22/23 | 313 | 725593.3 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3761 | 43776115201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 150 | 201 | 198 | 3 | 0 | 0 | 51 | 0 | 2870000 | 50000 | 2820000 | 2870000 | 2988110 | 0 | 0 | 0 | 2988110 | 3098877 | 110767 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 | 2021-10-29 | QTR2 | 21/22 | 321 | 3648686.57 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3762 | 43972815201 | 2021-03-31 | QTR3 | 20/21 | 5 | 1 | 295 | 413 | 390 | 23 | 0 | 0 | 118 | 0 | 7546444 | 66513 | 7479931 | 7547764 | 7602863 | 0 | 0 | 0 | 7602863 | 8039182 | 455459 | 1320 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5820 | 0 | F592270011 | CAPITAL ASPHALT INC | N/A | N/A | N/A | N/A | 2022-12-29 | QTR2 | 22/23 | 2022-09-25 | QTR1 | 22/23 | 321 | 6787720.74 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3778 | 44364315201 | 2021-10-27 | QTR2 | 21/22 | 1 | 0 | 150 | 186 | 185 | 1 | 0 | 0 | 36 | 0 | 5014999 | 58748 | 4956251 | 5014999 | 5263526 | 0 | 0 | 0 | 5263526 | 5470542 | 207016 | 0 | 28 | 0 | 0 | 4631 | 0 | 0 | 0 | 12960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17591 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-12-29 | QTR2 | 22/23 | 2022-07-06 | QTR1 | 22/23 | 321 | 5942459.32 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3781 | 44403115201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 60 | 92 | 89 | 3 | 0 | 0 | 32 | 0 | 577089 | 26811 | 550278 | 577089 | 562865 | 0 | 0 | 0 | 562865 | 562865 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-08-04 | QTR1 | 22/23 | 2022-03-28 | QTR3 | 21/22 | 314 | 581614.59 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3820 | 44364615201 | 2022-02-23 | QTR3 | 21/22 | 2 | 0 | 60 | 79 | 72 | 7 | 0 | 0 | 19 | 0 | 860079 | 32516 | 827563 | 860079 | 840896 | 0 | 0 | 0 | 840896 | 840896 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-17 | QTR2 | 22/23 | 2022-07-21 | QTR1 | 22/23 | 314 | 685675.54 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9020 | 44531215215 | 2019-10-30 | QTR2 | 19/20 | 1 | 0 | 45 | 57 | 1 | 56 | 0 | 0 | 12 | 0 | 456152 | 21600 | 434552 | 456152 | 434552 | 0 | 0 | 0 | 434552 | 434552 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2022-11-17 | QTR2 | 22/23 | 2020-04-20 | QTR4 | 19/20 | 306 | 457716.8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3O54 | 21860565201 | 2016-01-29 | QTR3 | 15/16 | 7 | 30 | 789 | 2118 | 2097 | 21 | 0 | 0 | 835 | 494 | 29137700 | 150000 | 28987700 | 36335019 | 36358268 | 0 | 150000 | 150000 | 36508268 | 37056965 | 724562 | 7197319 | 641 | 0 | 119 | 1770045 | 309387 | 9 | 3 | 686825 | 24327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 4298210 | 3702970 | 0 | 0 | 34680 | 34680 | 0 | 0 | 0 | 0 | 0 | 0 | 55099 | 0 | 0 | 0 | 211948 | 0 | 0 | 33 | 144197 | 144197 | 0 | 0 | 0 | 0 | 9 | 494 | 7201002 | 4215560 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-07-07 | QTR1 | 22/23 | 2022-01-14 | QTR3 | 21/22 | 306 | 26259676.56 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 2 | 185 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3R55 | 44147215201 | 2018-09-13 | QTR1 | 18/19 | 1 | 0 | 180 | 229 | 237 | -8 | 8 | 0 | 49 | 0 | 1397594 | 50000 | 1347594 | 1397594 | 1214442 | -13320 | 0 | -13320 | 1201122 | 1214442 | 13320 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2022-10-04 | QTR2 | 22/23 | 2019-09-21 | QTR1 | 19/20 | 313 | 1716536.28 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3S63 | 4452481G201 | 2019-04-16 | QTR4 | 18/19 | 4 | 3 | 180 | 796 | 796 | 0 | 0 | 0 | 616 | 0 | 1463233 | 0 | 1463233 | 1553233 | 3732786 | 0 | 0 | 0 | 3732786 | 0 | -3732786 | 90000 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 90000 | 0 | F452731396 | GOMEZ & SON FENCE CORP. | N/A | N/A | N/A | N/A | 2022-07-18 | QTR1 | 22/23 | 2021-10-12 | QTR2 | 21/22 | 321 | 1676149.95 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T33 | 40674255201 | 2021-08-12 | QTR1 | 21/22 | 1 | 0 | 180 | 199 | 92 | 107 | 0 | 0 | 16 | 3 | 671000 | 46442 | 624558 | 671000 | 620160 | 0 | 0 | 0 | 620160 | 620160 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 19087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 19087 | 0 | F454034656 | MONOKO LLC | N/A | N/A | N/A | N/A | 2022-08-09 | QTR1 | 22/23 | 2022-03-02 | QTR3 | 21/22 | 321 | 974400.82 |  |  | 3 | 11 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T37 | 44154715201 | 2020-12-17 | QTR2 | 20/21 | 4 | 0 | 150 | 219 | 228 | -9 | 9 | 0 | 57 | 12 | 1496843 | 58788 | 1438055 | 1496843 | 1510915 | -15210 | 0 | -15210 | 1495705 | 1559564 | 63859 | 0 | 31 | 0 | 9 | 9075 | 0 | 0 | 3 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20875 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-08-15 | QTR1 | 22/23 | 2021-12-16 | QTR2 | 21/22 | 321 | 2221301.11 |  |  | 12 | 17 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T54 | 44154415201 | 2021-06-10 | QTR4 | 20/21 | 1 | 0 | 210 | 278 | 288 | -10 | 10 | 0 | 68 | 0 | 3673382 | 50000 | 3623382 | 3673382 | 3504749 | -25790 | 0 | -25790 | 3478959 | 3661766 | 182807 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-02 | QTR2 | 22/23 | 2022-06-27 | QTR4 | 21/22 | 321 | 5542803.31 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T55 | 43974015201 | 2021-03-11 | QTR3 | 20/21 | 1 | 0 | 180 | 335 | 362 | -27 | 27 | 0 | 155 | 0 | 5227145 | 50000 | 5177145 | 5227145 | 5328540 | -101412 | 0 | -101412 | 5227128 | 5712178 | 485050 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-02 | QTR2 | 22/23 | 2022-05-31 | QTR4 | 21/22 | 314 | 4892771.41 |  |  | 0 | 53 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U03 | 43973915201 | 2020-12-17 | QTR2 | 20/21 | 1 | 1 | 335 | 433 | 433 | 0 | 0 | 0 | 92 | 6 | 3371488 | 50000 | 3321488 | 3376998 | 3480991 | 0 | 0 | 0 | 3480991 | 3693131 | 271808 | 5510 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 21671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 22488 | 0 | F591576957 | PEAVY & SON CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 | 2022-05-31 | QTR4 | 21/22 | 321 | 4444370.86 |  |  | 6 | 34 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U13 | 42357755201 | 2021-08-12 | QTR1 | 21/22 | 1 | 0 | 180 | 235 | 180 | 55 | 0 | 0 | 55 | 0 | 1172134 | 50000 | 1122134 | 1172134 | 929583 | 0 | 0 | 0 | 929583 | 929583 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 | 2022-05-02 | QTR4 | 21/22 | 314 | 2039783.8 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U33 | 44744415201 | 2021-12-09 | QTR2 | 21/22 | 1 | 0 | 90 | 94 | 52 | 42 | 0 | 0 | 4 | 0 | 680167 | 36771 | 643396 | 680167 | 561264 | 0 | 0 | 0 | 561264 | 561264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-12-06 | QTR2 | 22/23 | 2022-06-13 | QTR4 | 21/22 | 313 | 773440.66 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U40 | 22253935201 | 2021-10-14 | QTR2 | 21/22 | 1 | 0 | 120 | 140 | 140 | 0 | 0 | 0 | 18 | 2 | 2206400 | 50000 | 2156400 | 2206400 | 2130362 | 0 | 85000 | 85000 | 2215362 | 2130362 | -85000 | 0 | 11 | 0 | 2 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4770 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-10-27 | QTR2 | 22/23 | 2022-07-08 | QTR1 | 22/23 | 321 | 2401773.5 | B10 | ACC - BONUS/INCENT/DISINCENT | 2 | 7 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4522 | 43631915201 | 2019-09-25 | QTR1 | 19/20 | 4 | 0 | 737 | 860 | 857 | 3 | 0 | 0 | 123 | 0 | 11069050 | 129285 | 10939766 | 11069050 | 10764445 | 0 | 0 | 0 | 10764445 | 10777804 | 13359 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 25517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30043 | 0 | 0 | 0 | 9396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64956 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 | 2022-05-11 | QTR4 | 21/22 | 412 | 13112789.31 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4527 | 43689445201 | 2019-09-25 | QTR1 | 19/20 | 1 | 1 | 323 | 400 | 400 | 0 | 0 | 0 | 77 | 0 | 1334388 | 50000 | 1284388 | 1536888 | 1454286 | 0 | 0 | 0 | 1454286 | 1453044 | -1243 | 202500 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 4325 | 0 | 0 | 0 | 162500 | 162500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206825 | 202500 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 | 2021-03-08 | QTR3 | 20/21 | 409 | 2037845.47 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4544 | 43984715201 | 2020-05-20 | QTR4 | 19/20 | 3 | 3 | 450 | 534 | 531 | 3 | 0 | 0 | 67 | 17 | 7223964 | 83864 | 7140100 | 7285366 | 7104914 | 0 | 0 | 0 | 7104914 | 7178924 | 76645 | 61402 | 27 | 0 | 0 | 15957 | 0 | 0 | 0 | 68904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2326 | 0 | 0 | 17 | 28778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 115965 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-07-14 | QTR1 | 22/23 | 2022-05-03 | QTR4 | 21/22 | 408 | 8446703.33 |  |  | 17 | 40 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4546 | 42751625201 | 2020-04-29 | QTR4 | 19/20 | 2 | 7 | 401 | 493 | 493 | 0 | 0 | 0 | 92 | 0 | 11887967 | 111049 | 11776919 | 11268781 | 11300160 | 0 | 0 | 0 | 11300160 | 11435187 | 192865 | -619187 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 64334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907 | 0 | 0 | 0 | 148223 | 60298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -549449 | 60298 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2022-10-11 | QTR2 | 22/23 | 2022-05-11 | QTR4 | 21/22 | 409 | 11525995.08 |  |  | 0 | 26 | 0 | 0 | -762913 | 0 |  | CO
04CO | 04 | T4558 | 43975515201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 137 | 196 | 195 | 1 | 0 | 0 | 59 | 0 | 635419 | 33038 | 602381 | 635419 | 611152 | 0 | 0 | 0 | 611152 | 615668 | 8975 | 0 | 43 | 0 | 0 | 12282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12282 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-08-18 | QTR1 | 22/23 | 2022-05-18 | QTR4 | 21/22 | 409 | 656409.13 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4569 | 44177415201 | 2021-07-28 | QTR1 | 21/22 | 2 | 0 | 127 | 138 | 136 | 2 | 0 | 0 | 11 | 0 | 568800 | 26773 | 542026 | 568800 | 536000 | 0 | 0 | 0 | 536000 | 537990 | 1990 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6461 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2022-06-10 | QTR4 | 21/22 | 412 | 559587.35 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4R96 | 43310865201 | 2017-04-05 | QTR4 | 16/17 | 3 | 22 | 1500 | 1665 | 1573 | 92 | 0 | 0 | 165 | 0 | 102000000 | 150000 | 101850000 | 110058943 | 109950726 | 0 | 1500000 | 1500000 | 111450726 | 110900593 | -415056 | 8058943 | 68 | 0 | 0 | 4394429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707076 | 0 | 0 | 0 | 664098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7765602 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2021-10-29 | QTR2 | 21/22 | 412 | 111264427.38 | B1:B8:Y:B::Y | ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:ACC - NO EXCUSE BONUS:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 97 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U45 | 44147415201 | 2021-05-07 | QTR4 | 20/21 | 1 | 3 | 194 | 358 | 352 | 6 | 0 | 0 | 106 | 58 | 1428608 | 34621 | 1393987 | 1539147 | 1506769 | 0 | 0 | 0 | 1506769 | 1507294 | 525 | 110539 | 71 | 15 | 58 | 110539 | 0 | 0 | 0 | 7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 58 | 117941 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2022-11-21 | QTR2 | 22/23 | 2022-09-16 | QTR1 | 22/23 | 412 | 786261.04 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U70 | 44147015201 | 2021-05-07 | QTR4 | 20/21 | 1 | 3 | 185 | 250 | 249 | 1 | 0 | 0 | 55 | 10 | 2377932 | 50000 | 2327932 | 2509209 | 2450657 | 0 | 0 | 0 | 2450657 | 2450657 | 0 | 131278 | 26 | 4 | 10 | 131278 | 39847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 14 | 10 | 131278 | 39847 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-10-03 | QTR2 | 22/23 | 2022-08-19 | QTR1 | 22/23 | 409 | 1774051.34 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U73 | 44163315201 | 2021-03-05 | QTR3 | 20/21 | 1 | 2 | 280 | 328 | 324 | 4 | 0 | 0 | 48 | 0 | 3534228 | 50000 | 3484228 | 3576916 | 3502409 | 0 | 0 | 0 | 3502409 | 3641361 | 138951 | 42688 | 27 | 0 | 0 | 17161 | 0 | 0 | 0 | 6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33171 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-07-07 | QTR1 | 22/23 | 2022-05-25 | QTR4 | 21/22 | 409 | 4315430.08 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V05 | 44531515215 | 2021-10-01 | QTR2 | 21/22 | 1 | 0 | 126 | 132 | 96 | 36 | 0 | 0 | 6 | 0 | 676628 | 32349 | 644279 | 676628 | 625424 | 0 | 0 | 0 | 625424 | 625424 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 | 2022-06-10 | QTR4 | 21/22 | 408 | 664967.48 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5688 | 44103615201 | 2021-01-27 | QTR3 | 20/21 | 2 | 3 | 140 | 300 | 300 | 0 | 0 | 0 | 141 | 19 | 4662267 | 53000 | 4609267 | 4737267 | 4423238 | 0 | 0 | 0 | 4423238 | 4604586 | 211340 | 75000 | 63 | 0 | 19 | 61462 | 0 | 0 | 0 | 13201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 74663 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-11-01 | QTR2 | 22/23 | 2022-05-23 | QTR4 | 21/22 | 509 | 5545150.49 |  |  | 19 | 78 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5700 | 44293215201 | 2021-01-27 | QTR3 | 20/21 | 1 | 0 | 170 | 350 | 350 | 0 | 0 | 0 | 151 | 29 | 1579513 | 50000 | 1529513 | 1579513 | 1554158 | 0 | 0 | 0 | 1554158 | 1562899 | 19785 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 29 | 7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 7602 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-17 | QTR1 | 22/23 | 2022-07-08 | QTR1 | 22/23 | 513 | 1579888.21 |  |  | 29 | 118 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5704 | 44113315201 | 2020-11-18 | QTR2 | 20/21 | 1 | 5 | 300 | 515 | 515 | 0 | 0 | 0 | 191 | 24 | 10173619 | 124196 | 10049423 | 10199686 | 10343682 | 0 | 0 | 0 | 10343682 | 11087533 | 761044 | 26067 | 104 | 0 | 0 | 6721 | 0 | 0 | 24 | 50276 | 8139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20322 | 0 | 0 | 0 | 7261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 84580 | 8139 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-10-13 | QTR2 | 22/23 | 2022-08-11 | QTR1 | 22/23 | 513 | 12810546.48 |  |  | 0 | 87 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5708 | 44101415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 210 | 349 | 348 | 1 | 0 | 0 | 129 | 10 | 6490691 | 84382 | 6406309 | 6568600 | 6865453 | 0 | 0 | 0 | 6865453 | 7282431 | 416979 | 77909 | 53 | 0 | 10 | 77909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 92162 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-07-19 | QTR1 | 22/23 | 2022-03-18 | QTR3 | 21/22 | 515 | 8517614.92 |  |  | 0 | 76 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5709 | 44113525201 | 2021-01-27 | QTR3 | 20/21 | 2 | 0 | 280 | 431 | 431 | 0 | 0 | 0 | 135 | 16 | 8389168 | 85000 | 8304168 | 8389168 | 8382005 | 0 | 0 | 0 | 8382005 | 8827365 | 485238 | 0 | 98 | 0 | 4 | 20466 | 0 | 0 | 11 | 55149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 82960 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-09-09 | QTR1 | 22/23 | 2022-07-06 | QTR1 | 22/23 | 515 | 8661613.49 |  |  | 16 | 37 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5716 | 43745115201 | 2021-04-28 | QTR4 | 20/21 | 1 | 2 | 200 | 246 | 245 | 1 | 0 | 0 | 46 | 0 | 2263271 | 50000 | 2213271 | 2365506 | 2356172 | 0 | 0 | 0 | 2356172 | 2456514 | 130713 | 102234 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 129138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129138 | 0 | F851349245 | ACCE JV LLC | N/A | N/A | N/A | N/A | 2022-09-02 | QTR1 | 22/23 | 2022-06-30 | QTR4 | 21/22 | 509 | 2040645.74 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5722 | 44350715201 | 2021-07-28 | QTR1 | 21/22 | 1 | 0 | 150 | 208 | 208 | 0 | 0 | 0 | 58 | 0 | 1619760 | 50000 | 1569760 | 1619760 | 1578600 | 0 | 0 | 0 | 1578600 | 1598533 | 19933 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 6173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11639 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2022-09-02 | QTR1 | 22/23 | 2022-07-11 | QTR1 | 22/23 | 515 | 1216963.81 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E52A7 | 44194515201 | 2021-02-02 | QTR3 | 20/21 | 1 | 0 | 130 | 215 | 215 | 0 | 0 | 0 | 85 | 0 | 1902006 | 50000 | 1852006 | 1902006 | 1790542 | 0 | 0 | 0 | 1790542 | 1806715 | 16173 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 7806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14123 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-07-22 | QTR1 | 22/23 | 2022-04-08 | QTR4 | 21/22 | 514 | 1695842.63 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A5 | 44113915201 | 2020-12-15 | QTR2 | 20/21 | 1 | 3 | 300 | 373 | 373 | 0 | 0 | 0 | 73 | 0 | 1298860 | 50000 | 1248860 | 1434756 | 1399753 | 0 | 0 | 0 | 1399753 | 1404115 | 7240 | 135896 | 14 | 0 | 0 | 25354 | 0 | 0 | 0 | 4140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142824 | 0 | F813590186 | P&S PAVING & FLORIDA INDUSTRIAL | N/A | N/A | N/A | N/A | 2022-09-19 | QTR1 | 22/23 | 2022-04-02 | QTR4 | 21/22 | 513 | 1281104.01 |  |  | 0 | 59 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53A8 | 43632525201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 310 | 383 | 382 | 1 | 0 | 0 | 73 | 0 | 1713111 | 50000 | 1663111 | 1713111 | 1658956 | 0 | 0 | 0 | 1658956 | 1658958 | 33039 | 0 | 24 | 0 | 0 | 24573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24573 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-08 | QTR1 | 22/23 | 2022-06-17 | QTR4 | 21/22 | 513 | 1970561.3 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54A1 | 44326315201 | 2021-01-05 | QTR3 | 20/21 | 1 | 0 | 120 | 222 | 214 | 8 | 0 | 0 | 102 | 0 | 985800 | 50000 | 935800 | 985800 | 930200 | 0 | 0 | 0 | 930200 | 930222 | 22 | 0 | 42 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | F273238420 | OCEANIK.US INC. | N/A | N/A | N/A | N/A | 2022-11-08 | QTR2 | 22/23 | 2022-06-01 | QTR4 | 21/22 | 514 | 1158387 |  |  | 0 | 60 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56A2 | 44113415201 | 2021-07-07 | QTR1 | 21/22 | 1 | 1 | 110 | 173 | 173 | 0 | 0 | 0 | 43 | 20 | 1492986 | 50000 | 1442986 | 1574717 | 1530292 | 0 | 0 | 0 | 1530292 | 1569043 | 38751 | 81732 | 12 | 0 | 20 | 81732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 81732 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 | 2022-05-23 | QTR4 | 21/22 | 513 | 1629586.92 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A6 | 44713915201 | 2021-10-05 | QTR2 | 21/22 | 1 | 1 | 88 | 134 | 134 | 0 | 0 | 0 | 34 | 12 | 412340 | 20172 | 392168 | 412340 | 370378 | 0 | 0 | 0 | 370378 | 370378 | 0 | 0 | 17 | 0 | 12 | 19486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 19486 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-11-09 | QTR2 | 22/23 | 2022-07-10 | QTR1 | 22/23 | 509 | 433630.5 |  |  | 12 | 17 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58A6 | 44845415201 | 2021-12-07 | QTR2 | 21/22 | 1 | 0 | 230 | 234 | 120 | 114 | 0 | 0 | 4 | 0 | 710278 | 29452 | 680826 | 710278 | 702088 | 0 | 0 | 0 | 702088 | 702088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-09-22 | QTR1 | 22/23 | 2022-08-15 | QTR1 | 22/23 | 514 | 626464 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E5Z92 | 43913815201 | 2019-11-05 | QTR2 | 19/20 | 1 | 2 | 360 | 670 | 701 | -31 | 31 | 0 | 156 | 154 | 3448889 | 50000 | 3398889 | 3384670 | 3383592 | -477312 | 0 | -477312 | 2906280 | 3336127 | 429848 | -64219 | 83 | 0 | 3 | 7050 | 0 | 0 | 6 | 25464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | -71121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | -38606 | 0 | Z46-0204900 | WESTERN SURETY COMPANY | N/A | N/A | N/A | N/A | 2022-09-09 | QTR1 | 22/23 | 2022-02-08 | QTR3 | 21/22 | 515 | 3664930.24 |  |  | 5 | 73 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6433 | 42440715201 | 2018-06-13 | QTR4 | 17/18 | 3 | 15 | 700 | 1063 | 940 | 123 | 0 | 0 | 231 | 132 | 67230501 | 151730 | 67078771 | 72750415 | 73542354 | 0 | 4200000 | 4200000 | 77742354 | 73243755 | -4309470 | 5519914 | 198 | 0 | 0 | 557153 | 37295 | 0 | 132 | 4723947 | 3063646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450249 | 0 | 0 | 0 | 14733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34563 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 5471149 | 3100941 | F650394050 | GLF CONSTRUCTION CORPORATION | N/A | N/A | N/A | N/A | 2022-08-19 | QTR1 | 22/23 | 2021-12-16 | QTR2 | 21/22 | 606 | 76112026.4 | B2:B5 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 0 | 33 | 0 | 0 | -309497 | 0 |  | CO
06CO | 06 | T6480 | 44018215201 | 2021-02-17 | QTR3 | 20/21 | 2 | 0 | 170 | 277 | 267 | 10 | 0 | 0 | 107 | 0 | 515515 | 29915 | 485600 | 515515 | 456395 | 0 | 0 | 0 | 456395 | 456395 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-09-30 | QTR1 | 22/23 | 2022-06-27 | QTR4 | 21/22 | 636 | 619720.15 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6497 | 44516815201 | 2020-11-18 | QTR2 | 20/21 | 3 | 0 | 150 | 259 | 257 | 2 | 0 | 0 | 109 | 0 | 541368 | 29764 | 511604 | 541368 | 498909 | 0 | 0 | 0 | 498909 | 498909 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 4133 | 0 | 0 | 0 | 8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 12361 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-25 | QTR1 | 22/23 | 2022-05-23 | QTR4 | 21/22 | 613 | 585940.8 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6L38 | 25168465201 | 2018-05-02 | QTR4 | 17/18 | 2 | 6 | 1000 | 1287 | 1259 | 28 | 0 | 0 | 169 | 118 | 56331262 | 150000 | 56181262 | 61782326 | 61740658 | 0 | 0 | 0 | 61740658 | 61689883 | -2495 | 5451064 | 115 | 0 | 0 | 408613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 4906149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 5342031 | 0 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2022-08-10 | QTR1 | 22/23 | 2022-02-11 | QTR3 | 21/22 | 606 | 56289000 | B8:Y | ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT | 0 | 54 | 0 | 0 | -76933 | 0 |  | DO
06DO | 06 | E6M02 | 43952215201 | 2021-05-27 | QTR4 | 20/21 | 1 | 0 | 120 | 134 | 97 | 37 | 0 | 0 | 14 | 0 | 284704 | 15025 | 269679 | 284704 | 265754 | 0 | 0 | 0 | 265754 | 265754 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 1813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813 | 0 | F650445173 | UNDER POWER CORP | N/A | N/A | N/A | N/A | 2022-11-22 | QTR2 | 22/23 | 2022-09-27 | QTR1 | 22/23 | 613 | 309692.5 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M50 | 44196715201 | 2020-11-19 | QTR2 | 20/21 | 1 | 2 | 240 | 412 | 412 | 0 | 0 | 0 | 148 | 24 | 873331 | 43833 | 829498 | 1042774 | 969094 | 0 | 0 | 0 | 969094 | 969094 | 0 | 169443 | 104 | 20 | 24 | 162091 | 0 | 1 | 0 | 6118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24 | 168208 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2022-11-18 | QTR2 | 22/23 | 2022-08-30 | QTR1 | 22/23 | 613 | 905939.9 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6M84 | 44253915201 | 2020-08-27 | QTR1 | 20/21 | 2 | 1 | 150 | 220 | 220 | 0 | 0 | 0 | 70 | 0 | 608490 | 30869 | 577621 | 625609 | 579687 | 0 | 0 | 0 | 579687 | 585088 | 5401 | 17119 | 40 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 1768 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-08-29 | QTR1 | 22/23 | 2022-05-25 | QTR4 | 21/22 | 613 | 624645.65 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N00 | 44394015201 | 2022-02-24 | QTR3 | 21/22 | 1 | 0 | 120 | 158 | 123 | 35 | 0 | 0 | 38 | 0 | 510362 | 28444 | 481918 | 510362 | 479426 | 0 | 0 | 0 | 479426 | 473360 | -6066 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2022-12-08 | QTR2 | 22/23 | 2022-10-10 | QTR2 | 22/23 | 613 | 600250.3 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7408 | 42895315201 | 2018-06-13 | QTR4 | 17/18 | 4 | 25 | 1115 | 1267 | 1253 | 14 | 0 | 0 | 152 | 0 | 52309860 | 150000 | 52159860 | 53697121 | 53886362 | 0 | 0 | 0 | 53886362 | 53722937 | -163425 | 1387261 | 66 | 0 | 0 | 630838 | 47733 | 0 | 0 | 729633 | 81715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117242 | 0 | 0 | 0 | 35355 | 32626 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315397 | 162073 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-07-15 | QTR1 | 22/23 | 2022-02-18 | QTR3 | 21/22 | 714 | 61751000 |  |  | 0 | 86 | 0 | 0 | -227170 | 0 |  | CO
07CO | 07 | T7434 | 43734915201 | 2019-06-12 | QTR4 | 18/19 | 1 | 1 | 441 | 514 | 514 | 0 | 0 | 0 | 73 | 0 | 5555515 | 50000 | 5505515 | 5352409 | 5279909 | 0 | 0 | 0 | 5279909 | 5286766 | 6857 | -203106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -203106 | 0 | F592407001 | COMMERCIAL INDUSTRIAL CORP. | N/A | N/A | N/A | N/A | 2022-10-24 | QTR2 | 22/23 | 2022-03-02 | QTR3 | 21/22 | 798 | 5564432.46 |  |  | 0 | 38 | 0 | 0 | -203106 | 0 |  | CO
07CO | 07 | T7444 | 44108325201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 443 | 585 | 581 | 4 | 0 | 0 | 92 | 50 | 10034121 | 129550 | 9904571 | 10350046 | 9810424 | 0 | 0 | 0 | 9810424 | 9853179 | 103829 | 315925 | 59 | 0 | 0 | 0 | 0 | 0 | 50 | 344704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 411706 | 0 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2022-07-26 | QTR1 | 22/23 | 2022-05-31 | QTR4 | 21/22 | 714 | 12990036.6 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7446 | 43005125201 | 2020-02-26 | QTR3 | 19/20 | 2 | 1 | 240 | 272 | 272 | 0 | 0 | 0 | 32 | 0 | 4532943 | 100000 | 4432943 | 4557685 | 4389265 | 0 | 0 | 0 | 4389265 | 4384901 | -4365 | 24742 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 22996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29305 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-12-07 | QTR2 | 22/23 | 2021-05-11 | QTR4 | 20/21 | 798 | 4923200 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7459 | 44550725201 | 2021-02-17 | QTR3 | 20/21 | 2 | 0 | 210 | 355 | 354 | 1 | 0 | 0 | 145 | 0 | 1887858 | 50000 | 1837858 | 1887858 | 1854136 | 0 | 0 | 0 | 1854136 | 1854136 | 38612 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-09-12 | QTR1 | 22/23 | 2022-07-07 | QTR1 | 22/23 | 799 | 2521800 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7463 | 43762415201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 200 | 271 | 271 | 0 | 0 | 0 | 50 | 21 | 5399019 | 50000 | 5349019 | 5449019 | 5598998 | 0 | 0 | 0 | 5598998 | 5769676 | 201519 | 50000 | 30 | 0 | 0 | 15416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15416 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-08-02 | QTR1 | 22/23 | 2022-04-08 | QTR4 | 21/22 | 799 | 5600000 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7465 | 44110415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 200 | 288 | 288 | 0 | 0 | 0 | 50 | 38 | 1187466 | 40000 | 1147466 | 1227466 | 1221695 | 0 | 0 | 0 | 1221695 | 1225383 | 3688 | 40000 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-26 | QTR2 | 22/23 | 2022-04-25 | QTR4 | 21/22 | 798 | 941000 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7474 | 44555415201 | 2021-04-28 | QTR4 | 20/21 | 1 | 0 | 200 | 222 | 175 | 47 | 0 | 0 | 22 | 0 | 755204 | 42000 | 713204 | 755204 | 735925 | 0 | 0 | 0 | 735925 | 735925 | 40677 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-07-28 | QTR1 | 22/23 | 2022-05-06 | QTR4 | 21/22 | 796 | 918700 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7L92 | 43669715201 | 2018-06-13 | QTR4 | 17/18 | 2 | 11 | 675 | 1004 | 1004 | 0 | 0 | 0 | 301 | 28 | 4257317 | 50000 | 4207317 | 10851592 | 9627641 | 0 | 0 | 0 | 9627641 | 9622285 | -5356 | 6594276 | 66 | 32 | 0 | 8007524 | 0 | 0 | 0 | 265662 | 8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 28 | 365894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 28 | 6594983 | 8995 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-08 | QTR1 | 22/23 | 2022-01-26 | QTR3 | 21/22 | 799 | 4476953.25 |  |  | 0 | 157 | 0 | 0 | -2044097 | 0 |  | DO
07DO | 07 | E7N30 | 43473625201 | 2021-08-11 | QTR1 | 21/22 | 1 | 0 | 188 | 216 | 215 | 1 | 0 | 0 | 26 | 0 | 1297005 | 50000 | 1247005 | 1297005 | 1237378 | 0 | 0 | 0 | 1237378 | 1237963 | 585 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F752993152 | AMERICAN EMPIRE BUILDERS INC. | N/A | N/A | N/A | N/A | 2022-12-12 | QTR2 | 22/23 | 2022-08-05 | QTR1 | 22/23 | 796 | 1230300 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N54 | 43480735201 | 2021-01-29 | QTR3 | 20/21 | 1 | 1 | 150 | 255 | 190 | 65 | 0 | 0 | 26 | 79 | 1422150 | 50000 | 1372150 | 1360924 | 1310034 | 0 | 0 | 0 | 1310034 | 1310789 | 755 | -61226 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -61226 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-10-17 | QTR2 | 22/23 | 2022-02-21 | QTR3 | 21/22 | 799 | 1400000 |  |  | 0 | 18 | 0 | 0 | -61226 | 0 |  | DO
07DO | 07 | E7N99 | 44025425201 | 2021-07-14 | QTR1 | 21/22 | 3 | 1 | 140 | 155 | 155 | 0 | 0 | 0 | 15 | 0 | 1595242 | 50000 | 1545242 | 1718861 | 1294242 | 0 | 0 | 0 | 1294242 | 1316286 | 22044 | 123619 | 4 | 0 | 0 | 123619 | 113968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123619 | 113968 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-11-08 | QTR2 | 22/23 | 2022-05-09 | QTR4 | 21/22 | 799 | 1647300 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O21 | 44366415201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 60 | 60 | 44 | 16 | 0 | 0 | 0 | 0 | 397254 | 14000 | 383254 | 397254 | 370201 | 0 | 0 | 0 | 370201 | 370201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-07-11 | QTR1 | 22/23 | 2022-04-26 | QTR4 | 21/22 | 796 | 296700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P10 | 44948515201 | 2022-03-09 | QTR3 | 21/22 | 1 | 0 | 40 | 46 | 46 | 0 | 0 | 0 | 6 | 0 | 403261 | 17000 | 386261 | 403261 | 392075 | 0 | 0 | 0 | 392075 | 392075 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-11-28 | QTR2 | 22/23 | 2022-08-30 | QTR1 | 22/23 | 796 | 420300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R28 | 44769615201 | 2021-05-10 | QTR4 | 20/21 | 1 | 0 | 310 | 341 | 341 | 0 | 0 | 0 | 31 | 0 | 2063258 | 50000 | 2013258 | 2063258 | 2025710 | 0 | 0 | 0 | 2025710 | 2046401 | 20691 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-08-16 | QTR1 | 22/23 | 2022-06-17 | QTR4 | 21/22 | 796 | 1523991.28 | LBDB | LOW BID DESIGN BUILD | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R29 | 43982995201 | 2021-05-17 | QTR4 | 20/21 | 2 | 0 | 321 | 329 | 324 | 5 | 0 | 0 | 8 | 0 | 1887000 | 50000 | 1837000 | 1887000 | 1837000 | 0 | 0 | 0 | 1837000 | 1837000 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-08-01 | QTR1 | 22/23 | 2022-06-03 | QTR4 | 21/22 | 796 | 2845446.28 | A3:A3 | ICC - DESIGN/BUILD - MINOR:ICC - DESIGN/BUILD - MINOR | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S34 | 43798655201 | 2021-03-09 | QTR3 | 20/21 | 1 | 1 | 160 | 200 | 190 | 10 | 0 | 0 | 40 | 0 | 878913 | 50000 | 828913 | 870049 | 822741 | 0 | 0 | 0 | 822741 | 823180 | 7889 | -8864 | 24 | 0 | 0 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5345 | 0 | F208579873 | P&P CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-07-06 | QTR1 | 22/23 | 2022-05-06 | QTR4 | 21/22 | 854 | 1113411.37 |  |  | 0 | 16 | 0 | 0 | -8864 | 0 |  | DO
08DO | 08 | E8S70 | 44262215201 | 2020-11-17 | QTR2 | 20/21 | 5 | 0 | 303 | 380 | 378 | 2 | 0 | 0 | 77 | 0 | 4113457 | 78161 | 4035296 | 4113457 | 3489511 | 0 | 0 | 0 | 3489511 | 3489532 | 21 | 0 | 45 | 0 | 0 | 11159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 11159 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-08-19 | QTR1 | 22/23 | 2022-06-13 | QTR4 | 21/22 | 854 | 7220597.77 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0