## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 76427290 | 75767647 | 79680885 | 79324637 | 0 | 80677636 | 6.48% | 58.33% | 2366654 | 3.124% | 3253596 | 4.257% | 2929 | 915 | 31.24% | 261 | 8.911% | 108 | 3.687% | 180 | 6.145% | 3217 | 9.833% | 4437 | 4822 | 3646 | 24.48% | 58.33%
| District Let | 11103415 | 10928350 | 10994460 | 10985943 | 0 | 11528317 | 5.49% | 50% | -119826 | -1.096% | -108956 | -0.9813% | 685 | 148 | 21.61% | 62 | 9.051% | 12 | 1.752% | 0 | 0% | 697 | 1.752% | 907 | 882 | 672 | -1.898% | 100%
| All Contracts | 87530705 | 86695997 | 90675345 | 90310580 | 0 | 92205953 | 6.355% | 56.25% | 2246828 | 2.592% | 3144640 | 3.593% | 3614 | 1063 | 29.41% | 323 | 8.937% | 120 | 3.32% | 180 | 4.981% | 3914 | 8.301% | 5344 | 5704 | 4318 | 19.48% | 68.75%
2 | Central Let | 82528589 | 81531798 | 83157632 | 82352827 | 0 | 83358973 | 2.241% | 88.89% | 720761 | 0.884% | 490645 | 0.5945% | 4454 | 1070 | 24.02% | 575 | 12.91% | 541 | 12.15% | 790 | 17.74% | 5785 | 29.88% | 7526 | 7637 | 5992 | 34.53% | 50%
| District Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| All Contracts | 82528589 | 81531798 | 83157632 | 82352827 | 0 | 83358973 | 2.241% | 94.44% | 720761 | 0.884% | 490645 | 0.5945% | 4454 | 1070 | 24.02% | 575 | 12.91% | 541 | 12.15% | 790 | 17.74% | 5785 | 29.88% | 7526 | 7637 | 5992 | 34.53% | 50%
3 | Central Let | 80369324 | 79694549 | 81877811 | 84257172 | 0 | 86119704 | 8.062% | 83.33% | 1628270 | 2.043% | 1508488 | 1.877% | 3950 | 1456 | 36.86% | 564 | 14.28% | 215 | 5.443% | 307 | 7.772% | 4472 | 13.22% | 6418 | 6486 | 4466 | 13.06% | 91.67%
| District Let | 12030265 | 11888960 | 12060506 | 12413995 | 0 | 12624379 | 6.186% | 100% | 53455 | 0.4496% | 30241 | 0.2514% | 635 | 168 | 26.46% | 74 | 11.65% | 51 | 8.031% | 0 | 0% | 686 | 8.031% | 928 | 906 | 664 | 4.567% | 100%
| All Contracts | 92399589 | 91583509 | 93938317 | 96671167 | 0 | 98744083 | 7.819% | 86.67% | 1681725 | 1.836% | 1538729 | 1.665% | 4585 | 1624 | 35.42% | 638 | 13.91% | 266 | 5.802% | 307 | 6.696% | 5158 | 12.5% | 7346 | 7392 | 5130 | 11.89% | 93.33%
4 | Central Let | 16502269 | 16211477 | 16880717 | 16082131 | 0 | 16212062 | 0.003609% | 100% | 459479 | 2.834% | 381082 | 2.309% | 1418 | 581 | 40.97% | 156 | 11% | 41 | 2.891% | 0 | 0% | 1459 | 2.891% | 2196 | 2190 | 1453 | 2.468% | 100%
| District Let | 34359939 | 34032514 | 36063001 | 35210130 | 0 | 35396818 | 4.009% | 75% | 1722859 | 5.062% | 1703062 | 4.957% | 1247 | 424 | 34% | 105 | 8.42% | 7 | 0.5613% | 109 | 8.741% | 1363 | 9.302% | 1892 | 1879 | 1350 | 8.26% | 75%
| All Contracts | 50862208 | 50243991 | 52943718 | 51292261 | 0 | 51608880 | 2.717% | 90% | 2182338 | 4.343% | 2084144 | 4.098% | 2665 | 1005 | 37.71% | 261 | 9.794% | 48 | 1.801% | 109 | 4.09% | 2822 | 5.891% | 4088 | 4069 | 2803 | 5.178% | 90%
5 | Central Let | 93073664 | 92732664 | 104342687 | 106570067 | 0 | 108965904 | 17.51% | 33.33% | 4683748 | 5.051% | 11120122 | 11.95% | 1610 | 299 | 18.57% | 269 | 16.71% | 0 | 0% | 437 | 27.14% | 2047 | 27.14% | 2615 | 2617 | 2049 | 27.27% | 66.67%
| District Let | 16573002 | 16350175 | 17037241 | 16618727 | 0 | 17063900 | 4.365% | 100% | 360989 | 2.208% | 464239 | 2.801% | 879 | 185 | 21.05% | 366 | 41.64% | 0 | 0% | 36 | 4.096% | 915 | 4.096% | 1484 | 1466 | 915 | 4.096% | 100%
| All Contracts | 109646666 | 109082839 | 121379928 | 123188794 | 0 | 126029804 | 15.54% | 71.43% | 5044737 | 4.625% | 11584361 | 10.57% | 2489 | 484 | 19.45% | 635 | 25.51% | 0 | 0% | 473 | 19% | 2962 | 19% | 4099 | 4083 | 2964 | 19.08% | 85.71%
6 | Central Let | 6406366 | 6306366 | 6437437 | 6390718 | 0 | 6481799 | 2.782% | 100% | 64754 | 1.027% | 31071 | 0.485% | 600 | 42 | 7% | 37 | 6.167% | 0 | 0% | 0 | 0% | 600 | 0% | 679 | 546 | 467 | -22.17% | 100%
| District Let | 4251942 | 4104788 | 4326272 | 4092640 | 0 | 4079649 | -0.6124% | 100% | 89415 | 2.178% | 74329 | 1.748% | 770 | 135 | 17.53% | 32 | 4.156% | 55 | 7.143% | 0 | 0% | 825 | 7.143% | 992 | 851 | 684 | -11.17% | 100%
| All Contracts | 10658308 | 10411154 | 10763709 | 10483358 | 0 | 10561448 | 1.444% | 100% | 154169 | 1.481% | 105400 | 0.9889% | 1370 | 177 | 12.92% | 69 | 5.036% | 55 | 4.015% | 0 | 0% | 1425 | 4.015% | 1671 | 1397 | 1151 | -15.99% | 100%
7 | Central Let | 20478663 | 20219663 | 20937622 | 21397883 | 0 | 21605771 | 6.855% | 100% | 553454 | 2.737% | 458959 | 2.241% | 1233 | 118 | 9.57% | 88 | 7.137% | 0 | 0% | 93 | 7.543% | 1326 | 7.543% | 1532 | 1876 | 1670 | 35.44% | 50%
| District Let | 10159616 | 9997616 | 10312420 | 10428825 | 0 | 10977659 | 9.803% | 66.67% | 133970 | 1.34% | 152804 | 1.504% | 540 | 81 | 15% | 67 | 12.41% | 0 | 0% | 0 | 0% | 540 | 0% | 709 | 706 | 558 | 3.333% | 100%
| All Contracts | 30638279 | 30217279 | 31250042 | 31826708 | 0 | 32583430 | 7.83% | 85.71% | 687424 | 2.275% | 611763 | 1.997% | 1773 | 199 | 11.22% | 155 | 8.742% | 0 | 0% | 93 | 5.245% | 1866 | 5.245% | 2241 | 2582 | 2228 | 25.66% | 71.43%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 344410737 | 343575507 | 354489837 | 351535282 | 0 | 349352337 | 1.681% | 100% | 9332658 | 2.716% | 10079098 | 2.926% | 4704 | 557 | 11.84% | 344 | 7.313% | 28 | 0.5952% | -20 | -0.4252% | 4712 | 0.1701% | 5613 | 4958 | 4057 | -13.75% | #VALUE!
| All Contracts | 344410737 | 343575507 | 354489837 | 351535282 | 0 | 349352337 | 1.681% | 100% | 9332658 | 2.716% | 10079098 | 2.926% | 4704 | 557 | 11.84% | 344 | 7.313% | 28 | 0.5952% | -20 | -0.4252% | 4712 | 0.1701% | 5613 | 4958 | 4057 | -13.75% | 100%
Totals This Qtr | Central Let | 375786165 | 372464164 | 393314791 | 396375435 | 0 | 403421849 | 8.312% | 80.7% | 10477120 | 2.813% | 17243963 | 4.589% | 16194 | 4481 | 27.67% | 1950 | 12.04% | 905 | 5.588% | 1807 | 11.16% | 18906 | 16.75% | 25403 | 26174 | 19743 | 21.92% | 68.42%
| District Let | 432888916 | 430877910 | 445283737 | 441285542 | 0 | 441023059 | 2.355% | 90% | 11573520 | 2.686% | 12394817 | 2.863% | 9460 | 1698 | 17.95% | 1050 | 11.1% | 153 | 1.617% | 125 | 1.321% | 9738 | 2.939% | 12525 | 11648 | 8900 | -5.92% | 96.67%
| All Contracts | 808675081 | 803342074 | 838598528 | 837660977 | 0 | 844444908 | 5.116% | 83.91% | 22050640 | 2.745% | 29638780 | 3.665% | 25654 | 6179 | 24.09% | 3000 | 11.69% | 1058 | 4.124% | 1932 | 7.531% | 28644 | 11.66% | 37928 | 37822 | 28643 | 11.65% | 78.16%
Totals Previous Quarter | Central Let | 366812141 | 363322200 | 391791558 | 394582000 | 6114800 | 397147320 | 9.31% | 83.33% | 25965031 | 7.147% | 24967334 | 6.807% | 13122 | 1150 | 8.764% | 464 | 3.536% | 163 | 1.242% | 1629 | 12.41% | 14914 | 13.66% | 16867 | 16130 | 14516 | 10.62% | 85.42%
| District Let | 166347760 | 164757121 | 170581461 | 170154877 | 887500 | 171426463 | 4.048% | 88.24% | 4844362 | 2.94% | 4233700 | 2.545% | 7595 | 643 | 8.466% | 228 | 3.002% | 165 | 2.172% | 392 | 5.161% | 8152 | 7.334% | 9033 | 9067 | 8196 | 7.913% | 85.29%
| All Contracts | 533159901 | 528079321 | 562373019 | 564736877 | 7002300 | 568573783 | 7.668% | 85.37% | 30809393 | 5.834% | 29201034 | 5.477% | 20717 | 1793 | 8.655% | 692 | 3.34% | 328 | 1.583% | 2021 | 9.755% | 23066 | 11.34% | 25900 | 25197 | 22712 | 9.63% | 85.37%
Totals Fiscal Year 2023/2024 | Central Let | 1904589510 | 1886092009 | 1993084106 | 2006502139 | 25721847 | 2055719983.42 | 8.994% | 80.31% | 94676809 | 5.02% | 88424399 | 4.643% | 71233 | 7486 | 10.51% | 2113 | 2.966% | 82 | 0.1151% | 5738 | 8.055% | 77053 | 8.17% | 88094 | 85422 | 75823 | 6.444% | 84.56%
| District Let | 613805174 | 607909548 | 634330944 | 628814622 | 6707895 | 639448792 | 5.188% | 79.26% | 22862428 | 3.761% | 20525776 | 3.344% | 26478 | 2113 | 7.98% | 711 | 2.685% | 78 | 0.2946% | 1883 | 7.112% | 28439 | 7.406% | 32123 | 30637 | 27813 | 5.042% | 87.41%
| All Contracts | 2518394684 | 2494001557 | 2627415050 | 2635316761 | 32429742 | 2695168775.42 | 8.066% | 79.95% | 117539237 | 4.713% | 108950175 | 4.326% | 97711 | 9599 | 9.824% | 2824 | 2.89% | 160 | 0.1637% | 7621 | 7.8% | 105492 | 7.963% | 120217 | 116059 | 103636 | 6.064% | 85.53%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1751 | 41066635201 | 2020-04-29 | QTR4 | 19/20 | 4 | 15 | 875 | 1016 | 963 | 94.74% | 1 | 53 | 0 | 0 | 127 | 14 | 43563143 | 150000 | 43413143 | 43826539 | 44268970 | 0 | 0 | 0 | 44268970 | 45616616 | 105.1% | 1 | 1915546 | 263396 | 80 | 54 | 0 | 0 | 351912 | 3918 | 7 | 0 | 219896 | 30715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287200 | 0 | 7 | 0 | 320903 | 34633 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-09-11 | QTR1 | 23/24 |  | 2023-04-28 | QTR4 | 22/23 | 108 | 44746155.07
| 01 | T1761 | 42982315201 | 2021-06-09 | QTR4 | 20/21 | 2 | 18 | 275 | 545 | 530 | 130.2% | 0 | 15 | 0 | 0 | 223 | 47 | 4097408 | 50000 | 4047408 | 4902150 | 4899132 | 0 | 0 | 0 | 4899132 | 4822749 | 119.2% | 0 | 34379 | 804742 | 131 | 41 | 0 | 42 | 118523 | 55203 | 51 | 5 | 478225 | 97145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42992 | 42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 47 | 719910 | 195339 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2023-02-24 | QTR3 | 22/23 | 113 | 4251830.23
| 01 | T1772 | 44211515201 | 2020-09-30 | QTR1 | 20/21 | 3 | 1 | 150 | 177 | 607 | 386.7% | 0 | -430 | 430 | 0 | 11 | 16 | 668342 | 41495 | 626847 | 668342 | 605783 | 0 | 0 | 0 | 605783 | 595755 | 95.04% | 1 | 25365 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 6341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6341 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 |  | 2022-12-05 | QTR2 | 22/23 | 108 | 802465.89
| 01 | T1777 | 43943015201 | 2020-09-30 | QTR1 | 20/21 | 4 | 3 | 325 | 607 | 638 | 125.5% | 0 | -31 | 31 | 0 | 216 | 66 | 7973682 | 92806 | 7880876 | 8225110 | 8195027 | 0 | 0 | 0 | 8195027 | 8717413 | 110.6% | 0 | 815000 | 251428 | 207 | 23 | 0 | 0 | 126514 | 115529 | 0 | 52 | 124433 | 124433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 250947 | 239963 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 |  | 2022-10-18 | QTR2 | 22/23 | 118 | 9500361.49
| 01 | T1781 | 44151815201 | 2021-01-27 | QTR3 | 20/21 | 2 | 4 | 285 | 400 | 400 | 126% | 0 | 0 | 0 | 0 | 41 | 74 | 4960436 | 59129 | 4901307 | 5450251 | 5304714 | 0 | 0 | 0 | 5304714 | 5560151 | 113.4% | 0 | 265895 | 489815 | 14 | 27 | 0 | 74 | 470632 | 0 | 0 | 0 | 17986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 489815 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2022-06-30 | QTR4 | 21/22 | 118 | 5666706.37
| 01 | T1806 | 44155915201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 250 | 391 | 391 | 112% | 1 | 0 | 0 | 0 | 134 | 7 | 7108184 | 63330 | 7044854 | 8445969 | 8418621 | 0 | 0 | 0 | 8418621 | 7803372 | 110.8% | 0 | 265502 | 1337785 | 92 | 19 | 0 | 0 | 0 | 0 | 23 | 7 | 473396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 7 | 473396 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 |  | 2023-05-01 | QTR4 | 22/23 | 115 | 6181054.02
| 01 | T1808 | 44233315201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 140 | 293 | 293 | 118.6% | 1 | 0 | 0 | 0 | 153 | 0 | 1139701 | 50000 | 1089701 | 1148801 | 1029185 | 0 | 0 | 0 | 1029185 | 1021881 | 93.78% | 1 | 1796 | 9100 | 105 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-03-17 | QTR3 | 22/23 | 108 | 1098275.5
| 01 | T1817 | 44068815201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 80 | 165 | 165 | 133.8% | 0 | 0 | 0 | 0 | 85 | 0 | 650650 | 18505 | 632145 | 655279 | 608957 | 0 | 0 | 0 | 608957 | 609408 | 96.4% | 1 | 451 | 4629 | 47 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 8153 | 45738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 15989 | 45738 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 |  | 2022-12-13 | QTR2 | 22/23 | 115 | 447609.94
| 01 | T1826 | 44421215201 | 2021-08-25 | QTR1 | 21/22 | 1 | 3 | 107 | 259 | 259 | 116.8% | 1 | 0 | 0 | 0 | 44 | 108 | 1045874 | 41345 | 1004529 | 1076047 | 1015157 | 0 | 0 | 0 | 1015157 | 994639 | 99.02% | 1 | 0 | 30174 | 114 | 20 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10825 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2023-03-20 | QTR3 | 22/23 | 118 | 898648.05
| 01 | T1828 | 44033715201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 97 | 129 | 129 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 560933 | 21933 | 539000 | 623460 | 604533 | 0 | 0 | 0 | 604533 | 604533 | 112.2% | 0 | 0 | 62527 | 31 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 62527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65533 | 0 | F823160551 | LEON AMERICA CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-09-25 | QTR1 | 23/24 |  | 2023-05-15 | QTR4 | 22/23 | 113 | 517232.45 | B0 | ACC - LUMP SUM
| 01 | T1834 | 44632015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 215 | 280 | 272 | 96.28% | 1 | 8 | 0 | 0 | 65 | 0 | 4197476 | 50000 | 4147476 | 4197476 | 3945832 | 0 | 0 | 0 | 3945832 | 3902393 | 94.09% | 1 | -43439 | 0 | 47 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 |  | 2023-06-22 | QTR4 | 22/23 | 113 | 4322110.94
| 01 | T1839 | 44012715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 0 | 130 | 175 | 175 | 100% | 1 | 0 | 0 | 0 | 45 | 0 | 461461 | 21100 | 440361 | 461461 | 428726 | 0 | 0 | 0 | 428726 | 428726 | 97.36% | 1 | 0 | 0 | 29 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2023-03-06 | QTR3 | 22/23 | 115 | 438393.45
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 12 | 24 | 51 | 2929 | 4437 | 4822 | 58.33% | 7 | -385 | 461 | 0 | 1176 | 332 | 76427290 | 659643 | 75767647 | 79680885 | 79324637 | 0 | 0 | 0 | 79324637 | 80677636 | 58.33% | 7 | 3280495 | 3253596 | 915 | 261 | 0 | 116 | 1078406 | 174650 | 81 | 64 | 1395799 | 252293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91012 | 0 | 0 | 0 | 19174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 69462 | 88730 | 0 | 0 | 0 | 0 | 0 | 0 | -287200 | 0 | 108 | 180 | 2366654 | 515673
| 01 | E1U12 | 44155315201 | 2021-09-16 | QTR1 | 21/22 | 2 | 4 | 300 | 439 | 422 | 94.33% | 1 | 17 | 0 | 0 | 139 | 0 | 6272386 | 62629 | 6209757 | 6303322 | 6506395 | 0 | 0 | 0 | 6506395 | 6911842 | 111.3% | 0 | 427490 | 30935 | 115 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 8892 | 976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13429 | 976 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-12 | QTR1 | 23/24 |  | 2023-05-12 | QTR4 | 22/23 | 108 | 6222847.06
| 01 | E1U14 | 44477715201 | 2021-12-02 | QTR2 | 21/22 | 2 | 2 | 160 | 222 | 222 | 107.5% | 1 | 0 | 0 | 0 | 62 | 0 | 3819554 | 50000 | 3769554 | 3657701 | 3521817 | 0 | 0 | 0 | 3521817 | 3658011 | 97.04% | 1 | 136195 | -161853 | 29 | 21 | 12 | 0 | 56568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -218421 | 0 | 12 | 0 | -161853 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-07-21 | QTR1 | 23/24 |  | 2023-03-03 | QTR3 | 22/23 | 115 | 3928132.77 | B0 | ACC - LUMP SUM
| 01 | E1U17 | 44594115201 | 2022-02-17 | QTR3 | 21/22 | 1 | 0 | 150 | 171 | 166 | 96.67% | 1 | 5 | 0 | 0 | 21 | 0 | 722056 | 48017 | 674039 | 722056 | 642082 | 0 | 0 | 0 | 642082 | 642815 | 95.37% | 1 | 733 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-03-17 | QTR3 | 22/23 | 115 | 1070560.76 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1V07 | 44023115201 | 2022-09-15 | QTR1 | 22/23 | 1 | 3 | 75 | 75 | 72 | 96% | 1 | 3 | 0 | 0 | 0 | 0 | 289419 | 14419 | 275000 | 311381 | 315649 | 0 | 0 | 0 | 315649 | 315649 | 114.8% | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 6636 | 0 | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28598 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2023-08-09 | QTR1 | 23/24 |  | 2023-03-29 | QTR3 | 22/23 | 118 | 331704.75
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 4 | 6 | 9 | 685 | 907 | 882 | 100% | 4 | 25 | 0 | 0 | 222 | 0 | 11103415 | 175065 | 10928350 | 10994460 | 10985943 | 0 | 0 | 0 | 10985943 | 11528317 | 50% | 2 | 564418 | -108956 | 148 | 62 | 12 | 0 | 63204 | 0 | 0 | 0 | 30854 | 976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -218421 | 0 | 12 | 0 | -119826 | 976
| District 01 Totals |  |  |  |  | 16 | 30 | 60 | 3614 | 5344 | 5704 | 68.75% | 11 | -360 | 461 | 0 | 1398 | 332 | 87530705 | 834708 | 86695997 | 90675345 | 90310580 | 0 | 0 | 0 | 90310580 | 92205953 | 56.25% | 9 | 3844913 | 3144640 | 1063 | 323 | 12 | 116 | 1141610 | 174650 | 81 | 64 | 1426653 | 253269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92800 | 0 | 0 | 0 | 21924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 69462 | 88730 | 0 | 0 | 0 | 0 | 0 | 0 | -505621 | 0 | 120 | 180 | 2246828 | 516649
| 02 | T2703 | 21272425201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 550 | 719 | 968 | 145.3% | 0 | -249 | 249 | 0 | 169 | 0 | 11717625 | 120 | 11717505 | 11666748 | 11573612 | 0 | 0 | 0 | 11573612 | 10334162 | 88.19% | 1 | -1239450 | -50877 | 123 | 46 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68877 | 0 | 0 | 0 | -50877 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 |  | 2021-05-03 | QTR4 | 20/21 | 209 | 12539660.43
| 02 | T2725 | 42307145201 | 2018-12-05 | QTR2 | 18/19 | 1 | 5 | 300 | 737 | 737 | 185.3% | 0 | 0 | 0 | 0 | 181 | 256 | 7294444 | 68754 | 7225690 | 7636147 | 7798283 | 0 | 0 | 0 | 7798283 | 7754246 | 107.3% | 1 | -44037 | 341703 | 85 | 96 | 0 | 27 | 92502 | 0 | 0 | 229 | 220039 | 17548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4989 | 0 | 0 | 0 | 6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 330105 | 23598 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2021-06-17 | QTR4 | 20/21 | 214 | 7079691.78
| 02 | T2749 | 43946715201 | 2019-09-25 | QTR1 | 19/20 | 3 | 10 | 600 | 1149 | 1149 | 134% | 0 | 0 | 0 | 0 | 265 | 284 | 11950705 | 126323 | 11824382 | 12606239 | 12535468 | 0 | 0 | 0 | 12535468 | 12707911 | 107.5% | 1 | 309266 | 655533 | 237 | 108 | 0 | 39 | 488108 | 0 | 0 | 59 | 227908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 721990 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-28 | QTR1 | 23/24 |  | 2023-02-27 | QTR3 | 22/23 | 208 | 11844644.47
| 02 | T2802 | 43575715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 180 | 523 | 523 | 220% | 0 | 0 | 0 | 0 | 29 | 314 | 1262262 | 50000 | 1212262 | 1262262 | 1249368 | 0 | 0 | 0 | 1249368 | 1249498 | 103.1% | 1 | 130 | 0 | 103 | 24 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2022-12-23 | QTR2 | 22/23 | 208 | 1338362.89
| 02 | T2803 | 44126115201 | 2021-05-26 | QTR4 | 20/21 | 2 | 3 | 325 | 487 | 487 | 124.6% | 0 | 0 | 0 | 0 | 162 | 0 | 4633748 | 75000 | 4558748 | 3852057 | 3929376 | 0 | 0 | 0 | 3929376 | 4154909 | 91.14% | 1 | 225533 | -781691 | 40 | 42 | 30 | 0 | -739805 | 0 | 0 | 0 | 7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -732738 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2023-01-06 | QTR3 | 22/23 | 208 | 4540382.58
| 02 | T2813 | 43617815201 | 2021-06-09 | QTR4 | 20/21 | 3 | 2 | 350 | 501 | 501 | 112% | 1 | 0 | 0 | 0 | 109 | 42 | 6155492 | 64024 | 6091468 | 6241492 | 6261727 | 0 | 0 | 0 | 6261727 | 6665942 | 109.4% | 1 | 404215 | 86000 | 72 | 37 | 0 | 42 | 61451 | 0 | 0 | 0 | 59384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 120835 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 |  | 2023-01-20 | QTR3 | 22/23 | 209 | 7776561.61
| 02 | T2821 | 44327315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 150 | 289 | 271 | 122.7% | 0 | 18 | 0 | 0 | 118 | 21 | 4876894 | 52518 | 4824376 | 4984966 | 5022406 | 0 | 0 | 0 | 5022406 | 5415141 | 112.2% | 0 | 392735 | 108073 | 77 | 10 | 0 | 21 | 125561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 21 | 125561 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 |  | 2022-10-13 | QTR2 | 22/23 | 216 | 5483810.94
| 02 | T2824 | 44327415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 2 | 250 | 455 | 453 | 105.2% | 1 | 2 | 0 | 0 | 190 | 15 | 3471681 | 50000 | 3421681 | 3603585 | 3475517 | 0 | 0 | 0 | 3475517 | 3614982 | 105.6% | 1 | 141674 | 131904 | 166 | 24 | 0 | 0 | 14150 | 0 | 0 | 15 | 130039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 15 | 144189 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-05-04 | QTR4 | 22/23 | 216 | 3836185.04
| 02 | T2825 | 44328215201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 75 | 125 | 124 | 152% | 0 | 1 | 0 | 0 | 10 | 40 | 698919 | 27456 | 671464 | 698919 | 656099 | 0 | 0 | 0 | 656099 | 656099 | 97.71% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-14 | QTR1 | 23/24 |  | 2022-06-28 | QTR4 | 21/22 | 209 | 629198.54
| 02 | T2826 | 44331115201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 220 | 264 | 264 | 100% | 1 | 0 | 0 | 0 | 44 | 0 | 8657266 | 87492 | 8569774 | 8657266 | 8107793 | 0 | 0 | 0 | 8107793 | 8099899 | 94.52% | 1 | -7895 | 0 | 23 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-29 | QTR1 | 23/24 |  | 2023-05-05 | QTR4 | 22/23 | 209 | 10016766.94
| 02 | T2833 | 44325815201 | 2022-01-12 | QTR3 | 21/22 | 1 | 0 | 210 | 235 | 235 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 6173212 | 71171 | 6102041 | 6173212 | 6149692 | 0 | 0 | 0 | 6149692 | 6808147 | 111.6% | 0 | 658455 | 0 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2022-11-23 | QTR2 | 22/23 | 214 | 7484487.76
| 02 | T2837 | 44329415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 0 | 180 | 262 | 260 | 113.9% | 1 | 2 | 0 | 0 | 55 | 27 | 1371850 | 50000 | 1321850 | 1371850 | 1320562 | 0 | 0 | 0 | 1320562 | 1320562 | 99.9% | 1 | 0 | 0 | 29 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 |  | 2023-01-19 | QTR3 | 22/23 | 208 | 1352767.24
| 02 | T2855 | 43935815201 | 2021-06-09 | QTR4 | 20/21 | 2 | 0 | 350 | 464 | 459 | 106.6% | 1 | 5 | 0 | 0 | 86 | 28 | 7918962 | 100000 | 7818962 | 8057360 | 7962203 | 0 | 0 | 0 | 7962203 | 8267055 | 105.7% | 1 | 304853 | 0 | 42 | 44 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 |  | 2023-02-23 | QTR3 | 22/23 | 209 | 7233767.77
| 02 | T2857 | 44721115201 | 2022-01-26 | QTR3 | 21/22 | 1 | 0 | 120 | 193 | 185 | 131.7% | 0 | 8 | 0 | 0 | 27 | 46 | 1077522 | 44955 | 1032567 | 1077522 | 1075156 | 0 | 0 | 0 | 1075156 | 1075156 | 104.1% | 1 | 0 | 0 | 16 | 11 | 0 | 30 | 18350 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 18350 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2022-10-14 | QTR2 | 22/23 | 208 | 1339271.36
| 02 | T2869 | 43567925201 | 2022-06-08 | QTR4 | 21/22 | 2 | 0 | 180 | 199 | 178 | 88.33% | 1 | 21 | 0 | 0 | 19 | 0 | 1298306 | 50000 | 1248306 | 1298306 | 1209436 | 0 | 0 | 0 | 1209436 | 1209097 | 96.86% | 1 | -339 | 0 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 |  | 2023-04-19 | QTR4 | 22/23 | 209 | 1554775.94
| 02 | T2873 | 44557615201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 90 | 90 | 19 | 21.11% | 1 | 71 | 0 | 0 | 0 | 0 | 240110 | 17791 | 222319 | 240110 | 185940 | 0 | 0 | 0 | 185940 | 185940 | 83.64% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-03-31 | QTR3 | 22/23 | 208 | 402519.71
| 02 | T2923 | 44542625201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 74 | 101 | 94 | 91.89% | 1 | 7 | 0 | 0 | 26 | 1 | 212969 | 11187 | 201781 | 212969 | 198096 | 0 | 0 | 0 | 198096 | 198096 | 98.17% | 1 | 0 | 0 | 15 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-09-05 | QTR1 | 23/24 |  | 2023-03-01 | QTR3 | 22/23 | 208 | 251711.77
| 02 | T9023 | 44624515223 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 250 | 733 | 730 | 266.8% | 0 | 3 | 0 | 0 | 483 | 0 | 3516622 | 50000 | 3466622 | 3516622 | 3642093 | 0 | 0 | 0 | 3642093 | 3642131 | 105.1% | 1 | 38 | 0 | 14 | 49 | 420 | 0 | 0 | 0 | 0 | 0 | 30591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 41498 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-09-27 | QTR1 | 23/24 |  | 2023-08-03 | QTR1 | 23/24 | 209 | 3117936.11
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 18 | 25 | 25 | 4454 | 7526 | 7637 | 50% | 9 | -111 | 249 | 0 | 1998 | 1074 | 82528589 | 996791 | 81531798 | 83157632 | 82352827 | 0 | 0 | 0 | 82352827 | 83358973 | 88.89% | 16 | 1145178 | 490645 | 1070 | 575 | 450 | 404 | 78317 | 0 | 0 | 319 | 676876 | 17548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15896 | 0 | 0 | 0 | 12499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 6050 | 6050 | 91 | 40 | 0 | 0 | 0 | 0 | -68877 | 0 | 541 | 790 | 720761 | 23598
[29 empty] | 0% | 1
| Dist 02 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 02 Totals |  |  |  |  | 18 | 25 | 25 | 4454 | 7526 | 7637 | 50% | 9 | -111 | 249 | 0 | 1998 | 1074 | 82528589 | 996791 | 81531798 | 83157632 | 82352827 | 0 | 0 | 0 | 82352827 | 83358973 | 94.44% | 17 | 1145178 | 490645 | 1070 | 575 | 450 | 404 | 78317 | 0 | 0 | 319 | 676876 | 17548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15896 | 0 | 0 | 0 | 12499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 6050 | 6050 | 91 | 40 | 0 | 0 | 0 | 0 | -68877 | 0 | 541 | 790 | 720761 | 23598
| 03 | T3579 | 41413245201 | 2016-08-31 | QTR1 | 16/17 | 3 | 19 | 1090 | 1999 | 2171 | 139.2% | 0 | -172 | 172 | 0 | 798 | 111 | 42140000 | 150000 | 41990000 | 43136516 | 44789798 | 0 | 0 | 0 | 44789798 | 45150067 | 107.5% | 1 | 523319 | 996516 | 442 | 212 | 4 | 40 | 380492 | 1569 | 0 | 27 | 349096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 8 | 165208 | 0 | 0 | 0 | 18045 | 18045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -159429 | 0 | 80 | 121 | 848413 | 114614 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2022-10-21 | QTR2 | 22/23 | 308 | 37004160.16
| 03 | T3598 | 43357725201 | 2021-12-08 | QTR2 | 21/22 | 2 | 0 | 210 | 314 | 314 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 1449372 | 9292 | 1440080 | 1449372 | 1245314 | 0 | 0 | 0 | 1245314 | 1245462 | 86.49% | 1 | 147 | 0 | 73 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-01-13 | QTR3 | 22/23 | 308 | 1387512.95
| 03 | T3604 | 43282815201 | 2019-02-27 | QTR3 | 18/19 | 2 | 4 | 925 | 1322 | 1301 | 103.1% | 1 | 21 | 0 | 0 | 397 | 0 | 10228411 | 103267 | 10125144 | 10251581 | 10265075 | 0 | 0 | 0 | 10265075 | 10328004 | 102% | 1 | 62929 | 23170 | 263 | 84 | 0 | 0 | 24478 | 0 | 0 | 0 | 5148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 120 | 68927 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2022-12-06 | QTR2 | 22/23 | 308 | 10230057.88
| 03 | T3691 | 43717815201 | 2020-11-18 | QTR2 | 20/21 | 1 | 2 | 480 | 640 | 661 | 109% | 1 | -21 | 21 | 0 | 160 | 0 | 4269226 | 50000 | 4219226 | 4374816 | 4363593 | 0 | 0 | 0 | 4363593 | 4394715 | 104.2% | 1 | 107651 | 105591 | 98 | 40 | 8 | 0 | 95913 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 23399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 149628 | 0 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 |  | 2022-12-04 | QTR2 | 22/23 | 308 | 4154505.73
| 03 | T3703 | 43649925201 | 2019-09-25 | QTR1 | 19/20 | 3 | 0 | 150 | 292 | 262 | 100% | 1 | 30 | 0 | 0 | 112 | 30 | 2458081 | 51140 | 2406941 | 2458081 | 2572160 | 0 | 0 | 0 | 2572160 | 2554701 | 106.1% | 1 | -17459 | 0 | 100 | 12 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2020-10-02 | QTR2 | 20/21 | 314 | 2031385.77
| 03 | T3704 | 43938815201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 150 | 222 | 220 | 106% | 1 | 2 | 0 | 0 | 72 | 0 | 1462111 | 0 | 1462111 | 1462111 | 1360760 | 0 | 0 | 0 | 1360760 | 1370361 | 93.72% | 1 | 9601 | 0 | 49 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 |  | 2022-10-07 | QTR2 | 22/23 | 313 | 1750125.19
| 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 1 | 365 | 689 | 689 | 117.8% | 1 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6166449 | 6679471 | 0 | 0 | 0 | 6679471 | 7791843 | 128.1% | 0 | 1176465 | 0 | 170 | 89 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 21 | 67784 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29
| 03 | T3743 | 44173015201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 45 | 83 | 80 | 93.33% | 1 | 3 | 0 | 0 | 38 | 0 | 187229 | 12274 | 174955 | 187229 | 175598 | 0 | 0 | 0 | 175598 | 166353 | 95.08% | 1 | -9245 | 0 | 35 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2020-08-14 | QTR1 | 20/21 | 314 | 262871.46
| 03 | T3750 | 43811125201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 95 | 131 | 130 | 98.95% | 1 | 1 | 0 | 0 | 36 | 0 | 987732 | 41493 | 946239 | 927591 | 903555 | 0 | 0 | 0 | 903555 | 903555 | 95.49% | 1 | 0 | -60141 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-05-12 | QTR4 | 22/23 | 314 | 912225.16
| 03 | T3793 | 43467715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 3 | 230 | 481 | 480 | 106.1% | 1 | 1 | 0 | 0 | 236 | 15 | 6283852 | 73669 | 6210183 | 6727204 | 6844151 | 0 | 0 | 0 | 6844151 | 7176797 | 115.6% | 0 | 332646 | 443352 | 186 | 50 | 0 | 7 | 378034 | 0 | 0 | 8 | 133625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 511659 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2023-06-28 | QTR4 | 22/23 | 308 | 7460138.28
| 03 | T3794 | 44364415201 | 2022-06-15 | QTR4 | 21/22 | 1 | 1 | 100 | 125 | 92 | 67% | 1 | 33 | 0 | 0 | 25 | 0 | 2537432 | 50000 | 2487432 | 2537432 | 2741257 | 0 | 0 | 0 | 2741257 | 2721406 | 109.4% | 1 | -19851 | 0 | 14 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-03-06 | QTR3 | 22/23 | 313 | 2975156.64
| 03 | T3823 | 44565615201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 110 | 120 | 86 | 69.09% | 1 | 34 | 0 | 0 | 10 | 0 | 2199429 | 50000 | 2149429 | 2199429 | 2316440 | 0 | 0 | 0 | 2316440 | 2316440 | 107.8% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 |  | 2023-06-22 | QTR4 | 22/23 | 308 | 2955598
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 12 | 20 | 31 | 3950 | 6418 | 6486 | 91.67% | 11 | -68 | 193 | 0 | 2291 | 177 | 80369324 | 674775 | 79694549 | 81877811 | 84257172 | 0 | 0 | 0 | 84257172 | 86119704 | 83.33% | 10 | 2166203 | 1508488 | 1456 | 564 | 36 | 47 | 878917 | 1569 | 0 | 65 | 469963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 8 | 227908 | 0 | 0 | 0 | 18045 | 18045 | 0 | 0 | 0 | 0 | 0 | 141 | 97865 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | -159429 | 0 | 215 | 307 | 1628270 | 114614
| 03 | E3S70 | 43992635201 | 2021-05-13 | QTR4 | 20/21 | 2 | 1 | 395 | 597 | 597 | 112.9% | 1 | 0 | 0 | 0 | 202 | 0 | 8497804 | 70195 | 8427609 | 8518932 | 8878921 | 0 | 0 | 0 | 8878921 | 8997063 | 106.8% | 1 | 136935 | 21128 | 102 | 49 | 0 | 0 | 12464 | 0 | 30 | 0 | 28861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 41325 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 |  | 2023-03-30 | QTR3 | 22/23 | 321 | 7939245.14
| 03 | E3U04 | 21904225201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 65 | 65 | 45 | 69.23% | 1 | 20 | 0 | 0 | 0 | 0 | 278090 | 21110 | 256980 | 278090 | 249120 | 0 | 0 | 0 | 249120 | 249120 | 96.94% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2023-05-18 | QTR4 | 22/23 | 314 | 454253.61
| 03 | E3U84 | 44365915201 | 2022-02-10 | QTR3 | 21/22 | 2 | 1 | 175 | 266 | 264 | 98.86% | 1 | 2 | 0 | 0 | 91 | 0 | 3254371 | 50000 | 3204371 | 3263484 | 3285954 | 0 | 0 | 0 | 3285954 | 3378196 | 105.4% | 1 | 92242 | 9113 | 66 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-02-18 | QTR3 | 22/23 | 308 | 3044605.63
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 3 | 5 | 2 | 635 | 928 | 906 | 100% | 3 | 22 | 0 | 0 | 293 | 0 | 12030265 | 141305 | 11888960 | 12060506 | 12413995 | 0 | 0 | 0 | 12413995 | 12624379 | 100% | 3 | 229177 | 30241 | 168 | 74 | 0 | 0 | 12464 | 0 | 30 | 0 | 40991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 53455 | 0
| District 03 Totals |  |  |  |  | 15 | 25 | 33 | 4585 | 7346 | 7392 | 93.33% | 14 | -46 | 193 | 0 | 2584 | 177 | 92399589 | 816080 | 91583509 | 93938317 | 96671167 | 0 | 0 | 0 | 96671167 | 98744083 | 86.67% | 13 | 2395380 | 1538729 | 1624 | 638 | 36 | 47 | 891381 | 1569 | 30 | 65 | 510954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 8 | 227908 | 0 | 0 | 0 | 18045 | 18045 | 0 | 0 | 0 | 0 | 0 | 141 | 97865 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | -159429 | 0 | 266 | 307 | 1681725 | 114614
| 04 | T4562 | 43177035201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 384 | 492 | 492 | 100% | 1 | 0 | 0 | 0 | 108 | 0 | 3588218 | 50000 | 3538218 | 3660295 | 3546957 | 0 | 0 | 0 | 3546957 | 3613971 | 102.1% | 1 | 67014 | 72077 | 71 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 91148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14596 | 0 | 0 | 0 | -11203 | 0 | 0 | 0 | 94541 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2023-03-31 | QTR3 | 22/23 | 412 | 3732217.16
| 04 | T4573 | 43206675201 | 2021-07-28 | QTR1 | 21/22 | 2 | 3 | 195 | 470 | 465 | 97.44% | 1 | 5 | 0 | 0 | 275 | 0 | 3496673 | 50000 | 3446673 | 3721036 | 3515537 | 0 | 0 | 0 | 3515537 | 3603841 | 104.6% | 1 | 88304 | 224363 | 249 | 26 | 0 | 0 | -2094 | 0 | 0 | 0 | 267470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265376 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 |  | 2023-04-19 | QTR4 | 22/23 | 412 | 3657623.88
| 04 | T4594 | 43999015201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 212 | 352 | 351 | 113.7% | 1 | 1 | 0 | 0 | 140 | 0 | 2000000 | 50000 | 1950000 | 2008938 | 1868868 | 0 | 0 | 0 | 1868868 | 1862040 | 95.49% | 1 | 2110 | 8938 | 85 | 25 | 0 | 0 | 11450 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 11450 | 0 | F650814419 | ZAHLENE ENTERPRISES INC. | N/A | N/A | N/A | N/A | 2023-07-24 | QTR1 | 23/24 |  | 2023-05-31 | QTR4 | 22/23 | 412 | 2421037.86
| 04 | T4597 | 44177515201 | 2022-01-26 | QTR3 | 21/22 | 2 | 1 | 178 | 274 | 274 | 100% | 1 | 0 | 0 | 0 | 96 | 0 | 957661 | 40792 | 916869 | 958736 | 900445 | 0 | 0 | 0 | 900445 | 899370 | 98.09% | 1 | 0 | 1075 | 72 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 8111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8111 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-05-11 | QTR4 | 22/23 | 409 | 927528.71
| 04 | T4607 | 43999315201 | 2022-03-30 | QTR3 | 21/22 | 3 | 1 | 222 | 287 | 287 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 1967721 | 50000 | 1917721 | 1967721 | 1856962 | 0 | 0 | 0 | 1856962 | 1856374 | 96.8% | 1 | 2046 | 2634 | 47 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-09-18 | QTR1 | 23/24 |  | 2023-04-30 | QTR4 | 22/23 | 412 | 2135578.09
| 04 | T4614 | 44399415201 | 2022-04-27 | QTR4 | 21/22 | 2 | 3 | 227 | 321 | 321 | 104.8% | 1 | 0 | 0 | 0 | 94 | 0 | 4491996 | 50000 | 4441996 | 4563991 | 4393362 | 0 | 0 | 0 | 4393362 | 4376466 | 98.52% | 1 | -6110 | 71995 | 57 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 86648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51997 | 0 | 0 | 0 | 5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33274 | 33274 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 73161 | 33274 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-06-14 | QTR4 | 22/23 | 409 | 4062646.65
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 6 | 13 | 11 | 1418 | 2196 | 2190 | 100% | 6 | 6 | 0 | 0 | 778 | 0 | 16502269 | 290792 | 16211477 | 16880717 | 16082131 | 0 | 0 | 0 | 16082131 | 16212062 | 100% | 6 | 153364 | 381082 | 581 | 156 | 0 | 0 | 9356 | 0 | 30 | 0 | 460217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51997 | 0 | 0 | 0 | 5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33274 | 33274 | 0 | 0 | 0 | 0 | 11 | 0 | 14596 | 0 | 0 | 0 | -11203 | 0 | 41 | 0 | 459479 | 33274
| 04 | E4T68 | 44074615201 | 2020-05-06 | QTR4 | 19/20 | 6 | 1 | 730 | 939 | 934 | 99.32% | 1 | 5 | 0 | 0 | 209 | 0 | 17557323 | 125751 | 17431572 | 17588765 | 16726429 | 0 | 0 | 0 | 16726429 | 16980455 | 97.41% | 1 | 254025 | 31442 | 144 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31442 | 0 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37742 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-02-02 | QTR3 | 22/23 | 412 | 12972092.8
| 04 | E4U99 | 44146215201 | 2021-05-07 | QTR4 | 20/21 | 1 | 8 | 228 | 525 | 518 | 144.7% | 0 | 7 | 0 | 0 | 188 | 109 | 12200214 | 101674 | 12098540 | 13805766 | 14066534 | 0 | 0 | 0 | 14066534 | 14068003 | 116.3% | 0 | 140138 | 1605552 | 165 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 1129185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 448054 | 0 | 0 | 0 | 23731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1600970 | 0 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-06-23 | QTR4 | 22/23 | 412 | 10374505.8 | B10 | ACC - BONUS/INCENT/DISINCENT
| 04 | E4V75 | 44172215201 | 2022-02-04 | QTR3 | 21/22 | 2 | 4 | 156 | 248 | 248 | 104.5% | 1 | 0 | 0 | 0 | 92 | 0 | 1455255 | 50000 | 1405255 | 1515282 | 1451281 | 0 | 0 | 0 | 1451281 | 1452112 | 103.3% | 1 | 7917 | 60027 | 72 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 76040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 78106 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-09-01 | QTR1 | 23/24 |  | 2023-03-28 | QTR3 | 22/23 | 409 | 1403378.89
| 04 | E4V84 | 44609715201 | 2022-09-02 | QTR1 | 22/23 | 1 | 1 | 133 | 180 | 179 | 99.25% | 1 | 1 | 0 | 0 | 47 | 0 | 3147147 | 50000 | 3097147 | 3153188 | 2965886 | 0 | 0 | 0 | 2965886 | 2896248 | 93.51% | 1 | -69638 | 6041 | 43 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-08-03 | QTR1 | 23/24 | 409 | 3652108.96 | B1 | ACC - NO EXCUSE BONUS
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 4 | 10 | 14 | 1247 | 1892 | 1879 | 75% | 3 | 13 | 0 | 0 | 536 | 109 | 34359939 | 327425 | 34032514 | 36063001 | 35210130 | 0 | 0 | 0 | 35210130 | 35396818 | 75% | 3 | 332442 | 1703062 | 424 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 1137292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 479496 | 0 | 7 | 0 | 106071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 109 | 1722859 | 0
| District 04 Totals |  |  |  |  | 10 | 23 | 25 | 2665 | 4088 | 4069 | 90% | 9 | 19 | 0 | 0 | 1314 | 109 | 50862208 | 618217 | 50243991 | 52943718 | 51292261 | 0 | 0 | 0 | 51292261 | 51608880 | 90% | 9 | 485806 | 2084144 | 1005 | 261 | 0 | 0 | 9356 | 0 | 30 | 0 | 1597509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 427499 | 0 | 7 | 0 | 111308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33274 | 33274 | 0 | 0 | 0 | 0 | 11 | 0 | 14596 | 0 | 0 | 0 | -11203 | 0 | 48 | 109 | 2182338 | 33274
| 05 | T5552 | 40714345201 | 2016-06-08 | QTR4 | 15/16 | 21 | 32 | 1050 | 1826 | 1829 | 140% | 0 | -3 | 3 | 0 | 359 | 417 | 75824482 | 160000 | 75664482 | 86884143 | 89837352 | 0 | 0 | 0 | 89837352 | 90458012 | 119.6% | 0 | 815723 | 10910761 | 209 | 150 | 0 | 13 | 563442 | 81716 | 0 | 113 | 3719605 | 1534190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | -46035 | 0 | 0 | 0 | 107943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30316 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 417 | 4476317 | 1823881 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2021-10-13 | QTR2 | 21/22 | 509 | 88197361.71 | B2:B5:B7:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS
| 05 | T5733 | 44381515201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 290 | 440 | 439 | 106.6% | 1 | 1 | 0 | 0 | 130 | 20 | 7387943 | 81000 | 7306943 | 7578305 | 6929112 | 0 | 0 | 0 | 6929112 | 7638830 | 104.5% | 1 | 716998 | 190361 | 50 | 80 | 0 | 20 | 183081 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 183081 | 436 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2023-04-17 | QTR4 | 22/23 | 513 | 8754090.28
| 05 | T5738 | 44290915201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 270 | 349 | 349 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 9861239 | 100000 | 9761239 | 9880239 | 9803603 | 0 | 0 | 0 | 9803603 | 10869062 | 111.3% | 0 | 1065459 | 19000 | 40 | 39 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24350 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-02-28 | QTR3 | 22/23 | 514 | 13653415.96
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 3 | 25 | 36 | 1610 | 2615 | 2617 | 66.67% | 2 | -2 | 3 | 0 | 568 | 437 | 93073664 | 341000 | 92732664 | 104342687 | 106570067 | 0 | 0 | 0 | 106570067 | 108965904 | 33.33% | 1 | 2598180 | 11120122 | 299 | 269 | 0 | 33 | 751873 | 82152 | 0 | 113 | 3719605 | 1534190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | -46035 | 0 | 0 | 0 | 126943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30316 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 437 | 4683748 | 1824317
| 05 | E51A9 | 44102015201 | 2020-09-01 | QTR1 | 20/21 | 1 | 7 | 280 | 534 | 544 | 113.9% | 1 | -10 | 10 | 0 | 225 | 29 | 7501367 | 72000 | 7429367 | 7798794 | 7531686 | 0 | 0 | 0 | 7531686 | 7740983 | 104.2% | 1 | 222434 | 297427 | 61 | 164 | 0 | 0 | 19197 | 0 | 0 | 29 | 278231 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 297427 | 5549 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2022-05-27 | QTR4 | 21/22 | 514 | 7321146.81
| 05 | E55B4 | 44942515201 | 2022-11-01 | QTR2 | 22/23 | 1 | 0 | 170 | 174 | 149 | 85.29% | 1 | 25 | 0 | 0 | 4 | 0 | 967737 | 42032 | 925705 | 967737 | 851103 | 0 | 0 | 0 | 851103 | 851002 | 91.93% | 1 | -101 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-09-06 | QTR1 | 23/24 |  | 2023-07-10 | QTR1 | 23/24 | 514 | 882686.9
| 05 | E57A4 | 44113215201 | 2021-10-05 | QTR2 | 21/22 | 5 | 2 | 289 | 528 | 527 | 99.65% | 1 | 1 | 0 | 0 | 239 | 0 | 7424369 | 84545 | 7339824 | 7591181 | 7558842 | 0 | 0 | 0 | 7558842 | 7794728 | 106.2% | 1 | 394527 | 166812 | 75 | 164 | 0 | 0 | 15614 | 0 | 0 | 0 | 22253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63562 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-07-12 | QTR1 | 23/24 | 513 | 9276735.05
| 05 | E59A9 | 43913015201 | 2022-01-04 | QTR3 | 21/22 | 1 | 0 | 140 | 248 | 246 | 116.4% | 1 | 2 | 0 | 0 | 83 | 25 | 679529 | 24250 | 655279 | 679529 | 677096 | 0 | 0 | 0 | 677096 | 677187 | 103.3% | 1 | 92 | 0 | 49 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-06-08 | QTR4 | 22/23 | 514 | 681570.8
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 4 | 8 | 9 | 879 | 1484 | 1466 | 100% | 4 | 18 | 10 | 0 | 551 | 54 | 16573002 | 222827 | 16350175 | 17037241 | 16618727 | 0 | 0 | 0 | 16618727 | 17063900 | 100% | 4 | 616952 | 464239 | 185 | 366 | 0 | 0 | 34811 | 0 | 0 | 29 | 300484 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 25696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 360989 | 5549
| District 05 Totals |  |  |  |  | 7 | 33 | 45 | 2489 | 4099 | 4083 | 85.71% | 6 | 16 | 13 | 0 | 1119 | 491 | 109646666 | 563827 | 109082839 | 121379928 | 123188794 | 0 | 0 | 0 | 123188794 | 126029804 | 71.43% | 5 | 3215132 | 11584361 | 484 | 635 | 0 | 33 | 786684 | 82152 | 0 | 142 | 4020089 | 1539739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | -20339 | 0 | 0 | 0 | 126943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30316 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 473 | 5044737 | 1829866
| 06 | T6518 | 42918635201 | 2021-12-08 | QTR2 | 21/22 | 5 | 2 | 300 | 332 | 272 | 80% | 1 | 60 | 0 | 0 | 32 | 0 | 2919079 | 50000 | 2869079 | 2940250 | 2881342 | 0 | 0 | 0 | 2881342 | 2942048 | 102.5% | 1 | 63520 | 21171 | 17 | 15 | 0 | 0 | 16786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16786 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2023-04-22 | QTR4 | 22/23 | 613 | 3061117.05 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6519 | 43476835201 | 2022-01-26 | QTR3 | 21/22 | 3 | 1 | 300 | 347 | 274 | 75.67% | 1 | 73 | 0 | 0 | 47 | 0 | 3487287 | 50000 | 3437287 | 3497187 | 3509376 | 0 | 0 | 0 | 3509376 | 3539751 | 103% | 1 | 30375 | 9900 | 25 | 22 | 0 | 0 | 30134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47968 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2023-09-13 | QTR1 | 23/24 |  | 2023-07-05 | QTR1 | 23/24 | 613 | 3568827.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 2 | 8 | 3 | 600 | 679 | 546 | 100% | 2 | 133 | 0 | 0 | 79 | 0 | 6406366 | 100000 | 6306366 | 6437437 | 6390718 | 0 | 0 | 0 | 6390718 | 6481799 | 100% | 2 | 93895 | 31071 | 42 | 37 | 0 | 0 | 46920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64754 | 0
| 06 | E6N09 | 44480525201 | 2022-07-28 | QTR1 | 22/23 | 1 | 0 | 240 | 260 | 172 | 63.33% | 1 | 88 | 0 | 0 | 20 | 0 | 797552 | 50000 | 747552 | 797552 | 706126 | 0 | 0 | 0 | 706126 | 706126 | 94.46% | 1 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-08-11 | QTR1 | 23/24 |  | 2023-06-29 | QTR4 | 22/23 | 613 | 1509363.9
| 06 | E6N47 | 44445015201 | 2022-05-26 | QTR4 | 21/22 | 1 | 2 | 250 | 272 | 220 | 79.2% | 1 | 52 | 0 | 0 | 22 | 0 | 2697327 | 50000 | 2647327 | 2771657 | 2731695 | 0 | 0 | 0 | 2731695 | 2718704 | 102.7% | 1 | -12991 | 74329 | 14 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 41276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89415 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 |  | 2023-05-24 | QTR4 | 22/23 | 636 | 2883318.39 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6N55 | 44196815201 | 2021-08-26 | QTR1 | 21/22 | 1 | 0 | 280 | 460 | 459 | 119.3% | 1 | 1 | 0 | 0 | 180 | 0 | 757063 | 47154 | 709909 | 757063 | 654819 | 0 | 0 | 0 | 654819 | 654819 | 92.24% | 1 | 0 | 0 | 101 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2023-04-06 | QTR4 | 22/23 | 636 | 1042435.8
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 3 | 3 | 2 | 770 | 992 | 851 | 100% | 3 | 141 | 0 | 0 | 222 | 0 | 4251942 | 147154 | 4104788 | 4326272 | 4092640 | 0 | 0 | 0 | 4092640 | 4079649 | 100% | 3 | -12991 | 74329 | 135 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 41276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48138 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 89415 | 0
| District 06 Totals |  |  |  |  | 5 | 11 | 5 | 1370 | 1671 | 1397 | 100% | 5 | 274 | 0 | 0 | 301 | 0 | 10658308 | 247154 | 10411154 | 10763709 | 10483358 | 0 | 0 | 0 | 10483358 | 10561448 | 100% | 5 | 80904 | 105400 | 177 | 69 | 0 | 0 | 46920 | 0 | 0 | 0 | 41276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65972 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 154169 | 0
| 07 | T7428 | 43258435201 | 2019-02-27 | QTR3 | 18/19 | 3 | 6 | 445 | 671 | 685 | 128.3% | 0 | -14 | 14 | 0 | 114 | 112 | 9277781 | 90000 | 9187781 | 9481539 | 10184938 | 0 | 0 | 0 | 10184938 | 10081240 | 109.7% | 1 | -98504 | 203759 | 58 | 56 | 0 | 21 | 283799 | 0 | 0 | 0 | 16679 | 10786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -96529 | 0 | 0 | 0 | 12534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 216484 | 10786 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2021-06-25 | QTR4 | 20/21 | 796 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | T7451 | 43982985201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 170 | 178 | 550 | 318.8% | 0 | -372 | 372 | 0 | 8 | 0 | 698558 | 34000 | 664558 | 698558 | 557380 | 0 | 0 | 0 | 557380 | 531562 | 79.99% | 1 | -25818 | 0 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2022-07-07 | QTR1 | 22/23 | 799 | 691075.3
| 07 | T7468 | 44138615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 3 | 498 | 556 | 514 | 87.75% | 1 | 42 | 0 | 0 | 77 | -19 | 9161461 | 85000 | 9076461 | 9416662 | 9386983 | 0 | 0 | 0 | 9386983 | 9736387 | 107.3% | 1 | 388067 | 255200 | 53 | 24 | 0 | 0 | 337633 | 0 | 0 | 0 | 90042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 0 | -19 | 324328 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-13 | QTR1 | 23/24 |  | 2022-12-02 | QTR2 | 22/23 | 798 | 9040000
| 07 | T7498 | 44332015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 0 | 120 | 127 | 127 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 1340863 | 50000 | 1290863 | 1340863 | 1268582 | 0 | 0 | 0 | 1268582 | 1256582 | 97.34% | 1 | -12000 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 |  | 2023-05-22 | QTR4 | 22/23 | 796 | 2027300
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 4 | 6 | 10 | 1233 | 1532 | 1876 | 50% | 2 | -344 | 386 | 0 | 206 | 93 | 20478663 | 259000 | 20219663 | 20937622 | 21397883 | 0 | 0 | 0 | 21397883 | 21605771 | 100% | 4 | 251745 | 458959 | 118 | 88 | 0 | 21 | 621432 | 0 | 0 | 0 | 106721 | 10786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -83887 | 0 | 0 | 0 | 14653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 0 | 93 | 553454 | 10786
| 07 | E7N90 | 44822115201 | 2022-01-12 | QTR3 | 21/22 | 1 | 1 | 120 | 172 | 172 | 117.5% | 1 | 0 | 0 | 0 | 52 | 0 | 679686 | 28000 | 651686 | 695950 | 640611 | 0 | 0 | 0 | 640611 | 640611 | 98.3% | 1 | 0 | 16264 | 8 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-04-20 | QTR4 | 22/23 | 799 | 644500
| 07 | E7N95 | 44025115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 3 | 240 | 317 | 314 | 98.75% | 1 | 3 | 0 | 0 | 77 | 0 | 6430299 | 84000 | 6346299 | 6566839 | 6774752 | 0 | 0 | 0 | 6774752 | 7323867 | 115.4% | 0 | 551655 | 136540 | 52 | 25 | 0 | 0 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33706 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117706 | 33706 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 |  | 2023-02-24 | QTR3 | 22/23 | 796 | 8690700
| 07 | E7O11 | 44166515201 | 2022-02-09 | QTR3 | 21/22 | 2 | 0 | 180 | 220 | 220 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 3049631 | 50000 | 2999631 | 3049631 | 3013462 | 0 | 0 | 0 | 3013462 | 3013181 | 100.5% | 1 | -281 | 0 | 21 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-06-14 | QTR4 | 22/23 | 798 | 2409700
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 3 | 4 | 4 | 540 | 709 | 706 | 100% | 3 | 3 | 0 | 0 | 169 | 0 | 10159616 | 162000 | 9997616 | 10312420 | 10428825 | 0 | 0 | 0 | 10428825 | 10977659 | 66.67% | 2 | 551374 | 152804 | 81 | 67 | 0 | 0 | 84000 | 0 | 0 | 0 | 16264 | 16264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33706 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133970 | 49970
| District 07 Totals |  |  |  |  | 7 | 10 | 14 | 1773 | 2241 | 2582 | 71.43% | 5 | -341 | 386 | 0 | 375 | 93 | 30638279 | 421000 | 30217279 | 31250042 | 31826708 | 0 | 0 | 0 | 31826708 | 32583430 | 85.71% | 6 | 803119 | 611763 | 199 | 155 | 0 | 21 | 705432 | 0 | 0 | 0 | 122985 | 27050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -83887 | 0 | 0 | 0 | 48359 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 0 | 93 | 687424 | 60756
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8Q78 | 43554615201 | 2018-06-15 | QTR4 | 17/18 | 2 | 27 | 1430 | 1594 | 1265 | 76.99% | 1 | 329 | 0 | 0 | 164 | 0 | 143269821 | 150000 | 143119821 | 145759356 | 145166429 | 0 | 0 | 0 | 145166429 | 144192875 | 100.7% | 1 | -873129 | 2489535 | 81 | 83 | 0 | 0 | 398577 | 0 | 0 | 0 | 1404790 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131931 | 0 | 0 | 0 | 551048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140484 | 0 | 0 | 0 | 2359317 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 |  | 2022-03-01 | QTR3 | 21/22 | 854 | 156867749.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 08 | E8R77 | 43798615201 | 2019-05-14 | QTR4 | 18/19 | 3 | 5 | 738 | 1039 | 1039 | 103.8% | 1 | 0 | 0 | 0 | 301 | 0 | 31832323 | 150000 | 31682323 | 32865375 | 32938830 | 0 | 0 | 0 | 32938830 | 32271398 | 101.9% | 1 | -667433 | 1033052 | 175 | 98 | 0 | 0 | 62194 | 0 | 0 | 0 | 38182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 960260 | 0 | 0 | 0 | 77444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1138080 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2023-08-10 | QTR1 | 23/24 |  | 2022-08-17 | QTR1 | 22/23 | 854 | 33799887.12
| 08 | E8R97 | 43730045201 | 2019-09-17 | QTR1 | 19/20 | 1 | 35 | 939 | 1012 | 938 | 92.12% | 1 | 74 | 0 | 0 | 73 | 0 | 139979406 | 150000 | 139829406 | 145733672 | 144403400 | 0 | 0 | 0 | 144403400 | 143485400 | 102.6% | 1 | 457116 | 5754265 | 38 | 35 | 0 | 0 | 48807 | 0 | 0 | 0 | 4196617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94312 | 0 | 0 | 0 | 564973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4918551 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 |  | 2022-07-31 | QTR1 | 22/23 | 854 | 118749145.78 | B10 | ACC - BONUS/INCENT/DISINCENT
| 08 | E8S55 | 44070015201 | 2020-08-31 | QTR1 | 20/21 | 2 | 7 | 515 | 718 | 716 | 94.17% | 1 | 2 | 0 | 0 | 231 | -28 | 16707654 | 150000 | 16557654 | 17277221 | 16377036 | 0 | 0 | 0 | 16377036 | 16720673 | 101% | 1 | 485146 | 569567 | 175 | 56 | 0 | 0 | 18542 | 0 | 0 | 0 | 58747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469864 | 0 | 0 | 0 | 80825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28 | -50316 | 0 | 0 | -28 | 616415 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2022-12-20 | QTR2 | 22/23 | 854 | 20328685.57
| 08 | E8T38 | 43730095201 | 2022-02-08 | QTR3 | 21/22 | 1 | 0 | 192 | 242 | 235 | 96.35% | 1 | 7 | 0 | 0 | 50 | 0 | 5115331 | 50000 | 5065331 | 5115331 | 5070631 | 0 | 0 | 0 | 5070631 | 5070631 | 100.1% | 1 | 0 | 0 | 26 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-06-15 | QTR4 | 22/23 | 854 | 5087753.85
| 08 | E8T39 | 44430115201 | 2021-12-14 | QTR2 | 21/22 | 1 | 3 | 234 | 278 | 253 | 89.32% | 1 | 25 | 0 | 0 | 44 | 0 | 1975221 | 50000 | 1925221 | 2101149 | 2102097 | 0 | 0 | 0 | 2102097 | 2083906 | 108.2% | 1 | 7736 | 125928 | 25 | 19 | 0 | 0 | 102641 | 0 | 0 | 0 | 36105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148344 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 |  | 2023-03-08 | QTR3 | 22/23 | 854 | 1709882.3
| 08 | E8T42 | 43799015201 | 2022-03-08 | QTR3 | 21/22 | 2 | 3 | 321 | 359 | 286 | 72.27% | 1 | 73 | 0 | 0 | 54 | -16 | 4166000 | 50000 | 4116000 | 4217668 | 4164480 | 0 | 0 | 0 | 4164480 | 4215075 | 102.4% | 1 | 52263 | 51668 | 31 | 23 | 0 | 0 | 44026 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 0 | 0 | 0 | -16 | 96868 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-05-22 | QTR4 | 22/23 | 854 | 3910716.97 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8T86 | 43855115201 | 2022-08-16 | QTR1 | 22/23 | 1 | 1 | 136 | 169 | 142 | 97.79% | 1 | 27 | 0 | 0 | 9 | 24 | 597627 | 35230 | 562397 | 652711 | 607225 | 0 | 0 | 0 | 607225 | 607225 | 108% | 1 | 0 | 55083 | 6 | 3 | 0 | 24 | 55083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 55083 | 0 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-06-23 | QTR4 | 22/23 | 854 | 898718.41
| 08 | E8T87 | 43855015201 | 2022-08-16 | QTR1 | 22/23 | 1 | 0 | 199 | 202 | 84 | 40.7% | 1 | 118 | 0 | 0 | 3 | 0 | 767354 | 50000 | 717354 | 767354 | 705154 | 0 | 0 | 0 | 705154 | 705154 | 98.3% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2023-05-11 | QTR4 | 22/23 | 854 | 1243902.61
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 9 | 14 | 81 | 4704 | 5613 | 4958 | #VALUE! | 9 | 655 | 0 | 0 | 929 | -20 | 344410737 | 835230 | 343575507 | 354489837 | 351535282 | 0 | 0 | 0 | 351535282 | 349352337 | 100% | 9 | -538301 | 10079098 | 557 | 344 | 0 | 24 | 729870 | 0 | 0 | 0 | 5737708 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1665966 | 0 | 0 | 0 | 1323866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | -190800 | 0 | 28 | -20 | 9332658 | 0
| District 08 Totals |  |  |  |  | 9 | 14 | 81 | 4704 | 5613 | 4958 | 100% | 9 | 655 | 0 | 0 | 929 | -20 | 344410737 | 835230 | 343575507 | 354489837 | 351535282 | 0 | 0 | 0 | 351535282 | 349352337 | 100% | 9 | -538301 | 10079098 | 557 | 344 | 0 | 24 | 729870 | 0 | 0 | 0 | 5737708 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1665966 | 0 | 0 | 0 | 1323866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | -190800 | 0 | 28 | -20 | 9332658 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 57 | 121 | 167 | 16194 | 25403 | 26174 | 68.42% | 39 | -771 | 1292 | 0 | 7096 | 2113 | 375786165 | 3322001 | 372464164 | 393314791 | 396375435 | 0 | 0 | 0 | 396375435 | 403421849 | 80.7% | 46 | 9689060 | 17243963 | 4481 | 1950 | 486 | 621 | 3465221 | 258371 | 111 | 561 | 6829181 | 1814817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 354 | 170731 | 0 | 0 | 0 | 196551 | 18045 | 0 | 0 | 0 | 0 | 0 | 141 | 128181 | 0 | 0 | 46 | 128274 | 128274 | 65 | 63 | 283488 | 302756 | 191 | 40 | 14596 | 0 | 0 | -19 | -739104 | 0 | 905 | 1807 | 10477120 | 2522262
| Statewide District Let Contracts SubTotal |  |  |  |  | 30 | 50 | 121 | 9460 | 12525 | 11648 | 96.67% | 29 | 877 | 10 | 0 | 2922 | 143 | 432888916 | 2011006 | 430877910 | 445283737 | 441285542 | 0 | 0 | 0 | 441285542 | 441023059 | 90% | 27 | 1743071 | 12394817 | 1698 | 1050 | 12 | 24 | 924349 | 0 | 30 | 29 | 7304869 | 22789 | 0 | 0 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 28 | 116 | 2221084 | 0 | 62 | 0 | 1466393 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | -44 | -409221 | 0 | 153 | 125 | 11573520 | 56495
| Statewide Totals |  |  |  |  | 87 | 171 | 288 | 25654 | 37928 | 37822 | 78.16% | 68 | 106 | 1302 | 0 | 10018 | 2256 | 808675081 | 5333007 | 803342074 | 838598528 | 837660977 | 0 | 0 | 0 | 837660977 | 844444908 | 83.91% | 73 | 11432131 | 29638780 | 6179 | 3000 | 498 | 645 | 4389570 | 258371 | 141 | 590 | 14134050 | 1837606 | 0 | 0 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 80 | 470 | 2391815 | 0 | 62 | 0 | 1662944 | 51751 | 0 | 0 | 0 | 0 | 0 | 141 | 166935 | 0 | 0 | 46 | 128274 | 128274 | 65 | 63 | 283488 | 302756 | 212 | 40 | 14596 | 0 | 0 | -63 | -1148325 | 0 | 1058 | 1932 | 22050640 | 2578757

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1U12 | 44155315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-09-16 | 6272386 | 6303322 | 6506395 | 30935.13 | 0 | 6933886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6506395 | 6933886 | 427490 | 6222847
1 | E1U14 | 44477715201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2021-12-02 | 3819554 | 3657701 | 3521817 | -161853.09 | 0 | 3658011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3521817 | 3658011 | 136195 | 3928133 | B0 | ACC - LUMP SUM
1 | E1U17 | 44594115201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-02-17 | 722056 | 722056 | 642082 | 0 | 100000 | 642815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000 | 100000 | 742082 | 642815 | -99267 | 1070561 | B1 | ACC - NO EXCUSE BONUS
1 | E1V07 | 44023115201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2022-09-15 | 289419 | 311381 | 315649 | 21962 | 0 | 315649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315649 | 315649 | 0 | 331705
1 | T1751 | 41066635201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 43563143 | 43826539 | 44814363 | 263396.26 | 0 | 46184516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44814363 | 46184516 | 1370154 | 44746155
1 | T1761 | 42982315201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 4097408 | 4902150 | 4899132 | 804741.84 | 0 | 4933511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4899132 | 4933511 | 34379 | 4251830
1 | T1772 | 44211515201 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2020-09-30 | 668342 | 668342 | 641177 | 0 | 0 | 631148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641177 | 631148 | -10029 | 802466
1 | T1777 | 43943015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 7973682 | 8225110 | 8476176 | 251427.57 | -106857 | 9010027 | -106857 | 0 | 0 | 0 | 0 | 0 | -106857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -106857 | 8369319 | 9010027 | 640708 | 9500361
1 | T1781 | 44151815201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-01-27 | 4960436 | 5450251 | 5315172 | 489814.72 | 0 | 5587423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5315172 | 5587423 | 272251 | 5666706
1 | T1806 | 44155915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 7108184 | 8445969 | 8418621 | 1337785.07 | 0 | 8684123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8418621 | 8684123 | 265502 | 6181054
1 | T1808 | 44233315201 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-27 | 1139701 | 1148801 | 1029185 | 9099.67 | 0 | 1030981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1029185 | 1030981 | 1796 | 1098276
1 | T1817 | 44068815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 650650 | 655279 | 608957 | 4628.74 | 0 | 609408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608957 | 609408 | 451 | 447610
1 | T1826 | 44421215201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-25 | 1045874 | 1076047 | 1015157 | 30173.84 | 0 | 1015157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015157 | 1015157 | 0 | 898648
1 | T1828 | 44033715201 | F823160551 | LEON AMERICA CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-02-23 | 560933 | 623460 | 604533 | 62526.98 | 0 | 604533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604533 | 604533 | 0 | 517232 | B0 | ACC - LUMP SUM
1 | T1834 | 44632015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 4197476 | 4197476 | 3945832 | 0 | 0 | 3902393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3945832 | 3902393 | -43439 | 4322111
1 | T1839 | 44012715201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 461461 | 461461 | 428726 | 0 | 0 | 428726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428726 | 428726 | 0 | 438393
2 | T2703 | 21272425201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 11717625 | 11666748 | 11573612 | -50877.32 | -1206768 | 10334162 | -1206768 | 0 | 0 | 0 | 0 | 0 | -1206768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1206768 | 10366844 | 10334162 | -32682 | 12539660
2 | T2725 | 42307145201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2018-12-05 | 7294444 | 7636147 | 7798283 | 341702.82 | 0 | 7754246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7798283 | 7754246 | -44037 | 7079692
2 | T2749 | 43946715201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 11950705 | 12606239 | 12671373 | 655533.43 | 0 | 12844734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12671373 | 12844734 | 173361 | 11844644
2 | T2802 | 43575715201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 1262262 | 1262262 | 1249368 | 0 | 0 | 1249498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249368 | 1249498 | 130 | 1338363
2 | T2803 | 44126115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 4633748 | 3852057 | 3929376 | -781690.82 | 0 | 4154909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3929376 | 4154909 | 225533 | 4540383
2 | T2813 | 43617815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 6155492 | 6241492 | 6261727 | 86000 | 0 | 6665942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6261727 | 6665942 | 404215 | 7776562
2 | T2821 | 44327315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 4876894 | 4984966 | 5022406 | 108072.68 | 0 | 5415141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5022406 | 5415141 | 392735 | 5483811
2 | T2824 | 44327415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 3471681 | 3603585 | 3475517 | 131903.51 | 0 | 3617192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3475517 | 3617192 | 141674 | 3836185
2 | T2825 | 44328215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 698919 | 698919 | 656099 | 0 | 0 | 656099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656099 | 656099 | 0 | 629199
2 | T2826 | 44331115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 8657266 | 8657266 | 8107793 | 0 | 0 | 8099899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8107793 | 8099899 | -7895 | 10016767
2 | T2833 | 44325815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-01-12 | 6173212 | 6173212 | 6149692 | 0 | 0 | 6808147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6149692 | 6808147 | 658455 | 7484488
2 | T2837 | 44329415201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 1371850 | 1371850 | 1320562 | 0 | 0 | 1327034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320562 | 1327034 | 6472 | 1352767
2 | T2855 | 43935815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 7918962 | 8057360 | 7962203 | 0 | 0 | 8267055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7962203 | 8267055 | 304853 | 7233768
2 | T2857 | 44721115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 1077522 | 1077522 | 1075156 | 0 | 0 | 1075156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075156 | 1075156 | 0 | 1339271
2 | T2869 | 43567925201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 1298306 | 1298306 | 1209436 | 0 | 0 | 1209097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209436 | 1209097 | -339 | 1554776
2 | T2873 | 44557615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 240110 | 240110 | 185940 | 0 | 0 | 185940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185940 | 185940 | 0 | 402520
2 | T2923 | 44542625201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 212969 | 212969 | 198096 | 0 | 0 | 198096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198096 | 198096 | 0 | 251712
2 | T9023 | 44624515223 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 3516622 | 3516622 | 3642093 | 0 | 0 | 3642131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3642093 | 3642131 | 38 | 3117936
3 | E3S70 | 43992635201 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-05-13 | 8497804 | 8518932 | 8897714 | 21128.25 | 0 | 9015856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8897714 | 9015856 | 118142 | 7939245
3 | E3U04 | 21904225201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-01-12 | 278090 | 278090 | 249120 | 0 | 0 | 249120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249120 | 249120 | 0 | 454254
3 | E3U84 | 44365915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-10 | 3254371 | 3263484 | 3285954 | 9112.73 | 0 | 3378196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3285954 | 3378196 | 92242 | 3044606
3 | T3579 | 41413245201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-08-31 | 42140000 | 43136516 | 44812912 | 996516.18 | -789688 | 45313117 | -739708 | 0 | 0 | 0 | 0 | -49980 | -789688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -789688 | 44023224 | 45313117 | 1289893 | 37004160
3 | T3598 | 43357725201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2021-12-08 | 1449372 | 1449372 | 1245314 | 0 | 0 | 1245462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245314 | 1245462 | 147 | 1387513
3 | T3604 | 43282815201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 10228411 | 10251581 | 10265075 | 23170.26 | 0 | 10328004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10265075 | 10328004 | 62929 | 10230058
3 | T3691 | 43717815201 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2020-11-18 | 4269226 | 4374816 | 4440122 | 105590.54 | -30948 | 4471244 | -30948 | 0 | 0 | 0 | 0 | 0 | -30948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30948 | 4409174 | 4471244 | 62070 | 4154506
3 | T3703 | 43649925201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 2458081 | 2458081 | 2572160 | 0 | 0 | 2554701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2572160 | 2554701 | -17459 | 2031386
3 | T3704 | 43938815201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 1462111 | 1462111 | 1360760 | 0 | 0 | 1370361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360760 | 1370361 | 9601 | 1750125
3 | T3740 | 43626615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 6166449 | 6166449 | 6743565 | 0 | 0 | 7855936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6743565 | 7855936 | 1112372 | 7986598
3 | T3743 | 44173015201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-02-26 | 187229 | 187229 | 175598 | 0 | 0 | 166353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175598 | 166353 | -9245 | 262871
3 | T3750 | 43811125201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2022-07-27 | 987732 | 927591 | 903555 | -60141.3 | 0 | 903555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903555 | 903555 | 0 | 912225
3 | T3793 | 43467715201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-10-27 | 6283852 | 6727204 | 6844151 | 443352.47 | 0 | 7176797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6844151 | 7176797 | 332646 | 7460138
3 | T3794 | 44364415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 2537432 | 2537432 | 2741257 | 0 | 0 | 2721406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2741257 | 2721406 | -19851 | 2975157
3 | T3823 | 44565615201 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-01-25 | 2199429 | 2199429 | 2316440 | 0 | 0 | 2316440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2316440 | 2316440 | 0 | 2955598
4 | E4T68 | 44074615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-05-06 | 17557323 | 17588765 | 16726429 | 31442 | 0 | 16980455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16726429 | 16980455 | 254025 | 12972093
4 | E4U99 | 44146215201 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-05-07 | 12200214 | 13805766 | 14205204 | 1605551.79 | 0 | 14206673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14205204 | 14206673 | 1469 | 10374506 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | E4V75 | 44172215201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-02-04 | 1455255 | 1515282 | 1451281 | 60027.27 | 0 | 1459199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1451281 | 1459199 | 7917 | 1403379
4 | E4V84 | 44609715201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2022-09-02 | 3147147 | 3153188 | 2965886 | 6040.86 | 0 | 2896248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2965886 | 2896248 | -69638 | 3652109 | B1 | ACC - NO EXCUSE BONUS
4 | T4562 | 43177035201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 3588218 | 3660295 | 3546957 | 72077.49 | 0 | 3613971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3546957 | 3613971 | 67014 | 3732217
4 | T4573 | 43206675201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-28 | 3496673 | 3721036 | 3515537 | 224363.43 | 0 | 3603841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3515537 | 3603841 | 88304 | 3657624
4 | T4594 | 43999015201 | F650814419 | ZAHLENE ENTERPRISES INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 2000000 | 2008938 | 1868868 | 8938.46 | 0 | 1870979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1868868 | 1870979 | 2110 | 2421038
4 | T4597 | 44177515201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2022-01-26 | 957661 | 958736 | 900445 | 1074.85 | 0 | 900445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900445 | 900445 | 0 | 927529
4 | T4607 | 43999315201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2022-03-30 | 1967721 | 1967721 | 1856962 | 0 | 0 | 1859008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1856962 | 1859008 | 2046 | 2135578
4 | T4614 | 44399415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 4491996 | 4563991 | 4393362 | 71995.43 | 0 | 4387252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4393362 | 4387252 | -6110 | 4062647
5 | E51A9 | 44102015201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-09-01 | 7501367 | 7798794 | 7544823 | 297427.05 | -41316 | 7754120 | -41316 | 0 | 0 | 0 | 0 | 0 | -41316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41316 | 7503507 | 7754120 | 250613 | 7321147
5 | E55B4 | 44942515201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-11-01 | 967737 | 967737 | 851103 | 0 | 0 | 851002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851103 | 851002 | -101 | 882687
5 | E57A4 | 44113215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-10-05 | 7424369 | 7591181 | 7558842 | 166811.87 | 0 | 7953369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7558842 | 7953369 | 394527 | 9276735
5 | E59A9 | 43913015201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-01-04 | 679529 | 679529 | 677096 | 0 | 0 | 677187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677096 | 677187 | 92 | 681571
5 | T5552 | 40714345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-06-08 | 75824482 | 86884143 | 89837352 | 10910760.93 | 0 | 90653074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89837352 | 90653074 | 815723 | 88197362 | B2:B5:B7:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS
5 | T5733 | 44381515201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 7387943 | 7578305 | 6929112 | 190361.43 | 0 | 7646110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6929112 | 7646110 | 716998 | 8754090
5 | T5738 | 44290915201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 9861239 | 9880239 | 9803603 | 18999.77 | 0 | 10869062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9803603 | 10869062 | 1065459 | 13653416
6 | E6N09 | 44480525201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-07-28 | 797552 | 797552 | 706126 | 0 | 0 | 706126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706126 | 706126 | 0 | 1509364
6 | E6N47 | 44445015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2022-05-26 | 2697327 | 2771657 | 2731695 | 74329.48 | 180000 | 2718704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 2911695 | 2718704 | -192991 | 2883318 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6N55 | 44196815201 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2021-08-26 | 757063 | 757063 | 654819 | 0 | 0 | 654819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654819 | 654819 | 0 | 1042436
6 | T6518 | 42918635201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 2919079 | 2940250 | 2881342 | 21170.5 | 210000 | 2944862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 210000 | 210000 | 3091342 | 2944862 | -146480 | 3061117 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6519 | 43476835201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2022-01-26 | 3487287 | 3497187 | 3509376 | 9900 | 180000 | 3539751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 3689376 | 3539751 | -149625 | 3568828 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
7 | E7N90 | 44822115201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2022-01-12 | 679686 | 695950 | 640611 | 16263.93 | 0 | 640611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640611 | 640611 | 0 | 644500
7 | E7N95 | 44025115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 6430299 | 6566839 | 6774752 | 136540.44 | 0 | 7326407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6774752 | 7326407 | 551655 | 8690700
7 | E7O11 | 44166515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-09 | 3049631 | 3049631 | 3013462 | 0 | 0 | 3013181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3013462 | 3013181 | -281 | 2409700
7 | T7428 | 43258435201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 9277781 | 9481539 | 10184938 | 203758.52 | 251742 | 10145611 | -48258 | 0 | 0 | 0 | 0 | 0 | -48258 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 251742 | 10436680 | 10145611 | -291069 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | T7451 | 43982985201 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2020-04-29 | 698558 | 698558 | 557380 | 0 | -158860 | 531562 | -158860 | 0 | 0 | 0 | 0 | 0 | -158860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -158860 | 398520 | 531562 | 133042 | 691075
7 | T7468 | 44138615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-27 | 9161461 | 9416662 | 9425645 | 255200.4 | 0 | 9775049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9425645 | 9775049 | 349405 | 9040000
7 | T7498 | 44332015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 1340863 | 1340863 | 1268582 | 0 | -12000 | 1256582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12000 | 0 | 0 | 0 | 0 | 0 | -12000 | -12000 | 1256582 | 1256582 | 0 | 2027300
8 | E8Q78 | 43554615201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-06-15 | 143269821 | 145759356 | 145166429 | 2489534.99 | 5000000 | 144293300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 150166429 | 144293300 | -5873129 | 156867750 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
8 | E8R77 | 43798615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-05-14 | 31832323 | 32865375 | 32938830 | 1033051.69 | 0 | 32271398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32938830 | 32271398 | -667433 | 33799887
8 | E8R97 | 43730045201 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2019-09-17 | 139979406 | 145733672 | 144794963 | 5754265.13 | 6000000 | 144860516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000 | 150794963 | 144860516 | -5934447 | 118749146 | B10 | ACC - BONUS/INCENT/DISINCENT
8 | E8S55 | 44070015201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2020-08-31 | 16707654 | 17277221 | 16518546 | 569566.94 | 0 | 16862183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16518546 | 16862183 | 343637 | 20328686
8 | E8T38 | 43730095201 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2022-02-08 | 5115331 | 5115331 | 5070631 | 0 | 0 | 5070631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5070631 | 5070631 | 0 | 5087754
8 | E8T39 | 44430115201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-12-14 | 1975221 | 2101149 | 2102097 | 125927.59 | 0 | 2109833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2102097 | 2109833 | 7736 | 1709882
8 | E8T42 | 43799015201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-03-08 | 4166000 | 4217668 | 4164480 | 51668.12 | 138823 | 4216743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138823 | 0 | 0 | 0 | 0 | 0 | 138823 | 138823 | 4303303 | 4216743 | -86560 | 3910717 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8T86 | 43855115201 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2022-08-16 | 597627 | 652711 | 607225 | 55083.3 | 0 | 607225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607225 | 607225 | 0 | 898718
8 | E8T87 | 43855015201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2022-08-16 | 767354 | 767354 | 705154 | 0 | 0 | 705154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705154 | 705154 | 0 | 1243903

## Sheet1 (hidden)
01CO | 01 | T1751 | 41066635201 | 2020-04-29 | QTR4 | 19/20 | 4 | 15 | 875 | 1016 | 963 | 53 | 0 | 0 | 127 | 14 | 43563143 | 150000 | 43413143 | 43826539 | 44268970 | 0 | 0 | 0 | 44268970 | 45616616 | 1915546 | 263396 | 80 | 0 | 0 | 351912 | 3918 | 7 | 0 | 219896 | 30715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18317 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 320903 | 34633 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-09-11 | QTR1 | 23/24 | 2023-04-28 | QTR4 | 22/23 | 108 | 44746155.07 |  |  | 0 | 54 | 0 | 0 | -287200 | 0 |  | CO | 12 | 01co | 1 | 12
01CO | 01 | T1761 | 42982315201 | 2021-06-09 | QTR4 | 20/21 | 2 | 18 | 275 | 545 | 530 | 15 | 0 | 0 | 223 | 47 | 4097408 | 50000 | 4047408 | 4902150 | 4899132 | 0 | 0 | 0 | 4899132 | 4822749 | 34379 | 804742 | 131 | 0 | 42 | 118523 | 55203 | 51 | 5 | 478225 | 97145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42992 | 42992 | 0 | 0 | 0 | 0 | 51 | 47 | 719910 | 195339 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2023-02-24 | QTR3 | 22/23 | 113 | 4251830.23 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO | 4 | 01do | 13 | 16
01CO | 01 | T1772 | 44211515201 | 2020-09-30 | QTR1 | 20/21 | 3 | 1 | 150 | 177 | 607 | -430 | 430 | 0 | 11 | 16 | 668342 | 41495 | 626847 | 668342 | 605783 | 0 | 0 | 0 | 605783 | 595755 | 25365 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6341 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 | 2022-12-05 | QTR2 | 22/23 | 108 | 802465.89 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 18 | 02co | 17 | 34
01CO | 01 | T1777 | 43943015201 | 2020-09-30 | QTR1 | 20/21 | 4 | 3 | 325 | 607 | 638 | -31 | 31 | 0 | 216 | 66 | 7973682 | 92806 | 7880876 | 8225110 | 8195027 | 0 | 0 | 0 | 8195027 | 8717413 | 815000 | 251428 | 207 | 0 | 0 | 126514 | 115529 | 0 | 52 | 124433 | 124433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 250947 | 239963 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 | 2022-10-18 | QTR2 | 22/23 | 118 | 9500361.49 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 0 | 02do | 35 | 34
01CO | 01 | T1781 | 44151815201 | 2021-01-27 | QTR3 | 20/21 | 2 | 4 | 285 | 400 | 400 | 0 | 0 | 0 | 41 | 74 | 4960436 | 59129 | 4901307 | 5450251 | 5304714 | 0 | 0 | 0 | 5304714 | 5560151 | 265895 | 489815 | 14 | 0 | 74 | 470632 | 0 | 0 | 0 | 17986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 489815 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2022-06-30 | QTR4 | 21/22 | 118 | 5666706.37 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO | 12 | 03co | 35 | 46
01CO | 01 | T1806 | 44155915201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 250 | 391 | 391 | 0 | 0 | 0 | 134 | 7 | 7108184 | 63330 | 7044854 | 8445969 | 8418621 | 0 | 0 | 0 | 8418621 | 7803372 | 265502 | 1337785 | 92 | 0 | 0 | 0 | 0 | 23 | 7 | 473396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 7 | 473396 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 | 2023-05-01 | QTR4 | 22/23 | 115 | 6181054.02 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO | 3 | 03do | 47 | 49
01CO | 01 | T1808 | 44233315201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 140 | 293 | 293 | 0 | 0 | 0 | 153 | 0 | 1139701 | 50000 | 1089701 | 1148801 | 1029185 | 0 | 0 | 0 | 1029185 | 1021881 | 1796 | 9100 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-03-17 | QTR3 | 22/23 | 108 | 1098275.5 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 6 | 04co | 50 | 55
01CO | 01 | T1817 | 44068815201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 80 | 165 | 165 | 0 | 0 | 0 | 85 | 0 | 650650 | 18505 | 632145 | 655279 | 608957 | 0 | 0 | 0 | 608957 | 609408 | 451 | 4629 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 8153 | 45738 | 0 | 0 | 0 | 0 | 27 | 0 | 15989 | 45738 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 | 2022-12-13 | QTR2 | 22/23 | 115 | 447609.94 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO | 4 | 04do | 56 | 59
01CO | 01 | T1826 | 44421215201 | 2021-08-25 | QTR1 | 21/22 | 1 | 3 | 107 | 259 | 259 | 0 | 0 | 0 | 44 | 108 | 1045874 | 41345 | 1004529 | 1076047 | 1015157 | 0 | 0 | 0 | 1015157 | 994639 | 0 | 30174 | 114 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10825 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2023-03-20 | QTR3 | 22/23 | 118 | 898648.05 |  |  | 18 | 20 | 0 | 0 | 0 | 0 |  | CO | 3 | 05co | 60 | 62
01CO | 01 | T1828 | 44033715201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 97 | 129 | 129 | 0 | 0 | 0 | 32 | 0 | 560933 | 21933 | 539000 | 623460 | 604533 | 0 | 0 | 0 | 604533 | 604533 | 0 | 62527 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 62527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65533 | 0 | F823160551 | LEON AMERICA CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-09-25 | QTR1 | 23/24 | 2023-05-15 | QTR4 | 22/23 | 113 | 517232.45 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 | T | CO | 4 | 05do | 63 | 66
01CO | 01 | T1834 | 44632015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 215 | 280 | 272 | 8 | 0 | 0 | 65 | 0 | 4197476 | 50000 | 4147476 | 4197476 | 3945832 | 0 | 0 | 0 | 3945832 | 3902393 | -43439 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 | 2023-06-22 | QTR4 | 22/23 | 113 | 4322110.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 2 | 06co | 67 | 68
01CO | 01 | T1839 | 44012715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 0 | 130 | 175 | 175 | 0 | 0 | 0 | 45 | 0 | 461461 | 21100 | 440361 | 461461 | 428726 | 0 | 0 | 0 | 428726 | 428726 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2023-03-06 | QTR3 | 22/23 | 115 | 438393.45 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 3 | 06do | 69 | 71
01DO | 01 | E1U12 | 44155315201 | 2021-09-16 | QTR1 | 21/22 | 2 | 4 | 300 | 439 | 422 | 17 | 0 | 0 | 139 | 0 | 6272386 | 62629 | 6209757 | 6303322 | 6506395 | 0 | 0 | 0 | 6506395 | 6911842 | 427490 | 30935 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 8892 | 976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13429 | 976 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-12 | QTR1 | 23/24 | 2023-05-12 | QTR4 | 22/23 | 108 | 6222847.06 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO | 4 | 07co | 72 | 75
01DO | 01 | E1U14 | 44477715201 | 2021-12-02 | QTR2 | 21/22 | 2 | 2 | 160 | 222 | 222 | 0 | 0 | 0 | 62 | 0 | 3819554 | 50000 | 3769554 | 3657701 | 3521817 | 0 | 0 | 0 | 3521817 | 3658011 | 136195 | -161853 | 29 | 12 | 0 | 56568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | -161853 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-07-21 | QTR1 | 23/24 | 2023-03-03 | QTR3 | 22/23 | 115 | 3928132.77 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | -218421 | 0 |  | DO | 3 | 07do | 76 | 78
01DO | 01 | E1U17 | 44594115201 | 2022-02-17 | QTR3 | 21/22 | 1 | 0 | 150 | 171 | 166 | 5 | 0 | 0 | 21 | 0 | 722056 | 48017 | 674039 | 722056 | 642082 | 0 | 0 | 0 | 642082 | 642815 | 733 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-03-17 | QTR3 | 22/23 | 115 | 1070560.76 | B1 | ACC - NO EXCUSE BONUS | 0 | 17 | 0 | 0 | 0 | 0 |  | DO | 0 | 08co | 79 | 78
01DO | 01 | E1V07 | 44023115201 | 2022-09-15 | QTR1 | 22/23 | 1 | 3 | 75 | 75 | 72 | 3 | 0 | 0 | 0 | 0 | 289419 | 14419 | 275000 | 311381 | 315649 | 0 | 0 | 0 | 315649 | 315649 | 0 | 21962 | 0 | 0 | 0 | 6636 | 0 | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28598 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2023-08-09 | QTR1 | 23/24 | 2023-03-29 | QTR3 | 22/23 | 118 | 331704.75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO | 9 | 08do | 79 | 87
02CO | 02 | T2703 | 21272425201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 550 | 719 | 968 | -249 | 249 | 0 | 169 | 0 | 11717625 | 120 | 11717505 | 11666748 | 11573612 | 0 | 0 | 0 | 11573612 | 10334162 | -1239450 | -50877 | 123 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50877 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 | 2021-05-03 | QTR4 | 20/21 | 209 | 12539660.43 |  |  | 0 | 46 | 0 | 0 | -68877 | 0 |  | CO
02CO | 02 | T2725 | 42307145201 | 2018-12-05 | QTR2 | 18/19 | 1 | 5 | 300 | 737 | 737 | 0 | 0 | 0 | 181 | 256 | 7294444 | 68754 | 7225690 | 7636147 | 7798283 | 0 | 0 | 0 | 7798283 | 7754246 | -44037 | 341703 | 85 | 0 | 27 | 92502 | 0 | 0 | 229 | 220039 | 17548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4989 | 0 | 0 | 0 | 6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 256 | 330105 | 23598 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2021-06-17 | QTR4 | 20/21 | 214 | 7079691.78 |  |  | 244 | 96 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2749 | 43946715201 | 2019-09-25 | QTR1 | 19/20 | 3 | 10 | 600 | 1149 | 1149 | 0 | 0 | 0 | 265 | 284 | 11950705 | 126323 | 11824382 | 12606239 | 12535468 | 0 | 0 | 0 | 12535468 | 12707911 | 309266 | 655533 | 237 | 0 | 39 | 488108 | 0 | 0 | 59 | 227908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 721990 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-28 | QTR1 | 23/24 | 2023-02-27 | QTR3 | 22/23 | 208 | 11844644.47 |  |  | 166 | 108 | 0 | 0 | 0 | 0 |  | CO |  | 0
02CO | 02 | T2802 | 43575715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 180 | 523 | 523 | 0 | 0 | 0 | 29 | 314 | 1262262 | 50000 | 1212262 | 1262262 | 1249368 | 0 | 0 | 0 | 1249368 | 1249498 | 130 | 0 | 103 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2022-12-23 | QTR2 | 22/23 | 208 | 1338362.89 |  |  | 314 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2803 | 44126115201 | 2021-05-26 | QTR4 | 20/21 | 2 | 3 | 325 | 487 | 487 | 0 | 0 | 0 | 162 | 0 | 4633748 | 75000 | 4558748 | 3852057 | 3929376 | 0 | 0 | 0 | 3929376 | 4154909 | 225533 | -781691 | 40 | 30 | 0 | -739805 | 0 | 0 | 0 | 7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -732738 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2023-01-06 | QTR3 | 22/23 | 208 | 4540382.58 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2813 | 43617815201 | 2021-06-09 | QTR4 | 20/21 | 3 | 2 | 350 | 501 | 501 | 0 | 0 | 0 | 109 | 42 | 6155492 | 64024 | 6091468 | 6241492 | 6261727 | 0 | 0 | 0 | 6261727 | 6665942 | 404215 | 86000 | 72 | 0 | 42 | 61451 | 0 | 0 | 0 | 59384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 120835 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 | 2023-01-20 | QTR3 | 22/23 | 209 | 7776561.61 |  |  | 42 | 37 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2821 | 44327315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 150 | 289 | 271 | 18 | 0 | 0 | 118 | 21 | 4876894 | 52518 | 4824376 | 4984966 | 5022406 | 0 | 0 | 0 | 5022406 | 5415141 | 392735 | 108073 | 77 | 0 | 21 | 125561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31 | 21 | 125561 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 | 2022-10-13 | QTR2 | 22/23 | 216 | 5483810.94 |  |  | 6 | 10 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2824 | 44327415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 2 | 250 | 455 | 453 | 2 | 0 | 0 | 190 | 15 | 3471681 | 50000 | 3421681 | 3603585 | 3475517 | 0 | 0 | 0 | 3475517 | 3614982 | 141674 | 131904 | 166 | 0 | 0 | 14150 | 0 | 0 | 15 | 130039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 15 | 144189 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-05-04 | QTR4 | 22/23 | 216 | 3836185.04 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2825 | 44328215201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 75 | 125 | 124 | 1 | 0 | 0 | 10 | 40 | 698919 | 27456 | 671464 | 698919 | 656099 | 0 | 0 | 0 | 656099 | 656099 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-14 | QTR1 | 23/24 | 2022-06-28 | QTR4 | 21/22 | 209 | 629198.54 |  |  | 40 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2826 | 44331115201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 220 | 264 | 264 | 0 | 0 | 0 | 44 | 0 | 8657266 | 87492 | 8569774 | 8657266 | 8107793 | 0 | 0 | 0 | 8107793 | 8099899 | -7895 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-29 | QTR1 | 23/24 | 2023-05-05 | QTR4 | 22/23 | 209 | 10016766.94 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2833 | 44325815201 | 2022-01-12 | QTR3 | 21/22 | 1 | 0 | 210 | 235 | 235 | 0 | 0 | 0 | 25 | 0 | 6173212 | 71171 | 6102041 | 6173212 | 6149692 | 0 | 0 | 0 | 6149692 | 6808147 | 658455 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2022-11-23 | QTR2 | 22/23 | 214 | 7484487.76 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2837 | 44329415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 0 | 180 | 262 | 260 | 2 | 0 | 0 | 55 | 27 | 1371850 | 50000 | 1321850 | 1371850 | 1320562 | 0 | 0 | 0 | 1320562 | 1320562 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 | 2023-01-19 | QTR3 | 22/23 | 208 | 1352767.24 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2855 | 43935815201 | 2021-06-09 | QTR4 | 20/21 | 2 | 0 | 350 | 464 | 459 | 5 | 0 | 0 | 86 | 28 | 7918962 | 100000 | 7818962 | 8057360 | 7962203 | 0 | 0 | 0 | 7962203 | 8267055 | 304853 | 0 | 42 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 | 2023-02-23 | QTR3 | 22/23 | 209 | 7233767.77 |  |  | 28 | 44 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2857 | 44721115201 | 2022-01-26 | QTR3 | 21/22 | 1 | 0 | 120 | 193 | 185 | 8 | 0 | 0 | 27 | 46 | 1077522 | 44955 | 1032567 | 1077522 | 1075156 | 0 | 0 | 0 | 1075156 | 1075156 | 0 | 0 | 16 | 0 | 30 | 18350 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 18350 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2022-10-14 | QTR2 | 22/23 | 208 | 1339271.36 |  |  | 46 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2869 | 43567925201 | 2022-06-08 | QTR4 | 21/22 | 2 | 0 | 180 | 199 | 178 | 21 | 0 | 0 | 19 | 0 | 1298306 | 50000 | 1248306 | 1298306 | 1209436 | 0 | 0 | 0 | 1209436 | 1209097 | -339 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 | 2023-04-19 | QTR4 | 22/23 | 209 | 1554775.94 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2873 | 44557615201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 90 | 90 | 19 | 71 | 0 | 0 | 0 | 0 | 240110 | 17791 | 222319 | 240110 | 185940 | 0 | 0 | 0 | 185940 | 185940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-03-31 | QTR3 | 22/23 | 208 | 402519.71 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2923 | 44542625201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 74 | 101 | 94 | 7 | 0 | 0 | 26 | 1 | 212969 | 11187 | 201781 | 212969 | 198096 | 0 | 0 | 0 | 198096 | 198096 | 0 | 0 | 15 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-09-05 | QTR1 | 23/24 | 2023-03-01 | QTR3 | 22/23 | 208 | 251711.77 |  |  | 1 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9023 | 44624515223 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 250 | 733 | 730 | 3 | 0 | 0 | 483 | 0 | 3516622 | 50000 | 3466622 | 3516622 | 3642093 | 0 | 0 | 0 | 3642093 | 3642131 | 38 | 0 | 14 | 420 | 0 | 0 | 0 | 0 | 0 | 30591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 41498 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-09-27 | QTR1 | 23/24 | 2023-08-03 | QTR1 | 23/24 | 209 | 3117936.11 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3579 | 41413245201 | 2016-08-31 | QTR1 | 16/17 | 3 | 19 | 1090 | 1999 | 2171 | -172 | 172 | 0 | 798 | 111 | 42140000 | 150000 | 41990000 | 43136516 | 44789798 | 0 | 0 | 0 | 44789798 | 45150067 | 523319 | 996516 | 442 | 4 | 40 | 380492 | 1569 | 0 | 27 | 349096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 8 | 165208 | 0 | 0 | 0 | 18045 | 18045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 121 | 848413 | 114614 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2022-10-21 | QTR2 | 22/23 | 308 | 37004160.16 |  |  | 38 | 212 | 0 | 0 | -159429 | 0 |  | CO
03CO | 03 | T3598 | 43357725201 | 2021-12-08 | QTR2 | 21/22 | 2 | 0 | 210 | 314 | 314 | 0 | 0 | 0 | 104 | 0 | 1449372 | 9292 | 1440080 | 1449372 | 1245314 | 0 | 0 | 0 | 1245314 | 1245462 | 147 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-01-13 | QTR3 | 22/23 | 308 | 1387512.95 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3604 | 43282815201 | 2019-02-27 | QTR3 | 18/19 | 2 | 4 | 925 | 1322 | 1301 | 21 | 0 | 0 | 397 | 0 | 10228411 | 103267 | 10125144 | 10251581 | 10265075 | 0 | 0 | 0 | 10265075 | 10328004 | 62929 | 23170 | 263 | 0 | 0 | 24478 | 0 | 0 | 0 | 5148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 120 | 68927 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2022-12-06 | QTR2 | 22/23 | 308 | 10230057.88 |  |  | 0 | 84 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3691 | 43717815201 | 2020-11-18 | QTR2 | 20/21 | 1 | 2 | 480 | 640 | 661 | -21 | 21 | 0 | 160 | 0 | 4269226 | 50000 | 4219226 | 4374816 | 4363593 | 0 | 0 | 0 | 4363593 | 4394715 | 107651 | 105591 | 98 | 8 | 0 | 95913 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 23399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 149628 | 0 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 | 2022-12-04 | QTR2 | 22/23 | 308 | 4154505.73 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3703 | 43649925201 | 2019-09-25 | QTR1 | 19/20 | 3 | 0 | 150 | 292 | 262 | 30 | 0 | 0 | 112 | 30 | 2458081 | 51140 | 2406941 | 2458081 | 2572160 | 0 | 0 | 0 | 2572160 | 2554701 | -17459 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2020-10-02 | QTR2 | 20/21 | 314 | 2031385.77 |  |  | 30 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3704 | 43938815201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 150 | 222 | 220 | 2 | 0 | 0 | 72 | 0 | 1462111 | 0 | 1462111 | 1462111 | 1360760 | 0 | 0 | 0 | 1360760 | 1370361 | 9601 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 | 2022-10-07 | QTR2 | 22/23 | 313 | 1750125.19 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 1 | 365 | 689 | 689 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6166449 | 6679471 | 0 | 0 | 0 | 6679471 | 7791843 | 1176465 | 0 | 170 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 44 | 21 | 67784 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29 |  |  | 21 | 89 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3743 | 44173015201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 45 | 83 | 80 | 3 | 0 | 0 | 38 | 0 | 187229 | 12274 | 174955 | 187229 | 175598 | 0 | 0 | 0 | 175598 | 166353 | -9245 | 0 | 35 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2020-08-14 | QTR1 | 20/21 | 314 | 262871.46 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3750 | 43811125201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 95 | 131 | 130 | 1 | 0 | 0 | 36 | 0 | 987732 | 41493 | 946239 | 927591 | 903555 | 0 | 0 | 0 | 903555 | 903555 | 0 | -60141 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-05-12 | QTR4 | 22/23 | 314 | 912225.16 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3793 | 43467715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 3 | 230 | 481 | 480 | 1 | 0 | 0 | 236 | 15 | 6283852 | 73669 | 6210183 | 6727204 | 6844151 | 0 | 0 | 0 | 6844151 | 7176797 | 332646 | 443352 | 186 | 0 | 7 | 378034 | 0 | 0 | 8 | 133625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 511659 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2023-06-28 | QTR4 | 22/23 | 308 | 7460138.28 |  |  | 1 | 50 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3794 | 44364415201 | 2022-06-15 | QTR4 | 21/22 | 1 | 1 | 100 | 125 | 92 | 33 | 0 | 0 | 25 | 0 | 2537432 | 50000 | 2487432 | 2537432 | 2741257 | 0 | 0 | 0 | 2741257 | 2721406 | -19851 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-03-06 | QTR3 | 22/23 | 313 | 2975156.64 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3823 | 44565615201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 110 | 120 | 86 | 34 | 0 | 0 | 10 | 0 | 2199429 | 50000 | 2149429 | 2199429 | 2316440 | 0 | 0 | 0 | 2316440 | 2316440 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 | 2023-06-22 | QTR4 | 22/23 | 308 | 2955598 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3S70 | 43992635201 | 2021-05-13 | QTR4 | 20/21 | 2 | 1 | 395 | 597 | 597 | 0 | 0 | 0 | 202 | 0 | 8497804 | 70195 | 8427609 | 8518932 | 8878921 | 0 | 0 | 0 | 8878921 | 8997063 | 136935 | 21128 | 102 | 0 | 0 | 12464 | 0 | 30 | 0 | 28861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 51 | 0 | 41325 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 | 2023-03-30 | QTR3 | 22/23 | 321 | 7939245.14 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U04 | 21904225201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 65 | 65 | 45 | 20 | 0 | 0 | 0 | 0 | 278090 | 21110 | 256980 | 278090 | 249120 | 0 | 0 | 0 | 249120 | 249120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2023-05-18 | QTR4 | 22/23 | 314 | 454253.61 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U84 | 44365915201 | 2022-02-10 | QTR3 | 21/22 | 2 | 1 | 175 | 266 | 264 | 2 | 0 | 0 | 91 | 0 | 3254371 | 50000 | 3204371 | 3263484 | 3285954 | 0 | 0 | 0 | 3285954 | 3378196 | 92242 | 9113 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-02-18 | QTR3 | 22/23 | 308 | 3044605.63 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4562 | 43177035201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 384 | 492 | 492 | 0 | 0 | 0 | 108 | 0 | 3588218 | 50000 | 3538218 | 3660295 | 3546957 | 0 | 0 | 0 | 3546957 | 3613971 | 67014 | 72077 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 91148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14596 | 0 | 0 | 0 | 94541 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2023-03-31 | QTR3 | 22/23 | 412 | 3732217.16 |  |  | 0 | 37 | 0 | 0 | -11203 | 0 |  | CO
04CO | 04 | T4573 | 43206675201 | 2021-07-28 | QTR1 | 21/22 | 2 | 3 | 195 | 470 | 465 | 5 | 0 | 0 | 275 | 0 | 3496673 | 50000 | 3446673 | 3721036 | 3515537 | 0 | 0 | 0 | 3515537 | 3603841 | 88304 | 224363 | 249 | 0 | 0 | -2094 | 0 | 0 | 0 | 267470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265376 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 | 2023-04-19 | QTR4 | 22/23 | 412 | 3657623.88 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4594 | 43999015201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 212 | 352 | 351 | 1 | 0 | 0 | 140 | 0 | 2000000 | 50000 | 1950000 | 2008938 | 1868868 | 0 | 0 | 0 | 1868868 | 1862040 | 2110 | 8938 | 85 | 0 | 0 | 11450 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 11450 | 0 | F650814419 | ZAHLENE ENTERPRISES INC. | N/A | N/A | N/A | N/A | 2023-07-24 | QTR1 | 23/24 | 2023-05-31 | QTR4 | 22/23 | 412 | 2421037.86 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4597 | 44177515201 | 2022-01-26 | QTR3 | 21/22 | 2 | 1 | 178 | 274 | 274 | 0 | 0 | 0 | 96 | 0 | 957661 | 40792 | 916869 | 958736 | 900445 | 0 | 0 | 0 | 900445 | 899370 | 0 | 1075 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 8111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8111 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-05-11 | QTR4 | 22/23 | 409 | 927528.71 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4607 | 43999315201 | 2022-03-30 | QTR3 | 21/22 | 3 | 1 | 222 | 287 | 287 | 0 | 0 | 0 | 65 | 0 | 1967721 | 50000 | 1917721 | 1967721 | 1856962 | 0 | 0 | 0 | 1856962 | 1856374 | 2046 | 2634 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-09-18 | QTR1 | 23/24 | 2023-04-30 | QTR4 | 22/23 | 412 | 2135578.09 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4614 | 44399415201 | 2022-04-27 | QTR4 | 21/22 | 2 | 3 | 227 | 321 | 321 | 0 | 0 | 0 | 94 | 0 | 4491996 | 50000 | 4441996 | 4563991 | 4393362 | 0 | 0 | 0 | 4393362 | 4376466 | -6110 | 71995 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 86648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51997 | 0 | 0 | 0 | 5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33274 | 33274 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 73161 | 33274 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-06-14 | QTR4 | 22/23 | 409 | 4062646.65 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4T68 | 44074615201 | 2020-05-06 | QTR4 | 19/20 | 6 | 1 | 730 | 939 | 934 | 5 | 0 | 0 | 209 | 0 | 17557323 | 125751 | 17431572 | 17588765 | 16726429 | 0 | 0 | 0 | 16726429 | 16980455 | 254025 | 31442 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31442 | 0 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37742 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-02-02 | QTR3 | 22/23 | 412 | 12972092.8 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U99 | 44146215201 | 2021-05-07 | QTR4 | 20/21 | 1 | 8 | 228 | 525 | 518 | 7 | 0 | 0 | 188 | 109 | 12200214 | 101674 | 12098540 | 13805766 | 14066534 | 0 | 0 | 0 | 14066534 | 14068003 | 140138 | 1605552 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 1129185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 448054 | 0 | 0 | 0 | 23731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1600970 | 0 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-06-23 | QTR4 | 22/23 | 412 | 10374505.8 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V75 | 44172215201 | 2022-02-04 | QTR3 | 21/22 | 2 | 4 | 156 | 248 | 248 | 0 | 0 | 0 | 92 | 0 | 1455255 | 50000 | 1405255 | 1515282 | 1451281 | 0 | 0 | 0 | 1451281 | 1452112 | 7917 | 60027 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 76040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 78106 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-09-01 | QTR1 | 23/24 | 2023-03-28 | QTR3 | 22/23 | 409 | 1403378.89 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V84 | 44609715201 | 2022-09-02 | QTR1 | 22/23 | 1 | 1 | 133 | 180 | 179 | 1 | 0 | 0 | 47 | 0 | 3147147 | 50000 | 3097147 | 3153188 | 2965886 | 0 | 0 | 0 | 2965886 | 2896248 | -69638 | 6041 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-08-03 | QTR1 | 23/24 | 409 | 3652108.96 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5552 | 40714345201 | 2016-06-08 | QTR4 | 15/16 | 21 | 32 | 1050 | 1826 | 1829 | -3 | 3 | 0 | 359 | 417 | 75824482 | 160000 | 75664482 | 86884143 | 89837352 | 0 | 0 | 0 | 89837352 | 90458012 | 815723 | 10910761 | 209 | 0 | 13 | 563442 | 81716 | 0 | 113 | 3719605 | 1534190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | -46035 | 0 | 0 | 0 | 107943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30316 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 417 | 4476317 | 1823881 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2021-10-13 | QTR2 | 21/22 | 509 | 88197361.71 | B2:B5:B7:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS | 0 | 150 | 0 | 0 | -106929 | 0 |  | CO
05CO | 05 | T5733 | 44381515201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 290 | 440 | 439 | 1 | 0 | 0 | 130 | 20 | 7387943 | 81000 | 7306943 | 7578305 | 6929112 | 0 | 0 | 0 | 6929112 | 7638830 | 716998 | 190361 | 50 | 0 | 20 | 183081 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 183081 | 436 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2023-04-17 | QTR4 | 22/23 | 513 | 8754090.28 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5738 | 44290915201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 270 | 349 | 349 | 0 | 0 | 0 | 79 | 0 | 9861239 | 100000 | 9761239 | 9880239 | 9803603 | 0 | 0 | 0 | 9803603 | 10869062 | 1065459 | 19000 | 40 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24350 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-02-28 | QTR3 | 22/23 | 514 | 13653415.96 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E51A9 | 44102015201 | 2020-09-01 | QTR1 | 20/21 | 1 | 7 | 280 | 534 | 544 | -10 | 10 | 0 | 225 | 29 | 7501367 | 72000 | 7429367 | 7798794 | 7531686 | 0 | 0 | 0 | 7531686 | 7740983 | 222434 | 297427 | 61 | 0 | 0 | 19197 | 0 | 0 | 29 | 278231 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 297427 | 5549 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2022-05-27 | QTR4 | 21/22 | 514 | 7321146.81 |  |  | 5 | 164 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B4 | 44942515201 | 2022-11-01 | QTR2 | 22/23 | 1 | 0 | 170 | 174 | 149 | 25 | 0 | 0 | 4 | 0 | 967737 | 42032 | 925705 | 967737 | 851103 | 0 | 0 | 0 | 851103 | 851002 | -101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-09-06 | QTR1 | 23/24 | 2023-07-10 | QTR1 | 23/24 | 514 | 882686.9 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A4 | 44113215201 | 2021-10-05 | QTR2 | 21/22 | 5 | 2 | 289 | 528 | 527 | 1 | 0 | 0 | 239 | 0 | 7424369 | 84545 | 7339824 | 7591181 | 7558842 | 0 | 0 | 0 | 7558842 | 7794728 | 394527 | 166812 | 75 | 0 | 0 | 15614 | 0 | 0 | 0 | 22253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63562 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-07-12 | QTR1 | 23/24 | 513 | 9276735.05 |  |  | 0 | 164 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59A9 | 43913015201 | 2022-01-04 | QTR3 | 21/22 | 1 | 0 | 140 | 248 | 246 | 2 | 0 | 0 | 83 | 25 | 679529 | 24250 | 655279 | 679529 | 677096 | 0 | 0 | 0 | 677096 | 677187 | 92 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-06-08 | QTR4 | 22/23 | 514 | 681570.8 |  |  | 7 | 34 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6518 | 42918635201 | 2021-12-08 | QTR2 | 21/22 | 5 | 2 | 300 | 332 | 272 | 60 | 0 | 0 | 32 | 0 | 2919079 | 50000 | 2869079 | 2940250 | 2881342 | 0 | 0 | 0 | 2881342 | 2942048 | 63520 | 21171 | 17 | 0 | 0 | 16786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16786 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2023-04-22 | QTR4 | 22/23 | 613 | 3061117.05 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6519 | 43476835201 | 2022-01-26 | QTR3 | 21/22 | 3 | 1 | 300 | 347 | 274 | 73 | 0 | 0 | 47 | 0 | 3487287 | 50000 | 3437287 | 3497187 | 3509376 | 0 | 0 | 0 | 3509376 | 3539751 | 30375 | 9900 | 25 | 0 | 0 | 30134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47968 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2023-09-13 | QTR1 | 23/24 | 2023-07-05 | QTR1 | 23/24 | 613 | 3568827.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6N09 | 44480525201 | 2022-07-28 | QTR1 | 22/23 | 1 | 0 | 240 | 260 | 172 | 88 | 0 | 0 | 20 | 0 | 797552 | 50000 | 747552 | 797552 | 706126 | 0 | 0 | 0 | 706126 | 706126 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-08-11 | QTR1 | 23/24 | 2023-06-29 | QTR4 | 22/23 | 613 | 1509363.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N47 | 44445015201 | 2022-05-26 | QTR4 | 21/22 | 1 | 2 | 250 | 272 | 220 | 52 | 0 | 0 | 22 | 0 | 2697327 | 50000 | 2647327 | 2771657 | 2731695 | 0 | 0 | 0 | 2731695 | 2718704 | -12991 | 74329 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 41276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89415 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 | 2023-05-24 | QTR4 | 22/23 | 636 | 2883318.39 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N55 | 44196815201 | 2021-08-26 | QTR1 | 21/22 | 1 | 0 | 280 | 460 | 459 | 1 | 0 | 0 | 180 | 0 | 757063 | 47154 | 709909 | 757063 | 654819 | 0 | 0 | 0 | 654819 | 654819 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2023-04-06 | QTR4 | 22/23 | 636 | 1042435.8 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7428 | 43258435201 | 2019-02-27 | QTR3 | 18/19 | 3 | 6 | 445 | 671 | 685 | -14 | 14 | 0 | 114 | 112 | 9277781 | 90000 | 9187781 | 9481539 | 10184938 | 0 | 0 | 0 | 10184938 | 10081240 | -98504 | 203759 | 58 | 0 | 21 | 283799 | 0 | 0 | 0 | 16679 | 10786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -96529 | 0 | 0 | 0 | 12534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 216484 | 10786 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2021-06-25 | QTR4 | 20/21 | 796 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7451 | 43982985201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 170 | 178 | 550 | -372 | 372 | 0 | 8 | 0 | 698558 | 34000 | 664558 | 698558 | 557380 | 0 | 0 | 0 | 557380 | 531562 | -25818 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2022-07-07 | QTR1 | 22/23 | 799 | 691075.3 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7468 | 44138615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 3 | 498 | 556 | 514 | 42 | 0 | 0 | 77 | -19 | 9161461 | 85000 | 9076461 | 9416662 | 9386983 | 0 | 0 | 0 | 9386983 | 9736387 | 388067 | 255200 | 53 | 0 | 0 | 337633 | 0 | 0 | 0 | 90042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 324328 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-13 | QTR1 | 23/24 | 2022-12-02 | QTR2 | 22/23 | 798 | 9040000 |  |  | 0 | 24 | 0 | -19 | -105466 | 0 |  | CO
07CO | 07 | T7498 | 44332015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 0 | 120 | 127 | 127 | 0 | 0 | 0 | 7 | 0 | 1340863 | 50000 | 1290863 | 1340863 | 1268582 | 0 | 0 | 0 | 1268582 | 1256582 | -12000 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 | 2023-05-22 | QTR4 | 22/23 | 796 | 2027300 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7N90 | 44822115201 | 2022-01-12 | QTR3 | 21/22 | 1 | 1 | 120 | 172 | 172 | 0 | 0 | 0 | 52 | 0 | 679686 | 28000 | 651686 | 695950 | 640611 | 0 | 0 | 0 | 640611 | 640611 | 0 | 16264 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-04-20 | QTR4 | 22/23 | 799 | 644500 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N95 | 44025115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 3 | 240 | 317 | 314 | 3 | 0 | 0 | 77 | 0 | 6430299 | 84000 | 6346299 | 6566839 | 6774752 | 0 | 0 | 0 | 6774752 | 7323867 | 551655 | 136540 | 52 | 0 | 0 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33706 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117706 | 33706 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 | 2023-02-24 | QTR3 | 22/23 | 796 | 8690700 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O11 | 44166515201 | 2022-02-09 | QTR3 | 21/22 | 2 | 0 | 180 | 220 | 220 | 0 | 0 | 0 | 40 | 0 | 3049631 | 50000 | 2999631 | 3049631 | 3013462 | 0 | 0 | 0 | 3013462 | 3013181 | -281 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-06-14 | QTR4 | 22/23 | 798 | 2409700 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q78 | 43554615201 | 2018-06-15 | QTR4 | 17/18 | 2 | 27 | 1430 | 1594 | 1265 | 329 | 0 | 0 | 164 | 0 | 143269821 | 150000 | 143119821 | 145759356 | 145166429 | 0 | 0 | 0 | 145166429 | 144192875 | -873129 | 2489535 | 81 | 0 | 0 | 398577 | 0 | 0 | 0 | 1404790 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131931 | 0 | 0 | 0 | 551048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359317 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 | 2022-03-01 | QTR3 | 21/22 | 854 | 156867749.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 83 | 0 | 0 | -140484 | 0 |  | DO
08DO | 08 | E8R77 | 43798615201 | 2019-05-14 | QTR4 | 18/19 | 3 | 5 | 738 | 1039 | 1039 | 0 | 0 | 0 | 301 | 0 | 31832323 | 150000 | 31682323 | 32865375 | 32938830 | 0 | 0 | 0 | 32938830 | 32271398 | -667433 | 1033052 | 175 | 0 | 0 | 62194 | 0 | 0 | 0 | 38182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 960260 | 0 | 0 | 0 | 77444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1138080 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2023-08-10 | QTR1 | 23/24 | 2022-08-17 | QTR1 | 22/23 | 854 | 33799887.12 |  |  | 0 | 98 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R97 | 43730045201 | 2019-09-17 | QTR1 | 19/20 | 1 | 35 | 939 | 1012 | 938 | 74 | 0 | 0 | 73 | 0 | 139979406 | 150000 | 139829406 | 145733672 | 144403400 | 0 | 0 | 0 | 144403400 | 143485400 | 457116 | 5754265 | 38 | 0 | 0 | 48807 | 0 | 0 | 0 | 4196617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94312 | 0 | 0 | 0 | 564973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4918551 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 | 2022-07-31 | QTR1 | 22/23 | 854 | 118749145.78 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S55 | 44070015201 | 2020-08-31 | QTR1 | 20/21 | 2 | 7 | 515 | 718 | 716 | 2 | 0 | 0 | 231 | -28 | 16707654 | 150000 | 16557654 | 17277221 | 16377036 | 0 | 0 | 0 | 16377036 | 16720673 | 485146 | 569567 | 175 | 0 | 0 | 18542 | 0 | 0 | 0 | 58747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469864 | 0 | 0 | 0 | 80825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28 | 616415 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2022-12-20 | QTR2 | 22/23 | 854 | 20328685.57 |  |  | 0 | 56 | 0 | -28 | -50316 | 0 |  | DO
08DO | 08 | E8T38 | 43730095201 | 2022-02-08 | QTR3 | 21/22 | 1 | 0 | 192 | 242 | 235 | 7 | 0 | 0 | 50 | 0 | 5115331 | 50000 | 5065331 | 5115331 | 5070631 | 0 | 0 | 0 | 5070631 | 5070631 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-06-15 | QTR4 | 22/23 | 854 | 5087753.85 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T39 | 44430115201 | 2021-12-14 | QTR2 | 21/22 | 1 | 3 | 234 | 278 | 253 | 25 | 0 | 0 | 44 | 0 | 1975221 | 50000 | 1925221 | 2101149 | 2102097 | 0 | 0 | 0 | 2102097 | 2083906 | 7736 | 125928 | 25 | 0 | 0 | 102641 | 0 | 0 | 0 | 36105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148344 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 | 2023-03-08 | QTR3 | 22/23 | 854 | 1709882.3 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T42 | 43799015201 | 2022-03-08 | QTR3 | 21/22 | 2 | 3 | 321 | 359 | 286 | 73 | 0 | 0 | 54 | -16 | 4166000 | 50000 | 4116000 | 4217668 | 4164480 | 0 | 0 | 0 | 4164480 | 4215075 | 52263 | 51668 | 31 | 0 | 0 | 44026 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 96868 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-05-22 | QTR4 | 22/23 | 854 | 3910716.97 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | -16 | 0 | 0 |  | DO
08DO | 08 | E8T86 | 43855115201 | 2022-08-16 | QTR1 | 22/23 | 1 | 1 | 136 | 169 | 142 | 27 | 0 | 0 | 9 | 24 | 597627 | 35230 | 562397 | 652711 | 607225 | 0 | 0 | 0 | 607225 | 607225 | 0 | 55083 | 6 | 0 | 24 | 55083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 55083 | 0 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-06-23 | QTR4 | 22/23 | 854 | 898718.41 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T87 | 43855015201 | 2022-08-16 | QTR1 | 22/23 | 1 | 0 | 199 | 202 | 84 | 118 | 0 | 0 | 3 | 0 | 767354 | 50000 | 717354 | 767354 | 705154 | 0 | 0 | 0 | 705154 | 705154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2023-05-11 | QTR4 | 22/23 | 854 | 1243902.61 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0