## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 77124775 | 76465132 | 80381510 | 80023506 | 0 | 81376505 | 6.423% | 61.54% | 3424899 | 4.479% | 3256736 | 4.223% | 3039 | 954 | 31.39% | 266 | 8.753% | 371 | 12.21% | 373 | 12.27% | 3783 | 24.48% | 4582 | 4963 | 3743 | 23.17% | 61.54%
| District Let | 25809992 | 25453231 | 26417473 | 26416265 | 100000 | 27149320 | 6.664% | 42.86% | 690128 | 2.711% | 607481 | 2.354% | 1500 | 549 | 36.6% | 158 | 10.53% | 62 | 4.133% | 460 | 30.67% | 2022 | 34.8% | 2487 | 2449 | 1742 | 16.13% | 85.71%
| All Contracts | 102934767 | 101918363 | 106798983 | 106439771 | 100000 | 108525825 | 6.483% | 55% | 4115027 | 4.038% | 3864217 | 3.754% | 4539 | 1503 | 33.11% | 424 | 9.341% | 433 | 9.54% | 833 | 18.35% | 5805 | 27.89% | 7069 | 7412 | 5485 | 20.84% | 70%
2 | Central Let | 139062884 | 137359300 | 140223242 | 140539945 | 0 | 143471855 | 4.45% | 88.89% | 1480267 | 1.078% | 1160359 | 0.8344% | 6404 | 1827 | 28.53% | 812 | 12.68% | 906 | 14.15% | 1109 | 17.32% | 8419 | 31.46% | 10802 | 10900 | 8261 | 29% | 55.56%
| District Let | 4399943 | 4349943 | 4455060 | 4448788 | 0 | 4443671 | 2.155% | 200% | 83873 | 1.928% | 55117 | 1.253% | 400 | 115 | 28.75% | 144 | 36% | 0 | 0% | 308 | 77% | 708 | 77% | 967 | 967 | 708 | 77% | 0%
| All Contracts | 143462827 | 141709243 | 144678302 | 144988733 | 0 | 147915526 | 4.38% | 92.86% | 1564140 | 1.104% | 1215476 | 0.8472% | 6804 | 1942 | 28.54% | 956 | 14.05% | 906 | 13.32% | 1417 | 20.83% | 9127 | 34.14% | 11769 | 11867 | 8969 | 31.82% | 53.57%
3 | Central Let | 124822446 | 123587707 | 127221890 | 129086242 | 0 | 131504606 | 6.406% | 92.31% | 2475230 | 2.003% | 2399446 | 1.922% | 6461 | 2547 | 39.42% | 989 | 15.31% | 1038 | 16.07% | 520 | 8.048% | 8019 | 24.11% | 10983 | 10918 | 7382 | 14.25% | 84.62%
| District Let | 20054381 | 19789467 | 20087648 | 20341691 | 0 | 20680252 | 4.501% | 100% | 56480 | 0.2854% | 33266 | 0.1659% | 1110 | 341 | 30.72% | 157 | 14.14% | 183 | 16.49% | 0 | 0% | 1293 | 16.49% | 1668 | 1614 | 1116 | 0.5405% | 100%
| All Contracts | 144876827 | 143377174 | 147309538 | 149427933 | 0 | 152184858 | 6.143% | 93.94% | 2531710 | 1.766% | 2432712 | 1.679% | 7571 | 2888 | 38.15% | 1146 | 15.14% | 1221 | 16.13% | 520 | 6.868% | 9312 | 23% | 12651 | 12532 | 8498 | 12.24% | 87.88%
4 | Central Let | 53696550 | 53006714 | 55231467 | 54130541 | 0 | 54809288 | 3.401% | 100% | 1838080 | 3.468% | 1537552 | 2.863% | 3828 | 1226 | 32.03% | 365 | 9.535% | 699 | 18.26% | 6 | 0.1567% | 4533 | 18.42% | 5648 | 5605 | 4014 | 4.859% | 100%
| District Let | 39059700 | 38582275 | 40832572 | 39709451 | 0 | 39896139 | 3.405% | 85.71% | 1799755 | 4.665% | 1772872 | 4.539% | 1863 | 515 | 27.64% | 137 | 7.354% | 85 | 4.563% | 109 | 5.851% | 2057 | 10.41% | 2651 | 2480 | 1828 | -1.879% | 85.71%
| All Contracts | 92756250 | 91588989 | 96064039 | 93839992 | 0 | 94705427 | 3.403% | 94.74% | 3637835 | 3.972% | 3310424 | 3.569% | 5691 | 1741 | 30.59% | 502 | 8.821% | 784 | 13.78% | 115 | 2.021% | 6590 | 15.8% | 8299 | 8085 | 5842 | 2.653% | 94.74%
5 | Central Let | 97437583 | 96958825 | 108709088 | 110777281 | 0 | 113148544 | 16.7% | 66.67% | 11073608 | 11.42% | 11122604 | 11.42% | 2079 | 412 | 19.82% | 423 | 20.35% | 0 | 0% | 437 | 21.02% | 2516 | 21.02% | 3351 | 3333 | 2498 | 20.15% | 83.33%
| District Let | 27556091 | 27145900 | 28119375 | 27609222 | 0 | 28037176 | 3.283% | 100% | 668565 | 2.463% | 563284 | 2.044% | 1799 | 352 | 19.57% | 517 | 28.74% | 0 | 0% | 110 | 6.115% | 1909 | 6.115% | 2764 | 2651 | 1782 | -0.945% | 100%
| All Contracts | 124993674 | 124104725 | 136828463 | 138386503 | 0 | 141185720 | 13.76% | 85.71% | 11742173 | 9.462% | 11685888 | 9.349% | 3878 | 764 | 19.7% | 940 | 24.24% | 0 | 0% | 547 | 14.11% | 4425 | 14.11% | 6115 | 5984 | 4280 | 10.37% | 92.86%
6 | Central Let | 25446639 | 25081795 | 25884343 | 24994781 | 982000 | 25636764 | 2.213% | 100% | 409797 | 1.634% | 437704 | 1.72% | 2008 | 201 | 10.01% | 123 | 6.125% | 43 | 2.141% | 0 | 0% | 2051 | 2.141% | 2375 | 2145 | 1821 | -9.313% | 100%
| District Let | 7065207 | 6868053 | 7247849 | 7031315 | 180000 | 7007403 | 2.029% | 100% | 147727 | 2.151% | 182641 | 2.585% | 1220 | 147 | 12.05% | 53 | 4.344% | 55 | 4.508% | 0 | 0% | 1275 | 4.508% | 1475 | 1223 | 1023 | -16.15% | 100%
| All Contracts | 32511846 | 31949848 | 33132192 | 32026096 | 1162000 | 32644167 | 2.173% | 100% | 557524 | 1.745% | 620345 | 1.908% | 3228 | 348 | 10.78% | 176 | 5.452% | 98 | 3.036% | 0 | 0% | 3326 | 3.036% | 3850 | 3368 | 2844 | -11.9% | 100%
7 | Central Let | 50454973 | 49653080 | 51689029 | 51655148 | 288000 | 51983480 | 4.693% | 85.71% | 1323162 | 2.665% | 1234056 | 2.446% | 2473 | 289 | 11.69% | 173 | 6.996% | 0 | 0% | 107 | 4.327% | 2580 | 4.327% | 3042 | 3352 | 2890 | 16.86% | 71.43%
| District Let | 20125326 | 19744326 | 20472654 | 20161657 | 0 | 20620075 | 4.435% | 87.5% | 331034 | 1.677% | 347328 | 1.726% | 1450 | 158 | 10.9% | 127 | 8.759% | 0 | 0% | 0 | 0% | 1450 | 0% | 1771 | 1682 | 1397 | -3.655% | 100%
| All Contracts | 70580299 | 69397406 | 72161683 | 71816805 | 288000 | 72603555 | 4.62% | 86.67% | 1654196 | 2.384% | 1581384 | 2.241% | 3923 | 447 | 11.39% | 300 | 7.647% | 0 | 0% | 107 | 2.728% | 4030 | 2.728% | 4813 | 5034 | 4287 | 9.279% | 86.67%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 365803691 | 364725862 | 376340584 | 373200299 | 11138823 | 370944765 | 1.705% | 100% | 11015875 | 3.02% | 10536890 | 2.88% | 5563 | 771 | 13.86% | 435 | 7.82% | 73 | 1.312% | 39 | 0.7011% | 5675 | 2.013% | 6817 | 6095 | 4889 | -12.12% | 100%
| All Contracts | 365803691 | 364725862 | 376340584 | 373200299 | 11138823 | 370944765 | 1.705% | 100% | 11015875 | 3.02% | 10536890 | 2.88% | 5563 | 771 | 13.86% | 435 | 7.82% | 73 | 1.312% | 39 | 0.7011% | 5675 | 2.013% | 6817 | 6095 | 4889 | -12.12% | 100%
Totals This Qtr | Central Let | 568045850 | 562112553 | 589340569 | 591207444 | 1270000 | 601931042 | 7.084% | 86.73% | 22025043 | 3.918% | 21148457 | 3.723% | 26292 | 7456 | 28.36% | 3151 | 11.98% | 3057 | 11.63% | 2552 | 9.706% | 31901 | 21.33% | 40783 | 41216 | 30609 | 16.42% | 75.51%
| District Let | 509874331 | 506659057 | 523973215 | 518918688 | 11418823 | 518778801 | 2.392% | 90.91% | 14793437 | 2.92% | 14098879 | 2.765% | 14905 | 2948 | 19.78% | 1728 | 11.59% | 458 | 3.073% | 1026 | 6.884% | 16389 | 9.956% | 20600 | 19161 | 14485 | -2.818% | 94.55%
| All Contracts | 1077920181 | 1068771610 | 1113313784 | 1110126132 | 12688823 | 1120709843 | 4.86% | 88.24% | 36818480 | 3.445% | 35247336 | 3.27% | 41197 | 10404 | 25.25% | 4879 | 11.84% | 3515 | 8.532% | 3578 | 8.685% | 48290 | 17.22% | 61383 | 60377 | 45094 | 9.459% | 82.35%
Totals Previous Quarter | Central Let | 375786165 | 372464164 | 393314791 | 396375435 | 678000 | 403421849 | 8.312% | 80.7% | 10477120 | 2.813% | 17243963 | 4.589% | 16194 | 4347 | 26.84% | 1950 | 12.04% | 905 | 5.588% | 1807 | 11.16% | 18906 | 16.75% | 25403 | 26174 | 19877 | 22.74% | 66.67%
| District Let | 432888916 | 430877910 | 445283737 | 441285542 | 11418823 | 441023059 | 2.355% | 90% | 11573520 | 2.686% | 12394817 | 2.863% | 9460 | 1698 | 17.95% | 1050 | 11.1% | 153 | 1.617% | 125 | 1.321% | 9738 | 2.939% | 12525 | 11648 | 8900 | -5.92% | 96.67%
| All Contracts | 808675081 | 803342074 | 838598528 | 837660977 | 12096823 | 844444908 | 5.116% | 83.91% | 22050640 | 2.745% | 29638780 | 3.665% | 25654 | 6045 | 23.56% | 3000 | 11.69% | 1058 | 4.124% | 1932 | 7.531% | 28644 | 11.66% | 37928 | 37822 | 28777 | 12.17% | 77.01%
Totals Fiscal Year 2022/2023 | Central Let | 807702821 | 799341758 | 833390919 | 832957794 | 5000000 | 841586229 | 5.285% | 85.71% | 27156959 | 3.397% | 25521410 | 3.16% | 34471 | 8229 | 23.87% | 4495 | 13.04% | 1098 | 3.185% | 3338 | 9.684% | 38907 | 12.87% | 52035 | 51766 | 39042 | 13.26% | 80.95%
| District Let | 1250337631 | 1243631654 | 1383433987 | 1382096402 | 7902900 | 1384395798 | 11.32% | 85.59% | 131523221 | 10.58% | 133096359 | 10.64% | 34310 | 6575 | 19.16% | 4659 | 13.58% | 1662 | 4.844% | 5020 | 14.63% | 40992 | 19.48% | 52622 | 51185 | 39951 | 16.44% | 83.9%
| All Contracts | 2058040452 | 2042973412 | 2216824906 | 2215054196 | 12902900 | 2225982027 | 8.958% | 85.66% | 158680180 | 7.767% | 158617769 | 7.707% | 68781 | 14804 | 21.52% | 9154 | 13.31% | 2760 | 4.013% | 8358 | 12.15% | 79899 | 16.16% | 104657 | 102951 | 78993 | 14.85% | 82.38%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1751 | 41066635201 | 2020-04-29 | QTR4 | 19/20 | 4 | 15 | 875 | 1016 | 963 | 94.74% | 1 | 53 | 0 | 0 | 127 | 14 | 43563143 | 150000 | 43413143 | 43826539 | 44268970 | 0 | 0 | 0 | 44268970 | 45616616 | 105.1% | 1 | 1915546 | 263396 | 80 | 54 | 0 | 0 | 351912 | 3918 | 7 | 0 | 219896 | 30715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17978 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 22507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287200 | 0 | 7 | 14 | 343410 | 34633 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-09-11 | QTR1 | 23/24 |  | 2023-04-28 | QTR4 | 22/23 | 108 | 44746155.07
| 01 | T1761 | 42982315201 | 2021-06-09 | QTR4 | 20/21 | 2 | 18 | 275 | 545 | 530 | 130.2% | 0 | 15 | 0 | 0 | 223 | 47 | 4097408 | 50000 | 4047408 | 4902150 | 4899132 | 0 | 0 | 0 | 4899132 | 4822749 | 119.2% | 0 | 34379 | 804742 | 131 | 41 | 0 | 42 | 118523 | 55203 | 51 | 5 | 478225 | 97145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42992 | 42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 47 | 830672 | 195339 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2023-02-24 | QTR3 | 22/23 | 113 | 4251830.23
| 01 | T1772 | 44211515201 | 2020-09-30 | QTR1 | 20/21 | 3 | 1 | 150 | 177 | 607 | 386.7% | 0 | -430 | 430 | 0 | 11 | 16 | 668342 | 41495 | 626847 | 668342 | 605783 | 0 | 0 | 0 | 605783 | 595755 | 95.04% | 1 | 25365 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 6341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 6341 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 |  | 2022-12-05 | QTR2 | 22/23 | 108 | 802465.89
| 01 | T1777 | 43943015201 | 2020-09-30 | QTR1 | 20/21 | 4 | 3 | 325 | 607 | 638 | 125.5% | 0 | -31 | 31 | 0 | 216 | 66 | 7973682 | 92806 | 7880876 | 8225110 | 8195027 | -106857 | 0 | -106857 | 8088170 | 8717413 | 110.6% | 0 | 921857 | 251428 | 207 | 23 | 0 | 0 | 126514 | 115529 | 0 | 52 | 124433 | 124433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 14 | 11465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 66 | 262412 | 239963 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 |  | 2022-10-18 | QTR2 | 22/23 | 118 | 9500361.49
| 01 | T1781 | 44151815201 | 2021-01-27 | QTR3 | 20/21 | 2 | 4 | 285 | 400 | 400 | 126% | 0 | 0 | 0 | 0 | 41 | 74 | 4960436 | 59129 | 4901307 | 5450251 | 5304714 | 0 | 0 | 0 | 5304714 | 5560151 | 113.4% | 0 | 265895 | 489815 | 14 | 27 | 0 | 74 | 470632 | 0 | 0 | 0 | 17986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 489815 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2022-06-30 | QTR4 | 21/22 | 118 | 5666706.37
| 01 | T1790 | 44240115201 | 2020-08-26 | QTR1 | 20/21 | 1 | 1 | 110 | 145 | 141 | 104.5% | 1 | 4 | 0 | 0 | 26 | 9 | 697485 | 0 | 697485 | 700625 | 698869 | 0 | 0 | 0 | 698869 | 698869 | 100.2% | 1 | 0 | 3140 | 21 | 5 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140 | 3140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3140 | 3140 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-24 | QTR2 | 23/24 |  | 2021-07-09 | QTR1 | 21/22 | 108 | 802615.61 | B0 | ACC - LUMP SUM
| 01 | T1806 | 44155915201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 250 | 391 | 391 | 112% | 1 | 0 | 0 | 0 | 134 | 7 | 7108184 | 63330 | 7044854 | 8445969 | 8418621 | 0 | 0 | 0 | 8418621 | 7803372 | 110.8% | 0 | 265502 | 1337785 | 92 | 19 | 0 | 0 | 0 | 0 | 23 | 7 | 473396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 880751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 39 | 1354148 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 |  | 2023-05-01 | QTR4 | 22/23 | 115 | 6181054.02
| 01 | T1808 | 44233315201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 140 | 293 | 293 | 118.6% | 1 | 0 | 0 | 0 | 153 | 0 | 1139701 | 50000 | 1089701 | 1148801 | 1029185 | 0 | 0 | 0 | 1029185 | 1021881 | 93.78% | 1 | 1796 | 9100 | 105 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 9100 | 0 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-03-17 | QTR3 | 22/23 | 108 | 1098275.5
| 01 | T1817 | 44068815201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 80 | 165 | 165 | 133.8% | 0 | 0 | 0 | 0 | 85 | 0 | 650650 | 18505 | 632145 | 655279 | 608957 | 0 | 0 | 0 | 608957 | 609408 | 96.4% | 1 | 451 | 4629 | 47 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 8153 | 45738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 15989 | 45738 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 |  | 2022-12-13 | QTR2 | 22/23 | 115 | 447609.94
| 01 | T1826 | 44421215201 | 2021-08-25 | QTR1 | 21/22 | 1 | 3 | 107 | 259 | 259 | 100% | 1 | 0 | 0 | 0 | 44 | 108 | 1045874 | 41345 | 1004529 | 1076047 | 1015157 | 0 | 0 | 0 | 1015157 | 994639 | 99.02% | 1 | 0 | 30174 | 132 | 20 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 20519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 31344 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2023-03-20 | QTR3 | 22/23 | 118 | 898648.05
| 01 | T1828 | 44033715201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 97 | 129 | 129 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 560933 | 21933 | 539000 | 623460 | 604533 | 0 | 0 | 0 | 604533 | 604533 | 112.2% | 0 | 0 | 62527 | 31 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 62527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65533 | 0 | F823160551 | LEON AMERICA CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-09-25 | QTR1 | 23/24 |  | 2023-05-15 | QTR4 | 22/23 | 113 | 517232.45 | B0 | ACC - LUMP SUM
| 01 | T1834 | 44632015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 215 | 280 | 272 | 96.28% | 1 | 8 | 0 | 0 | 65 | 0 | 4197476 | 50000 | 4147476 | 4197476 | 3945832 | 0 | 0 | 0 | 3945832 | 3902393 | 94.09% | 1 | -43439 | 0 | 47 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 |  | 2023-06-22 | QTR4 | 22/23 | 113 | 4322110.94
| 01 | T1839 | 44012715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 0 | 130 | 175 | 175 | 100% | 1 | 0 | 0 | 0 | 45 | 0 | 461461 | 21100 | 440361 | 461461 | 428726 | 0 | 0 | 0 | 428726 | 428726 | 97.36% | 1 | 0 | 0 | 29 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2023-03-06 | QTR3 | 22/23 | 115 | 438393.45
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 13 | 25 | 52 | 3039 | 4582 | 4963 | 61.54% | 8 | -381 | 461 | 0 | 1202 | 341 | 77124775 | 659643 | 76465132 | 80381510 | 80023506 | -106857 | 0 | -106857 | 79916649 | 81376505 | 61.54% | 8 | 3387352 | 3256736 | 954 | 266 | 0 | 125 | 1078406 | 174650 | 81 | 64 | 1395799 | 252293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94152 | 3140 | 0 | 0 | 19174 | 0 | 0 | 0 | 0 | 0 | 263 | 184 | 1055103 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 69462 | 88730 | 0 | 0 | 0 | 0 | 0 | 0 | -287200 | 0 | 371 | 373 | 3424899 | 518813
| 01 | E1S66 | 43813715201 | 2020-12-03 | QTR2 | 20/21 | 6 | 8 | 450 | 845 | 838 | 156.9% | 0 | 7 | 0 | 0 | 132 | 263 | 8623489 | 90613 | 8532876 | 9397066 | 9294008 | 0 | 0 | 0 | 9294008 | 9490393 | 111.2% | 0 | 487144 | 773578 | 84 | 48 | 0 | 71 | 305583 | 0 | 0 | 84 | 299190 | 27177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 15720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 815494 | 27177 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 |  | 2023-06-30 | QTR4 | 22/23 | 115 | 7399516.3 | B10:B2:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 01 | E1S92 | 44153415201 | 2021-11-04 | QTR2 | 21/22 | 3 | 2 | 275 | 390 | 390 | 101.8% | 1 | 0 | 0 | 0 | 115 | 0 | 5052712 | 52873 | 4999839 | 4990876 | 4942213 | 0 | 0 | 0 | 4942213 | 4940854 | 98.82% | 1 | -1360 | -61836 | 87 | 23 | 0 | 0 | 0 | 0 | 5 | 0 | 6022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42313 | 0 | 5 | 0 | -55813 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-12-20 | QTR2 | 23/24 |  | 2023-09-11 | QTR1 | 23/24 | 115 | 4924224.57
| 01 | E1U10 | 44592715201 | 2021-10-21 | QTR2 | 21/22 | 1 | 2 | 90 | 345 | 339 | 93.33% | 1 | 6 | 0 | 0 | 58 | 197 | 1030376 | 38210 | 992166 | 1035071 | 1194101 | 0 | 0 | 0 | 1194101 | 1189756 | 119.9% | 0 | 0 | 4695 | 230 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18641 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 28229 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-10-27 | QTR2 | 23/24 |  | 2023-07-16 | QTR1 | 23/24 | 108 | 838447.1
| 01 | E1U12 | 44155315201 | 2021-09-16 | QTR1 | 21/22 | 2 | 4 | 300 | 439 | 422 | 94.33% | 1 | 17 | 0 | 0 | 139 | 0 | 6272386 | 62629 | 6209757 | 6303322 | 6506395 | 0 | 0 | 0 | 6506395 | 6911842 | 111.3% | 0 | 427490 | 30935 | 115 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 8892 | 976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 22043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 35473 | 976 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-12 | QTR1 | 23/24 |  | 2023-05-12 | QTR4 | 22/23 | 108 | 6222847.06
| 01 | E1U14 | 44477715201 | 2021-12-02 | QTR2 | 21/22 | 2 | 2 | 160 | 222 | 222 | 107.5% | 1 | 0 | 0 | 0 | 62 | 0 | 3819554 | 50000 | 3769554 | 3657701 | 3521817 | 0 | 0 | 0 | 3521817 | 3658011 | 97.04% | 1 | 136195 | -161853 | 29 | 21 | 12 | 0 | 56568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -218421 | 0 | 12 | 0 | -161853 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-07-21 | QTR1 | 23/24 |  | 2023-03-03 | QTR3 | 22/23 | 115 | 3928132.77 | B0 | ACC - LUMP SUM
| 01 | E1U17 | 44594115201 | 2022-02-17 | QTR3 | 21/22 | 1 | 0 | 150 | 171 | 166 | 96.67% | 1 | 5 | 0 | 0 | 21 | 0 | 722056 | 48017 | 674039 | 722056 | 642082 | 0 | 100000 | 100000 | 742082 | 642815 | 95.37% | 1 | -99267 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-03-17 | QTR3 | 22/23 | 115 | 1070560.76 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1V07 | 44023115201 | 2022-09-15 | QTR1 | 22/23 | 1 | 3 | 75 | 75 | 72 | 96% | 1 | 3 | 0 | 0 | 0 | 0 | 289419 | 14419 | 275000 | 311381 | 315649 | 0 | 0 | 0 | 315649 | 315649 | 114.8% | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 6636 | 0 | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28598 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2023-08-09 | QTR1 | 23/24 |  | 2023-03-29 | QTR3 | 22/23 | 118 | 331704.75
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 7 | 16 | 21 | 1500 | 2487 | 2449 | 85.71% | 6 | 38 | 0 | 0 | 527 | 460 | 25809992 | 356761 | 25453231 | 26417473 | 26416265 | 0 | 100000 | 100000 | 26516265 | 27149320 | 42.86% | 3 | 950202 | 607481 | 549 | 158 | 12 | 71 | 368787 | 0 | 5 | 84 | 341310 | 28153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177266 | 0 | 0 | 0 | 21391 | 0 | 0 | 0 | 0 | 0 | 45 | 245 | 42108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | -260734 | 0 | 62 | 460 | 690128 | 28153
| District 01 Totals |  |  |  |  | 20 | 41 | 73 | 4539 | 7069 | 7412 | 70% | 14 | -343 | 461 | 0 | 1729 | 801 | 102934767 | 1016404 | 101918363 | 106798983 | 106439771 | -106857 | 100000 | -6857 | 106432914 | 108525825 | 55% | 11 | 4337554 | 3864217 | 1503 | 424 | 12 | 196 | 1447193 | 174650 | 86 | 148 | 1737109 | 280446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271418 | 3140 | 0 | 0 | 40565 | 0 | 0 | 0 | 0 | 0 | 308 | 429 | 1097211 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 69462 | 88730 | 0 | 60 | 0 | 0 | 0 | 0 | -547934 | 0 | 433 | 833 | 4115027 | 546966
| 02 | T2703 | 21272425201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 550 | 719 | 968 | 145.3% | 0 | -249 | 249 | 0 | 169 | 0 | 11717625 | 120 | 11717505 | 11666748 | 11573612 | -1206768 | 0 | -1206768 | 10366844 | 10334162 | 88.19% | 1 | -32682 | -50877 | 123 | 46 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68877 | 0 | 0 | 0 | -50877 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 |  | 2021-05-03 | QTR4 | 20/21 | 209 | 12539660.43
| 02 | T2725 | 42307145201 | 2018-12-05 | QTR2 | 18/19 | 1 | 5 | 300 | 737 | 737 | 185.3% | 0 | 0 | 0 | 0 | 181 | 256 | 7294444 | 68754 | 7225690 | 7636147 | 7798283 | 0 | 0 | 0 | 7798283 | 7754246 | 107.3% | 1 | -44037 | 341703 | 85 | 96 | 0 | 27 | 92502 | 0 | 0 | 229 | 220039 | 17548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4989 | 0 | 0 | 0 | 6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 330105 | 23598 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2021-06-17 | QTR4 | 20/21 | 214 | 7079691.78
| 02 | T2749 | 43946715201 | 2019-09-25 | QTR1 | 19/20 | 3 | 10 | 600 | 1149 | 1149 | 134% | 0 | 0 | 0 | 0 | 265 | 284 | 11950705 | 126323 | 11824382 | 12606239 | 12535468 | 0 | 0 | 0 | 12535468 | 12707911 | 107.5% | 1 | 309266 | 655533 | 237 | 108 | 0 | 39 | 488108 | 0 | 0 | 59 | 227908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 4468 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 726457 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-28 | QTR1 | 23/24 |  | 2023-02-27 | QTR3 | 22/23 | 208 | 11844644.47
| 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 127.2% | 0 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 109.4% | 1 | 329791 | 87098 | 104 | 52 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-11-17 | QTR2 | 23/24 |  | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6
| 02 | T2787 | 44105915201 | 2020-07-29 | QTR1 | 20/21 | 1 | 2 | 250 | 376 | 373 | 116.8% | 1 | 3 | 0 | 0 | 81 | 45 | 13904803 | 145464 | 13759339 | 14427901 | 14501738 | 0 | 0 | 0 | 14501738 | 14430355 | 104.9% | 1 | -71383 | 523099 | 59 | 22 | 0 | 45 | 523099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 523099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-16 | QTR2 | 23/24 |  | 2021-09-15 | QTR1 | 21/22 | 209 | 14722615.57
| 02 | T2788 | 44258115201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 240 | 516 | 513 | 122.1% | 0 | 3 | 0 | 0 | 220 | 56 | 7945667 | 68632 | 7877035 | 7945667 | 8114839 | 0 | 0 | 0 | 8114839 | 8571019 | 108.8% | 1 | 459557 | 0 | 196 | 24 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-16 | QTR2 | 23/24 |  | 2022-07-07 | QTR1 | 22/23 | 209 | 6919711.56
| 02 | T2802 | 43575715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 180 | 523 | 523 | 220% | 0 | 0 | 0 | 0 | 29 | 314 | 1262262 | 50000 | 1212262 | 1262262 | 1249368 | 0 | 0 | 0 | 1249368 | 1249498 | 103.1% | 1 | 130 | 0 | 103 | 24 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2022-12-23 | QTR2 | 22/23 | 208 | 1338362.89
| 02 | T2803 | 44126115201 | 2021-05-26 | QTR4 | 20/21 | 2 | 3 | 325 | 487 | 487 | 124.6% | 0 | 0 | 0 | 0 | 162 | 0 | 4633748 | 75000 | 4558748 | 3852057 | 3929376 | 0 | 0 | 0 | 3929376 | 4154909 | 91.14% | 1 | 225533 | -781691 | 40 | 42 | 30 | 0 | -739805 | 0 | 0 | 0 | 7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -732738 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2023-01-06 | QTR3 | 22/23 | 208 | 4540382.58
| 02 | T2813 | 43617815201 | 2021-06-09 | QTR4 | 20/21 | 3 | 2 | 350 | 501 | 501 | 112% | 1 | 0 | 0 | 0 | 109 | 42 | 6155492 | 64024 | 6091468 | 6241492 | 6261727 | 0 | 0 | 0 | 6261727 | 6665942 | 109.4% | 1 | 404215 | 86000 | 72 | 37 | 0 | 42 | 61451 | 0 | 0 | 0 | 59384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 120835 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 |  | 2023-01-20 | QTR3 | 22/23 | 209 | 7776561.61
| 02 | T2821 | 44327315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 150 | 289 | 271 | 122.7% | 0 | 18 | 0 | 0 | 118 | 21 | 4876894 | 52518 | 4824376 | 4984966 | 5022406 | 0 | 0 | 0 | 5022406 | 5415141 | 112.2% | 0 | 392735 | 108073 | 77 | 10 | 0 | 21 | 125561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 21 | 125561 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 |  | 2022-10-13 | QTR2 | 22/23 | 216 | 5483810.94
| 02 | T2822 | 44331315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 250 | 488 | 483 | 98.8% | 1 | 5 | 0 | 0 | 236 | 2 | 9173879 | 91638 | 9082241 | 9173879 | 9342688 | 0 | 0 | 0 | 9342688 | 9910699 | 109.1% | 1 | 568010 | 0 | 205 | 31 | 28 | 0 | 0 | 0 | 0 | 0 | 12476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 2 | 12476 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-03 | QTR2 | 23/24 |  | 2023-06-29 | QTR4 | 22/23 | 209 | 9935885.58
| 02 | T2824 | 44327415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 2 | 250 | 455 | 453 | 105.2% | 1 | 2 | 0 | 0 | 190 | 15 | 3471681 | 50000 | 3421681 | 3603585 | 3475517 | 0 | 0 | 0 | 3475517 | 3614982 | 105.6% | 1 | 141674 | 131904 | 166 | 24 | 0 | 0 | 14150 | 0 | 0 | 15 | 130039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 15 | 146399 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-05-04 | QTR4 | 22/23 | 216 | 3836185.04
| 02 | T2825 | 44328215201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 75 | 125 | 124 | 152% | 0 | 1 | 0 | 0 | 10 | 40 | 698919 | 27456 | 671464 | 698919 | 656099 | 0 | 0 | 0 | 656099 | 656099 | 97.71% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-14 | QTR1 | 23/24 |  | 2022-06-28 | QTR4 | 21/22 | 209 | 629198.54
| 02 | T2826 | 44331115201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 220 | 264 | 264 | 100% | 1 | 0 | 0 | 0 | 44 | 0 | 8657266 | 87492 | 8569774 | 8657266 | 8107793 | 0 | 0 | 0 | 8107793 | 8099899 | 94.52% | 1 | -7895 | 0 | 23 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-29 | QTR1 | 23/24 |  | 2023-05-05 | QTR4 | 22/23 | 209 | 10016766.94
| 02 | T2829 | 44120815201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 150 | 227 | 224 | 117.3% | 1 | 3 | 0 | 0 | 48 | 29 | 1047740 | 50000 | 997740 | 1047740 | 1004140 | 0 | 0 | 0 | 1004140 | 1004137 | 100.6% | 1 | -3 | 0 | 28 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-10-03 | QTR2 | 23/24 |  | 2023-06-01 | QTR4 | 22/23 | 208 | 1984965.49
| 02 | T2833 | 44325815201 | 2022-01-12 | QTR3 | 21/22 | 1 | 0 | 210 | 235 | 235 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 6173212 | 71171 | 6102041 | 6173212 | 6149692 | 0 | 0 | 0 | 6149692 | 6808147 | 111.6% | 0 | 658455 | 0 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2022-11-23 | QTR2 | 22/23 | 214 | 7484487.76
| 02 | T2836 | 44325915201 | 2022-02-23 | QTR3 | 21/22 | 2 | 2 | 210 | 287 | 287 | 118.6% | 1 | 0 | 0 | 0 | 72 | 5 | 4069827 | 50000 | 4019827 | 4084043 | 4107794 | 0 | 0 | 0 | 4107794 | 4236681 | 105.4% | 1 | 130239 | 14216 | 19 | 19 | 0 | 0 | 0 | 0 | 34 | 0 | 12864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 14216 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-02 | QTR2 | 23/24 |  | 2023-04-17 | QTR4 | 22/23 | 208 | 5072861.67
| 02 | T2837 | 44329415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 0 | 180 | 262 | 260 | 113.9% | 1 | 2 | 0 | 0 | 55 | 27 | 1371850 | 50000 | 1321850 | 1371850 | 1320562 | 0 | 0 | 0 | 1320562 | 1320562 | 99.9% | 1 | 0 | 0 | 29 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 |  | 2023-01-19 | QTR3 | 22/23 | 208 | 1352767.24
| 02 | T2846 | 44126015201 | 2022-01-12 | QTR3 | 21/22 | 2 | 1 | 300 | 413 | 418 | 101.7% | 1 | -5 | 5 | 0 | 113 | 0 | 9551621 | 106078 | 9445543 | 9552942 | 9869457 | -18930 | 0 | -18930 | 9850527 | 10484168 | 111% | 0 | 634962 | 1321 | 83 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2504 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-11-02 | QTR2 | 23/24 |  | 2023-05-25 | QTR4 | 22/23 | 208 | 11919284.18
| 02 | T2855 | 43935815201 | 2021-06-09 | QTR4 | 20/21 | 2 | 0 | 350 | 464 | 459 | 106.6% | 1 | 5 | 0 | 0 | 86 | 28 | 7918962 | 100000 | 7818962 | 7918962 | 7962203 | 0 | 0 | 0 | 7962203 | 8267055 | 105.7% | 1 | 304853 | 0 | 42 | 44 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 |  | 2023-02-23 | QTR3 | 22/23 | 209 | 7233767.77
| 02 | T2857 | 44721115201 | 2022-01-26 | QTR3 | 21/22 | 1 | 0 | 120 | 193 | 185 | 131.7% | 0 | 8 | 0 | 0 | 27 | 46 | 1077522 | 44955 | 1032567 | 1077522 | 1075156 | 0 | 0 | 0 | 1075156 | 1075156 | 104.1% | 1 | 0 | 0 | 16 | 11 | 0 | 30 | 18350 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 18350 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2022-10-14 | QTR2 | 22/23 | 208 | 1339271.36
| 02 | T2869 | 43567925201 | 2022-06-08 | QTR4 | 21/22 | 2 | 0 | 180 | 199 | 178 | 88.33% | 1 | 21 | 0 | 0 | 19 | 0 | 1298306 | 50000 | 1248306 | 1298306 | 1209436 | 0 | 0 | 0 | 1209436 | 1209097 | 96.86% | 1 | -339 | 0 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 |  | 2023-04-19 | QTR4 | 22/23 | 209 | 1554775.94
| 02 | T2873 | 44557615201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 90 | 90 | 19 | 21.11% | 1 | 71 | 0 | 0 | 0 | 0 | 240110 | 17791 | 222319 | 240110 | 185940 | 0 | 0 | 0 | 185940 | 185940 | 83.64% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-03-31 | QTR3 | 22/23 | 208 | 402519.71
| 02 | T2875 | 44912925201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 60 | 160 | 160 | 151.7% | 0 | 0 | 0 | 0 | 69 | 31 | 1386562 | 50000 | 1336562 | 1386562 | 1349510 | 0 | 0 | 0 | 1349510 | 1349510 | 101% | 1 | 0 | 0 | 53 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-30 | QTR2 | 23/24 |  | 2023-03-14 | QTR3 | 22/23 | 208 | 1705476.65
| 02 | T2877 | 20954355201 | 2022-06-15 | QTR4 | 21/22 | 2 | 3 | 90 | 144 | 140 | 118.9% | 1 | 4 | 0 | 0 | 47 | 7 | 744369 | 43296 | 701073 | 788349 | 712669 | 0 | 0 | 0 | 712669 | 709731 | 101.2% | 1 | 0 | 43980 | 10 | 23 | 0 | 0 | 0 | 0 | 0 | 7 | 41042 | 41042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7 | 43980 | 41042 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-07 | QTR2 | 23/24 |  | 2023-01-24 | QTR3 | 22/23 | 208 | 931264.85
| 02 | T2923 | 44542625201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 74 | 101 | 94 | 91.89% | 1 | 7 | 0 | 0 | 26 | 1 | 212969 | 11187 | 201781 | 212969 | 198096 | 0 | 0 | 0 | 198096 | 198096 | 98.17% | 1 | 0 | 0 | 15 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-09-05 | QTR1 | 23/24 |  | 2023-03-01 | QTR3 | 22/23 | 208 | 251711.77
| 02 | T9023 | 44624515223 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 250 | 733 | 730 | 266.8% | 0 | 3 | 0 | 0 | 483 | 0 | 3516622 | 50000 | 3466622 | 3516622 | 3642093 | 0 | 0 | 0 | 3642093 | 3642131 | 105.1% | 1 | 38 | 0 | 14 | 49 | 420 | 0 | 0 | 0 | 0 | 0 | 30591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 41498 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-09-27 | QTR1 | 23/24 |  | 2023-08-03 | QTR1 | 23/24 | 209 | 3117936.11
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 27 | 37 | 34 | 6404 | 10802 | 10900 | 55.56% | 15 | -98 | 254 | 0 | 3149 | 1249 | 139062884 | 1703583 | 137359300 | 140223242 | 140539945 | -1225698 | 0 | -1225698 | 139314247 | 143471855 | 88.89% | 24 | 4403119 | 1160359 | 1827 | 812 | 498 | 449 | 635791 | 0 | 34 | 329 | 773833 | 72138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 15896 | 0 | 0 | 2 | 102114 | 67137 | 0 | 0 | 0 | 0 | 180 | 209 | 15461 | 872 | 0 | 0 | 0 | 0 | 0 | 27 | 6050 | 6050 | 180 | 93 | 0 | 0 | 0 | 0 | -68877 | 0 | 906 | 1109 | 1480267 | 146196
| 02 | E2Y76 | 20972255201 | 2020-04-15 | QTR4 | 19/20 | 2 | 2 | 400 | 967 | 967 | 177% | 0 | 0 | 0 | 0 | 259 | 308 | 4399943 | 50000 | 4349943 | 4455060 | 4448788 | 0 | 0 | 0 | 4448788 | 4443671 | 102.2% | 1 | 52479 | 55117 | 115 | 144 | 0 | 246 | 22225 | 0 | 0 | 0 | 56531 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 83873 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2023-11-28 | QTR2 | 23/24 |  | 2023-07-24 | QTR1 | 23/24 | 208 | 4855272.24
[29 empty] | 0% | 1
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 1 | 2 | 2 | 400 | 967 | 967 | 0% | 0 | 0 | 0 | 0 | 259 | 308 | 4399943 | 50000 | 4349943 | 4455060 | 4448788 | 0 | 0 | 0 | 4448788 | 4443671 | 200% | 2 | 52479 | 55117 | 115 | 144 | 0 | 246 | 22225 | 0 | 0 | 0 | 56531 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 83873 | 0
| District 02 Totals |  |  |  |  | 28 | 39 | 36 | 6804 | 11769 | 11867 | 53.57% | 15 | -98 | 254 | 0 | 3408 | 1557 | 143462827 | 1753583 | 141709243 | 144678302 | 144988733 | -1225698 | 0 | -1225698 | 143763035 | 147915526 | 92.86% | 26 | 4455598 | 1215476 | 1942 | 956 | 498 | 695 | 658016 | 0 | 34 | 329 | 830364 | 72138 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 15896 | 0 | 0 | 2 | 102114 | 67137 | 0 | 0 | 0 | 0 | 180 | 209 | 20578 | 872 | 0 | 0 | 0 | 0 | 0 | 27 | 6050 | 6050 | 180 | 93 | 0 | 0 | 0 | 0 | -68877 | 0 | 906 | 1417 | 1564140 | 146196
| 03 | T3579 | 41413245201 | 2016-08-31 | QTR1 | 16/17 | 3 | 19 | 1090 | 1999 | 2171 | 139.2% | 0 | -172 | 172 | 0 | 798 | 111 | 42140000 | 150000 | 41990000 | 43136516 | 44789798 | -789688 | 0 | -789688 | 44000110 | 45150067 | 107.5% | 1 | 1313007 | 996516 | 442 | 212 | 4 | 40 | 380492 | 1569 | 0 | 27 | 349096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 8 | 165208 | 0 | 0 | 0 | 18045 | 18045 | 0 | 0 | 0 | 0 | 0 | 0 | 50586 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -159429 | 0 | 80 | 121 | 898999 | 114614 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2022-10-21 | QTR2 | 22/23 | 308 | 37004160.16
| 03 | T3598 | 43357725201 | 2021-12-08 | QTR2 | 21/22 | 2 | 0 | 210 | 314 | 314 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 1449372 | 9292 | 1440080 | 1449372 | 1245314 | 0 | 0 | 0 | 1245314 | 1245462 | 86.49% | 1 | 147 | 0 | 73 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-01-13 | QTR3 | 22/23 | 308 | 1387512.95
| 03 | T3604 | 43282815201 | 2019-02-27 | QTR3 | 18/19 | 2 | 4 | 925 | 1322 | 1301 | 103.1% | 1 | 21 | 0 | 0 | 397 | 0 | 10228411 | 103267 | 10125144 | 10251581 | 10265075 | 0 | 0 | 0 | 10265075 | 10328004 | 102% | 1 | 62929 | 23170 | 263 | 84 | 0 | 0 | 24478 | 0 | 0 | 0 | 5148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 120 | 68927 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2022-12-06 | QTR2 | 22/23 | 308 | 10230057.88
| 03 | T3664 | 43375115201 | 2021-06-09 | QTR4 | 20/21 | 4 | 1 | 185 | 509 | 508 | 217.8% | 0 | 1 | 0 | 0 | 275 | 49 | 2044978 | 50000 | 1994978 | 2045473 | 1900355 | 0 | 0 | 0 | 1900355 | 1888581 | 94.67% | 1 | -11773 | 495 | 40 | 65 | 0 | 0 | 0 | 0 | 80 | 49 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 49 | 495 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-03-03 | QTR3 | 22/23 | 313 | 2066195.42
| 03 | T3691 | 43717815201 | 2020-11-18 | QTR2 | 20/21 | 1 | 2 | 480 | 640 | 661 | 109% | 1 | -21 | 21 | 0 | 160 | 0 | 4269226 | 50000 | 4219226 | 4374816 | 4363593 | -30948 | 0 | -30948 | 4332645 | 4394715 | 104.2% | 1 | 138599 | 105591 | 98 | 40 | 8 | 0 | 95913 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 23399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 149628 | 0 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 |  | 2022-12-04 | QTR2 | 22/23 | 308 | 4154505.73
| 03 | T3703 | 43649925201 | 2019-09-25 | QTR1 | 19/20 | 3 | 0 | 150 | 292 | 262 | 100% | 1 | 30 | 0 | 0 | 112 | 30 | 2458081 | 51140 | 2406941 | 2458081 | 2572160 | 0 | 0 | 0 | 2572160 | 2554701 | 106.1% | 1 | -17459 | 0 | 100 | 12 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2020-10-02 | QTR2 | 20/21 | 314 | 2031385.77
| 03 | T3704 | 43938815201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 150 | 222 | 220 | 106% | 1 | 2 | 0 | 0 | 72 | 0 | 1462111 | 0 | 1462111 | 1462111 | 1360760 | 0 | 0 | 0 | 1360760 | 1370361 | 93.72% | 1 | 9601 | 0 | 49 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 |  | 2022-10-07 | QTR2 | 22/23 | 313 | 1750125.19
| 03 | T3728 | 21898425201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 420 | 706 | 706 | 112.6% | 1 | 0 | 0 | 0 | 286 | 0 | 5503848 | 53988 | 5449859 | 5503848 | 5615605 | 0 | 0 | 0 | 5615605 | 5632695 | 103.4% | 1 | 85241 | 0 | 181 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2023-10-30 | QTR2 | 23/24 |  | 2023-07-24 | QTR1 | 23/24 | 314 | 7823905.33
| 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 1 | 365 | 689 | 689 | 117.8% | 1 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6166449 | 6679471 | 0 | 0 | 0 | 6679471 | 7791843 | 128.1% | 0 | 1176465 | 0 | 170 | 89 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 21 | 67784 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29
| 03 | T3743 | 44173015201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 45 | 83 | 80 | 93.33% | 1 | 3 | 0 | 0 | 38 | 0 | 187229 | 12274 | 174955 | 187229 | 175598 | 0 | 0 | 0 | 175598 | 166353 | 95.08% | 1 | -9245 | 0 | 35 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2020-08-14 | QTR1 | 20/21 | 314 | 262871.46
| 03 | T3750 | 43811125201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 95 | 131 | 130 | 98.95% | 1 | 1 | 0 | 0 | 36 | 0 | 987732 | 41493 | 946239 | 927591 | 903555 | 0 | 0 | 0 | 903555 | 903555 | 95.49% | 1 | 0 | -60141 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-05-12 | QTR4 | 22/23 | 314 | 912225.16
| 03 | T3759 | 44014915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 11 | 454 | 705 | 664 | 114.8% | 1 | 41 | 0 | 0 | 187 | 64 | 6899119 | 54298 | 6844821 | 7276831 | 6961458 | 0 | 0 | 0 | 6961458 | 7377187 | 107.8% | 1 | 425549 | 377713 | 82 | 61 | 0 | 28 | 279407 | 0 | 4 | 36 | -2323 | 6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 64 | 278484 | 6394 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 |  | 2023-04-26 | QTR4 | 22/23 | 314 | 5086089.54
| 03 | T3784 | 43938515201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 100 | 119 | 100 | 81% | 1 | 19 | 0 | 0 | 19 | 0 | 830333 | 0 | 830333 | 830333 | 808692 | 0 | 0 | 0 | 808692 | 808692 | 97.39% | 1 | 0 | 0 | 10 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 |  | 2023-08-01 | QTR1 | 23/24 | 313 | 771890.7
| 03 | T3793 | 43467715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 3 | 230 | 481 | 480 | 106.1% | 1 | 1 | 0 | 0 | 236 | 15 | 6283852 | 73669 | 6210183 | 6727204 | 6844151 | 0 | 0 | 0 | 6844151 | 7176797 | 115.6% | 0 | 332646 | 443352 | 186 | 50 | 0 | 7 | 378034 | 0 | 0 | 8 | 133625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | -51237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 15 | 460422 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2023-06-28 | QTR4 | 22/23 | 308 | 7460138.28
| 03 | T3794 | 44364415201 | 2022-06-15 | QTR4 | 21/22 | 1 | 1 | 100 | 125 | 92 | 67% | 1 | 33 | 0 | 0 | 25 | 0 | 2537432 | 50000 | 2487432 | 2537432 | 2741257 | 0 | 0 | 0 | 2741257 | 2721406 | 109.4% | 1 | -19851 | 0 | 14 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-03-06 | QTR3 | 22/23 | 313 | 2975156.64
| 03 | T3800 | 44851815201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 140 | 252 | 239 | 141.4% | 0 | 13 | 0 | 0 | 90 | 22 | 3545980 | 0 | 3545980 | 3707781 | 3707779 | 0 | 0 | 0 | 3707779 | 3707779 | 104.6% | 1 | 0 | 161801 | 35 | 6 | 0 | 22 | 93590 | 0 | 49 | 0 | 68210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 22 | 161801 | 0 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-10-30 | QTR2 | 23/24 |  | 2023-08-28 | QTR1 | 23/24 | 308 | 3713438.76
| 03 | T3810 | 44365015201 | 2022-01-26 | QTR3 | 21/22 | 1 | 1 | 270 | 474 | 472 | 121.1% | 0 | 2 | 0 | 0 | 156 | 48 | 10527718 | 106380 | 10421339 | 10784785 | 11111656 | 0 | 0 | 0 | 11111656 | 11389685 | 109.3% | 1 | 278029 | 257067 | 87 | 58 | 5 | 0 | 0 | 0 | 0 | 48 | 274363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 48 | 274363 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 |  | 2023-08-02 | QTR1 | 23/24 | 313 | 10728439.32
| 03 | T3817 | 44387515201 | 2022-08-31 | QTR1 | 22/23 | 1 | 2 | 60 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 156 | 30 | 535084 | 0 | 535084 | 538384 | 583904 | 0 | 0 | 0 | 583904 | 580604 | 108.5% | 1 | 0 | 3300 | 165 | 21 | 0 | 0 | 0 | 0 | 0 | 30 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 30 | 3300 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-08-02 | QTR1 | 23/24 | 313 | 438194
| 03 | T3823 | 44565615201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 110 | 120 | 86 | 69.09% | 1 | 34 | 0 | 0 | 10 | 0 | 2199429 | 50000 | 2149429 | 2199429 | 2316440 | 0 | 0 | 0 | 2316440 | 2316440 | 107.8% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 |  | 2023-06-22 | QTR4 | 22/23 | 308 | 2955598
| 03 | T3825 | 44565715201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 89 | 101 | 67 | 61.8% | 1 | 34 | 0 | 0 | 12 | 0 | 1398733 | 50000 | 1348733 | 1398733 | 1268603 | 0 | 0 | 0 | 1268603 | 1268603 | 94.06% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-08-21 | QTR1 | 23/24 | 321 | 2259061
| 03 | T3828 | 44404415201 | 2022-02-23 | QTR3 | 21/22 | 1 | 0 | 90 | 183 | 168 | 114.4% | 1 | 15 | 0 | 0 | 93 | 0 | 1388656 | 50000 | 1338656 | 1388656 | 1401865 | 0 | 0 | 0 | 1401865 | 1401865 | 104.7% | 1 | 0 | 0 | 53 | 12 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F432094655 | H.G. CONSTRUCTION DEVELOPMENT & INVESTM | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2022-10-26 | QTR2 | 22/23 | 313 | 1545933
| 03 | T3830 | 43256615201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 180 | 290 | 288 | 98.89% | 1 | 2 | 0 | 0 | 110 | 0 | 3353932 | 50000 | 3303932 | 3353932 | 3387610 | 0 | 0 | 0 | 3387610 | 3371222 | 102% | 1 | -16388 | 0 | 67 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-07-16 | QTR1 | 23/24 | 308 | 3164048.08
| 03 | T3833 | 44560315201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 44 | 49 | 45 | 90.91% | 1 | 4 | 0 | 0 | 5 | 0 | 192351 | 8394 | 183958 | 192351 | 176477 | 0 | 0 | 0 | 176477 | 176477 | 95.93% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2022-12-22 | QTR2 | 22/23 | 308 | 173499.64
| 03 | T3836 | 43974415201 | 2022-10-05 | QTR2 | 22/23 | 1 | 0 | 169 | 238 | 238 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 4469056 | 50000 | 4419056 | 4469056 | 4076218 | 0 | 0 | 0 | 4076218 | 3952664 | 89.45% | 1 | -123554 | 0 | 30 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2023-08-21 | QTR1 | 23/24 | 314 | 6832323.6
| 03 | T9024 | 44199335223 | 2021-04-28 | QTR4 | 20/21 | 1 | 2 | 250 | 622 | 620 | 99.2% | 1 | 2 | 0 | 0 | 372 | 0 | 3198515 | 50000 | 3148515 | 3289097 | 3304055 | 0 | 0 | 0 | 3304055 | 3304055 | 104.9% | 1 | 39515 | 90582 | 322 | 50 | 90 | 0 | 6000 | 0 | 90 | 0 | 49780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 58960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 126040 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 |  | 2023-06-08 | QTR4 | 22/23 | 314 | 3552350.22
| 03 | T9027 | 44531315215 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 60 | 71 | 71 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 564819 | 36905 | 527914 | 564819 | 524793 | 0 | 0 | 0 | 524793 | 524793 | 99.41% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2022-05-13 | QTR4 | 21/22 | 306 | 932089.13
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 26 | 38 | 51 | 6461 | 10983 | 10918 | 84.62% | 22 | 65 | 193 | 0 | 4132 | 390 | 124822446 | 1234740 | 123587707 | 127221890 | 129086242 | -820636 | 0 | -820636 | 128265606 | 131504606 | 92.31% | 24 | 3663458 | 2399446 | 2547 | 989 | 159 | 97 | 1257914 | 1569 | 223 | 228 | 863788 | 6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 8 | 242336 | 0 | 0 | 0 | 77005 | 18045 | 0 | 0 | 0 | 0 | 221 | 141 | 98614 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 339 | 0 | 0 | 0 | 0 | 0 | -159429 | 0 | 1038 | 520 | 2475230 | 121008
| 03 | E3S70 | 43992635201 | 2021-05-13 | QTR4 | 20/21 | 2 | 1 | 395 | 597 | 597 | 112.9% | 1 | 0 | 0 | 0 | 202 | 0 | 8497804 | 70195 | 8427609 | 8518932 | 8878921 | 0 | 0 | 0 | 8878921 | 8997063 | 106.8% | 1 | 136935 | 21128 | 102 | 49 | 0 | 0 | 12464 | 0 | 30 | 0 | 28861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 41325 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 |  | 2023-03-30 | QTR3 | 22/23 | 321 | 7939245.14
| 03 | E3U04 | 21904225201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 65 | 65 | 45 | 69.23% | 1 | 20 | 0 | 0 | 0 | 0 | 278090 | 21110 | 256980 | 278090 | 249120 | 0 | 0 | 0 | 249120 | 249120 | 96.94% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2023-05-18 | QTR4 | 22/23 | 314 | 454253.61
| 03 | E3U32 | 42187425201 | 2022-01-13 | QTR3 | 21/22 | 1 | 0 | 45 | 55 | 52 | 93.33% | 1 | 3 | 0 | 0 | 10 | 0 | 109495 | 5918 | 103577 | 109495 | 105102 | 0 | 0 | 0 | 105102 | 105102 | 101.5% | 1 | 0 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2022-06-09 | QTR4 | 21/22 | 308 | 135676.68
| 03 | E3U47 | 44158915201 | 2021-11-10 | QTR2 | 21/22 | 2 | 3 | 285 | 527 | 526 | 102.8% | 1 | 1 | 0 | 0 | 242 | 0 | 6190992 | 53456 | 6137537 | 6194018 | 6101074 | -18750 | 0 | -18750 | 6082324 | 6229251 | 101.5% | 1 | 146927 | 3025 | 162 | 71 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 0 | 3025 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 |  | 2023-08-02 | QTR1 | 23/24 | 308 | 5430315.21
| 03 | E3U84 | 44365915201 | 2022-02-10 | QTR3 | 21/22 | 2 | 1 | 175 | 266 | 264 | 98.86% | 1 | 2 | 0 | 0 | 91 | 0 | 3254371 | 50000 | 3204371 | 3263484 | 3285954 | 0 | 0 | 0 | 3285954 | 3378196 | 105.4% | 1 | 92242 | 9113 | 66 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-02-18 | QTR3 | 22/23 | 308 | 3044605.63
| 03 | E3V33 | 44891315201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 75 | 80 | 53 | 64% | 1 | 27 | 0 | 0 | 5 | 0 | 223976 | 14236 | 209740 | 223976 | 187027 | 0 | 0 | 0 | 187027 | 187027 | 89.17% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-06-01 | QTR4 | 22/23 | 308 | 298951.28
| 03 | E3V90 | 44575815201 | 2023-01-12 | QTR3 | 22/23 | 1 | 1 | 70 | 78 | 77 | 98.57% | 1 | 1 | 0 | 0 | 8 | 0 | 1499653 | 50000 | 1449653 | 1499653 | 1534493 | 0 | 0 | 0 | 1534493 | 1534493 | 105.9% | 1 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-10-02 | QTR2 | 23/24 |  | 2023-06-27 | QTR4 | 22/23 | 308 | 1524311.21
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 7 | 10 | 6 | 1110 | 1668 | 1614 | 100% | 7 | 54 | 0 | 0 | 558 | 0 | 20054381 | 264915 | 19789467 | 20087648 | 20341691 | -18750 | 0 | -18750 | 20322941 | 20680252 | 100% | 7 | 376104 | 33266 | 341 | 157 | 0 | 0 | 12464 | 0 | 39 | 0 | 40991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 0 | 56480 | 0
| District 03 Totals |  |  |  |  | 33 | 48 | 57 | 7571 | 12651 | 12532 | 87.88% | 29 | 119 | 193 | 0 | 4690 | 390 | 144876827 | 1499655 | 143377174 | 147309538 | 149427933 | -839386 | 0 | -839386 | 148588547 | 152184858 | 93.94% | 31 | 4039562 | 2432712 | 2888 | 1146 | 159 | 97 | 1270378 | 1569 | 262 | 228 | 904779 | 6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 8 | 245361 | 0 | 0 | 0 | 77005 | 18045 | 0 | 0 | 0 | 0 | 344 | 141 | 98614 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | -159429 | 0 | 1221 | 520 | 2531710 | 121008
| 04 | T4552 | 43696215201 | 2020-05-20 | QTR4 | 19/20 | 2 | 14 | 642 | 1093 | 1084 | 116.7% | 1 | 9 | 0 | 0 | 445 | 6 | 26406739 | 150000 | 26256739 | 27530140 | 27615738 | 0 | 0 | 0 | 27615738 | 28097247 | 107% | 1 | 1507029 | 1123402 | 284 | 51 | 0 | 0 | 40935 | 0 | 110 | 0 | 428405 | 32084 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223929 | 0 | 0 | 0 | 320493 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 11175 | 0 | 0 | 0 | 308488 | 0 | 0 | 6 | 42593 | 42593 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 6 | 1272542 | 74677 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-09-08 | QTR1 | 23/24 | 412 | 27323787.5 | B10 | ACC - BONUS/INCENT/DISINCENT
| 04 | T4562 | 43177035201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 384 | 492 | 492 | 100% | 1 | 0 | 0 | 0 | 108 | 0 | 3588218 | 50000 | 3538218 | 3660295 | 3546957 | 0 | 0 | 0 | 3546957 | 3613971 | 102.1% | 1 | 67014 | 72077 | 71 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 91148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14596 | 0 | 0 | 0 | -11203 | 0 | 0 | 0 | 94541 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2023-03-31 | QTR3 | 22/23 | 412 | 3732217.16
| 04 | T4567 | 43839415201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 388 | 574 | 574 | 119.1% | 1 | 0 | 0 | 0 | 186 | 0 | 2505478 | 50000 | 2455478 | 2517687 | 2397524 | 0 | 0 | 0 | 2397524 | 2420702 | 98.58% | 1 | 167234 | 12209 | 70 | 42 | 0 | 0 | 10842 | 0 | 0 | 0 | 23398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6534 | 0 | 0 | 0 | 1247 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 8119 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 50141 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-10-03 | QTR2 | 23/24 |  | 2023-06-08 | QTR4 | 22/23 | 409 | 2223138.08
| 04 | T4571 | 43839515201 | 2021-01-27 | QTR3 | 20/21 | 2 | 5 | 575 | 701 | 701 | 100% | 1 | 0 | 0 | 0 | 126 | 0 | 2029422 | 50000 | 1979422 | 2048533 | 1920549 | 0 | 0 | 0 | 1920549 | 1968644 | 99.46% | 1 | 49459 | 19111 | 81 | 45 | 0 | 0 | 1911 | 0 | 0 | 0 | 3545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17675 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-06-16 | QTR4 | 22/23 | 409 | 2213111.22
| 04 | T4572 | 43838415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 454 | 621 | 611 | 97.8% | 1 | 10 | 0 | 0 | 167 | 0 | 2952231 | 50000 | 2902231 | 2953979 | 2876141 | 0 | 0 | 0 | 2876141 | 2874393 | 99.04% | 1 | 28318 | 1748 | 122 | 45 | 0 | 0 | 7776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 9524 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-07-24 | QTR1 | 23/24 | 409 | 3045126.89
| 04 | T4573 | 43206675201 | 2021-07-28 | QTR1 | 21/22 | 2 | 3 | 195 | 470 | 465 | 97.44% | 1 | 5 | 0 | 0 | 275 | 0 | 3496673 | 50000 | 3446673 | 3721036 | 3515537 | 0 | 0 | 0 | 3515537 | 3603841 | 104.6% | 1 | 88304 | 224363 | 249 | 26 | 0 | 0 | -2094 | 0 | 0 | 0 | 267470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 265376 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 |  | 2023-04-19 | QTR4 | 22/23 | 412 | 3657623.88
| 04 | T4594 | 43999015201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 212 | 352 | 351 | 113.7% | 1 | 1 | 0 | 0 | 140 | 0 | 2000000 | 50000 | 1950000 | 2008938 | 1868868 | 0 | 0 | 0 | 1868868 | 1862040 | 95.49% | 1 | 2110 | 8938 | 85 | 25 | 0 | 0 | 11450 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 20388 | 0 | F650814419 | ZAHLENE ENTERPRISES INC. | N/A | N/A | N/A | N/A | 2023-07-24 | QTR1 | 23/24 |  | 2023-05-31 | QTR4 | 22/23 | 412 | 2421037.86
| 04 | T4597 | 44177515201 | 2022-01-26 | QTR3 | 21/22 | 2 | 1 | 178 | 274 | 274 | 100% | 1 | 0 | 0 | 0 | 96 | 0 | 957661 | 40792 | 916869 | 958736 | 900445 | 0 | 0 | 0 | 900445 | 899370 | 98.09% | 1 | 0 | 1075 | 72 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 8111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 9186 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-05-11 | QTR4 | 22/23 | 409 | 927528.71
| 04 | T4603 | 44157815201 | 2022-03-30 | QTR3 | 21/22 | 3 | 0 | 229 | 338 | 338 | 100% | 1 | 0 | 0 | 0 | 109 | 0 | 2249738 | 50000 | 2199738 | 2249738 | 2253443 | 0 | 0 | 0 | 2253443 | 2251225 | 102.3% | 1 | -2218 | 0 | 87 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-09 | QTR2 | 23/24 |  | 2023-08-09 | QTR1 | 23/24 | 412 | 2503871.57
| 04 | T4607 | 43999315201 | 2022-03-30 | QTR3 | 21/22 | 3 | 1 | 222 | 287 | 287 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 1967721 | 50000 | 1917721 | 1967721 | 1856962 | 0 | 0 | 0 | 1856962 | 1856374 | 96.8% | 1 | 2046 | 2634 | 47 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-09-18 | QTR1 | 23/24 |  | 2023-04-30 | QTR4 | 22/23 | 412 | 2135578.09
| 04 | T4614 | 44399415201 | 2022-04-27 | QTR4 | 21/22 | 2 | 3 | 227 | 321 | 321 | 104.8% | 1 | 0 | 0 | 0 | 94 | 0 | 4491996 | 50000 | 4441996 | 4563991 | 4393362 | 0 | 0 | 0 | 4393362 | 4376466 | 98.52% | 1 | -6110 | 71995 | 57 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 86648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51997 | 0 | 0 | 0 | 5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10786 | 0 | 0 | 0 | 33274 | 33274 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 83947 | 33274 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-06-14 | QTR4 | 22/23 | 409 | 4062646.65
| 04 | T4629 | 44562315201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 122 | 125 | 107 | 83.61% | 1 | 18 | 0 | 0 | 5 | 0 | 1050673 | 49045 | 1001629 | 1050673 | 985015 | 0 | 0 | 0 | 985015 | 985015 | 98.34% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-06 | QTR2 | 23/24 |  | 2023-10-30 | QTR2 | 23/24 | 409 | 1029940.35
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 12 | 25 | 33 | 3828 | 5648 | 5605 | 100% | 12 | 43 | 0 | 0 | 1816 | 6 | 53696550 | 689837 | 53006714 | 55231467 | 54130541 | 0 | 0 | 0 | 54130541 | 54809288 | 100% | 12 | 1903186 | 1537552 | 1226 | 365 | 0 | 0 | 70820 | 0 | 140 | 0 | 915565 | 32084 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178466 | 0 | 0 | 0 | 334897 | 0 | 0 | 0 | 0 | 0 | 451 | 0 | 53064 | 0 | 0 | 0 | 341762 | 33274 | 74 | 6 | 43588 | 42593 | 34 | 0 | 14596 | 0 | 0 | 0 | -11203 | 0 | 699 | 6 | 1838080 | 107951
| 04 | E4T68 | 44074615201 | 2020-05-06 | QTR4 | 19/20 | 6 | 1 | 730 | 939 | 934 | 99.32% | 1 | 5 | 0 | 0 | 209 | 0 | 17557323 | 125751 | 17431572 | 17588765 | 16726429 | 0 | 0 | 0 | 16726429 | 16980455 | 97.41% | 1 | 254025 | 31442 | 144 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31442 | 0 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37742 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-02-02 | QTR3 | 22/23 | 412 | 12972092.8
| 04 | E4U99 | 44146215201 | 2021-05-07 | QTR4 | 20/21 | 1 | 8 | 228 | 525 | 518 | 144.7% | 0 | 7 | 0 | 0 | 188 | 109 | 12200214 | 101674 | 12098540 | 13805766 | 14066534 | 0 | 0 | 0 | 14066534 | 14068003 | 116.3% | 0 | 140138 | 1605552 | 165 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 1129185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 448054 | 0 | 0 | 0 | 23731 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 109 | 1600970 | 0 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-06-23 | QTR4 | 22/23 | 412 | 10374505.8 | B10 | ACC - BONUS/INCENT/DISINCENT
| 04 | E4V19 | 43215215201 | 2022-01-07 | QTR3 | 21/22 | 1 | 0 | 307 | 326 | 171 | 49.51% | 1 | 155 | 0 | 0 | 19 | 0 | 2335539 | 50000 | 2285539 | 2335539 | 2159702 | 0 | 0 | 0 | 2159702 | 2159702 | 94.49% | 1 | 0 | 0 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-11-20 | QTR2 | 23/24 |  | 2023-10-25 | QTR2 | 23/24 | 409 | 4011283.36 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4V55 | 44359415201 | 2022-05-06 | QTR4 | 21/22 | 1 | 1 | 127 | 224 | 221 | 113.4% | 1 | 3 | 0 | 0 | 97 | 0 | 895596 | 50000 | 845596 | 965406 | 917671 | 0 | 0 | 0 | 917671 | 917671 | 108.5% | 1 | 0 | 69810 | 62 | 15 | 0 | 0 | 69810 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 69810 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 |  | 2023-07-15 | QTR1 | 23/24 | 412 | 1122910.5
| 04 | E4V75 | 44172215201 | 2022-02-04 | QTR3 | 21/22 | 2 | 4 | 156 | 248 | 248 | 104.5% | 1 | 0 | 0 | 0 | 92 | 0 | 1455255 | 50000 | 1405255 | 1515282 | 1451281 | 0 | 0 | 0 | 1451281 | 1452112 | 103.3% | 1 | 7917 | 60027 | 72 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 76040 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 85192 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-09-01 | QTR1 | 23/24 |  | 2023-03-28 | QTR3 | 22/23 | 409 | 1403378.89
| 04 | E4V84 | 44609715201 | 2022-09-02 | QTR1 | 22/23 | 1 | 1 | 133 | 180 | 179 | 99.25% | 1 | 1 | 0 | 0 | 47 | 0 | 3147147 | 50000 | 3097147 | 3153188 | 2965886 | 0 | 0 | 0 | 2965886 | 2896248 | 93.51% | 1 | -69638 | 6041 | 43 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-08-03 | QTR1 | 23/24 | 409 | 3652108.96 | B1 | ACC - NO EXCUSE BONUS
| 04 | E4W04 | 45059015201 | 2022-06-14 | QTR4 | 21/22 | 1 | 0 | 182 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 1468626 | 50000 | 1418626 | 1468626 | 1421948 | 0 | 0 | 0 | 1421948 | 1421948 | 100.2% | 1 | 0 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2023-11-20 | QTR2 | 23/24 |  | 2023-10-25 | QTR2 | 23/24 | 408 | 2551166.8
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 7 | 13 | 15 | 1863 | 2651 | 2480 | 85.71% | 6 | 171 | 0 | 0 | 679 | 109 | 39059700 | 477425 | 38582275 | 40832572 | 39709451 | 0 | 0 | 0 | 39709451 | 39896139 | 85.71% | 6 | 332442 | 1772872 | 515 | 137 | 0 | 0 | 69810 | 0 | 20 | 0 | 1137292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 479496 | 0 | 7 | 0 | 106071 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 109 | 1799755 | 0
| District 04 Totals |  |  |  |  | 19 | 38 | 48 | 5691 | 8299 | 8085 | 94.74% | 18 | 214 | 0 | 0 | 2495 | 115 | 92756250 | 1167262 | 91588989 | 96064039 | 93839992 | 0 | 0 | 0 | 93839992 | 94705427 | 94.74% | 18 | 2235628 | 3310424 | 1741 | 502 | 0 | 0 | 140630 | 0 | 160 | 0 | 2052857 | 32084 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 657962 | 0 | 7 | 0 | 440968 | 0 | 0 | 0 | 0 | 0 | 509 | 0 | 60151 | 0 | 0 | 0 | 341762 | 33274 | 74 | 6 | 43588 | 42593 | 34 | 0 | 14596 | 0 | 0 | 0 | -11203 | 0 | 784 | 115 | 3637835 | 107951
| 05 | T5552 | 40714345201 | 2016-06-08 | QTR4 | 15/16 | 21 | 32 | 1050 | 1826 | 1829 | 140% | 0 | -3 | 3 | 0 | 359 | 417 | 75824482 | 160000 | 75664482 | 86884143 | 89837352 | 0 | 0 | 0 | 89837352 | 90458012 | 119.6% | 0 | 815723 | 10910761 | 209 | 150 | 0 | 13 | 563442 | 81716 | 0 | 113 | 3719605 | 1534190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | -46035 | 0 | 0 | 0 | 107943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189623 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 417 | 10835624 | 1823881 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2021-10-13 | QTR2 | 21/22 | 509 | 88197361.71 | B2:B2:B5:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B/BONUS
| 05 | T5733 | 44381515201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 290 | 440 | 439 | 106.6% | 1 | 1 | 0 | 0 | 130 | 20 | 7387943 | 81000 | 7306943 | 7578305 | 6929112 | 0 | 0 | 0 | 6929112 | 7638830 | 104.5% | 1 | 716998 | 190361 | 50 | 80 | 0 | 20 | 183081 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 190361 | 436 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2023-04-17 | QTR4 | 22/23 | 513 | 8754090.28
| 05 | T5737 | 44288115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 140 | 343 | 342 | 99.29% | 1 | 1 | 0 | 0 | 203 | 0 | 1605048 | 49058 | 1555990 | 1606653 | 1573163 | 0 | 0 | 0 | 1573163 | 1576898 | 101.3% | 1 | 3735 | 1605 | 66 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-11-30 | QTR2 | 23/24 |  | 2023-07-21 | QTR1 | 23/24 | 514 | 1288583.85
| 05 | T5738 | 44290915201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 270 | 349 | 349 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 9861239 | 100000 | 9761239 | 9880239 | 9803603 | 0 | 0 | 0 | 9803603 | 10869062 | 111.3% | 0 | 1065459 | 19000 | 40 | 39 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24350 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-02-28 | QTR3 | 22/23 | 514 | 13653415.96
| 05 | T5763 | 44569015201 | 2022-08-31 | QTR1 | 22/23 | 2 | 1 | 139 | 176 | 176 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 1690095 | 50000 | 1640095 | 1690972 | 1630216 | 0 | 0 | 0 | 1630216 | 1601935 | 97.67% | 1 | -27404 | 877 | 28 | 9 | 0 | 0 | 20792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21668 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 |  | 2023-09-11 | QTR1 | 23/24 | 513 | 2378838.75
| 05 | T5765 | 43759625201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 190 | 217 | 198 | 90% | 1 | 19 | 0 | 0 | 27 | 0 | 1068776 | 38700 | 1030076 | 1068776 | 1003835 | 0 | 0 | 0 | 1003835 | 1003807 | 97.45% | 1 | -28 | 0 | 19 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263013168 | MEJIA INTERNATIONAL GROUP CORPORATION | N/A | N/A | N/A | N/A | 2023-10-13 | QTR2 | 23/24 |  | 2023-08-29 | QTR1 | 23/24 | 512 | 1065459.45
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 6 | 29 | 38 | 2079 | 3351 | 3333 | 83.33% | 5 | 18 | 3 | 0 | 835 | 437 | 97437583 | 478758 | 96958825 | 108709088 | 110777281 | 0 | 0 | 0 | 110777281 | 113148544 | 66.67% | 4 | 2574483 | 11122604 | 412 | 423 | 0 | 33 | 772665 | 82152 | 0 | 113 | 3721210 | 1534190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | -46035 | 0 | 0 | 0 | 126943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197780 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 437 | 11073608 | 1824317
| 05 | E50B4 | 44290615201 | 2022-07-06 | QTR1 | 22/23 | 1 | 1 | 200 | 317 | 317 | 107% | 1 | 0 | 0 | 0 | 103 | 14 | 3079406 | 50000 | 3029406 | 3129406 | 3205711 | 0 | 0 | 0 | 3205711 | 3130395 | 103.3% | 1 | -75316 | 50000 | 26 | 77 | 0 | 0 | 3862 | 0 | 0 | 28 | 3528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 54904 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 |  | 2023-08-11 | QTR1 | 23/24 | 513 | 3825881.85
| 05 | E51A9 | 44102015201 | 2020-09-01 | QTR1 | 20/21 | 1 | 7 | 280 | 534 | 544 | 113.9% | 1 | -10 | 10 | 0 | 225 | 29 | 7501367 | 72000 | 7429367 | 7798794 | 7531686 | -41316 | 0 | -41316 | 7490370 | 7740983 | 104.2% | 1 | 263750 | 297427 | 61 | 164 | 0 | 0 | 19197 | 0 | 0 | 29 | 278231 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 297427 | 5549 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2022-05-27 | QTR4 | 21/22 | 514 | 7321146.81
| 05 | E53B6 | 43901715201 | 2022-09-07 | QTR1 | 22/23 | 1 | 0 | 220 | 261 | 166 | 56.82% | 1 | 95 | 0 | 0 | 41 | 0 | 1640053 | 50000 | 1590053 | 1640053 | 1539808 | 0 | 0 | 0 | 1539808 | 1539808 | 96.84% | 1 | 0 | 0 | 32 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-11-01 | QTR2 | 23/24 |  | 2023-09-15 | QTR1 | 23/24 | 514 | 2062514.65
| 05 | E55B3 | 44942415201 | 2022-12-06 | QTR2 | 22/23 | 1 | 0 | 150 | 187 | 187 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 950694 | 34728 | 915966 | 950694 | 969481 | 0 | 0 | 0 | 969481 | 969481 | 105.8% | 1 | 0 | 0 | 28 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 |  | 2023-09-14 | QTR1 | 23/24 | 509 | 729303.27
| 05 | E55B4 | 44942515201 | 2022-11-01 | QTR2 | 22/23 | 1 | 0 | 170 | 174 | 149 | 85.29% | 1 | 25 | 0 | 0 | 4 | 0 | 967737 | 42032 | 925705 | 967737 | 851103 | 0 | 0 | 0 | 851103 | 851002 | 91.93% | 1 | -101 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-09-06 | QTR1 | 23/24 |  | 2023-07-10 | QTR1 | 23/24 | 514 | 882686.9
| 05 | E57A1 | 44343315201 | 2021-11-02 | QTR2 | 21/22 | 3 | 1 | 350 | 515 | 515 | 108% | 1 | 0 | 0 | 0 | 137 | 28 | 5312936 | 52636 | 5260300 | 5361981 | 5275495 | 0 | 0 | 0 | 5275495 | 5333592 | 101.4% | 1 | 107142 | 49045 | 81 | 56 | 0 | 0 | 2577 | 0 | 0 | 28 | 12635 | 2522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 81860 | 2522 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-12-22 | QTR2 | 23/24 |  | 2023-08-11 | QTR1 | 23/24 | 513 | 6332507.08
| 05 | E57A4 | 44113215201 | 2021-10-05 | QTR2 | 21/22 | 5 | 2 | 289 | 528 | 527 | 99.65% | 1 | 1 | 0 | 0 | 239 | 0 | 7424369 | 84545 | 7339824 | 7591181 | 7558842 | 0 | 0 | 0 | 7558842 | 7794728 | 106.2% | 1 | 394527 | 166812 | 75 | 164 | 0 | 0 | 15614 | 0 | 0 | 0 | 22253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222204 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-07-12 | QTR1 | 23/24 | 513 | 9276735.05
| 05 | E59A9 | 43913015201 | 2022-01-04 | QTR3 | 21/22 | 1 | 0 | 140 | 248 | 246 | 116.4% | 1 | 2 | 0 | 0 | 83 | 25 | 679529 | 24250 | 655279 | 679529 | 677096 | 0 | 0 | 0 | 677096 | 677187 | 103.3% | 1 | 92 | 0 | 49 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1848 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-06-08 | QTR4 | 22/23 | 514 | 681570.8
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 8 | 14 | 11 | 1799 | 2764 | 2651 | 100% | 8 | 113 | 10 | 0 | 869 | 96 | 27556091 | 410191 | 27145900 | 28119375 | 27609222 | -41316 | 0 | -41316 | 27567906 | 28037176 | 100% | 8 | 690094 | 563284 | 352 | 517 | 0 | 0 | 41250 | 0 | 0 | 85 | 318700 | 8071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 83327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 668565 | 8071
| District 05 Totals |  |  |  |  | 14 | 43 | 49 | 3878 | 6115 | 5984 | 92.86% | 13 | 131 | 13 | 0 | 1704 | 533 | 124993674 | 888949 | 124104725 | 136828463 | 138386503 | -41316 | 0 | -41316 | 138345187 | 141185720 | 85.71% | 12 | 3264577 | 11685888 | 764 | 940 | 0 | 33 | 813915 | 82152 | 0 | 198 | 4039910 | 1542261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 37292 | 0 | 0 | 0 | 126943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423070 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 547 | 11742173 | 1832388
| 06 | T6496 | 44182715201 | 2021-03-31 | QTR3 | 20/21 | 5 | 5 | 218 | 318 | 318 | 119.7% | 1 | 0 | 0 | 0 | 100 | 0 | 5245136 | 63284 | 5181852 | 5346913 | 5060388 | 0 | 0 | 0 | 5060388 | 5419442 | 104.6% | 1 | 359054 | 101776 | 49 | 8 | 0 | 0 | 49966 | 0 | 43 | 0 | -13886 | 12524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 40024 | 12524 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-12-20 | QTR2 | 23/24 |  | 2022-11-23 | QTR2 | 22/23 | 636 | 5969736.88 | B2:B2:B5:B5 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6505 | 43326435201 | 2020-08-26 | QTR1 | 20/21 | 4 | 2 | 350 | 382 | 376 | 98.29% | 1 | 6 | 0 | 0 | 32 | 0 | 4604161 | 51560 | 4552601 | 4652806 | 4445340 | -1 | 400000 | 399999 | 4845339 | 4484965 | 98.51% | 1 | -360374 | 48646 | 14 | 18 | 0 | 0 | 8472 | 0 | 0 | 0 | 7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25475 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-10-27 | QTR2 | 23/24 |  | 2022-02-11 | QTR3 | 21/22 | 636 | 4947288.63 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6513 | 43998615201 | 2022-03-30 | QTR3 | 21/22 | 3 | 2 | 240 | 265 | 220 | 81.25% | 1 | 45 | 0 | 0 | 25 | 0 | 2569128 | 50000 | 2519128 | 2717271 | 2543862 | 0 | 120000 | 120000 | 2663862 | 2540376 | 100.8% | 1 | -123486 | 148143 | 5 | 20 | 0 | 0 | 25836 | 0 | 0 | 0 | 105162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130998 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-06-14 | QTR4 | 22/23 | 636 | 2452591.81 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6515 | 43274845201 | 2022-03-30 | QTR3 | 21/22 | 3 | 2 | 240 | 257 | 221 | 85% | 1 | 36 | 0 | 0 | 17 | 0 | 2455465 | 50000 | 2405465 | 2510141 | 2443596 | 0 | 72000 | 72000 | 2515596 | 2440177 | 101.4% | 1 | -75419 | 54676 | 4 | 13 | 0 | 0 | 16029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68583 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-15 | QTR2 | 23/24 |  | 2023-07-14 | QTR1 | 23/24 | 636 | 2281095.15 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6516 | 43998115201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 360 | 474 | 464 | 97.22% | 1 | 10 | 0 | 0 | 114 | 0 | 4166383 | 50000 | 4116383 | 4219775 | 4110877 | 0 | 0 | 0 | 4110877 | 4270005 | 103.7% | 1 | 159128 | 53392 | 87 | 27 | 0 | 0 | 31602 | 0 | 0 | 0 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77149 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-15 | QTR2 | 23/24 |  | 2023-06-30 | QTR4 | 22/23 | 613 | 4661947.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6518 | 42918635201 | 2021-12-08 | QTR2 | 21/22 | 5 | 2 | 300 | 332 | 272 | 80% | 1 | 60 | 0 | 0 | 32 | 0 | 2919079 | 50000 | 2869079 | 2940250 | 2881342 | 0 | 210000 | 210000 | 3091342 | 2942048 | 102.5% | 1 | -146480 | 21171 | 17 | 15 | 0 | 0 | 16786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19600 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2023-04-22 | QTR4 | 22/23 | 613 | 3061117.05 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6519 | 43476835201 | 2022-01-26 | QTR3 | 21/22 | 3 | 1 | 300 | 347 | 274 | 75.67% | 1 | 73 | 0 | 0 | 47 | 0 | 3487287 | 50000 | 3437287 | 3497187 | 3509376 | 0 | 180000 | 180000 | 3689376 | 3539751 | 103% | 1 | -149625 | 9900 | 25 | 22 | 0 | 0 | 30134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47968 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2023-09-13 | QTR1 | 23/24 |  | 2023-07-05 | QTR1 | 23/24 | 613 | 3568827.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 7 | 26 | 17 | 2008 | 2375 | 2145 | 100% | 7 | 230 | 0 | 0 | 367 | 0 | 25446639 | 364844 | 25081795 | 25884343 | 24994781 | -1 | 982000 | 981999 | 25976780 | 25636764 | 100% | 7 | -337202 | 437704 | 201 | 123 | 0 | 0 | 178825 | 0 | 43 | 0 | 99599 | 12524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 409797 | 12524
| 06 | E6N08 | 44196015201 | 2022-01-27 | QTR3 | 21/22 | 2 | 5 | 450 | 483 | 372 | 75.33% | 1 | 111 | 0 | 0 | 33 | 0 | 2813265 | 50000 | 2763265 | 2921577 | 2938675 | 0 | 0 | 0 | 2938675 | 2927754 | 106% | 1 | 65 | 108312 | 12 | 21 | 0 | 0 | 47426 | 0 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58312 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2023-10-17 | QTR2 | 23/24 |  | 2023-08-21 | QTR1 | 23/24 | 613 | 3044682.74
| 06 | E6N09 | 44480525201 | 2022-07-28 | QTR1 | 22/23 | 1 | 0 | 240 | 260 | 172 | 63.33% | 1 | 88 | 0 | 0 | 20 | 0 | 797552 | 50000 | 747552 | 797552 | 706126 | 0 | 0 | 0 | 706126 | 706126 | 94.46% | 1 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-08-11 | QTR1 | 23/24 |  | 2023-06-29 | QTR4 | 22/23 | 613 | 1509363.9
| 06 | E6N47 | 44445015201 | 2022-05-26 | QTR4 | 21/22 | 1 | 2 | 250 | 272 | 220 | 79.2% | 1 | 52 | 0 | 0 | 22 | 0 | 2697327 | 50000 | 2647327 | 2771657 | 2731695 | 0 | 180000 | 180000 | 2911695 | 2718704 | 102.7% | 1 | -192991 | 74329 | 14 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 41276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89415 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 |  | 2023-05-24 | QTR4 | 22/23 | 636 | 2883318.39 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6N55 | 44196815201 | 2021-08-26 | QTR1 | 21/22 | 1 | 0 | 280 | 460 | 459 | 119.3% | 1 | 1 | 0 | 0 | 180 | 0 | 757063 | 47154 | 709909 | 757063 | 654819 | 0 | 0 | 0 | 654819 | 654819 | 92.24% | 1 | 0 | 0 | 101 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2023-04-06 | QTR4 | 22/23 | 636 | 1042435.8
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 4 | 5 | 7 | 1220 | 1475 | 1223 | 100% | 4 | 252 | 0 | 0 | 255 | 0 | 7065207 | 197154 | 6868053 | 7247849 | 7031315 | 0 | 180000 | 180000 | 7211315 | 7007403 | 100% | 4 | -192926 | 182641 | 147 | 53 | 0 | 0 | 47426 | 0 | 0 | 0 | 41176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48138 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 147727 | 0
| District 06 Totals |  |  |  |  | 11 | 31 | 24 | 3228 | 3850 | 3368 | 100% | 11 | 482 | 0 | 0 | 622 | 0 | 32511846 | 561998 | 31949848 | 33132192 | 32026096 | -1 | 1162000 | 1161999 | 33188095 | 32644167 | 100% | 11 | -530128 | 620345 | 348 | 176 | 0 | 0 | 226251 | 0 | 43 | 0 | 140775 | 12524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176699 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 557524 | 12524
| 07 | T7424 | 25729855201 | 2019-03-27 | QTR3 | 18/19 | 3 | 4 | 860 | 964 | 931 | 96.16% | 1 | 33 | 0 | 0 | 104 | 0 | 20155312 | 406894 | 19748419 | 20804212 | 20013184 | 0 | 0 | 0 | 20013184 | 19790050 | 100.2% | 1 | -223135 | 648900 | 54 | 50 | 0 | 0 | 350213 | 0 | 0 | 0 | 262060 | 6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637979 | 6325 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-11-03 | QTR2 | 23/24 |  | 2022-04-12 | QTR4 | 21/22 | 798 | 29301814.47
| 07 | T7428 | 43258435201 | 2019-02-27 | QTR3 | 18/19 | 3 | 6 | 445 | 671 | 685 | 128.3% | 0 | -14 | 14 | 0 | 114 | 112 | 9277781 | 90000 | 9187781 | 9481539 | 10184938 | -48258 | 300000 | 251742 | 10436680 | 10081240 | 109.7% | 1 | -350246 | 203759 | 58 | 56 | 0 | 21 | 283799 | 0 | 0 | 0 | 16679 | 10786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -96529 | 0 | 0 | 0 | 12534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 216484 | 10786 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2021-06-25 | QTR4 | 20/21 | 796 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | T7451 | 43982985201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 170 | 178 | 550 | 318.8% | 0 | -372 | 372 | 0 | 8 | 0 | 698558 | 34000 | 664558 | 698558 | 557380 | -158860 | 0 | -158860 | 398520 | 531562 | 79.99% | 1 | 133042 | 0 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2022-07-07 | QTR1 | 22/23 | 799 | 691075.3
| 07 | T7468 | 44138615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 3 | 498 | 556 | 514 | 87.75% | 1 | 42 | 0 | 0 | 77 | -19 | 9161461 | 85000 | 9076461 | 9416662 | 9386983 | 0 | 0 | 0 | 9386983 | 9736387 | 107.3% | 1 | 388067 | 255200 | 53 | 24 | 0 | 0 | 337633 | 0 | 0 | 0 | 90042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 0 | -19 | 324328 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-13 | QTR1 | 23/24 |  | 2022-12-02 | QTR2 | 22/23 | 798 | 9040000
| 07 | T7480 | 44025315201 | 2021-12-08 | QTR2 | 21/22 | 1 | 2 | 230 | 353 | 352 | 105.7% | 1 | 1 | 0 | 0 | 109 | 14 | 8381553 | 92000 | 8289553 | 8507750 | 8880433 | 0 | 0 | 0 | 8880433 | 9224126 | 111.3% | 0 | 351217 | 126197 | 83 | 26 | 0 | 0 | 0 | 0 | 0 | 14 | 124206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7524 | 7524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 131729 | 7524 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 |  | 2023-07-21 | QTR1 | 23/24 | 796 | 9618300
| 07 | T7491 | 44358325201 | 2022-02-23 | QTR3 | 21/22 | 1 | 0 | 150 | 193 | 193 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 1439445 | 44000 | 1395445 | 1439445 | 1363648 | 0 | 0 | 0 | 1363648 | 1363533 | 97.71% | 1 | -115 | 0 | 34 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-12-06 | QTR2 | 23/24 |  | 2023-09-14 | QTR1 | 23/24 | 796 | 1085600
| 07 | T7498 | 44332015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 0 | 120 | 127 | 127 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 1340863 | 50000 | 1290863 | 1340863 | 1268582 | 0 | -12000 | -12000 | 1256582 | 1256582 | 97.34% | 1 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 |  | 2023-05-22 | QTR4 | 22/23 | 796 | 2027300
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 7 | 11 | 16 | 2473 | 3042 | 3352 | 71.43% | 5 | -310 | 386 | 0 | 462 | 107 | 50454973 | 801894 | 49653080 | 51689029 | 51655148 | -207118 | 288000 | 80882 | 51736030 | 51983480 | 85.71% | 6 | 298830 | 1234056 | 289 | 173 | 0 | 21 | 971645 | 0 | 0 | 14 | 492987 | 17111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -83887 | 0 | 0 | 0 | 14653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33230 | 7524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 0 | 107 | 1323162 | 24635
| 07 | E7N90 | 44822115201 | 2022-01-12 | QTR3 | 21/22 | 1 | 1 | 120 | 172 | 172 | 117.5% | 1 | 0 | 0 | 0 | 52 | 0 | 679686 | 28000 | 651686 | 695950 | 640611 | 0 | 0 | 0 | 640611 | 640611 | 98.3% | 1 | 0 | 16264 | 8 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-04-20 | QTR4 | 22/23 | 799 | 644500
| 07 | E7N95 | 44025115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 3 | 240 | 317 | 314 | 98.75% | 1 | 3 | 0 | 0 | 77 | 0 | 6430299 | 84000 | 6346299 | 6566839 | 6774752 | 0 | 0 | 0 | 6774752 | 7323867 | 115.4% | 0 | 551655 | 136540 | 52 | 25 | 0 | 0 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33706 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 2540 | 2540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120246 | 36246 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 |  | 2023-02-24 | QTR3 | 22/23 | 796 | 8690700
| 07 | E7O04 | 43952615201 | 2021-09-08 | QTR1 | 21/22 | 1 | 2 | 210 | 235 | 235 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 1944266 | 50000 | 1894266 | 2045152 | 1898792 | 0 | 0 | 0 | 1898792 | 1886359 | 99.58% | 1 | 0 | 100885 | 10 | 15 | 0 | 0 | 17204 | 0 | 0 | 0 | 71248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12433 | 12433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100885 | 12433 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2022-12-09 | QTR2 | 22/23 | 799 | 1797400
| 07 | E7O11 | 44166515201 | 2022-02-09 | QTR3 | 21/22 | 2 | 0 | 180 | 220 | 220 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 3049631 | 50000 | 2999631 | 3049631 | 3013462 | 0 | 0 | 0 | 3013462 | 3013181 | 100.5% | 1 | -281 | 0 | 21 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-06-14 | QTR4 | 22/23 | 798 | 2409700
| 07 | E7P30 | 44761415201 | 2022-04-13 | QTR4 | 21/22 | 1 | 1 | 140 | 171 | 171 | 100% | 1 | 0 | 0 | 0 | 31 | 0 | 2231499 | 50000 | 2181499 | 2259063 | 2052581 | 0 | 0 | 0 | 2052581 | 2046856 | 93.83% | 1 | -5724 | 27565 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 27565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27565 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2023-12-08 | QTR2 | 23/24 |  | 2023-09-13 | QTR1 | 23/24 | 714 | 1792600
| 07 | E7P36 | 44978015201 | 2022-06-08 | QTR4 | 21/22 | 3 | 3 | 300 | 361 | 338 | 92.33% | 1 | 23 | 0 | 0 | 61 | 0 | 4664000 | 50000 | 4614000 | 4709230 | 4734993 | 0 | 0 | 0 | 4734993 | 4662735 | 101.1% | 1 | -72258 | 45230 | 37 | 24 | 0 | 0 | 25230 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45230 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-10-26 | QTR2 | 23/24 |  | 2023-08-01 | QTR1 | 23/24 | 799 | 5588200 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 07 | E7P61 | 44383615201 | 2023-01-11 | QTR3 | 22/23 | 1 | 1 | 140 | 165 | 161 | 107.9% | 1 | 4 | 0 | 0 | 10 | 15 | 506794 | 19000 | 487794 | 527638 | 475289 | 0 | 0 | 0 | 475289 | 475289 | 97.44% | 1 | 0 | 20844 | 1 | 9 | 0 | 0 | 20844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20844 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-11-17 | QTR2 | 23/24 |  | 2023-10-16 | QTR2 | 23/24 | 799 | 441600
| 07 | E7P63 | 44774815201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 120 | 130 | 71 | 50.83% | 1 | 59 | 0 | 0 | 10 | 0 | 619151 | 50000 | 569151 | 619151 | 571177 | 0 | 0 | 0 | 571177 | 571177 | 100.4% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-10-12 | QTR2 | 23/24 |  | 2023-07-24 | QTR1 | 23/24 | 799 | 1320700
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 8 | 11 | 11 | 1450 | 1771 | 1682 | 100% | 8 | 89 | 0 | 0 | 306 | 15 | 20125326 | 381000 | 19744326 | 20472654 | 20161657 | 0 | 0 | 0 | 20161657 | 20620075 | 87.5% | 7 | 473392 | 347328 | 158 | 127 | 0 | 0 | 147278 | 0 | 0 | 0 | 135077 | 16264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33706 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 14973 | 14973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331034 | 64943
| District 07 Totals |  |  |  |  | 15 | 22 | 27 | 3923 | 4813 | 5034 | 86.67% | 13 | -221 | 386 | 0 | 768 | 122 | 70580299 | 1182894 | 69397406 | 72161683 | 71816805 | -207118 | 288000 | 80882 | 71897687 | 72603555 | 86.67% | 13 | 772222 | 1581384 | 447 | 300 | 0 | 21 | 1118923 | 0 | 0 | 14 | 628064 | 33375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -83887 | 0 | 0 | 0 | 48359 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 48203 | 22497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 0 | 107 | 1654196 | 89578
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8Q78 | 43554615201 | 2018-06-15 | QTR4 | 17/18 | 2 | 27 | 1430 | 1594 | 1265 | 76.99% | 1 | 329 | 0 | 0 | 164 | 0 | 143269821 | 150000 | 143119821 | 145759356 | 145166429 | 0 | 5000000 | 5000000 | 150166429 | 144192875 | 100.7% | 1 | -5873129 | 2489535 | 81 | 83 | 0 | 0 | 398577 | 0 | 0 | 0 | 1404790 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131931 | 0 | 0 | 0 | 551048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140484 | 0 | 0 | 0 | 2379872 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 |  | 2022-03-01 | QTR3 | 21/22 | 854 | 156867749.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 08 | E8R77 | 43798615201 | 2019-05-14 | QTR4 | 18/19 | 3 | 5 | 738 | 1039 | 1039 | 103.8% | 1 | 0 | 0 | 0 | 301 | 0 | 31832323 | 150000 | 31682323 | 32865375 | 32938830 | 0 | 0 | 0 | 32938830 | 32271398 | 101.9% | 1 | -667433 | 1033052 | 175 | 98 | 0 | 0 | 62194 | 0 | 0 | 0 | 38182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 960260 | 0 | 0 | 0 | 77444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1138080 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2023-08-10 | QTR1 | 23/24 |  | 2022-08-17 | QTR1 | 22/23 | 854 | 33799887.12
| 08 | E8R97 | 43730045201 | 2019-09-17 | QTR1 | 19/20 | 1 | 35 | 939 | 1012 | 938 | 92.12% | 1 | 74 | 0 | 0 | 73 | 0 | 139979406 | 150000 | 139829406 | 145733672 | 144403400 | 0 | 6000000 | 6000000 | 150403400 | 143485400 | 102.6% | 1 | -5542884 | 5754265 | 38 | 35 | 0 | 0 | 48807 | 0 | 0 | 0 | 4196617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94312 | 0 | 0 | 0 | 564973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 983554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5902105 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 |  | 2022-07-31 | QTR1 | 22/23 | 854 | 118749145.78 | B10 | ACC - BONUS/INCENT/DISINCENT
| 08 | E8S55 | 44070015201 | 2020-08-31 | QTR1 | 20/21 | 2 | 7 | 515 | 718 | 716 | 94.17% | 1 | 2 | 0 | 0 | 231 | -28 | 16707654 | 150000 | 16557654 | 17277221 | 16377036 | 0 | 0 | 0 | 16377036 | 16720673 | 101% | 1 | 485146 | 569567 | 175 | 56 | 0 | 0 | 18542 | 0 | 0 | 0 | 58747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469864 | 0 | 0 | 0 | 80825 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28 | -50316 | 0 | 45 | -28 | 616415 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2022-12-20 | QTR2 | 22/23 | 854 | 20328685.57
| 08 | E8T21 | 44029215201 | 2021-09-14 | QTR1 | 21/22 | 2 | 6 | 350 | 617 | 614 | 110.6% | 1 | 3 | 0 | 0 | 208 | 59 | 13350942 | 121421 | 13229522 | 13774510 | 13575224 | 0 | 0 | 0 | 13575224 | 13523826 | 102.2% | 1 | 353962 | 423568 | 176 | 51 | 0 | 0 | 5500 | 0 | 0 | 0 | 24055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 97132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 405361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 532048 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-09-08 | QTR1 | 23/24 | 854 | 12351694.57
| 08 | E8T38 | 43730095201 | 2022-02-08 | QTR3 | 21/22 | 1 | 0 | 192 | 242 | 235 | 96.35% | 1 | 7 | 0 | 0 | 50 | 0 | 5115331 | 50000 | 5065331 | 5115331 | 5070631 | 0 | 0 | 0 | 5070631 | 5070631 | 100.1% | 1 | 0 | 0 | 26 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-06-15 | QTR4 | 22/23 | 854 | 5087753.85
| 08 | E8T39 | 44430115201 | 2021-12-14 | QTR2 | 21/22 | 1 | 3 | 234 | 278 | 253 | 89.32% | 1 | 25 | 0 | 0 | 44 | 0 | 1975221 | 50000 | 1925221 | 2101149 | 2102097 | 0 | 0 | 0 | 2102097 | 2083906 | 108.2% | 1 | 7736 | 125928 | 25 | 19 | 0 | 0 | 102641 | 0 | 0 | 0 | 36105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174272 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 |  | 2023-03-08 | QTR3 | 22/23 | 854 | 1709882.3
| 08 | E8T42 | 43799015201 | 2022-03-08 | QTR3 | 21/22 | 2 | 3 | 321 | 359 | 286 | 72.27% | 1 | 73 | 0 | 0 | 54 | -16 | 4166000 | 50000 | 4116000 | 4217668 | 4164480 | 0 | 138823 | 138823 | 4303303 | 4215075 | 102.4% | 1 | -86560 | 51668 | 31 | 23 | 0 | 0 | 44026 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 0 | 0 | 0 | -16 | 98536 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-05-22 | QTR4 | 22/23 | 854 | 3910716.97 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8T68 | 44448615201 | 2022-04-12 | QTR4 | 21/22 | 1 | 2 | 329 | 389 | 389 | 100% | 1 | 0 | 0 | 0 | 60 | 0 | 6695054 | 50000 | 6645054 | 6727768 | 6880189 | 0 | 0 | 0 | 6880189 | 6860508 | 103.2% | 1 | -11968 | 32714 | 26 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 74099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81813 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-11-28 | QTR2 | 23/24 |  | 2023-10-05 | QTR2 | 23/24 | 854 | 6191721.36
| 08 | E8T86 | 43855115201 | 2022-08-16 | QTR1 | 22/23 | 1 | 1 | 136 | 169 | 142 | 97.79% | 1 | 27 | 0 | 0 | 9 | 24 | 597627 | 35230 | 562397 | 652711 | 607225 | 0 | 0 | 0 | 607225 | 607225 | 108% | 1 | 0 | 55083 | 6 | 3 | 0 | 24 | 55083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 55083 | 0 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-06-23 | QTR4 | 22/23 | 854 | 898718.41
| 08 | E8T87 | 43855015201 | 2022-08-16 | QTR1 | 22/23 | 1 | 0 | 199 | 202 | 84 | 40.7% | 1 | 118 | 0 | 0 | 3 | 0 | 767354 | 50000 | 717354 | 767354 | 705154 | 0 | 0 | 0 | 705154 | 705154 | 98.3% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2023-05-11 | QTR4 | 22/23 | 854 | 1243902.61
| 08 | E8U24 | 44122465201 | 2023-02-14 | QTR3 | 22/23 | 1 | 1 | 94 | 108 | 107 | 98.94% | 1 | 1 | 0 | 0 | 14 | 0 | 855737 | 38426 | 817311 | 857248 | 864748 | 0 | 0 | 0 | 864748 | 863238 | 105.6% | 1 | 0 | 1510 | 12 | 2 | 0 | 0 | 2884 | 0 | 0 | 0 | 30181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37651 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-01 | QTR2 | 23/24 |  | 2023-09-25 | QTR1 | 23/24 | 854 | 859411.5
| 08 | E8U28 | 44261825201 | 2023-05-09 | QTR4 | 22/23 | 1 | 0 | 86 | 90 | 27 | 26.74% | 1 | 63 | 0 | 0 | 4 | 0 | 491221 | 32753 | 458468 | 491221 | 344856 | 0 | 0 | 0 | 344856 | 344856 | 75.22% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F721180277 | JACK B. HARPER CONTRACTOR L.L.C. | N/A | N/A | N/A | N/A | 2023-11-27 | QTR2 | 23/24 |  | 2023-09-15 | QTR1 | 23/24 | 854 | 690819.2
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 13 | 19 | 90 | 5563 | 6817 | 6095 | 100% | 13 | 722 | 0 | 0 | 1215 | 39 | 365803691 | 1077830 | 364725862 | 376340584 | 373200299 | 0 | 11138823 | 11138823 | 384339122 | 370944765 | 100% | 13 | -11335130 | 10536890 | 771 | 435 | 0 | 24 | 738254 | 0 | 0 | 0 | 5866043 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 28 | 40 | 1763098 | 0 | 0 | 0 | 1326941 | 0 | 0 | 0 | 0 | 0 | 45 | 19 | 1485044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | -190800 | 0 | 73 | 39 | 11015875 | 0
| District 08 Totals |  |  |  |  | 13 | 19 | 90 | 5563 | 6817 | 6095 | 100% | 13 | 722 | 0 | 0 | 1215 | 39 | 365803691 | 1077830 | 364725862 | 376340584 | 373200299 | 0 | 11138823 | 11138823 | 384339122 | 370944765 | 100% | 13 | -11335130 | 10536890 | 771 | 435 | 0 | 24 | 738254 | 0 | 0 | 0 | 5866043 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 28 | 40 | 1763098 | 0 | 0 | 0 | 1326941 | 0 | 0 | 0 | 0 | 0 | 45 | 19 | 1485044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | -190800 | 0 | 73 | 39 | 11015875 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 98 | 191 | 241 | 26292 | 40783 | 41216 | 75.51% | 74 | -433 | 1297 | 0 | 11963 | 2530 | 568045850 | 5933299 | 562112553 | 589340569 | 591207444 | -2360310 | 1270000 | -1090310 | 590117134 | 601931042 | 86.73% | 85 | 15893226 | 21148457 | 7456 | 3151 | 657 | 725 | 4966066 | 258371 | 521 | 748 | 8262781 | 1926734 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 72 | 354 | 529489 | 3140 | 0 | 2 | 674786 | 85182 | 0 | 0 | 0 | 0 | 1115 | 534 | 1456066 | 8396 | 0 | 46 | 6636762 | 128274 | 139 | 69 | 327076 | 345349 | 553 | 93 | 14596 | 0 | 0 | -19 | -739104 | 0 | 3057 | 2552 | 22025043 | 2755444
| Statewide District Let Contracts SubTotal |  |  |  |  | 55 | 90 | 163 | 14905 | 20600 | 19161 | 94.55% | 52 | 1439 | 10 | 0 | 4668 | 1027 | 509874331 | 3215276 | 506659057 | 523973215 | 518918688 | -60066 | 11418823 | 11358757 | 530277445 | 518778801 | 90.91% | 50 | -8653343 | 14098879 | 2948 | 1728 | 12 | 341 | 1447494 | 0 | 64 | 169 | 7937120 | 52488 | 0 | 62 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 28 | 174 | 2554350 | 0 | 62 | 0 | 1488109 | 33706 | 0 | 0 | 0 | 0 | 271 | 264 | 1790605 | 14973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 60 | 0 | 0 | 0 | -44 | -451534 | 0 | 458 | 1026 | 14793437 | 101167
| Statewide Totals |  |  |  |  | 153 | 281 | 404 | 41197 | 61383 | 60377 | 82.35% | 126 | 1006 | 1307 | 0 | 16631 | 3557 | 1077920181 | 9148575 | 1068771610 | 1113313784 | 1110126132 | -2420376 | 12688823 | 10268447 | 1120394579 | 1120709843 | 88.24% | 135 | 7239883 | 35247336 | 10404 | 4879 | 669 | 1066 | 6413560 | 258371 | 585 | 917 | 16199901 | 1979222 | 0 | 62 | 13454 | 0 | 0 | 0 | -89635 | 0 | 0 | 0 | 0 | 0 | 100 | 528 | 3083839 | 3140 | 62 | 2 | 2162895 | 118888 | 0 | 0 | 0 | 0 | 1386 | 798 | 3246671 | 23369 | 0 | 46 | 6636762 | 128274 | 139 | 69 | 327076 | 345349 | 574 | 153 | 14596 | 0 | 0 | -63 | -1190638 | 0 | 3515 | 3578 | 36818480 | 2856611

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1S66 | 43813715201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-12-03 | 8623489 | 9397066 | 9569047 | 773577.77 | 0 | 9781152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9569047 | 9781152 | 212105 | 7399516 | B10:B2:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
1 | E1S92 | 44153415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-11-04 | 5052712 | 4990876 | 4942213 | -61835.5 | 0 | 4940854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4942213 | 4940854 | -1360 | 4924225
1 | E1U10 | 44592715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-10-21 | 1030376 | 1035071 | 1194101 | 4694.69 | 0 | 1194101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1194101 | 1194101 | 0 | 838447
1 | E1U12 | 44155315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-09-16 | 6272386 | 6303322 | 6506395 | 30935.13 | 0 | 6933886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6506395 | 6933886 | 427490 | 6222847
1 | E1U14 | 44477715201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2021-12-02 | 3819554 | 3657701 | 3521817 | -161853.09 | 0 | 3658011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3521817 | 3658011 | 136195 | 3928133 | B0 | ACC - LUMP SUM
1 | E1U17 | 44594115201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-02-17 | 722056 | 722056 | 642082 | 0 | 100000 | 642815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000 | 100000 | 742082 | 642815 | -99267 | 1070561 | B1 | ACC - NO EXCUSE BONUS
1 | E1V07 | 44023115201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2022-09-15 | 289419 | 311381 | 315649 | 21962 | 0 | 315649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315649 | 315649 | 0 | 331705
1 | T1751 | 41066635201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 43563143 | 43826539 | 44814363 | 263396.26 | 0 | 46184516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44814363 | 46184516 | 1370154 | 44746155
1 | T1761 | 42982315201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 4097408 | 4902150 | 4899132 | 804741.84 | 0 | 4933511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4899132 | 4933511 | 34379 | 4251830
1 | T1772 | 44211515201 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2020-09-30 | 668342 | 668342 | 641177 | 0 | 0 | 631148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641177 | 631148 | -10029 | 802466
1 | T1777 | 43943015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 7973682 | 8225110 | 8476176 | 251427.57 | -106857 | 9010027 | -106857 | 0 | 0 | 0 | 0 | 0 | -106857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -106857 | 8369319 | 9010027 | 640708 | 9500361
1 | T1781 | 44151815201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-01-27 | 4960436 | 5450251 | 5315172 | 489814.72 | 0 | 5587423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5315172 | 5587423 | 272251 | 5666706
1 | T1790 | 44240115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-26 | 697485 | 700625 | 698869 | 3140.32 | 0 | 698869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698869 | 698869 | 0 | 802616 | B0 | ACC - LUMP SUM
1 | T1806 | 44155915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 7108184 | 8445969 | 8418621 | 1337785.07 | 0 | 8684123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8418621 | 8684123 | 265502 | 6181054
1 | T1808 | 44233315201 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-27 | 1139701 | 1148801 | 1029185 | 9099.67 | 0 | 1030981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1029185 | 1030981 | 1796 | 1098276
1 | T1817 | 44068815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 650650 | 655279 | 608957 | 4628.74 | 0 | 609408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608957 | 609408 | 451 | 447610
1 | T1826 | 44421215201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-25 | 1045874 | 1076047 | 1015157 | 30173.84 | 0 | 1015157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015157 | 1015157 | 0 | 898648
1 | T1828 | 44033715201 | F823160551 | LEON AMERICA CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-02-23 | 560933 | 623460 | 604533 | 62526.98 | 0 | 604533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604533 | 604533 | 0 | 517232 | B0 | ACC - LUMP SUM
1 | T1834 | 44632015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 4197476 | 4197476 | 3945832 | 0 | 0 | 3902393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3945832 | 3902393 | -43439 | 4322111
1 | T1839 | 44012715201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 461461 | 461461 | 428726 | 0 | 0 | 428726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428726 | 428726 | 0 | 438393
2 | E2Y76 | 20972255201 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2020-04-15 | 4399943 | 4455060 | 4501267 | 55116.96 | 0 | 4501267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4501267 | 4501267 | 0 | 4855272
2 | T2703 | 21272425201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 11717625 | 11666748 | 11573612 | -50877.32 | -1206768 | 10334162 | -1206768 | 0 | 0 | 0 | 0 | 0 | -1206768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1206768 | 10366844 | 10334162 | -32682 | 12539660
2 | T2725 | 42307145201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2018-12-05 | 7294444 | 7636147 | 7798283 | 341702.82 | 0 | 7754246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7798283 | 7754246 | -44037 | 7079692
2 | T2749 | 43946715201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 11950705 | 12606239 | 12671373 | 655533.43 | 0 | 12844734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12671373 | 12844734 | 173361 | 11844644
2 | T2757 | 43761115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 8709827 | 8796925 | 9281776 | 87098.27 | 0 | 9514074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9281776 | 9514074 | 232299 | 10240285
2 | T2787 | 44105915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 13904803 | 14427901 | 14501738 | 523098.66 | 0 | 14430355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14501738 | 14430355 | -71383 | 14722616
2 | T2788 | 44258115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 7945667 | 7945667 | 8118217 | 0 | 0 | 8574396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8118217 | 8574396 | 456179 | 6919712
2 | T2802 | 43575715201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 1262262 | 1262262 | 1249368 | 0 | 0 | 1249498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249368 | 1249498 | 130 | 1338363
2 | T2803 | 44126115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 4633748 | 3852057 | 3929376 | -781690.82 | 0 | 4154909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3929376 | 4154909 | 225533 | 4540383
2 | T2813 | 43617815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 6155492 | 6241492 | 6261727 | 86000 | 0 | 6665942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6261727 | 6665942 | 404215 | 7776562
2 | T2821 | 44327315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 4876894 | 4984966 | 5022406 | 108072.68 | 0 | 5415141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5022406 | 5415141 | 392735 | 5483811
2 | T2822 | 44331315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 9173879 | 9173879 | 9342688 | 0 | 0 | 9910699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9342688 | 9910699 | 568010 | 9935886
2 | T2824 | 44327415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 3471681 | 3603585 | 3475517 | 131903.51 | 0 | 3617192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3475517 | 3617192 | 141674 | 3836185
2 | T2825 | 44328215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 698919 | 698919 | 656099 | 0 | 0 | 656099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656099 | 656099 | 0 | 629199
2 | T2826 | 44331115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 8657266 | 8657266 | 8107793 | 0 | 0 | 8099899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8107793 | 8099899 | -7895 | 10016767
2 | T2829 | 44120815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-04-27 | 1047740 | 1047740 | 1004140 | 0 | 0 | 1004137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1004140 | 1004137 | -3 | 1984965
2 | T2833 | 44325815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-01-12 | 6173212 | 6173212 | 6149692 | 0 | 0 | 6808147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6149692 | 6808147 | 658455 | 7484488
2 | T2836 | 44325915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 4069827 | 4084043 | 4107794 | 14216.4 | 0 | 4238033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4107794 | 4238033 | 130239 | 5072862
2 | T2837 | 44329415201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 1371850 | 1371850 | 1320562 | 0 | 0 | 1327034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320562 | 1327034 | 6472 | 1352767
2 | T2846 | 44126015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-01-12 | 9551621 | 9552942 | 9869457 | 1320.8 | -18930 | 10485489 | -18930 | 0 | 0 | 0 | 0 | 0 | -18930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18930 | 9850527 | 10485489 | 634962 | 11919284
2 | T2855 | 43935815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 7918962 | 7918962 | 7962203 | 0 | 0 | 8267055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7962203 | 8267055 | 304853 | 7233768
2 | T2857 | 44721115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 1077522 | 1077522 | 1075156 | 0 | 0 | 1075156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075156 | 1075156 | 0 | 1339271
2 | T2869 | 43567925201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 1298306 | 1298306 | 1209436 | 0 | 0 | 1209097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209436 | 1209097 | -339 | 1554776
2 | T2873 | 44557615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 240110 | 240110 | 185940 | 0 | 0 | 185940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185940 | 185940 | 0 | 402520
2 | T2875 | 44912925201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 1386562 | 1386562 | 1349510 | 0 | 0 | 1349510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349510 | 1349510 | 0 | 1705477
2 | T2877 | 20954355201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 744369 | 788349 | 712669 | 43979.98 | 0 | 717926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712669 | 717926 | 5257 | 931265
2 | T2923 | 44542625201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 212969 | 212969 | 198096 | 0 | 0 | 198096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198096 | 198096 | 0 | 251712
2 | T9023 | 44624515223 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 3516622 | 3516622 | 3642093 | 0 | 0 | 3642131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3642093 | 3642131 | 38 | 3117936
3 | E3S70 | 43992635201 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-05-13 | 8497804 | 8518932 | 8897714 | 21128.25 | 0 | 9015856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8897714 | 9015856 | 118142 | 7939245
3 | E3U04 | 21904225201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-01-12 | 278090 | 278090 | 249120 | 0 | 0 | 249120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249120 | 249120 | 0 | 454254
3 | E3U32 | 42187425201 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2022-01-13 | 109495 | 109495 | 105102 | 0 | 0 | 105102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105102 | 105102 | 0 | 135677
3 | E3U47 | 44158915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-11-10 | 6190992 | 6194018 | 6101074 | 3025.35 | -18750 | 6229251 | 0 | 0 | 0 | 0 | 0 | -18750 | -18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18750 | 6082324 | 6229251 | 146927 | 5430315
3 | E3U84 | 44365915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-10 | 3254371 | 3263484 | 3285954 | 9112.73 | 0 | 3378196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3285954 | 3378196 | 92242 | 3044606
3 | E3V33 | 44891315201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2023-01-12 | 223976 | 223976 | 187027 | 0 | 0 | 187027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187027 | 187027 | 0 | 298951
3 | E3V90 | 44575815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-01-12 | 1499653 | 1499653 | 1534493 | 0 | 0 | 1534493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534493 | 1534493 | 0 | 1524311
3 | T3579 | 41413245201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-08-31 | 42140000 | 43136516 | 44812912 | 996516.18 | -789688 | 45313117 | -739708 | 0 | 0 | 0 | 0 | -49980 | -789688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -789688 | 44023224 | 45313117 | 1289893 | 37004160
3 | T3598 | 43357725201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2021-12-08 | 1449372 | 1449372 | 1245314 | 0 | 0 | 1245462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245314 | 1245462 | 147 | 1387513
3 | T3604 | 43282815201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 10228411 | 10251581 | 10265075 | 23170.26 | 0 | 10328004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10265075 | 10328004 | 62929 | 10230058
3 | T3664 | 43375115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 2044978 | 2045473 | 1900355 | 495 | 0 | 1888581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900355 | 1888581 | -11773 | 2066195
3 | T3691 | 43717815201 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2020-11-18 | 4269226 | 4374816 | 4440122 | 105590.54 | -30948 | 4471244 | -30948 | 0 | 0 | 0 | 0 | 0 | -30948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30948 | 4409174 | 4471244 | 62070 | 4154506
3 | T3703 | 43649925201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 2458081 | 2458081 | 2572160 | 0 | 0 | 2554701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2572160 | 2554701 | -17459 | 2031386
3 | T3704 | 43938815201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 1462111 | 1462111 | 1360760 | 0 | 0 | 1370361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360760 | 1370361 | 9601 | 1750125
3 | T3728 | 21898425201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2021-06-09 | 5503848 | 5503848 | 5683756 | 0 | 0 | 5700846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5683756 | 5700846 | 17090 | 7823905
3 | T3740 | 43626615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 6166449 | 6166449 | 6743565 | 0 | 0 | 7855936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6743565 | 7855936 | 1112372 | 7986598
3 | T3743 | 44173015201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-02-26 | 187229 | 187229 | 175598 | 0 | 0 | 166353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175598 | 166353 | -9245 | 262871
3 | T3750 | 43811125201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2022-07-27 | 987732 | 927591 | 903555 | -60141.3 | 0 | 903555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903555 | 903555 | 0 | 912225
3 | T3759 | 44014915201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 6899119 | 7276831 | 6971277 | 377712.53 | 0 | 7387006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6971277 | 7387006 | 415730 | 5086090
3 | T3784 | 43938515201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 830333 | 830333 | 808692 | 0 | 0 | 808692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808692 | 808692 | 0 | 771891
3 | T3793 | 43467715201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-10-27 | 6283852 | 6727204 | 6844151 | 443352.47 | 0 | 7176797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6844151 | 7176797 | 332646 | 7460138
3 | T3794 | 44364415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 2537432 | 2537432 | 2741257 | 0 | 0 | 2721406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2741257 | 2721406 | -19851 | 2975157
3 | T3800 | 44851815201 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 3545980 | 3707781 | 3707779 | 161800.68 | 0 | 3707779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3707779 | 3707779 | 0 | 3713439
3 | T3810 | 44365015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 10527718 | 10784785 | 11111656 | 257066.75 | 0 | 11389685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11111656 | 11389685 | 278029 | 10728439
3 | T3817 | 44387515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 535084 | 538384 | 583904 | 3300 | 0 | 583904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583904 | 583904 | 0 | 438194
3 | T3823 | 44565615201 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-01-25 | 2199429 | 2199429 | 2316440 | 0 | 0 | 2316440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2316440 | 2316440 | 0 | 2955598
3 | T3825 | 44565715201 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-03-29 | 1398733 | 1398733 | 1268603 | 0 | 0 | 1268603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268603 | 1268603 | 0 | 2259061
3 | T3828 | 44404415201 | F432094655 | H.G. CONSTRUCTION DEVELOPMENT & INVESTM | N/A | N/A | N/A | N/A | 2022-02-23 | 1388656 | 1388656 | 1401865 | 0 | 0 | 1401865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401865 | 1401865 | 0 | 1545933
3 | T3830 | 43256615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 3353932 | 3353932 | 3387610 | 0 | 0 | 3371222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3387610 | 3371222 | -16388 | 3164048
3 | T3833 | 44560315201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 192351 | 192351 | 176477 | 0 | 0 | 176477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176477 | 176477 | 0 | 173500
3 | T3836 | 43974415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 4469056 | 4469056 | 4076218 | 0 | 0 | 3952664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4076218 | 3952664 | -123554 | 6832324
3 | T9024 | 44199335223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 3198515 | 3289097 | 3343570 | 90581.99 | 0 | 3343570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3343570 | 3343570 | 0 | 3552350
3 | T9027 | 44531315215 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-10-27 | 564819 | 564819 | 524793 | 0 | 0 | 524793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524793 | 524793 | 0 | 932089
4 | E4T68 | 44074615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-05-06 | 17557323 | 17588765 | 16726429 | 31442 | 0 | 16980455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16726429 | 16980455 | 254025 | 12972093
4 | E4U99 | 44146215201 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-05-07 | 12200214 | 13805766 | 14205204 | 1605551.79 | 0 | 14206673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14205204 | 14206673 | 1469 | 10374506 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | E4V19 | 43215215201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-01-07 | 2335539 | 2335539 | 2159702 | 0 | 0 | 2159702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159702 | 2159702 | 0 | 4011283 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4V55 | 44359415201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-05-06 | 895596 | 965406 | 917671 | 69809.69 | 0 | 917671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917671 | 917671 | 0 | 1122911
4 | E4V75 | 44172215201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-02-04 | 1455255 | 1515282 | 1451281 | 60027.27 | 0 | 1459199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1451281 | 1459199 | 7917 | 1403379
4 | E4V84 | 44609715201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2022-09-02 | 3147147 | 3153188 | 2965886 | 6040.86 | 0 | 2896248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2965886 | 2896248 | -69638 | 3652109 | B1 | ACC - NO EXCUSE BONUS
4 | E4W04 | 45059015201 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2022-06-14 | 1468626 | 1468626 | 1421948 | 0 | 0 | 1421948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1421948 | 1421948 | 0 | 2551167
4 | T4552 | 43696215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2020-05-20 | 26406739 | 27530140 | 28635441 | 1123401.87 | 0 | 29122767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28635441 | 29122767 | 487326 | 27323788 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | T4562 | 43177035201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 3588218 | 3660295 | 3546957 | 72077.49 | 0 | 3613971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3546957 | 3613971 | 67014 | 3732217
4 | T4567 | 43839415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 2505478 | 2517687 | 2533462 | 12209.09 | 0 | 2567224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533462 | 2567224 | 33762 | 2223138
4 | T4571 | 43839515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 2029422 | 2048533 | 1920549 | 19111.21 | 0 | 1970008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920549 | 1970008 | 49459 | 2213111
4 | T4572 | 43838415201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-01-27 | 2952231 | 2953979 | 2904459 | 1747.99 | 0 | 2904459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2904459 | 2904459 | 0 | 3045127
4 | T4573 | 43206675201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-28 | 3496673 | 3721036 | 3515537 | 224363.43 | 0 | 3603841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3515537 | 3603841 | 88304 | 3657624
4 | T4594 | 43999015201 | F650814419 | ZAHLENE ENTERPRISES INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 2000000 | 2008938 | 1868868 | 8938.46 | 0 | 1870979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1868868 | 1870979 | 2110 | 2421038
4 | T4597 | 44177515201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2022-01-26 | 957661 | 958736 | 900445 | 1074.85 | 0 | 900445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900445 | 900445 | 0 | 927529
4 | T4603 | 44157815201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 2249738 | 2249738 | 2253443 | 0 | 0 | 2251225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253443 | 2251225 | -2218 | 2503872
4 | T4607 | 43999315201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2022-03-30 | 1967721 | 1967721 | 1856962 | 0 | 0 | 1859008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1856962 | 1859008 | 2046 | 2135578
4 | T4614 | 44399415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 4491996 | 4563991 | 4393362 | 71995.43 | 0 | 4387252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4393362 | 4387252 | -6110 | 4062647
4 | T4629 | 44562315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-12-07 | 1050673 | 1050673 | 985015 | 0 | 0 | 985015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985015 | 985015 | 0 | 1029940
5 | E50B4 | 44290615201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-07-06 | 3079406 | 3129406 | 3205711 | 50000 | 0 | 3130395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3205711 | 3130395 | -75316 | 3825882
5 | E51A9 | 44102015201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-09-01 | 7501367 | 7798794 | 7544823 | 297427.05 | -41316 | 7754120 | -41316 | 0 | 0 | 0 | 0 | 0 | -41316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41316 | 7503507 | 7754120 | 250613 | 7321147
5 | E53B6 | 43901715201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-09-07 | 1640053 | 1640053 | 1539808 | 0 | 0 | 1539808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1539808 | 1539808 | 0 | 2062515
5 | E55B3 | 44942415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-12-06 | 950694 | 950694 | 969481 | 0 | 0 | 969481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969481 | 969481 | 0 | 729303
5 | E55B4 | 44942515201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-11-01 | 967737 | 967737 | 851103 | 0 | 0 | 851002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851103 | 851002 | -101 | 882687
5 | E57A1 | 44343315201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-11-02 | 5312936 | 5361981 | 5275495 | 49044.96 | 0 | 5382637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5275495 | 5382637 | 107142 | 6332507
5 | E57A4 | 44113215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-10-05 | 7424369 | 7591181 | 7558842 | 166811.87 | 0 | 7953369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7558842 | 7953369 | 394527 | 9276735
5 | E59A9 | 43913015201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-01-04 | 679529 | 679529 | 677096 | 0 | 0 | 677187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677096 | 677187 | 92 | 681571
5 | T5552 | 40714345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-06-08 | 75824482 | 86884143 | 89837352 | 10910760.93 | 0 | 90653074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89837352 | 90653074 | 815723 | 88197362 | B2:B2:B5:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B/BONUS
5 | T5733 | 44381515201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 7387943 | 7578305 | 6929112 | 190361.43 | 0 | 7646110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6929112 | 7646110 | 716998 | 8754090
5 | T5737 | 44288115201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-12-08 | 1605048 | 1606653 | 1573163 | 1605 | 0 | 1576898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573163 | 1576898 | 3735 | 1288584
5 | T5738 | 44290915201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 9861239 | 9880239 | 9803603 | 18999.77 | 0 | 10869062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9803603 | 10869062 | 1065459 | 13653416
5 | T5763 | 44569015201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 1690095 | 1690972 | 1630216 | 876.83 | 0 | 1602812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630216 | 1602812 | -27404 | 2378839
5 | T5765 | 43759625201 | F263013168 | MEJIA INTERNATIONAL GROUP CORPORATION | N/A | N/A | N/A | N/A | 2022-10-26 | 1068776 | 1068776 | 1003835 | 0 | 0 | 1003807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1003835 | 1003807 | -28 | 1065459
6 | E6N08 | 44196015201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2022-01-27 | 2813265 | 2921577 | 2938675 | 108311.92 | 0 | 2938740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938675 | 2938740 | 65 | 3044683
6 | E6N09 | 44480525201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-07-28 | 797552 | 797552 | 706126 | 0 | 0 | 706126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706126 | 706126 | 0 | 1509364
6 | E6N47 | 44445015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2022-05-26 | 2697327 | 2771657 | 2731695 | 74329.48 | 180000 | 2718704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 2911695 | 2718704 | -192991 | 2883318 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6N55 | 44196815201 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2021-08-26 | 757063 | 757063 | 654819 | 0 | 0 | 654819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654819 | 654819 | 0 | 1042436
6 | T6496 | 44182715201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-03-31 | 5245136 | 5346913 | 5060388 | 101776.46 | 0 | 5419442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5060388 | 5419442 | 359054 | 5969737 | B2:B2:B5:B5 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6505 | 43326435201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-08-26 | 4604161 | 4652806 | 4445340 | 48645.61 | 399999 | 4484965 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000 | 399999 | 4845339 | 4484965 | -360374 | 4947289 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6513 | 43998615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-03-30 | 2569128 | 2717271 | 2543862 | 148143.16 | 120000 | 2540376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 2663862 | 2540376 | -123486 | 2452592 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6515 | 43274845201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-03-30 | 2455465 | 2510141 | 2443596 | 54676.34 | 72000 | 2440177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 2515596 | 2440177 | -75419 | 2281095 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6516 | 43998115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 4166383 | 4219775 | 4110877 | 53391.64 | 0 | 4270005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4110877 | 4270005 | 159128 | 4661947 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6518 | 42918635201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 2919079 | 2940250 | 2881342 | 21170.5 | 210000 | 2944862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 210000 | 210000 | 3091342 | 2944862 | -146480 | 3061117 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6519 | 43476835201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2022-01-26 | 3487287 | 3497187 | 3509376 | 9900 | 180000 | 3539751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 3689376 | 3539751 | -149625 | 3568828 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
7 | E7N90 | 44822115201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2022-01-12 | 679686 | 695950 | 640611 | 16263.93 | 0 | 640611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640611 | 640611 | 0 | 644500
7 | E7N95 | 44025115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 6430299 | 6566839 | 6774752 | 136540.44 | 0 | 7326407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6774752 | 7326407 | 551655 | 8690700
7 | E7O04 | 43952615201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2021-09-08 | 1944266 | 2045152 | 1898792 | 100885.18 | 0 | 1898792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898792 | 1898792 | 0 | 1797400
7 | E7O11 | 44166515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-09 | 3049631 | 3049631 | 3013462 | 0 | 0 | 3013181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3013462 | 3013181 | -281 | 2409700
7 | E7P30 | 44761415201 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2022-04-13 | 2231499 | 2259063 | 2052581 | 27564.52 | 0 | 2046856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052581 | 2046856 | -5724 | 1792600
7 | E7P36 | 44978015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-06-08 | 4664000 | 4709230 | 4734993 | 45229.8 | 0 | 4662735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4734993 | 4662735 | -72258 | 5588200 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
7 | E7P61 | 44383615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-01-11 | 506794 | 527638 | 475289 | 20844.36 | 0 | 475289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475289 | 475289 | 0 | 441600
7 | E7P63 | 44774815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-01-11 | 619151 | 619151 | 571177 | 0 | 0 | 571177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571177 | 571177 | 0 | 1320700
7 | T7424 | 25729855201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 20155312 | 20804212 | 20013184 | 648899.65 | 0 | 19790050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20013184 | 19790050 | -223135 | 29301814
7 | T7428 | 43258435201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 9277781 | 9481539 | 10184938 | 203758.52 | 251742 | 10145611 | -48258 | 0 | 0 | 0 | 0 | 0 | -48258 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 251742 | 10436680 | 10145611 | -291069 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | T7451 | 43982985201 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2020-04-29 | 698558 | 698558 | 557380 | 0 | -158860 | 531562 | -158860 | 0 | 0 | 0 | 0 | 0 | -158860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -158860 | 398520 | 531562 | 133042 | 691075
7 | T7468 | 44138615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-27 | 9161461 | 9416662 | 9425645 | 255200.4 | 0 | 9775049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9425645 | 9775049 | 349405 | 9040000
7 | T7480 | 44025315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 8381553 | 8507750 | 8880433 | 126196.94 | 0 | 9233589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8880433 | 9233589 | 353156 | 9618300
7 | T7491 | 44358325201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-02-23 | 1439445 | 1439445 | 1363648 | 0 | 0 | 1363533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1363648 | 1363533 | -115 | 1085600
7 | T7498 | 44332015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 1340863 | 1340863 | 1268582 | 0 | -12000 | 1256582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12000 | 0 | 0 | 0 | 0 | 0 | -12000 | -12000 | 1256582 | 1256582 | 0 | 2027300
8 | E8Q78 | 43554615201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-06-15 | 143269821 | 145759356 | 145166429 | 2489534.99 | 5000000 | 144293300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 150166429 | 144293300 | -5873129 | 156867750 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
8 | E8R77 | 43798615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-05-14 | 31832323 | 32865375 | 32938830 | 1033051.69 | 0 | 32271398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32938830 | 32271398 | -667433 | 33799887
8 | E8R97 | 43730045201 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2019-09-17 | 139979406 | 145733672 | 144794963 | 5754265.13 | 6000000 | 144860516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000 | 150794963 | 144860516 | -5934447 | 118749146 | B10 | ACC - BONUS/INCENT/DISINCENT
8 | E8S55 | 44070015201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2020-08-31 | 16707654 | 17277221 | 16518546 | 569566.94 | 0 | 16862183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16518546 | 16862183 | 343637 | 20328686
8 | E8T21 | 44029215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-14 | 13350942 | 13774510 | 13575224 | 423567.64 | 0 | 13929187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13575224 | 13929187 | 353962 | 12351695
8 | E8T38 | 43730095201 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2022-02-08 | 5115331 | 5115331 | 5070631 | 0 | 0 | 5070631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5070631 | 5070631 | 0 | 5087754
8 | E8T39 | 44430115201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-12-14 | 1975221 | 2101149 | 2102097 | 125927.59 | 0 | 2109833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2102097 | 2109833 | 7736 | 1709882
8 | E8T42 | 43799015201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-03-08 | 4166000 | 4217668 | 4164480 | 51668.12 | 138823 | 4216743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138823 | 0 | 0 | 0 | 0 | 0 | 138823 | 138823 | 4303303 | 4216743 | -86560 | 3910717 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8T68 | 44448615201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-04-12 | 6695054 | 6727768 | 6880189 | 32713.79 | 0 | 6868222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6880189 | 6868222 | -11968 | 6191721
8 | E8T86 | 43855115201 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2022-08-16 | 597627 | 652711 | 607225 | 55083.3 | 0 | 607225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607225 | 607225 | 0 | 898718
8 | E8T87 | 43855015201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2022-08-16 | 767354 | 767354 | 705154 | 0 | 0 | 705154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705154 | 705154 | 0 | 1243903
8 | E8U24 | 44122465201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-02-14 | 855737 | 857248 | 864748 | 1510.44 | 0 | 864748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864748 | 864748 | 0 | 859412
8 | E8U28 | 44261825201 | F721180277 | JACK B. HARPER CONTRACTOR L.L.C. | N/A | N/A | N/A | N/A | 2023-05-09 | 491221 | 491221 | 344856 | 0 | 0 | 344856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344856 | 344856 | 0 | 690819

## Sheet1 (hidden)
01CO | 01 | T1751 | 41066635201 | 2020-04-29 | QTR4 | 19/20 | 4 | 15 | 875 | 1016 | 963 | 53 | 0 | 0 | 127 | 14 | 43563143 | 150000 | 43413143 | 43826539 | 44268970 | 0 | 0 | 0 | 44268970 | 45616616 | 1915546 | 263396 | 80 | 0 | 0 | 351912 | 3918 | 7 | 0 | 219896 | 30715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17978 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 22507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18317 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 343410 | 34633 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-09-11 | QTR1 | 23/24 | 2023-04-28 | QTR4 | 22/23 | 108 | 44746155.07 |  |  | 0 | 54 | 0 | 0 | -287200 | 0 |  | CO | 13 | 01co | 1 | 13
01CO | 01 | T1761 | 42982315201 | 2021-06-09 | QTR4 | 20/21 | 2 | 18 | 275 | 545 | 530 | 15 | 0 | 0 | 223 | 47 | 4097408 | 50000 | 4047408 | 4902150 | 4899132 | 0 | 0 | 0 | 4899132 | 4822749 | 34379 | 804742 | 131 | 0 | 42 | 118523 | 55203 | 51 | 5 | 478225 | 97145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42992 | 42992 | 0 | 0 | 0 | 0 | 51 | 47 | 830672 | 195339 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2023-02-24 | QTR3 | 22/23 | 113 | 4251830.23 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO | 7 | 01do | 14 | 20
01CO | 01 | T1772 | 44211515201 | 2020-09-30 | QTR1 | 20/21 | 3 | 1 | 150 | 177 | 607 | -430 | 430 | 0 | 11 | 16 | 668342 | 41495 | 626847 | 668342 | 605783 | 0 | 0 | 0 | 605783 | 595755 | 25365 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 6341 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 | 2022-12-05 | QTR2 | 22/23 | 108 | 802465.89 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 27 | 02co | 21 | 47
01CO | 01 | T1777 | 43943015201 | 2020-09-30 | QTR1 | 20/21 | 4 | 3 | 325 | 607 | 638 | -31 | 31 | 0 | 216 | 66 | 7973682 | 92806 | 7880876 | 8225110 | 8195027 | -106857 | 0 | -106857 | 8088170 | 8717413 | 921857 | 251428 | 207 | 0 | 0 | 126514 | 115529 | 0 | 52 | 124433 | 124433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 14 | 11465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 66 | 262412 | 239963 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 | 2022-10-18 | QTR2 | 22/23 | 118 | 9500361.49 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 1 | 02do | 48 | 48
01CO | 01 | T1781 | 44151815201 | 2021-01-27 | QTR3 | 20/21 | 2 | 4 | 285 | 400 | 400 | 0 | 0 | 0 | 41 | 74 | 4960436 | 59129 | 4901307 | 5450251 | 5304714 | 0 | 0 | 0 | 5304714 | 5560151 | 265895 | 489815 | 14 | 0 | 74 | 470632 | 0 | 0 | 0 | 17986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 489815 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2022-06-30 | QTR4 | 21/22 | 118 | 5666706.37 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO | 26 | 03co | 49 | 74
01CO | 01 | T1790 | 44240115201 | 2020-08-26 | QTR1 | 20/21 | 1 | 1 | 110 | 145 | 141 | 4 | 0 | 0 | 26 | 9 | 697485 | 0 | 697485 | 700625 | 698869 | 0 | 0 | 0 | 698869 | 698869 | 0 | 3140 | 21 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140 | 3140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3140 | 3140 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-24 | QTR2 | 23/24 | 2021-07-09 | QTR1 | 21/22 | 108 | 802615.61 | B0 | ACC - LUMP SUM | 9 | 5 | 0 | 0 | 0 | 0 |  | CO | 7 | 03do | 75 | 81
01CO | 01 | T1806 | 44155915201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 250 | 391 | 391 | 0 | 0 | 0 | 134 | 7 | 7108184 | 63330 | 7044854 | 8445969 | 8418621 | 0 | 0 | 0 | 8418621 | 7803372 | 265502 | 1337785 | 92 | 0 | 0 | 0 | 0 | 23 | 7 | 473396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 880751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 39 | 1354148 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 | 2023-05-01 | QTR4 | 22/23 | 115 | 6181054.02 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO | 12 | 04co | 82 | 93
01CO | 01 | T1808 | 44233315201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 140 | 293 | 293 | 0 | 0 | 0 | 153 | 0 | 1139701 | 50000 | 1089701 | 1148801 | 1029185 | 0 | 0 | 0 | 1029185 | 1021881 | 1796 | 9100 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 9100 | 0 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-03-17 | QTR3 | 22/23 | 108 | 1098275.5 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 7 | 04do | 94 | 100
01CO | 01 | T1817 | 44068815201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 80 | 165 | 165 | 0 | 0 | 0 | 85 | 0 | 650650 | 18505 | 632145 | 655279 | 608957 | 0 | 0 | 0 | 608957 | 609408 | 451 | 4629 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 8153 | 45738 | 0 | 0 | 0 | 0 | 27 | 0 | 15989 | 45738 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 | 2022-12-13 | QTR2 | 22/23 | 115 | 447609.94 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO | 6 | 05co | 101 | 106
01CO | 01 | T1826 | 44421215201 | 2021-08-25 | QTR1 | 21/22 | 1 | 3 | 107 | 259 | 259 | 0 | 0 | 0 | 44 | 108 | 1045874 | 41345 | 1004529 | 1076047 | 1015157 | 0 | 0 | 0 | 1015157 | 994639 | 0 | 30174 | 132 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 20519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 31344 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2023-03-20 | QTR3 | 22/23 | 118 | 898648.05 |  |  | 18 | 20 | 0 | 0 | 0 | 0 | T | CO | 8 | 05do | 107 | 114
01CO | 01 | T1828 | 44033715201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 97 | 129 | 129 | 0 | 0 | 0 | 32 | 0 | 560933 | 21933 | 539000 | 623460 | 604533 | 0 | 0 | 0 | 604533 | 604533 | 0 | 62527 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 62527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65533 | 0 | F823160551 | LEON AMERICA CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-09-25 | QTR1 | 23/24 | 2023-05-15 | QTR4 | 22/23 | 113 | 517232.45 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO | 7 | 06co | 115 | 121
01CO | 01 | T1834 | 44632015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 215 | 280 | 272 | 8 | 0 | 0 | 65 | 0 | 4197476 | 50000 | 4147476 | 4197476 | 3945832 | 0 | 0 | 0 | 3945832 | 3902393 | -43439 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 | 2023-06-22 | QTR4 | 22/23 | 113 | 4322110.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO | 4 | 06do | 122 | 125
01CO | 01 | T1839 | 44012715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 0 | 130 | 175 | 175 | 0 | 0 | 0 | 45 | 0 | 461461 | 21100 | 440361 | 461461 | 428726 | 0 | 0 | 0 | 428726 | 428726 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2023-03-06 | QTR3 | 22/23 | 115 | 438393.45 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO | 7 | 07co | 126 | 132
01DO | 01 | E1S66 | 43813715201 | 2020-12-03 | QTR2 | 20/21 | 6 | 8 | 450 | 845 | 838 | 7 | 0 | 0 | 132 | 263 | 8623489 | 90613 | 8532876 | 9397066 | 9294008 | 0 | 0 | 0 | 9294008 | 9490393 | 487144 | 773578 | 84 | 0 | 71 | 305583 | 0 | 0 | 84 | 299190 | 27177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 15720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 263 | 815494 | 27177 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 | 2023-06-30 | QTR4 | 22/23 | 115 | 7399516.3 | B10:B2:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 7 | 48 | 0 | 0 | 0 | 0 |  | DO | 8 | 07do | 133 | 140
01DO | 01 | E1S92 | 44153415201 | 2021-11-04 | QTR2 | 21/22 | 3 | 2 | 275 | 390 | 390 | 0 | 0 | 0 | 115 | 0 | 5052712 | 52873 | 4999839 | 4990876 | 4942213 | 0 | 0 | 0 | 4942213 | 4940854 | -1360 | -61836 | 87 | 0 | 0 | 0 | 0 | 5 | 0 | 6022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -55813 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-12-20 | QTR2 | 23/24 | 2023-09-11 | QTR1 | 23/24 | 115 | 4924224.57 |  |  | 0 | 23 | 0 | 0 | -42313 | 0 |  | DO | 0 | 08co | 141 | 140
01DO | 01 | E1U10 | 44592715201 | 2021-10-21 | QTR2 | 21/22 | 1 | 2 | 90 | 345 | 339 | 6 | 0 | 0 | 58 | 197 | 1030376 | 38210 | 992166 | 1035071 | 1194101 | 0 | 0 | 0 | 1194101 | 1189756 | 0 | 4695 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 5244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18641 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 28229 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-10-27 | QTR2 | 23/24 | 2023-07-16 | QTR1 | 23/24 | 108 | 838447.1 |  |  | 197 | 25 | 0 | 0 | 0 | 0 |  | DO | 13 | 08do | 141 | 153
01DO | 01 | E1U12 | 44155315201 | 2021-09-16 | QTR1 | 21/22 | 2 | 4 | 300 | 439 | 422 | 17 | 0 | 0 | 139 | 0 | 6272386 | 62629 | 6209757 | 6303322 | 6506395 | 0 | 0 | 0 | 6506395 | 6911842 | 427490 | 30935 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 8892 | 976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 22043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 35473 | 976 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-12 | QTR1 | 23/24 | 2023-05-12 | QTR4 | 22/23 | 108 | 6222847.06 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1U14 | 44477715201 | 2021-12-02 | QTR2 | 21/22 | 2 | 2 | 160 | 222 | 222 | 0 | 0 | 0 | 62 | 0 | 3819554 | 50000 | 3769554 | 3657701 | 3521817 | 0 | 0 | 0 | 3521817 | 3658011 | 136195 | -161853 | 29 | 12 | 0 | 56568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | -161853 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-07-21 | QTR1 | 23/24 | 2023-03-03 | QTR3 | 22/23 | 115 | 3928132.77 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | -218421 | 0 |  | DO
01DO | 01 | E1U17 | 44594115201 | 2022-02-17 | QTR3 | 21/22 | 1 | 0 | 150 | 171 | 166 | 5 | 0 | 0 | 21 | 0 | 722056 | 48017 | 674039 | 722056 | 642082 | 0 | 100000 | 100000 | 742082 | 642815 | -99267 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-03-17 | QTR3 | 22/23 | 115 | 1070560.76 | B1 | ACC - NO EXCUSE BONUS | 0 | 17 | 0 | 0 | 0 | 0 |  | DO |  | 0
01DO | 01 | E1V07 | 44023115201 | 2022-09-15 | QTR1 | 22/23 | 1 | 3 | 75 | 75 | 72 | 3 | 0 | 0 | 0 | 0 | 289419 | 14419 | 275000 | 311381 | 315649 | 0 | 0 | 0 | 315649 | 315649 | 0 | 21962 | 0 | 0 | 0 | 6636 | 0 | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28598 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2023-08-09 | QTR1 | 23/24 | 2023-03-29 | QTR3 | 22/23 | 118 | 331704.75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2703 | 21272425201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 550 | 719 | 968 | -249 | 249 | 0 | 169 | 0 | 11717625 | 120 | 11717505 | 11666748 | 11573612 | -1206768 | 0 | -1206768 | 10366844 | 10334162 | -32682 | -50877 | 123 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50877 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 | 2021-05-03 | QTR4 | 20/21 | 209 | 12539660.43 |  |  | 0 | 46 | 0 | 0 | -68877 | 0 |  | CO
02CO | 02 | T2725 | 42307145201 | 2018-12-05 | QTR2 | 18/19 | 1 | 5 | 300 | 737 | 737 | 0 | 0 | 0 | 181 | 256 | 7294444 | 68754 | 7225690 | 7636147 | 7798283 | 0 | 0 | 0 | 7798283 | 7754246 | -44037 | 341703 | 85 | 0 | 27 | 92502 | 0 | 0 | 229 | 220039 | 17548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4989 | 0 | 0 | 0 | 6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 256 | 330105 | 23598 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2021-06-17 | QTR4 | 20/21 | 214 | 7079691.78 |  |  | 244 | 96 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2749 | 43946715201 | 2019-09-25 | QTR1 | 19/20 | 3 | 10 | 600 | 1149 | 1149 | 0 | 0 | 0 | 265 | 284 | 11950705 | 126323 | 11824382 | 12606239 | 12535468 | 0 | 0 | 0 | 12535468 | 12707911 | 309266 | 655533 | 237 | 0 | 39 | 488108 | 0 | 0 | 59 | 227908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 4468 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 726457 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-28 | QTR1 | 23/24 | 2023-02-27 | QTR3 | 22/23 | 208 | 11844644.47 |  |  | 166 | 108 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 329791 | 87098 | 104 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-11-17 | QTR2 | 23/24 | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2787 | 44105915201 | 2020-07-29 | QTR1 | 20/21 | 1 | 2 | 250 | 376 | 373 | 3 | 0 | 0 | 81 | 45 | 13904803 | 145464 | 13759339 | 14427901 | 14501738 | 0 | 0 | 0 | 14501738 | 14430355 | -71383 | 523099 | 59 | 0 | 45 | 523099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 523099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-16 | QTR2 | 23/24 | 2021-09-15 | QTR1 | 21/22 | 209 | 14722615.57 |  |  | 15 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2788 | 44258115201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 240 | 516 | 513 | 3 | 0 | 0 | 220 | 56 | 7945667 | 68632 | 7877035 | 7945667 | 8114839 | 0 | 0 | 0 | 8114839 | 8571019 | 459557 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 56 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-16 | QTR2 | 23/24 | 2022-07-07 | QTR1 | 22/23 | 209 | 6919711.56 |  |  | 56 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2802 | 43575715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 180 | 523 | 523 | 0 | 0 | 0 | 29 | 314 | 1262262 | 50000 | 1212262 | 1262262 | 1249368 | 0 | 0 | 0 | 1249368 | 1249498 | 130 | 0 | 103 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2022-12-23 | QTR2 | 22/23 | 208 | 1338362.89 |  |  | 314 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2803 | 44126115201 | 2021-05-26 | QTR4 | 20/21 | 2 | 3 | 325 | 487 | 487 | 0 | 0 | 0 | 162 | 0 | 4633748 | 75000 | 4558748 | 3852057 | 3929376 | 0 | 0 | 0 | 3929376 | 4154909 | 225533 | -781691 | 40 | 30 | 0 | -739805 | 0 | 0 | 0 | 7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -732738 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2023-01-06 | QTR3 | 22/23 | 208 | 4540382.58 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2813 | 43617815201 | 2021-06-09 | QTR4 | 20/21 | 3 | 2 | 350 | 501 | 501 | 0 | 0 | 0 | 109 | 42 | 6155492 | 64024 | 6091468 | 6241492 | 6261727 | 0 | 0 | 0 | 6261727 | 6665942 | 404215 | 86000 | 72 | 0 | 42 | 61451 | 0 | 0 | 0 | 59384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 120835 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 | 2023-01-20 | QTR3 | 22/23 | 209 | 7776561.61 |  |  | 42 | 37 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2821 | 44327315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 150 | 289 | 271 | 18 | 0 | 0 | 118 | 21 | 4876894 | 52518 | 4824376 | 4984966 | 5022406 | 0 | 0 | 0 | 5022406 | 5415141 | 392735 | 108073 | 77 | 0 | 21 | 125561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31 | 21 | 125561 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 | 2022-10-13 | QTR2 | 22/23 | 216 | 5483810.94 |  |  | 6 | 10 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2822 | 44331315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 250 | 488 | 483 | 5 | 0 | 0 | 236 | 2 | 9173879 | 91638 | 9082241 | 9173879 | 9342688 | 0 | 0 | 0 | 9342688 | 9910699 | 568010 | 0 | 205 | 28 | 0 | 0 | 0 | 0 | 0 | 12476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 2 | 12476 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-03 | QTR2 | 23/24 | 2023-06-29 | QTR4 | 22/23 | 209 | 9935885.58 |  |  | 2 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2824 | 44327415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 2 | 250 | 455 | 453 | 2 | 0 | 0 | 190 | 15 | 3471681 | 50000 | 3421681 | 3603585 | 3475517 | 0 | 0 | 0 | 3475517 | 3614982 | 141674 | 131904 | 166 | 0 | 0 | 14150 | 0 | 0 | 15 | 130039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 15 | 146399 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-05-04 | QTR4 | 22/23 | 216 | 3836185.04 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2825 | 44328215201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 75 | 125 | 124 | 1 | 0 | 0 | 10 | 40 | 698919 | 27456 | 671464 | 698919 | 656099 | 0 | 0 | 0 | 656099 | 656099 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-14 | QTR1 | 23/24 | 2022-06-28 | QTR4 | 21/22 | 209 | 629198.54 |  |  | 40 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2826 | 44331115201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 220 | 264 | 264 | 0 | 0 | 0 | 44 | 0 | 8657266 | 87492 | 8569774 | 8657266 | 8107793 | 0 | 0 | 0 | 8107793 | 8099899 | -7895 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-29 | QTR1 | 23/24 | 2023-05-05 | QTR4 | 22/23 | 209 | 10016766.94 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2829 | 44120815201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 150 | 227 | 224 | 3 | 0 | 0 | 48 | 29 | 1047740 | 50000 | 997740 | 1047740 | 1004140 | 0 | 0 | 0 | 1004140 | 1004137 | -3 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-10-03 | QTR2 | 23/24 | 2023-06-01 | QTR4 | 22/23 | 208 | 1984965.49 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2833 | 44325815201 | 2022-01-12 | QTR3 | 21/22 | 1 | 0 | 210 | 235 | 235 | 0 | 0 | 0 | 25 | 0 | 6173212 | 71171 | 6102041 | 6173212 | 6149692 | 0 | 0 | 0 | 6149692 | 6808147 | 658455 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2022-11-23 | QTR2 | 22/23 | 214 | 7484487.76 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2836 | 44325915201 | 2022-02-23 | QTR3 | 21/22 | 2 | 2 | 210 | 287 | 287 | 0 | 0 | 0 | 72 | 5 | 4069827 | 50000 | 4019827 | 4084043 | 4107794 | 0 | 0 | 0 | 4107794 | 4236681 | 130239 | 14216 | 19 | 0 | 0 | 0 | 0 | 34 | 0 | 12864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 14216 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-02 | QTR2 | 23/24 | 2023-04-17 | QTR4 | 22/23 | 208 | 5072861.67 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2837 | 44329415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 0 | 180 | 262 | 260 | 2 | 0 | 0 | 55 | 27 | 1371850 | 50000 | 1321850 | 1371850 | 1320562 | 0 | 0 | 0 | 1320562 | 1320562 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 | 2023-01-19 | QTR3 | 22/23 | 208 | 1352767.24 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2846 | 44126015201 | 2022-01-12 | QTR3 | 21/22 | 2 | 1 | 300 | 413 | 418 | -5 | 5 | 0 | 113 | 0 | 9551621 | 106078 | 9445543 | 9552942 | 9869457 | -18930 | 0 | -18930 | 9850527 | 10484168 | 634962 | 1321 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 1184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2504 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-11-02 | QTR2 | 23/24 | 2023-05-25 | QTR4 | 22/23 | 208 | 11919284.18 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2855 | 43935815201 | 2021-06-09 | QTR4 | 20/21 | 2 | 0 | 350 | 464 | 459 | 5 | 0 | 0 | 86 | 28 | 7918962 | 100000 | 7818962 | 7918962 | 7962203 | 0 | 0 | 0 | 7962203 | 8267055 | 304853 | 0 | 42 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 | 2023-02-23 | QTR3 | 22/23 | 209 | 7233767.77 |  |  | 28 | 44 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2857 | 44721115201 | 2022-01-26 | QTR3 | 21/22 | 1 | 0 | 120 | 193 | 185 | 8 | 0 | 0 | 27 | 46 | 1077522 | 44955 | 1032567 | 1077522 | 1075156 | 0 | 0 | 0 | 1075156 | 1075156 | 0 | 0 | 16 | 0 | 30 | 18350 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 18350 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2022-10-14 | QTR2 | 22/23 | 208 | 1339271.36 |  |  | 46 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2869 | 43567925201 | 2022-06-08 | QTR4 | 21/22 | 2 | 0 | 180 | 199 | 178 | 21 | 0 | 0 | 19 | 0 | 1298306 | 50000 | 1248306 | 1298306 | 1209436 | 0 | 0 | 0 | 1209436 | 1209097 | -339 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 | 2023-04-19 | QTR4 | 22/23 | 209 | 1554775.94 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2873 | 44557615201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 90 | 90 | 19 | 71 | 0 | 0 | 0 | 0 | 240110 | 17791 | 222319 | 240110 | 185940 | 0 | 0 | 0 | 185940 | 185940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-03-31 | QTR3 | 22/23 | 208 | 402519.71 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2875 | 44912925201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 60 | 160 | 160 | 0 | 0 | 0 | 69 | 31 | 1386562 | 50000 | 1336562 | 1386562 | 1349510 | 0 | 0 | 0 | 1349510 | 1349510 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-30 | QTR2 | 23/24 | 2023-03-14 | QTR3 | 22/23 | 208 | 1705476.65 |  |  | 31 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2877 | 20954355201 | 2022-06-15 | QTR4 | 21/22 | 2 | 3 | 90 | 144 | 140 | 4 | 0 | 0 | 47 | 7 | 744369 | 43296 | 701073 | 788349 | 712669 | 0 | 0 | 0 | 712669 | 709731 | 0 | 43980 | 10 | 0 | 0 | 0 | 0 | 0 | 7 | 41042 | 41042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7 | 43980 | 41042 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-07 | QTR2 | 23/24 | 2023-01-24 | QTR3 | 22/23 | 208 | 931264.85 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2923 | 44542625201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 74 | 101 | 94 | 7 | 0 | 0 | 26 | 1 | 212969 | 11187 | 201781 | 212969 | 198096 | 0 | 0 | 0 | 198096 | 198096 | 0 | 0 | 15 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-09-05 | QTR1 | 23/24 | 2023-03-01 | QTR3 | 22/23 | 208 | 251711.77 |  |  | 1 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9023 | 44624515223 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 250 | 733 | 730 | 3 | 0 | 0 | 483 | 0 | 3516622 | 50000 | 3466622 | 3516622 | 3642093 | 0 | 0 | 0 | 3642093 | 3642131 | 38 | 0 | 14 | 420 | 0 | 0 | 0 | 0 | 0 | 30591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 41498 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-09-27 | QTR1 | 23/24 | 2023-08-03 | QTR1 | 23/24 | 209 | 3117936.11 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E2Y76 | 20972255201 | 2020-04-15 | QTR4 | 19/20 | 2 | 2 | 400 | 967 | 967 | 0 | 0 | 0 | 259 | 308 | 4399943 | 50000 | 4349943 | 4455060 | 4448788 | 0 | 0 | 0 | 4448788 | 4443671 | 52479 | 55117 | 115 | 0 | 246 | 22225 | 0 | 0 | 0 | 56531 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 83873 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2023-11-28 | QTR2 | 23/24 | 2023-07-24 | QTR1 | 23/24 | 208 | 4855272.24 |  |  | 308 | 144 | 0 | 0 | 0 | 0 |  | DO
03CO | 03 | T3579 | 41413245201 | 2016-08-31 | QTR1 | 16/17 | 3 | 19 | 1090 | 1999 | 2171 | -172 | 172 | 0 | 798 | 111 | 42140000 | 150000 | 41990000 | 43136516 | 44789798 | -789688 | 0 | -789688 | 44000110 | 45150067 | 1313007 | 996516 | 442 | 4 | 40 | 380492 | 1569 | 0 | 27 | 349096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 8 | 165208 | 0 | 0 | 0 | 18045 | 18045 | 0 | 0 | 0 | 0 | 0 | 0 | 50586 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 121 | 898999 | 114614 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2022-10-21 | QTR2 | 22/23 | 308 | 37004160.16 |  |  | 38 | 212 | 0 | 0 | -159429 | 0 |  | CO
03CO | 03 | T3598 | 43357725201 | 2021-12-08 | QTR2 | 21/22 | 2 | 0 | 210 | 314 | 314 | 0 | 0 | 0 | 104 | 0 | 1449372 | 9292 | 1440080 | 1449372 | 1245314 | 0 | 0 | 0 | 1245314 | 1245462 | 147 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-01-13 | QTR3 | 22/23 | 308 | 1387512.95 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3604 | 43282815201 | 2019-02-27 | QTR3 | 18/19 | 2 | 4 | 925 | 1322 | 1301 | 21 | 0 | 0 | 397 | 0 | 10228411 | 103267 | 10125144 | 10251581 | 10265075 | 0 | 0 | 0 | 10265075 | 10328004 | 62929 | 23170 | 263 | 0 | 0 | 24478 | 0 | 0 | 0 | 5148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 120 | 68927 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2022-12-06 | QTR2 | 22/23 | 308 | 10230057.88 |  |  | 0 | 84 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3664 | 43375115201 | 2021-06-09 | QTR4 | 20/21 | 4 | 1 | 185 | 509 | 508 | 1 | 0 | 0 | 275 | 49 | 2044978 | 50000 | 1994978 | 2045473 | 1900355 | 0 | 0 | 0 | 1900355 | 1888581 | -11773 | 495 | 40 | 0 | 0 | 0 | 0 | 80 | 49 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 170 | 49 | 495 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-03-03 | QTR3 | 22/23 | 313 | 2066195.42 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3691 | 43717815201 | 2020-11-18 | QTR2 | 20/21 | 1 | 2 | 480 | 640 | 661 | -21 | 21 | 0 | 160 | 0 | 4269226 | 50000 | 4219226 | 4374816 | 4363593 | -30948 | 0 | -30948 | 4332645 | 4394715 | 138599 | 105591 | 98 | 8 | 0 | 95913 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 23399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 149628 | 0 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 | 2022-12-04 | QTR2 | 22/23 | 308 | 4154505.73 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3703 | 43649925201 | 2019-09-25 | QTR1 | 19/20 | 3 | 0 | 150 | 292 | 262 | 30 | 0 | 0 | 112 | 30 | 2458081 | 51140 | 2406941 | 2458081 | 2572160 | 0 | 0 | 0 | 2572160 | 2554701 | -17459 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2020-10-02 | QTR2 | 20/21 | 314 | 2031385.77 |  |  | 30 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3704 | 43938815201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 150 | 222 | 220 | 2 | 0 | 0 | 72 | 0 | 1462111 | 0 | 1462111 | 1462111 | 1360760 | 0 | 0 | 0 | 1360760 | 1370361 | 9601 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 | 2022-10-07 | QTR2 | 22/23 | 313 | 1750125.19 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3728 | 21898425201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 420 | 706 | 706 | 0 | 0 | 0 | 286 | 0 | 5503848 | 53988 | 5449859 | 5503848 | 5615605 | 0 | 0 | 0 | 5615605 | 5632695 | 85241 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2023-10-30 | QTR2 | 23/24 | 2023-07-24 | QTR1 | 23/24 | 314 | 7823905.33 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 1 | 365 | 689 | 689 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6166449 | 6679471 | 0 | 0 | 0 | 6679471 | 7791843 | 1176465 | 0 | 170 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 100 | 21 | 67784 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29 |  |  | 21 | 89 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3743 | 44173015201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 45 | 83 | 80 | 3 | 0 | 0 | 38 | 0 | 187229 | 12274 | 174955 | 187229 | 175598 | 0 | 0 | 0 | 175598 | 166353 | -9245 | 0 | 35 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2020-08-14 | QTR1 | 20/21 | 314 | 262871.46 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3750 | 43811125201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 95 | 131 | 130 | 1 | 0 | 0 | 36 | 0 | 987732 | 41493 | 946239 | 927591 | 903555 | 0 | 0 | 0 | 903555 | 903555 | 0 | -60141 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-05-12 | QTR4 | 22/23 | 314 | 912225.16 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3759 | 44014915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 11 | 454 | 705 | 664 | 41 | 0 | 0 | 187 | 64 | 6899119 | 54298 | 6844821 | 7276831 | 6961458 | 0 | 0 | 0 | 6961458 | 7377187 | 425549 | 377713 | 82 | 0 | 28 | 279407 | 0 | 4 | 36 | -2323 | 6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 44 | 64 | 278484 | 6394 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 | 2023-04-26 | QTR4 | 22/23 | 314 | 5086089.54 |  |  | 26 | 61 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3784 | 43938515201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 100 | 119 | 100 | 19 | 0 | 0 | 19 | 0 | 830333 | 0 | 830333 | 830333 | 808692 | 0 | 0 | 0 | 808692 | 808692 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 | 2023-08-01 | QTR1 | 23/24 | 313 | 771890.7 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3793 | 43467715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 3 | 230 | 481 | 480 | 1 | 0 | 0 | 236 | 15 | 6283852 | 73669 | 6210183 | 6727204 | 6844151 | 0 | 0 | 0 | 6844151 | 7176797 | 332646 | 443352 | 186 | 0 | 7 | 378034 | 0 | 0 | 8 | 133625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | -51237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 15 | 460422 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2023-06-28 | QTR4 | 22/23 | 308 | 7460138.28 |  |  | 1 | 50 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3794 | 44364415201 | 2022-06-15 | QTR4 | 21/22 | 1 | 1 | 100 | 125 | 92 | 33 | 0 | 0 | 25 | 0 | 2537432 | 50000 | 2487432 | 2537432 | 2741257 | 0 | 0 | 0 | 2741257 | 2721406 | -19851 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-03-06 | QTR3 | 22/23 | 313 | 2975156.64 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3800 | 44851815201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 140 | 252 | 239 | 13 | 0 | 0 | 90 | 22 | 3545980 | 0 | 3545980 | 3707781 | 3707779 | 0 | 0 | 0 | 3707779 | 3707779 | 0 | 161801 | 35 | 0 | 22 | 93590 | 0 | 49 | 0 | 68210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 22 | 161801 | 0 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-10-30 | QTR2 | 23/24 | 2023-08-28 | QTR1 | 23/24 | 308 | 3713438.76 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3810 | 44365015201 | 2022-01-26 | QTR3 | 21/22 | 1 | 1 | 270 | 474 | 472 | 2 | 0 | 0 | 156 | 48 | 10527718 | 106380 | 10421339 | 10784785 | 11111656 | 0 | 0 | 0 | 11111656 | 11389685 | 278029 | 257067 | 87 | 5 | 0 | 0 | 0 | 0 | 48 | 274363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 48 | 274363 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 | 2023-08-02 | QTR1 | 23/24 | 313 | 10728439.32 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3817 | 44387515201 | 2022-08-31 | QTR1 | 22/23 | 1 | 2 | 60 | 246 | 246 | 0 | 0 | 0 | 156 | 30 | 535084 | 0 | 535084 | 538384 | 583904 | 0 | 0 | 0 | 583904 | 580604 | 0 | 3300 | 165 | 0 | 0 | 0 | 0 | 0 | 30 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 30 | 3300 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-08-02 | QTR1 | 23/24 | 313 | 438194 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3823 | 44565615201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 110 | 120 | 86 | 34 | 0 | 0 | 10 | 0 | 2199429 | 50000 | 2149429 | 2199429 | 2316440 | 0 | 0 | 0 | 2316440 | 2316440 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 | 2023-06-22 | QTR4 | 22/23 | 308 | 2955598 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3825 | 44565715201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 89 | 101 | 67 | 34 | 0 | 0 | 12 | 0 | 1398733 | 50000 | 1348733 | 1398733 | 1268603 | 0 | 0 | 0 | 1268603 | 1268603 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-08-21 | QTR1 | 23/24 | 321 | 2259061 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3828 | 44404415201 | 2022-02-23 | QTR3 | 21/22 | 1 | 0 | 90 | 183 | 168 | 15 | 0 | 0 | 93 | 0 | 1388656 | 50000 | 1338656 | 1388656 | 1401865 | 0 | 0 | 0 | 1401865 | 1401865 | 0 | 0 | 53 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F432094655 | H.G. CONSTRUCTION DEVELOPMENT & INVESTM | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2022-10-26 | QTR2 | 22/23 | 313 | 1545933 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3830 | 43256615201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 180 | 290 | 288 | 2 | 0 | 0 | 110 | 0 | 3353932 | 50000 | 3303932 | 3353932 | 3387610 | 0 | 0 | 0 | 3387610 | 3371222 | -16388 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-07-16 | QTR1 | 23/24 | 308 | 3164048.08 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3833 | 44560315201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 44 | 49 | 45 | 4 | 0 | 0 | 5 | 0 | 192351 | 8394 | 183958 | 192351 | 176477 | 0 | 0 | 0 | 176477 | 176477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2022-12-22 | QTR2 | 22/23 | 308 | 173499.64 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3836 | 43974415201 | 2022-10-05 | QTR2 | 22/23 | 1 | 0 | 169 | 238 | 238 | 0 | 0 | 0 | 69 | 0 | 4469056 | 50000 | 4419056 | 4469056 | 4076218 | 0 | 0 | 0 | 4076218 | 3952664 | -123554 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2023-08-21 | QTR1 | 23/24 | 314 | 6832323.6 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9024 | 44199335223 | 2021-04-28 | QTR4 | 20/21 | 1 | 2 | 250 | 622 | 620 | 2 | 0 | 0 | 372 | 0 | 3198515 | 50000 | 3148515 | 3289097 | 3304055 | 0 | 0 | 0 | 3304055 | 3304055 | 39515 | 90582 | 322 | 90 | 0 | 6000 | 0 | 90 | 0 | 49780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 58960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 300 | 0 | 126040 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 | 2023-06-08 | QTR4 | 22/23 | 314 | 3552350.22 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9027 | 44531315215 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 60 | 71 | 71 | 0 | 0 | 0 | 11 | 0 | 564819 | 36905 | 527914 | 564819 | 524793 | 0 | 0 | 0 | 524793 | 524793 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2022-05-13 | QTR4 | 21/22 | 306 | 932089.13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3S70 | 43992635201 | 2021-05-13 | QTR4 | 20/21 | 2 | 1 | 395 | 597 | 597 | 0 | 0 | 0 | 202 | 0 | 8497804 | 70195 | 8427609 | 8518932 | 8878921 | 0 | 0 | 0 | 8878921 | 8997063 | 136935 | 21128 | 102 | 0 | 0 | 12464 | 0 | 30 | 0 | 28861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 96 | 0 | 41325 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 | 2023-03-30 | QTR3 | 22/23 | 321 | 7939245.14 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U04 | 21904225201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 65 | 65 | 45 | 20 | 0 | 0 | 0 | 0 | 278090 | 21110 | 256980 | 278090 | 249120 | 0 | 0 | 0 | 249120 | 249120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2023-05-18 | QTR4 | 22/23 | 314 | 454253.61 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U32 | 42187425201 | 2022-01-13 | QTR3 | 21/22 | 1 | 0 | 45 | 55 | 52 | 3 | 0 | 0 | 10 | 0 | 109495 | 5918 | 103577 | 109495 | 105102 | 0 | 0 | 0 | 105102 | 105102 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2022-06-09 | QTR4 | 21/22 | 308 | 135676.68 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U47 | 44158915201 | 2021-11-10 | QTR2 | 21/22 | 2 | 3 | 285 | 527 | 526 | 1 | 0 | 0 | 242 | 0 | 6190992 | 53456 | 6137537 | 6194018 | 6101074 | -18750 | 0 | -18750 | 6082324 | 6229251 | 146927 | 3025 | 162 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 0 | 3025 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 | 2023-08-02 | QTR1 | 23/24 | 308 | 5430315.21 |  |  | 0 | 71 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U84 | 44365915201 | 2022-02-10 | QTR3 | 21/22 | 2 | 1 | 175 | 266 | 264 | 2 | 0 | 0 | 91 | 0 | 3254371 | 50000 | 3204371 | 3263484 | 3285954 | 0 | 0 | 0 | 3285954 | 3378196 | 92242 | 9113 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-02-18 | QTR3 | 22/23 | 308 | 3044605.63 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V33 | 44891315201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 75 | 80 | 53 | 27 | 0 | 0 | 5 | 0 | 223976 | 14236 | 209740 | 223976 | 187027 | 0 | 0 | 0 | 187027 | 187027 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-06-01 | QTR4 | 22/23 | 308 | 298951.28 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V90 | 44575815201 | 2023-01-12 | QTR3 | 22/23 | 1 | 1 | 70 | 78 | 77 | 1 | 0 | 0 | 8 | 0 | 1499653 | 50000 | 1449653 | 1499653 | 1534493 | 0 | 0 | 0 | 1534493 | 1534493 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-10-02 | QTR2 | 23/24 | 2023-06-27 | QTR4 | 22/23 | 308 | 1524311.21 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4552 | 43696215201 | 2020-05-20 | QTR4 | 19/20 | 2 | 14 | 642 | 1093 | 1084 | 9 | 0 | 0 | 445 | 6 | 26406739 | 150000 | 26256739 | 27530140 | 27615738 | 0 | 0 | 0 | 27615738 | 28097247 | 1507029 | 1123402 | 284 | 0 | 0 | 40935 | 0 | 110 | 0 | 428405 | 32084 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223929 | 0 | 0 | 0 | 320493 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 11175 | 0 | 0 | 0 | 308488 | 0 | 0 | 6 | 42593 | 42593 | 23 | 0 | 0 | 0 | 280 | 6 | 1272542 | 74677 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-09-08 | QTR1 | 23/24 | 412 | 27323787.5 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4562 | 43177035201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 384 | 492 | 492 | 0 | 0 | 0 | 108 | 0 | 3588218 | 50000 | 3538218 | 3660295 | 3546957 | 0 | 0 | 0 | 3546957 | 3613971 | 67014 | 72077 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 91148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14596 | 0 | 0 | 0 | 94541 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2023-03-31 | QTR3 | 22/23 | 412 | 3732217.16 |  |  | 0 | 37 | 0 | 0 | -11203 | 0 |  | CO
04CO | 04 | T4567 | 43839415201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 388 | 574 | 574 | 0 | 0 | 0 | 186 | 0 | 2505478 | 50000 | 2455478 | 2517687 | 2397524 | 0 | 0 | 0 | 2397524 | 2420702 | 167234 | 12209 | 70 | 0 | 0 | 10842 | 0 | 0 | 0 | 23398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6534 | 0 | 0 | 0 | 1247 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 8119 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 50141 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-10-03 | QTR2 | 23/24 | 2023-06-08 | QTR4 | 22/23 | 409 | 2223138.08 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4571 | 43839515201 | 2021-01-27 | QTR3 | 20/21 | 2 | 5 | 575 | 701 | 701 | 0 | 0 | 0 | 126 | 0 | 2029422 | 50000 | 1979422 | 2048533 | 1920549 | 0 | 0 | 0 | 1920549 | 1968644 | 49459 | 19111 | 81 | 0 | 0 | 1911 | 0 | 0 | 0 | 3545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17675 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-06-16 | QTR4 | 22/23 | 409 | 2213111.22 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4572 | 43838415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 454 | 621 | 611 | 10 | 0 | 0 | 167 | 0 | 2952231 | 50000 | 2902231 | 2953979 | 2876141 | 0 | 0 | 0 | 2876141 | 2874393 | 28318 | 1748 | 122 | 0 | 0 | 7776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 9524 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-07-24 | QTR1 | 23/24 | 409 | 3045126.89 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4573 | 43206675201 | 2021-07-28 | QTR1 | 21/22 | 2 | 3 | 195 | 470 | 465 | 5 | 0 | 0 | 275 | 0 | 3496673 | 50000 | 3446673 | 3721036 | 3515537 | 0 | 0 | 0 | 3515537 | 3603841 | 88304 | 224363 | 249 | 0 | 0 | -2094 | 0 | 0 | 0 | 267470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 265376 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 | 2023-04-19 | QTR4 | 22/23 | 412 | 3657623.88 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4594 | 43999015201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 212 | 352 | 351 | 1 | 0 | 0 | 140 | 0 | 2000000 | 50000 | 1950000 | 2008938 | 1868868 | 0 | 0 | 0 | 1868868 | 1862040 | 2110 | 8938 | 85 | 0 | 0 | 11450 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 20388 | 0 | F650814419 | ZAHLENE ENTERPRISES INC. | N/A | N/A | N/A | N/A | 2023-07-24 | QTR1 | 23/24 | 2023-05-31 | QTR4 | 22/23 | 412 | 2421037.86 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4597 | 44177515201 | 2022-01-26 | QTR3 | 21/22 | 2 | 1 | 178 | 274 | 274 | 0 | 0 | 0 | 96 | 0 | 957661 | 40792 | 916869 | 958736 | 900445 | 0 | 0 | 0 | 900445 | 899370 | 0 | 1075 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 8111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 9186 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-05-11 | QTR4 | 22/23 | 409 | 927528.71 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4603 | 44157815201 | 2022-03-30 | QTR3 | 21/22 | 3 | 0 | 229 | 338 | 338 | 0 | 0 | 0 | 109 | 0 | 2249738 | 50000 | 2199738 | 2249738 | 2253443 | 0 | 0 | 0 | 2253443 | 2251225 | -2218 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-09 | QTR2 | 23/24 | 2023-08-09 | QTR1 | 23/24 | 412 | 2503871.57 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4607 | 43999315201 | 2022-03-30 | QTR3 | 21/22 | 3 | 1 | 222 | 287 | 287 | 0 | 0 | 0 | 65 | 0 | 1967721 | 50000 | 1917721 | 1967721 | 1856962 | 0 | 0 | 0 | 1856962 | 1856374 | 2046 | 2634 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-09-18 | QTR1 | 23/24 | 2023-04-30 | QTR4 | 22/23 | 412 | 2135578.09 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4614 | 44399415201 | 2022-04-27 | QTR4 | 21/22 | 2 | 3 | 227 | 321 | 321 | 0 | 0 | 0 | 94 | 0 | 4491996 | 50000 | 4441996 | 4563991 | 4393362 | 0 | 0 | 0 | 4393362 | 4376466 | -6110 | 71995 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 86648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51997 | 0 | 0 | 0 | 5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10786 | 0 | 0 | 0 | 33274 | 33274 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 83947 | 33274 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-06-14 | QTR4 | 22/23 | 409 | 4062646.65 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4629 | 44562315201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 122 | 125 | 107 | 18 | 0 | 0 | 5 | 0 | 1050673 | 49045 | 1001629 | 1050673 | 985015 | 0 | 0 | 0 | 985015 | 985015 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-06 | QTR2 | 23/24 | 2023-10-30 | QTR2 | 23/24 | 409 | 1029940.35 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4T68 | 44074615201 | 2020-05-06 | QTR4 | 19/20 | 6 | 1 | 730 | 939 | 934 | 5 | 0 | 0 | 209 | 0 | 17557323 | 125751 | 17431572 | 17588765 | 16726429 | 0 | 0 | 0 | 16726429 | 16980455 | 254025 | 31442 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31442 | 0 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37742 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-02-02 | QTR3 | 22/23 | 412 | 12972092.8 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U99 | 44146215201 | 2021-05-07 | QTR4 | 20/21 | 1 | 8 | 228 | 525 | 518 | 7 | 0 | 0 | 188 | 109 | 12200214 | 101674 | 12098540 | 13805766 | 14066534 | 0 | 0 | 0 | 14066534 | 14068003 | 140138 | 1605552 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 1129185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 448054 | 0 | 0 | 0 | 23731 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 109 | 1600970 | 0 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-06-23 | QTR4 | 22/23 | 412 | 10374505.8 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V19 | 43215215201 | 2022-01-07 | QTR3 | 21/22 | 1 | 0 | 307 | 326 | 171 | 155 | 0 | 0 | 19 | 0 | 2335539 | 50000 | 2285539 | 2335539 | 2159702 | 0 | 0 | 0 | 2159702 | 2159702 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-11-20 | QTR2 | 23/24 | 2023-10-25 | QTR2 | 23/24 | 409 | 4011283.36 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V55 | 44359415201 | 2022-05-06 | QTR4 | 21/22 | 1 | 1 | 127 | 224 | 221 | 3 | 0 | 0 | 97 | 0 | 895596 | 50000 | 845596 | 965406 | 917671 | 0 | 0 | 0 | 917671 | 917671 | 0 | 69810 | 62 | 0 | 0 | 69810 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 69810 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 | 2023-07-15 | QTR1 | 23/24 | 412 | 1122910.5 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V75 | 44172215201 | 2022-02-04 | QTR3 | 21/22 | 2 | 4 | 156 | 248 | 248 | 0 | 0 | 0 | 92 | 0 | 1455255 | 50000 | 1405255 | 1515282 | 1451281 | 0 | 0 | 0 | 1451281 | 1452112 | 7917 | 60027 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 76040 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 85192 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-09-01 | QTR1 | 23/24 | 2023-03-28 | QTR3 | 22/23 | 409 | 1403378.89 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V84 | 44609715201 | 2022-09-02 | QTR1 | 22/23 | 1 | 1 | 133 | 180 | 179 | 1 | 0 | 0 | 47 | 0 | 3147147 | 50000 | 3097147 | 3153188 | 2965886 | 0 | 0 | 0 | 2965886 | 2896248 | -69638 | 6041 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-08-03 | QTR1 | 23/24 | 409 | 3652108.96 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W04 | 45059015201 | 2022-06-14 | QTR4 | 21/22 | 1 | 0 | 182 | 209 | 209 | 0 | 0 | 0 | 27 | 0 | 1468626 | 50000 | 1418626 | 1468626 | 1421948 | 0 | 0 | 0 | 1421948 | 1421948 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2023-11-20 | QTR2 | 23/24 | 2023-10-25 | QTR2 | 23/24 | 408 | 2551166.8 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5552 | 40714345201 | 2016-06-08 | QTR4 | 15/16 | 21 | 32 | 1050 | 1826 | 1829 | -3 | 3 | 0 | 359 | 417 | 75824482 | 160000 | 75664482 | 86884143 | 89837352 | 0 | 0 | 0 | 89837352 | 90458012 | 815723 | 10910761 | 209 | 0 | 13 | 563442 | 81716 | 0 | 113 | 3719605 | 1534190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | -46035 | 0 | 0 | 0 | 107943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189623 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 417 | 10835624 | 1823881 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2021-10-13 | QTR2 | 21/22 | 509 | 88197361.71 | B2:B2:B5:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B/BONUS | 0 | 150 | 0 | 0 | -106929 | 0 |  | CO
05CO | 05 | T5733 | 44381515201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 290 | 440 | 439 | 1 | 0 | 0 | 130 | 20 | 7387943 | 81000 | 7306943 | 7578305 | 6929112 | 0 | 0 | 0 | 6929112 | 7638830 | 716998 | 190361 | 50 | 0 | 20 | 183081 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 190361 | 436 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2023-04-17 | QTR4 | 22/23 | 513 | 8754090.28 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5737 | 44288115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 140 | 343 | 342 | 1 | 0 | 0 | 203 | 0 | 1605048 | 49058 | 1555990 | 1606653 | 1573163 | 0 | 0 | 0 | 1573163 | 1576898 | 3735 | 1605 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-11-30 | QTR2 | 23/24 | 2023-07-21 | QTR1 | 23/24 | 514 | 1288583.85 |  |  | 0 | 137 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5738 | 44290915201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 270 | 349 | 349 | 0 | 0 | 0 | 79 | 0 | 9861239 | 100000 | 9761239 | 9880239 | 9803603 | 0 | 0 | 0 | 9803603 | 10869062 | 1065459 | 19000 | 40 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24350 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-02-28 | QTR3 | 22/23 | 514 | 13653415.96 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5763 | 44569015201 | 2022-08-31 | QTR1 | 22/23 | 2 | 1 | 139 | 176 | 176 | 0 | 0 | 0 | 37 | 0 | 1690095 | 50000 | 1640095 | 1690972 | 1630216 | 0 | 0 | 0 | 1630216 | 1601935 | -27404 | 877 | 28 | 0 | 0 | 20792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21668 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 | 2023-09-11 | QTR1 | 23/24 | 513 | 2378838.75 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5765 | 43759625201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 190 | 217 | 198 | 19 | 0 | 0 | 27 | 0 | 1068776 | 38700 | 1030076 | 1068776 | 1003835 | 0 | 0 | 0 | 1003835 | 1003807 | -28 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263013168 | MEJIA INTERNATIONAL GROUP CORPORATION | N/A | N/A | N/A | N/A | 2023-10-13 | QTR2 | 23/24 | 2023-08-29 | QTR1 | 23/24 | 512 | 1065459.45 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50B4 | 44290615201 | 2022-07-06 | QTR1 | 22/23 | 1 | 1 | 200 | 317 | 317 | 0 | 0 | 0 | 103 | 14 | 3079406 | 50000 | 3029406 | 3129406 | 3205711 | 0 | 0 | 0 | 3205711 | 3130395 | -75316 | 50000 | 26 | 0 | 0 | 3862 | 0 | 0 | 28 | 3528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 54904 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 | 2023-08-11 | QTR1 | 23/24 | 513 | 3825881.85 |  |  | 14 | 77 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51A9 | 44102015201 | 2020-09-01 | QTR1 | 20/21 | 1 | 7 | 280 | 534 | 544 | -10 | 10 | 0 | 225 | 29 | 7501367 | 72000 | 7429367 | 7798794 | 7531686 | -41316 | 0 | -41316 | 7490370 | 7740983 | 263750 | 297427 | 61 | 0 | 0 | 19197 | 0 | 0 | 29 | 278231 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 297427 | 5549 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2022-05-27 | QTR4 | 21/22 | 514 | 7321146.81 |  |  | 5 | 164 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53B6 | 43901715201 | 2022-09-07 | QTR1 | 22/23 | 1 | 0 | 220 | 261 | 166 | 95 | 0 | 0 | 41 | 0 | 1640053 | 50000 | 1590053 | 1640053 | 1539808 | 0 | 0 | 0 | 1539808 | 1539808 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-11-01 | QTR2 | 23/24 | 2023-09-15 | QTR1 | 23/24 | 514 | 2062514.65 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B3 | 44942415201 | 2022-12-06 | QTR2 | 22/23 | 1 | 0 | 150 | 187 | 187 | 0 | 0 | 0 | 37 | 0 | 950694 | 34728 | 915966 | 950694 | 969481 | 0 | 0 | 0 | 969481 | 969481 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 | 2023-09-14 | QTR1 | 23/24 | 509 | 729303.27 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B4 | 44942515201 | 2022-11-01 | QTR2 | 22/23 | 1 | 0 | 170 | 174 | 149 | 25 | 0 | 0 | 4 | 0 | 967737 | 42032 | 925705 | 967737 | 851103 | 0 | 0 | 0 | 851103 | 851002 | -101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-09-06 | QTR1 | 23/24 | 2023-07-10 | QTR1 | 23/24 | 514 | 882686.9 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A1 | 44343315201 | 2021-11-02 | QTR2 | 21/22 | 3 | 1 | 350 | 515 | 515 | 0 | 0 | 0 | 137 | 28 | 5312936 | 52636 | 5260300 | 5361981 | 5275495 | 0 | 0 | 0 | 5275495 | 5333592 | 107142 | 49045 | 81 | 0 | 0 | 2577 | 0 | 0 | 28 | 12635 | 2522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 81860 | 2522 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-12-22 | QTR2 | 23/24 | 2023-08-11 | QTR1 | 23/24 | 513 | 6332507.08 |  |  | 28 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A4 | 44113215201 | 2021-10-05 | QTR2 | 21/22 | 5 | 2 | 289 | 528 | 527 | 1 | 0 | 0 | 239 | 0 | 7424369 | 84545 | 7339824 | 7591181 | 7558842 | 0 | 0 | 0 | 7558842 | 7794728 | 394527 | 166812 | 75 | 0 | 0 | 15614 | 0 | 0 | 0 | 22253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222204 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-07-12 | QTR1 | 23/24 | 513 | 9276735.05 |  |  | 0 | 164 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59A9 | 43913015201 | 2022-01-04 | QTR3 | 21/22 | 1 | 0 | 140 | 248 | 246 | 2 | 0 | 0 | 83 | 25 | 679529 | 24250 | 655279 | 679529 | 677096 | 0 | 0 | 0 | 677096 | 677187 | 92 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1848 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-06-08 | QTR4 | 22/23 | 514 | 681570.8 |  |  | 25 | 34 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6496 | 44182715201 | 2021-03-31 | QTR3 | 20/21 | 5 | 5 | 218 | 318 | 318 | 0 | 0 | 0 | 100 | 0 | 5245136 | 63284 | 5181852 | 5346913 | 5060388 | 0 | 0 | 0 | 5060388 | 5419442 | 359054 | 101776 | 49 | 0 | 0 | 49966 | 0 | 43 | 0 | -13886 | 12524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 40024 | 12524 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-12-20 | QTR2 | 23/24 | 2022-11-23 | QTR2 | 22/23 | 636 | 5969736.88 | B2:B2:B5:B5 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6505 | 43326435201 | 2020-08-26 | QTR1 | 20/21 | 4 | 2 | 350 | 382 | 376 | 6 | 0 | 0 | 32 | 0 | 4604161 | 51560 | 4552601 | 4652806 | 4445340 | -1 | 400000 | 399999 | 4845339 | 4484965 | -360374 | 48646 | 14 | 0 | 0 | 8472 | 0 | 0 | 0 | 7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25475 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-10-27 | QTR2 | 23/24 | 2022-02-11 | QTR3 | 21/22 | 636 | 4947288.63 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6513 | 43998615201 | 2022-03-30 | QTR3 | 21/22 | 3 | 2 | 240 | 265 | 220 | 45 | 0 | 0 | 25 | 0 | 2569128 | 50000 | 2519128 | 2717271 | 2543862 | 0 | 120000 | 120000 | 2663862 | 2540376 | -123486 | 148143 | 5 | 0 | 0 | 25836 | 0 | 0 | 0 | 105162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130998 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-06-14 | QTR4 | 22/23 | 636 | 2452591.81 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6515 | 43274845201 | 2022-03-30 | QTR3 | 21/22 | 3 | 2 | 240 | 257 | 221 | 36 | 0 | 0 | 17 | 0 | 2455465 | 50000 | 2405465 | 2510141 | 2443596 | 0 | 72000 | 72000 | 2515596 | 2440177 | -75419 | 54676 | 4 | 0 | 0 | 16029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68583 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-15 | QTR2 | 23/24 | 2023-07-14 | QTR1 | 23/24 | 636 | 2281095.15 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6516 | 43998115201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 360 | 474 | 464 | 10 | 0 | 0 | 114 | 0 | 4166383 | 50000 | 4116383 | 4219775 | 4110877 | 0 | 0 | 0 | 4110877 | 4270005 | 159128 | 53392 | 87 | 0 | 0 | 31602 | 0 | 0 | 0 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77149 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-15 | QTR2 | 23/24 | 2023-06-30 | QTR4 | 22/23 | 613 | 4661947.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6518 | 42918635201 | 2021-12-08 | QTR2 | 21/22 | 5 | 2 | 300 | 332 | 272 | 60 | 0 | 0 | 32 | 0 | 2919079 | 50000 | 2869079 | 2940250 | 2881342 | 0 | 210000 | 210000 | 3091342 | 2942048 | -146480 | 21171 | 17 | 0 | 0 | 16786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19600 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2023-04-22 | QTR4 | 22/23 | 613 | 3061117.05 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6519 | 43476835201 | 2022-01-26 | QTR3 | 21/22 | 3 | 1 | 300 | 347 | 274 | 73 | 0 | 0 | 47 | 0 | 3487287 | 50000 | 3437287 | 3497187 | 3509376 | 0 | 180000 | 180000 | 3689376 | 3539751 | -149625 | 9900 | 25 | 0 | 0 | 30134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47968 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2023-09-13 | QTR1 | 23/24 | 2023-07-05 | QTR1 | 23/24 | 613 | 3568827.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6N08 | 44196015201 | 2022-01-27 | QTR3 | 21/22 | 2 | 5 | 450 | 483 | 372 | 111 | 0 | 0 | 33 | 0 | 2813265 | 50000 | 2763265 | 2921577 | 2938675 | 0 | 0 | 0 | 2938675 | 2927754 | 65 | 108312 | 12 | 0 | 0 | 47426 | 0 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58312 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2023-10-17 | QTR2 | 23/24 | 2023-08-21 | QTR1 | 23/24 | 613 | 3044682.74 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N09 | 44480525201 | 2022-07-28 | QTR1 | 22/23 | 1 | 0 | 240 | 260 | 172 | 88 | 0 | 0 | 20 | 0 | 797552 | 50000 | 747552 | 797552 | 706126 | 0 | 0 | 0 | 706126 | 706126 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-08-11 | QTR1 | 23/24 | 2023-06-29 | QTR4 | 22/23 | 613 | 1509363.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N47 | 44445015201 | 2022-05-26 | QTR4 | 21/22 | 1 | 2 | 250 | 272 | 220 | 52 | 0 | 0 | 22 | 0 | 2697327 | 50000 | 2647327 | 2771657 | 2731695 | 0 | 180000 | 180000 | 2911695 | 2718704 | -192991 | 74329 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 41276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89415 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 | 2023-05-24 | QTR4 | 22/23 | 636 | 2883318.39 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N55 | 44196815201 | 2021-08-26 | QTR1 | 21/22 | 1 | 0 | 280 | 460 | 459 | 1 | 0 | 0 | 180 | 0 | 757063 | 47154 | 709909 | 757063 | 654819 | 0 | 0 | 0 | 654819 | 654819 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2023-04-06 | QTR4 | 22/23 | 636 | 1042435.8 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7424 | 25729855201 | 2019-03-27 | QTR3 | 18/19 | 3 | 4 | 860 | 964 | 931 | 33 | 0 | 0 | 104 | 0 | 20155312 | 406894 | 19748419 | 20804212 | 20013184 | 0 | 0 | 0 | 20013184 | 19790050 | -223135 | 648900 | 54 | 0 | 0 | 350213 | 0 | 0 | 0 | 262060 | 6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637979 | 6325 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-11-03 | QTR2 | 23/24 | 2022-04-12 | QTR4 | 21/22 | 798 | 29301814.47 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7428 | 43258435201 | 2019-02-27 | QTR3 | 18/19 | 3 | 6 | 445 | 671 | 685 | -14 | 14 | 0 | 114 | 112 | 9277781 | 90000 | 9187781 | 9481539 | 10184938 | -48258 | 300000 | 251742 | 10436680 | 10081240 | -350246 | 203759 | 58 | 0 | 21 | 283799 | 0 | 0 | 0 | 16679 | 10786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -96529 | 0 | 0 | 0 | 12534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 216484 | 10786 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2021-06-25 | QTR4 | 20/21 | 796 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7451 | 43982985201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 170 | 178 | 550 | -372 | 372 | 0 | 8 | 0 | 698558 | 34000 | 664558 | 698558 | 557380 | -158860 | 0 | -158860 | 398520 | 531562 | 133042 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2022-07-07 | QTR1 | 22/23 | 799 | 691075.3 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7468 | 44138615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 3 | 498 | 556 | 514 | 42 | 0 | 0 | 77 | -19 | 9161461 | 85000 | 9076461 | 9416662 | 9386983 | 0 | 0 | 0 | 9386983 | 9736387 | 388067 | 255200 | 53 | 0 | 0 | 337633 | 0 | 0 | 0 | 90042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 324328 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-13 | QTR1 | 23/24 | 2022-12-02 | QTR2 | 22/23 | 798 | 9040000 |  |  | 0 | 24 | 0 | -19 | -105466 | 0 |  | CO
07CO | 07 | T7480 | 44025315201 | 2021-12-08 | QTR2 | 21/22 | 1 | 2 | 230 | 353 | 352 | 1 | 0 | 0 | 109 | 14 | 8381553 | 92000 | 8289553 | 8507750 | 8880433 | 0 | 0 | 0 | 8880433 | 9224126 | 351217 | 126197 | 83 | 0 | 0 | 0 | 0 | 0 | 14 | 124206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7524 | 7524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 131729 | 7524 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 | 2023-07-21 | QTR1 | 23/24 | 796 | 9618300 |  |  | 14 | 26 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7491 | 44358325201 | 2022-02-23 | QTR3 | 21/22 | 1 | 0 | 150 | 193 | 193 | 0 | 0 | 0 | 43 | 0 | 1439445 | 44000 | 1395445 | 1439445 | 1363648 | 0 | 0 | 0 | 1363648 | 1363533 | -115 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-12-06 | QTR2 | 23/24 | 2023-09-14 | QTR1 | 23/24 | 796 | 1085600 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7498 | 44332015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 0 | 120 | 127 | 127 | 0 | 0 | 0 | 7 | 0 | 1340863 | 50000 | 1290863 | 1340863 | 1268582 | 0 | -12000 | -12000 | 1256582 | 1256582 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 | 2023-05-22 | QTR4 | 22/23 | 796 | 2027300 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7N90 | 44822115201 | 2022-01-12 | QTR3 | 21/22 | 1 | 1 | 120 | 172 | 172 | 0 | 0 | 0 | 52 | 0 | 679686 | 28000 | 651686 | 695950 | 640611 | 0 | 0 | 0 | 640611 | 640611 | 0 | 16264 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-04-20 | QTR4 | 22/23 | 799 | 644500 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N95 | 44025115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 3 | 240 | 317 | 314 | 3 | 0 | 0 | 77 | 0 | 6430299 | 84000 | 6346299 | 6566839 | 6774752 | 0 | 0 | 0 | 6774752 | 7323867 | 551655 | 136540 | 52 | 0 | 0 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33706 | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 2540 | 2540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120246 | 36246 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 | 2023-02-24 | QTR3 | 22/23 | 796 | 8690700 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O04 | 43952615201 | 2021-09-08 | QTR1 | 21/22 | 1 | 2 | 210 | 235 | 235 | 0 | 0 | 0 | 25 | 0 | 1944266 | 50000 | 1894266 | 2045152 | 1898792 | 0 | 0 | 0 | 1898792 | 1886359 | 0 | 100885 | 10 | 0 | 0 | 17204 | 0 | 0 | 0 | 71248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12433 | 12433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100885 | 12433 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2022-12-09 | QTR2 | 22/23 | 799 | 1797400 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O11 | 44166515201 | 2022-02-09 | QTR3 | 21/22 | 2 | 0 | 180 | 220 | 220 | 0 | 0 | 0 | 40 | 0 | 3049631 | 50000 | 2999631 | 3049631 | 3013462 | 0 | 0 | 0 | 3013462 | 3013181 | -281 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-06-14 | QTR4 | 22/23 | 798 | 2409700 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P30 | 44761415201 | 2022-04-13 | QTR4 | 21/22 | 1 | 1 | 140 | 171 | 171 | 0 | 0 | 0 | 31 | 0 | 2231499 | 50000 | 2181499 | 2259063 | 2052581 | 0 | 0 | 0 | 2052581 | 2046856 | -5724 | 27565 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 27565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27565 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2023-12-08 | QTR2 | 23/24 | 2023-09-13 | QTR1 | 23/24 | 714 | 1792600 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P36 | 44978015201 | 2022-06-08 | QTR4 | 21/22 | 3 | 3 | 300 | 361 | 338 | 23 | 0 | 0 | 61 | 0 | 4664000 | 50000 | 4614000 | 4709230 | 4734993 | 0 | 0 | 0 | 4734993 | 4662735 | -72258 | 45230 | 37 | 0 | 0 | 25230 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45230 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-10-26 | QTR2 | 23/24 | 2023-08-01 | QTR1 | 23/24 | 799 | 5588200 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P61 | 44383615201 | 2023-01-11 | QTR3 | 22/23 | 1 | 1 | 140 | 165 | 161 | 4 | 0 | 0 | 10 | 15 | 506794 | 19000 | 487794 | 527638 | 475289 | 0 | 0 | 0 | 475289 | 475289 | 0 | 20844 | 1 | 0 | 0 | 20844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20844 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-11-17 | QTR2 | 23/24 | 2023-10-16 | QTR2 | 23/24 | 799 | 441600 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P63 | 44774815201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 120 | 130 | 71 | 59 | 0 | 0 | 10 | 0 | 619151 | 50000 | 569151 | 619151 | 571177 | 0 | 0 | 0 | 571177 | 571177 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-10-12 | QTR2 | 23/24 | 2023-07-24 | QTR1 | 23/24 | 799 | 1320700 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q78 | 43554615201 | 2018-06-15 | QTR4 | 17/18 | 2 | 27 | 1430 | 1594 | 1265 | 329 | 0 | 0 | 164 | 0 | 143269821 | 150000 | 143119821 | 145759356 | 145166429 | 0 | 5000000 | 5000000 | 150166429 | 144192875 | -5873129 | 2489535 | 81 | 0 | 0 | 398577 | 0 | 0 | 0 | 1404790 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131931 | 0 | 0 | 0 | 551048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2379872 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 | 2022-03-01 | QTR3 | 21/22 | 854 | 156867749.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 83 | 0 | 0 | -140484 | 0 |  | DO
08DO | 08 | E8R77 | 43798615201 | 2019-05-14 | QTR4 | 18/19 | 3 | 5 | 738 | 1039 | 1039 | 0 | 0 | 0 | 301 | 0 | 31832323 | 150000 | 31682323 | 32865375 | 32938830 | 0 | 0 | 0 | 32938830 | 32271398 | -667433 | 1033052 | 175 | 0 | 0 | 62194 | 0 | 0 | 0 | 38182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 960260 | 0 | 0 | 0 | 77444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1138080 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2023-08-10 | QTR1 | 23/24 | 2022-08-17 | QTR1 | 22/23 | 854 | 33799887.12 |  |  | 0 | 98 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R97 | 43730045201 | 2019-09-17 | QTR1 | 19/20 | 1 | 35 | 939 | 1012 | 938 | 74 | 0 | 0 | 73 | 0 | 139979406 | 150000 | 139829406 | 145733672 | 144403400 | 0 | 6000000 | 6000000 | 150403400 | 143485400 | -5542884 | 5754265 | 38 | 0 | 0 | 48807 | 0 | 0 | 0 | 4196617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94312 | 0 | 0 | 0 | 564973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 983554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5902105 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SOUTHLAND C | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 | 2022-07-31 | QTR1 | 22/23 | 854 | 118749145.78 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S55 | 44070015201 | 2020-08-31 | QTR1 | 20/21 | 2 | 7 | 515 | 718 | 716 | 2 | 0 | 0 | 231 | -28 | 16707654 | 150000 | 16557654 | 17277221 | 16377036 | 0 | 0 | 0 | 16377036 | 16720673 | 485146 | 569567 | 175 | 0 | 0 | 18542 | 0 | 0 | 0 | 58747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469864 | 0 | 0 | 0 | 80825 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | -28 | 616415 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2022-12-20 | QTR2 | 22/23 | 854 | 20328685.57 |  |  | 0 | 56 | 0 | -28 | -50316 | 0 |  | DO
08DO | 08 | E8T21 | 44029215201 | 2021-09-14 | QTR1 | 21/22 | 2 | 6 | 350 | 617 | 614 | 3 | 0 | 0 | 208 | 59 | 13350942 | 121421 | 13229522 | 13774510 | 13575224 | 0 | 0 | 0 | 13575224 | 13523826 | 353962 | 423568 | 176 | 0 | 0 | 5500 | 0 | 0 | 0 | 24055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 97132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 405361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 532048 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-09-08 | QTR1 | 23/24 | 854 | 12351694.57 |  |  | 40 | 51 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T38 | 43730095201 | 2022-02-08 | QTR3 | 21/22 | 1 | 0 | 192 | 242 | 235 | 7 | 0 | 0 | 50 | 0 | 5115331 | 50000 | 5065331 | 5115331 | 5070631 | 0 | 0 | 0 | 5070631 | 5070631 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-06-15 | QTR4 | 22/23 | 854 | 5087753.85 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T39 | 44430115201 | 2021-12-14 | QTR2 | 21/22 | 1 | 3 | 234 | 278 | 253 | 25 | 0 | 0 | 44 | 0 | 1975221 | 50000 | 1925221 | 2101149 | 2102097 | 0 | 0 | 0 | 2102097 | 2083906 | 7736 | 125928 | 25 | 0 | 0 | 102641 | 0 | 0 | 0 | 36105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174272 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 | 2023-03-08 | QTR3 | 22/23 | 854 | 1709882.3 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T42 | 43799015201 | 2022-03-08 | QTR3 | 21/22 | 2 | 3 | 321 | 359 | 286 | 73 | 0 | 0 | 54 | -16 | 4166000 | 50000 | 4116000 | 4217668 | 4164480 | 0 | 138823 | 138823 | 4303303 | 4215075 | -86560 | 51668 | 31 | 0 | 0 | 44026 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 98536 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-05-22 | QTR4 | 22/23 | 854 | 3910716.97 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | -16 | 0 | 0 |  | DO
08DO | 08 | E8T68 | 44448615201 | 2022-04-12 | QTR4 | 21/22 | 1 | 2 | 329 | 389 | 389 | 0 | 0 | 0 | 60 | 0 | 6695054 | 50000 | 6645054 | 6727768 | 6880189 | 0 | 0 | 0 | 6880189 | 6860508 | -11968 | 32714 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 74099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81813 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-11-28 | QTR2 | 23/24 | 2023-10-05 | QTR2 | 23/24 | 854 | 6191721.36 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T86 | 43855115201 | 2022-08-16 | QTR1 | 22/23 | 1 | 1 | 136 | 169 | 142 | 27 | 0 | 0 | 9 | 24 | 597627 | 35230 | 562397 | 652711 | 607225 | 0 | 0 | 0 | 607225 | 607225 | 0 | 55083 | 6 | 0 | 24 | 55083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 55083 | 0 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-06-23 | QTR4 | 22/23 | 854 | 898718.41 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T87 | 43855015201 | 2022-08-16 | QTR1 | 22/23 | 1 | 0 | 199 | 202 | 84 | 118 | 0 | 0 | 3 | 0 | 767354 | 50000 | 717354 | 767354 | 705154 | 0 | 0 | 0 | 705154 | 705154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2023-05-11 | QTR4 | 22/23 | 854 | 1243902.61 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U24 | 44122465201 | 2023-02-14 | QTR3 | 22/23 | 1 | 1 | 94 | 108 | 107 | 1 | 0 | 0 | 14 | 0 | 855737 | 38426 | 817311 | 857248 | 864748 | 0 | 0 | 0 | 864748 | 863238 | 0 | 1510 | 12 | 0 | 0 | 2884 | 0 | 0 | 0 | 30181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37651 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-01 | QTR2 | 23/24 | 2023-09-25 | QTR1 | 23/24 | 854 | 859411.5 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U28 | 44261825201 | 2023-05-09 | QTR4 | 22/23 | 1 | 0 | 86 | 90 | 27 | 63 | 0 | 0 | 4 | 0 | 491221 | 32753 | 458468 | 491221 | 344856 | 0 | 0 | 0 | 344856 | 344856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F721180277 | JACK B. HARPER CONTRACTOR L.L.C. | N/A | N/A | N/A | N/A | 2023-11-27 | QTR2 | 23/24 | 2023-09-15 | QTR1 | 23/24 | 854 | 690819.2 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
CO |  | CO | 0 | 01co | 1 | 0
CO |  | CO | 0 | 01do | 1 | 0
CO |  | CO | 0 | 02co | 1 | 0
CO |  | CO | 0 | 02do | 1 | 0
CO |  | CO | 0 | 03co | 1 | 0
CO |  | CO | 0 | 03do | 1 | 0
CO |  | CO | 0 | 04co | 1 | 0
CO |  | CO | 0 | 04do | 1 | 0
CO |  | CO | 0 | 05co | 1 | 0
CO | T | CO | 0 | 05do | 1 | 0
CO |  | CO | 0 | 06co | 1 | 0
CO |  | CO | 0 | 06do | 1 | 0
CO |  | CO | 0 | 07co | 1 | 0
CO |  | CO | 0 | 07do | 1 | 0
CO |  | CO | 0 | 08co | 1 | 0
CO |  | CO | 0 | 08do | 1 | 0
CO |  | CO
CO |  | CO
CO |  | CO |  | 0