## Summary
District | Contract Lettings | Original Contract Amount | Adjusted Original Amount (less Contingency Pay Item Amount) | Present Contract Amount | Regular Work To Date (See Note 1 below) | Amount Paid For Innovative Contracting | Actual Expenditures (See Note 2 Below) |  | % Contracts < 10% Increase in Cost | Supplemental Agreement (Including Contingency) (See Note 4 Below) |  | Supplemental Agreement (Excluding Contingency) (See Note 3 Below) |  | Original Contract Days | Weather Days |  | Holiday Time Extensions |  | Time Extensions |  | Supplemental Agreement |  | Total Days (Less Weather & Holidays) |  | Present Days | Days Used | Days Used (Less Weather & Holiday) | % Increase (Less Weather & Holiday) | % Contracts < 20% Increase in Time
[7 empty] | Amount | % Increase Over Adjusted Original Amount |  | Amount | % Of Original Amount | Amount | % Of Original Amount |  | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days | Days Added | % of Original Days
1 | Central Let | 150255175 | 148779137 | 157497293 | 156021987 | 0 | 157545620 | 5.892% | 77.78% | 7520943 | 5.055% | 7242116 | 4.82% | 7864 | 2666 | 33.9% | 740 | 9.41% | 955 | 12.14% | 1051 | 13.36% | 9870 | 25.51% | 12097 | 12578 | 9172 | 16.63% | 62.96%
| District Let | 54255746 | 53398985 | 55622696 | 55044591 | 100000 | 55403537 | 3.754% | 70.59% | 1624176 | 3.042% | 1366950 | 2.519% | 3967 | 774 | 19.51% | 376 | 9.478% | 134 | 3.378% | 486 | 12.25% | 4587 | 15.63% | 5495 | 5584 | 4434 | 11.77% | 88.24%
| All Contracts | 204510921 | 202178122 | 213119989 | 211066578 | 100000 | 212949157 | 5.327% | 75% | 9145119 | 4.523% | 8609066 | 4.21% | 11831 | 3440 | 29.08% | 1116 | 9.433% | 1089 | 9.205% | 1537 | 12.99% | 14457 | 22.2% | 17592 | 18162 | 13606 | 15% | 72.73%
2 | Central Let | 238386498 | 235488212 | 240959322 | 242098132 | 0 | 245286682 | 4.161% | 85.11% | 3231271 | 1.372% | 2572824 | 1.079% | 10524 | 3268 | 31.05% | 1367 | 12.99% | 1451 | 13.79% | 2109 | 20.04% | 14084 | 33.83% | 17994 | 18034 | 13399 | 27.32% | 57.45%
| District Let | 162322311 | 161682621 | 175681251 | 176298782 | 0 | 175845068 | 8.759% | 77.78% | 13557119 | 8.385% | 13358940 | 8.23% | 3465 | 1302 | 37.58% | 629 | 18.15% | 477 | 13.77% | 1122 | 32.38% | 5064 | 46.15% | 6435 | 6420 | 4489 | 29.55% | 66.67%
| All Contracts | 400708809 | 397170833 | 416640573 | 418396914 | 0 | 421131750 | 6.033% | 83.93% | 16788390 | 4.227% | 15931764 | 3.976% | 13989 | 4570 | 32.67% | 1996 | 14.27% | 1928 | 13.78% | 3231 | 23.1% | 19148 | 36.88% | 24429 | 24454 | 17888 | 27.87% | 58.93%
3 | Central Let | 236886404 | 234814665 | 246245815 | 251944992 | -102692 | 253787971 | 8.08% | 87.8% | 9647740 | 4.109% | 9359413 | 3.951% | 10289 | 4055 | 39.41% | 1550 | 15.06% | 1349 | 13.11% | 1002 | 9.739% | 12640 | 22.85% | 17533 | 17787 | 12182 | 18.4% | 73.17%
| District Let | 29014863 | 28458634 | 29150438 | 28676228 | 12500 | 28964037 | 1.776% | 93.75% | 178070 | 0.6257% | 135574 | 0.4673% | 2100 | 602 | 28.67% | 312 | 14.86% | 263 | 12.52% | 17 | 0.8095% | 2380 | 13.33% | 3133 | 2953 | 2039 | -2.905% | 87.5%
| All Contracts | 265901267 | 263273299 | 275396253 | 280621220 | -90192 | 282752008 | 7.399% | 89.47% | 9825810 | 3.732% | 9494987 | 3.571% | 12389 | 4657 | 37.59% | 1862 | 15.03% | 1612 | 13.01% | 1019 | 8.225% | 15020 | 21.24% | 20666 | 20740 | 14221 | 14.79% | 77.19%
4 | Central Let | 87093207 | 85869189 | 89250065 | 87553356 | 0 | 89378786 | 4.087% | 95.24% | 2700458 | 3.145% | 2245299 | 2.578% | 6551 | 2374 | 36.24% | 671 | 10.24% | 878 | 13.4% | 77 | 1.175% | 7506 | 14.58% | 9997 | 9930 | 6885 | 5.098% | 100%
| District Let | 62341564 | 61559650 | 64357872 | 62870417 | 225000 | 63250347 | 2.746% | 92.31% | 2230961 | 3.624% | 2016307 | 3.234% | 3271 | 897 | 27.42% | 276 | 8.438% | 130 | 3.974% | 71 | 2.171% | 3472 | 6.145% | 4587 | 4403 | 3230 | -1.253% | 92.31%
| All Contracts | 149434771 | 147428839 | 153607937 | 150423773 | 225000 | 152629133 | 3.527% | 94.12% | 4931419 | 3.345% | 4261606 | 2.852% | 9822 | 3271 | 33.3% | 947 | 9.642% | 1008 | 10.26% | 148 | 1.507% | 10978 | 11.77% | 14584 | 14333 | 10115 | 2.983% | 97.06%
5 | Central Let | 238963453 | 237735745 | 258484305 | 267296725 | 0 | 266217103 | 11.98% | 83.33% | 18945012 | 7.969% | 19130758 | 8.006% | 5603 | 1249 | 22.29% | 970 | 17.31% | 0 | 0% | 875 | 15.62% | 6478 | 15.62% | 8658 | 8631 | 6412 | 14.44% | 94.44%
| District Let | 70552740 | 69470844 | 71367620 | 70412255 | 0 | 70916287 | 2.081% | 100% | 1191418 | 1.715% | 814879 | 1.155% | 4269 | 718 | 16.82% | 1058 | 24.78% | 11 | 0.2577% | 272 | 6.372% | 4552 | 6.629% | 6252 | 6142 | 4366 | 2.272% | 100%
| All Contracts | 309516193 | 307206589 | 329851925 | 337708980 | 0 | 337133390 | 9.742% | 91.67% | 20136430 | 6.555% | 19945637 | 6.444% | 9872 | 1967 | 19.93% | 2028 | 20.54% | 11 | 0.1114% | 1147 | 11.62% | 11030 | 11.73% | 14910 | 14773 | 10778 | 9.177% | 97.22%
6 | Central Let | 82674388 | 81867860 | 83667059 | 82574041 | 5849010 | 83018730 | 1.406% | 100% | 1189567 | 1.453% | 992670 | 1.201% | 4479 | 462 | 10.31% | 285 | 6.363% | 15 | 0.3349% | 0 | 0% | 4494 | 0.3349% | 5241 | 4510 | 3763 | -15.99% | 100%
| District Let | 21006163 | 20571330 | 21249066 | 21310921 | 180000 | 21358911 | 3.829% | 87.5% | 411849 | 2.002% | 242902 | 1.156% | 2560 | 395 | 15.43% | 164 | 6.406% | 59 | 2.305% | 10 | 0.3906% | 2629 | 2.695% | 3188 | 2818 | 2259 | -11.76% | 100%
| All Contracts | 103680551 | 102439190 | 104916125 | 103884962 | 6029010 | 104377641 | 1.892% | 95.65% | 1601416 | 1.563% | 1235572 | 1.192% | 7039 | 857 | 12.18% | 449 | 6.379% | 74 | 1.051% | 10 | 0.1421% | 7123 | 1.193% | 8429 | 7328 | 6022 | -14.45% | 100%
7 | Central Let | 88730267 | 87578374 | 94995797 | 95004828 | 300000 | 92396468 | 5.501% | 91.67% | 6281571 | 7.173% | 6265529 | 7.061% | 4173 | 616 | 14.76% | 379 | 9.082% | 44 | 1.054% | 519 | 12.44% | 4736 | 13.49% | 5740 | 7111 | 6116 | 46.56% | 75%
| District Let | 124359068 | 123327068 | 127142808 | 126194753 | 200000 | 126751170 | 2.776% | 95% | 3042205 | 2.467% | 2783739 | 2.238% | 4722 | 588 | 12.45% | 476 | 10.08% | 62 | 1.313% | 123 | 2.605% | 4907 | 3.918% | 6046 | 5853 | 4789 | 1.419% | 100%
| All Contracts | 213089335 | 210905442 | 222138605 | 221199581 | 500000 | 219147638 | 3.908% | 93.75% | 9323776 | 4.421% | 9049268 | 4.247% | 8895 | 1204 | 13.54% | 855 | 9.612% | 106 | 1.192% | 642 | 7.218% | 9643 | 8.409% | 11786 | 12964 | 10905 | 22.6% | 90.62%
8 | Central Let | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0 | 0% | 0%
| District Let | 446501853 | 444699774 | 458533838 | 452213862 | 11138823 | 449798293 | 1.147% | 100% | 12844460 | 2.888% | 12031982 | 2.695% | 8726 | 1468 | 16.82% | 870 | 9.97% | 212 | 2.43% | 176 | 2.017% | 9114 | 4.446% | 11264 | 10508 | 8170 | -6.372% | 100%
| All Contracts | 446501853 | 444699774 | 458533838 | 452213862 | 11138823 | 449798293 | 1.147% | 100% | 12844460 | 2.888% | 12031982 | 2.695% | 8726 | 1468 | 16.82% | 870 | 9.97% | 212 | 2.43% | 176 | 2.017% | 9114 | 4.446% | 11264 | 10508 | 8170 | -6.372% | 100%
Totals This Qtr | Central Let | 1122989392 | 1112133182 | 1171099656 | 1182494061 | 6046318 | 1187631360 | 6.789% | 87.1% | 49516562 | 4.452% | 47808609 | 4.257% | 49483 | 14690 | 29.69% | 5962 | 12.05% | 4692 | 9.482% | 5633 | 11.38% | 59808 | 20.87% | 77260 | 78581 | 57929 | 17.07% | 74.73%
| District Let | 970354308 | 963168906 | 1003105589 | 993021809 | 11856323 | 992287650 | 3.023% | 91.06% | 35080258 | 3.642% | 32751273 | 3.375% | 33080 | 6744 | 20.39% | 4161 | 12.58% | 1348 | 4.075% | 2277 | 6.883% | 36705 | 10.96% | 46400 | 44681 | 33776 | 2.104% | 93.5%
| All Contracts | 2093343700 | 2075302088 | 2174205245 | 2175515870 | 17902641 | 2179919010 | 5.041% | 88.67% | 84596820 | 4.076% | 80559882 | 3.848% | 82563 | 21434 | 25.96% | 10123 | 12.26% | 6040 | 7.316% | 7910 | 9.581% | 96513 | 16.9% | 123660 | 123262 | 91705 | 11.07% | 82.2%
Totals Previous Quarter | Central Let | 797674751 | 789002510 | 824460943 | 824879041 | 5879010 | 838987770 | 6.335% | 88.51% | 28117823 | 3.564% | 26725732 | 3.35% | 37408 | 11846 | 31.67% | 4463 | 11.93% | 4657 | 12.45% | 3984 | 10.65% | 46049 | 23.1% | 59310 | 59777 | 43468 | 16.2% | 74.32%
| District Let | 623056194 | 618161049 | 639539827 | 633155412 | 11843823 | 632825241 | 2.372% | 91.95% | 17931048 | 2.901% | 16483626 | 2.646% | 23131 | 4206 | 18.18% | 2769 | 11.97% | 732 | 3.165% | 1300 | 5.62% | 25163 | 8.785% | 31477 | 29827 | 22852 | -1.206% | 95.4%
| All Contracts | 1420730945 | 1407163559 | 1464000770 | 1458034453 | 17722833 | 1471813011 | 4.594% | 89.79% | 46048871 | 3.272% | 43209358 | 3.041% | 60539 | 16052 | 26.52% | 7232 | 11.95% | 5389 | 8.902% | 5284 | 8.728% | 71212 | 17.63% | 90787 | 89604 | 66320 | 9.549% | 82.13%
Totals Fiscal Year 2023/2024 | Central Let | 1122989392 | 1112133182 | 1171099656 | 1182494061 | 6046318 | 1187631360 | 6.789% | 87.1% | 49516562 | 4.452% | 47808609 | 4.257% | 49483 | 14690 | 29.69% | 5962 | 12.05% | 4692 | 9.482% | 5633 | 11.38% | 59808 | 20.87% | 77260 | 78581 | 57929 | 17.07% | 74.73%
| District Let | 970354308 | 963168906 | 1003105589 | 993021809 | 11856323 | 992287650 | 3.023% | 91.06% | 35080258 | 3.642% | 32751273 | 3.375% | 33080 | 6744 | 20.39% | 4161 | 12.58% | 1348 | 4.075% | 2277 | 6.883% | 36705 | 10.96% | 46400 | 44681 | 33776 | 2.104% | 93.5%
| All Contracts | 2093343700 | 2075302088 | 2174205245 | 2175515870 | 17902641 | 2179919010 | 5.041% | 88.67% | 84596820 | 4.076% | 80559882 | 3.848% | 82563 | 21434 | 25.96% | 10123 | 12.26% | 6040 | 7.316% | 7910 | 9.581% | 96513 | 16.9% | 123660 | 123262 | 91705 | 11.07% | 82.2%
Notes:
|  | 1 | "Regular Work To Date" is the total value of work paid to contractor as reported in the Department's Construction Reporting System (SiteManager and CRS).
|  | 2 | "Actual Expenditures" is the total amount paid for work as recorded in the Department's Financial Management System and reflects all expenditures against each contract.
|  | 3 | "Supplemental Agreement (Excluding Contingency)" is the total amount of contract changes that were recorded as being expended by reason code in the Department's
Contract Change Tracking System.
|  | 4 | "Supplemental Agreement (Including Contingency)" is the total amount allocated within the Department's Construction Reporting System (SiteManager and CRS)
for contract changes.
Highlighted Column indicates Performance Measures Reported by Construction Office

## Detailed Data
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
| 01 | T1191 | 43355045201 | 2021-06-09 | QTR4 | 20/21 | 2 | 6 | 320 | 579 | 579 | 126.2% | 0 | 0 | 0 | 0 | 207 | 52 | 6386200 | 56445 | 6329755 | 6748926 | 6664293 | 0 | 0 | 0 | 6664293 | 6748506 | 106.6% | 1 | 143879 | 362725 | 149 | 26 | 7 | 20 | 118601 | 0 | 0 | 32 | 264904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 8221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 120 | 52 | 391726 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2024-01-23 | QTR3 | 23/24 |  | 2023-08-04 | QTR1 | 23/24 | 115 | 5529849.57
| 01 | T1676 | 43131315201 | 2018-06-13 | QTR4 | 17/18 | 3 | 32 | 1200 | 1846 | 1845 | 122.8% | 0 | 1 | 0 | 0 | 357 | 289 | 20052828 | 150000 | 19902828 | 22892173 | 22098737 | 0 | 0 | 0 | 22098737 | 22107645 | 111.1% | 0 | 112471 | 2839344 | 254 | 117 | 0 | 275 | 1504569 | 159745 | 0 | 0 | 752980 | 13922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470970 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 103564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 2840833 | 173668 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-05-10 | QTR4 | 23/24 |  | 2023-12-29 | QTR2 | 23/24 | 113 | 16688857.48
| 01 | T1751 | 41066635201 | 2020-04-29 | QTR4 | 19/20 | 4 | 15 | 875 | 1016 | 963 | 94.74% | 1 | 53 | 0 | 0 | 127 | 14 | 43563143 | 150000 | 43413143 | 43826539 | 44268970 | 0 | 0 | 0 | 44268970 | 45616616 | 105.1% | 1 | 1915546 | 263396 | 80 | 54 | 0 | 0 | 351912 | 3918 | 7 | 0 | 219896 | 30715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17978 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 22507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -287200 | 0 | 7 | 14 | 343410 | 34633 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-09-11 | QTR1 | 23/24 |  | 2023-04-28 | QTR4 | 22/23 | 108 | 44746155.07
| 01 | T1761 | 42982315201 | 2021-06-09 | QTR4 | 20/21 | 2 | 18 | 275 | 545 | 530 | 130.2% | 0 | 15 | 0 | 0 | 223 | 47 | 4097408 | 50000 | 4047408 | 4902150 | 4899132 | 0 | 0 | 0 | 4899132 | 4822749 | 119.2% | 0 | 34379 | 804742 | 131 | 41 | 0 | 42 | 118523 | 55203 | 51 | 5 | 478225 | 97145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42992 | 42992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 47 | 830672 | 195339 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2023-02-24 | QTR3 | 22/23 | 113 | 4251830.23
| 01 | T1762 | 43943415201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 350 | 634 | 731 | 130.6% | 0 | -97 | 97 | 0 | 263 | 21 | 10278123 | 111374 | 10166749 | 10447272 | 10596778 | -421368 | 0 | -421368 | 10175410 | 10869033 | 106.9% | 1 | 858028 | 169149 | 239 | 35 | 0 | 0 | 0 | 0 | 0 | 10 | 155202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24064 | 0 | 0 | 0 | 0 | 0 | 189 | 11 | 28454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 21 | 207720 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-06-04 | QTR4 | 23/24 |  | 2023-03-09 | QTR3 | 22/23 | 118 | 10803856.75
| 01 | T1770 | 44068615201 | 2021-03-31 | QTR3 | 20/21 | 1 | 5 | 400 | 597 | 734 | 147% | 0 | -137 | 137 | 0 | 156 | 41 | 2574061 | 50000 | 2524061 | 2608561 | 2446996 | -275991 | 0 | -275991 | 2171004 | 2221824 | 88.03% | 1 | 53387 | 34500 | 101 | 45 | 3 | 0 | 0 | 0 | 7 | 5 | 18309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27300 | 0 | 0 | 0 | -5115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 41 | 43394 | 0 | F204003511 | E&M EQUIPMENT | N/A | N/A | N/A | N/A | 2024-05-03 | QTR4 | 23/24 |  | 2023-07-15 | QTR1 | 23/24 | 115 | 2478688.72
| 01 | T1772 | 44211515201 | 2020-09-30 | QTR1 | 20/21 | 3 | 1 | 150 | 177 | 607 | 386.7% | 0 | -430 | 430 | 0 | 11 | 16 | 668342 | 41495 | 626847 | 668342 | 605783 | 0 | 0 | 0 | 605783 | 595755 | 95.04% | 1 | 25365 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 6341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 6341 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 |  | 2022-12-05 | QTR2 | 22/23 | 108 | 802465.89
| 01 | T1777 | 43943015201 | 2020-09-30 | QTR1 | 20/21 | 4 | 3 | 325 | 607 | 638 | 125.5% | 0 | -31 | 31 | 0 | 216 | 66 | 7973682 | 92806 | 7880876 | 8225110 | 8195027 | -106857 | 0 | -106857 | 8088170 | 8717413 | 110.6% | 0 | 921857 | 251428 | 207 | 23 | 0 | 0 | 126514 | 115529 | 0 | 52 | 124433 | 124433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 14 | 11465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 66 | 262412 | 239963 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 |  | 2022-10-18 | QTR2 | 22/23 | 118 | 9500361.49
| 01 | T1781 | 44151815201 | 2021-01-27 | QTR3 | 20/21 | 2 | 4 | 285 | 400 | 400 | 126% | 0 | 0 | 0 | 0 | 41 | 74 | 4960436 | 59129 | 4901307 | 5450251 | 5304714 | 0 | 0 | 0 | 5304714 | 5560151 | 113.4% | 0 | 265895 | 489815 | 14 | 27 | 0 | 74 | 470632 | 0 | 0 | 0 | 17986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 489815 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2022-06-30 | QTR4 | 21/22 | 118 | 5666706.37
| 01 | T1790 | 44240115201 | 2020-08-26 | QTR1 | 20/21 | 1 | 1 | 110 | 145 | 141 | 104.5% | 1 | 4 | 0 | 0 | 26 | 9 | 697485 | 0 | 697485 | 700625 | 698869 | 0 | 0 | 0 | 698869 | 698869 | 100.2% | 1 | 0 | 3140 | 21 | 5 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140 | 3140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3140 | 3140 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-24 | QTR2 | 23/24 |  | 2021-07-09 | QTR1 | 21/22 | 108 | 802615.61 | B0 | ACC - LUMP SUM
| 01 | T1797 | 44013415201 | 2021-04-28 | QTR4 | 20/21 | 1 | 3 | 250 | 536 | 536 | 100% | 1 | 0 | 0 | 0 | 286 | 0 | 1568347 | 50000 | 1518347 | 1712719 | 1597886 | 0 | 0 | 0 | 1597886 | 1566868 | 103.2% | 1 | 119180 | 144372 | 249 | 37 | 0 | 0 | 85263 | 0 | 0 | 0 | 28090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144372 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-14 | QTR3 | 23/24 |  | 2023-12-08 | QTR2 | 23/24 | 113 | 1575091.8
| 01 | T1799 | 44421315201 | 2021-07-28 | QTR1 | 21/22 | 2 | 4 | 150 | 427 | 427 | 142% | 0 | 0 | 0 | 0 | 277 | 0 | 1799984 | 50000 | 1749984 | 1831736 | 1823093 | 0 | 0 | 0 | 1823093 | 1813838 | 103.6% | 1 | 12989 | 31752 | 189 | 25 | 0 | 0 | 5503 | 0 | 0 | 0 | 8913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 22244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 42196 | 0 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2024-03-15 | QTR3 | 23/24 |  | 2023-08-31 | QTR1 | 23/24 | 118 | 1712726.18
| 01 | T1803 | 44485625201 | 2022-02-23 | QTR3 | 21/22 | 1 | 3 | 290 | 335 | 325 | 96.55% | 1 | 10 | 0 | 0 | 45 | 0 | 3990760 | 0 | 3990760 | 3990760 | 3720606 | 0 | 0 | 0 | 3720606 | 3720606 | 93.23% | 1 | 0 | 0 | 19 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-06-05 | QTR4 | 23/24 |  | 2024-02-28 | QTR3 | 23/24 | 113 | 4528912.63
| 01 | T1806 | 44155915201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 250 | 391 | 391 | 112% | 1 | 0 | 0 | 0 | 134 | 7 | 7108184 | 63330 | 7044854 | 8445969 | 8418621 | 0 | 0 | 0 | 8418621 | 7803372 | 110.8% | 0 | 265502 | 1337785 | 92 | 19 | 0 | 0 | 0 | 0 | 23 | 7 | 473396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 880751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 39 | 1354148 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 |  | 2023-05-01 | QTR4 | 22/23 | 115 | 6181054.02
| 01 | T1808 | 44233315201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 140 | 293 | 293 | 118.6% | 1 | 0 | 0 | 0 | 153 | 0 | 1139701 | 50000 | 1089701 | 1148801 | 1029185 | 0 | 0 | 0 | 1029185 | 1021881 | 93.78% | 1 | 1796 | 9100 | 105 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 9100 | 0 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-03-17 | QTR3 | 22/23 | 108 | 1098275.5
| 01 | T1811 | 44033915201 | 2022-01-26 | QTR3 | 21/22 | 1 | 3 | 200 | 464 | 464 | 100% | 1 | 0 | 0 | 0 | 84 | 180 | 2754382 | 50000 | 2704382 | 2849902 | 2874882 | 0 | 0 | 0 | 2874882 | 2854767 | 105.6% | 1 | 2576 | 95519 | 236 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 58096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 22690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 80786 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2024-03-12 | QTR3 | 23/24 |  | 2023-10-24 | QTR2 | 23/24 | 108 | 2214962.73
| 01 | T1817 | 44068815201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 80 | 165 | 165 | 133.8% | 0 | 0 | 0 | 0 | 85 | 0 | 650650 | 18505 | 632145 | 655279 | 608957 | 0 | 0 | 0 | 608957 | 609408 | 96.4% | 1 | 451 | 4629 | 47 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 8153 | 45738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 15989 | 45738 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 |  | 2022-12-13 | QTR2 | 22/23 | 115 | 447609.94
| 01 | T1826 | 44421215201 | 2021-08-25 | QTR1 | 21/22 | 1 | 3 | 107 | 259 | 259 | 100% | 1 | 0 | 0 | 0 | 44 | 108 | 1045874 | 41345 | 1004529 | 1076047 | 1015157 | 0 | 0 | 0 | 1015157 | 994639 | 99.02% | 1 | 0 | 30174 | 132 | 20 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 20519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 31344 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2023-03-20 | QTR3 | 22/23 | 118 | 898648.05
| 01 | T1828 | 44033715201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 97 | 129 | 129 | 100% | 1 | 0 | 0 | 0 | 32 | 0 | 560933 | 21933 | 539000 | 623460 | 604533 | 0 | 0 | 0 | 604533 | 604533 | 112.2% | 0 | 0 | 62527 | 31 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 62527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65533 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2023-09-25 | QTR1 | 23/24 |  | 2023-05-15 | QTR4 | 22/23 | 113 | 517232.45 | B0 | ACC - LUMP SUM
| 01 | T1829 | 44514215201 | 2022-03-30 | QTR3 | 21/22 | 1 | 2 | 250 | 396 | 396 | 100% | 1 | 0 | 0 | 0 | 72 | 74 | 5872391 | 66763 | 5805628 | 5912809 | 6112682 | 0 | 0 | 0 | 6112682 | 6149957 | 105.9% | 1 | 50818 | 40418 | 122 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 26875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 13543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 40418 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-02-19 | QTR3 | 23/24 |  | 2023-10-17 | QTR2 | 23/24 | 108 | 6322955.67
| 01 | T1831 | 43708815201 | 2022-03-30 | QTR3 | 21/22 | 1 | 3 | 175 | 281 | 281 | 112% | 1 | 0 | 0 | 0 | 85 | 21 | 1393708 | 50000 | 1343708 | 1475766 | 1415171 | 0 | 0 | 0 | 1415171 | 1415090 | 105.3% | 1 | -81 | 82058 | 70 | 15 | 0 | 21 | 11441 | 0 | 0 | 0 | 74605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 86046 | 0 | F814212997 | NATIONAL TRAFFIC SOLUTION INC | N/A | N/A | N/A | N/A | 2024-01-11 | QTR3 | 23/24 |  | 2023-10-04 | QTR2 | 23/24 | 118 | 1903169.56
| 01 | T1832 | 44880215201 | 2022-03-30 | QTR3 | 21/22 | 1 | 1 | 280 | 310 | 262 | 82.86% | 1 | 48 | 0 | 0 | 30 | 0 | 1651156 | 50000 | 1601156 | 1659184 | 1593043 | 0 | 0 | 0 | 1593043 | 1593043 | 99.49% | 1 | 0 | 8028 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 8028 | 4095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8028 | 4095 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-03-21 | QTR3 | 23/24 |  | 2023-12-27 | QTR2 | 23/24 | 113 | 2046036.83
| 01 | T1834 | 44632015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 215 | 280 | 272 | 96.28% | 1 | 8 | 0 | 0 | 65 | 0 | 4197476 | 50000 | 4147476 | 4197476 | 3945832 | 0 | 0 | 0 | 3945832 | 3902393 | 94.09% | 1 | -43439 | 0 | 47 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 |  | 2023-06-22 | QTR4 | 22/23 | 113 | 4322110.94
| 01 | T1836 | 44155835201 | 2022-03-30 | QTR3 | 21/22 | 2 | 5 | 250 | 279 | 279 | 100% | 1 | 0 | 0 | 0 | 29 | 0 | 3587382 | 0 | 3587382 | 3716421 | 3659641 | 0 | 0 | 0 | 3659641 | 3667717 | 102.2% | 1 | 8077 | 129039 | 7 | 22 | 0 | 0 | 10283 | 0 | 0 | 0 | 118756 | 3604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129039 | 3604 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-05-21 | QTR4 | 23/24 |  | 2023-09-08 | QTR1 | 23/24 | 115 | 2875279.8
| 01 | T1839 | 44012715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 0 | 130 | 175 | 175 | 100% | 1 | 0 | 0 | 0 | 45 | 0 | 461461 | 21100 | 440361 | 461461 | 428726 | 0 | 0 | 0 | 428726 | 428726 | 97.36% | 1 | 0 | 0 | 29 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2023-03-06 | QTR3 | 22/23 | 115 | 438393.45
| 01 | T1842 | 44404915201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 160 | 206 | 206 | 100% | 1 | 0 | 0 | 0 | 46 | 0 | 1796523 | 50000 | 1746523 | 1801104 | 1763228 | 0 | 0 | 0 | 1763228 | 1760169 | 100.8% | 1 | 1522 | 4581 | 27 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4581 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-03-26 | QTR3 | 23/24 |  | 2023-03-25 | QTR3 | 22/23 | 115 | 1217941.81
| 01 | T1844 | 43982615201 | 2022-02-23 | QTR3 | 21/22 | 2 | 5 | 550 | 625 | 550 | 86.36% | 1 | 75 | 0 | 0 | 75 | 0 | 9424555 | 81813 | 9342742 | 9468450 | 9631445 | 0 | 0 | 0 | 9631445 | 9680052 | 103.6% | 1 | 92003 | 43895 | 40 | 35 | 0 | 0 | 3920 | 0 | 0 | 0 | 3096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76905 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2024-05-23 | QTR4 | 23/24 |  | 2023-12-01 | QTR2 | 23/24 | 108 | 9297482.95
| Dist 01 - Central Let Contrats SubTotal |  |  |  |  | 27 | 47 | 127 | 7864 | 12097 | 12578 | 62.96% | 17 | -481 | 695 | 0 | 3214 | 1019 | 150255175 | 1476038 | 148779137 | 157497293 | 156021987 | -804216 | 0 | -804216 | 155217770 | 157545620 | 77.78% | 21 | 4842201 | 7242116 | 2666 | 740 | 10 | 441 | 2817986 | 334395 | 88 | 111 | 2913653 | 273914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36050 | 0 | 0 | 0 | 121064 | 3140 | 0 | 0 | 514208 | 0 | 0 | 0 | 0 | 0 | 805 | 499 | 1332815 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 72362 | 88730 | 0 | 0 | 0 | 0 | 25 | 0 | -287200 | 0 | 955 | 1051 | 7520943 | 700180
| 01 | E1S66 | 43813715201 | 2020-12-03 | QTR2 | 20/21 | 6 | 8 | 450 | 845 | 838 | 156.9% | 0 | 7 | 0 | 0 | 132 | 263 | 8623489 | 90613 | 8532876 | 9397066 | 9294008 | 0 | 0 | 0 | 9294008 | 9490393 | 111.2% | 0 | 487144 | 773578 | 84 | 48 | 0 | 71 | 305583 | 0 | 0 | 84 | 299190 | 27177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 15720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 815494 | 27177 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 |  | 2023-06-30 | QTR4 | 22/23 | 115 | 7399516.3 | B10:B2:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
| 01 | E1S92 | 44153415201 | 2021-11-04 | QTR2 | 21/22 | 3 | 2 | 275 | 390 | 390 | 101.8% | 1 | 0 | 0 | 0 | 115 | 0 | 5052712 | 52873 | 4999839 | 4990876 | 4942213 | 0 | 0 | 0 | 4942213 | 5001843 | 100% | 1 | 59630 | -61836 | 87 | 23 | 0 | 0 | 0 | 0 | 5 | 0 | 6022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42313 | 0 | 5 | 0 | -55813 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-12-20 | QTR2 | 23/24 |  | 2023-09-11 | QTR1 | 23/24 | 115 | 4924224.57
| 01 | E1U10 | 44592715201 | 2021-10-21 | QTR2 | 21/22 | 1 | 2 | 90 | 345 | 339 | 93.33% | 1 | 6 | 0 | 0 | 58 | 197 | 1030376 | 38210 | 992166 | 1035071 | 1194101 | 0 | 0 | 0 | 1194101 | 1189756 | 119.9% | 0 | 0 | 4695 | 230 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18641 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 28229 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-10-27 | QTR2 | 23/24 |  | 2023-07-16 | QTR1 | 23/24 | 108 | 838447.1
| 01 | E1U11 | 43503825201 | 2021-09-16 | QTR1 | 21/22 | 1 | 1 | 197 | 242 | 472 | 216.8% | 0 | -230 | 230 | 0 | 45 | 0 | 2146553 | 50000 | 2096553 | 2448898 | 2092854 | -195268 | 0 | -195268 | 1897587 | 1897587 | 90.51% | 1 | 0 | 302345 | 27 | 18 | 0 | 0 | 14495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349794 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-03-27 | QTR3 | 23/24 |  | 2023-12-20 | QTR2 | 23/24 | 115 | 1604001.39
| 01 | E1U12 | 44155315201 | 2021-09-16 | QTR1 | 21/22 | 2 | 4 | 300 | 439 | 422 | 94.33% | 1 | 17 | 0 | 0 | 139 | 0 | 6272386 | 62629 | 6209757 | 6303322 | 6506395 | 0 | 0 | 0 | 6506395 | 6911842 | 111.3% | 0 | 427490 | 30935 | 115 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 8892 | 976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 22043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 35473 | 976 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-12 | QTR1 | 23/24 |  | 2023-05-12 | QTR4 | 22/23 | 108 | 6222847.06
| 01 | E1U14 | 44477715201 | 2021-12-02 | QTR2 | 21/22 | 2 | 2 | 160 | 222 | 222 | 107.5% | 1 | 0 | 0 | 0 | 62 | 0 | 3819554 | 50000 | 3769554 | 3657701 | 3521817 | 0 | 0 | 0 | 3521817 | 3658011 | 97.04% | 1 | 136195 | -161853 | 29 | 21 | 12 | 0 | 56568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -218421 | 0 | 12 | 0 | -161853 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-07-21 | QTR1 | 23/24 |  | 2023-03-03 | QTR3 | 22/23 | 115 | 3928132.77 | B0 | ACC - LUMP SUM
| 01 | E1U17 | 44594115201 | 2022-02-17 | QTR3 | 21/22 | 1 | 0 | 150 | 171 | 166 | 96.67% | 1 | 5 | 0 | 0 | 21 | 0 | 722056 | 48017 | 674039 | 722056 | 642082 | 0 | 100000 | 100000 | 742082 | 642815 | 95.37% | 1 | -99267 | 0 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-03-17 | QTR3 | 22/23 | 115 | 1070560.76 | B1 | ACC - NO EXCUSE BONUS
| 01 | E1U22 | 44198315201 | 2022-07-21 | QTR1 | 22/23 | 2 | 2 | 170 | 194 | 187 | 95.88% | 1 | 7 | 0 | 0 | 24 | 0 | 2187528 | 50000 | 2137528 | 2184764 | 2110755 | 0 | 0 | 0 | 2110755 | 2091701 | 97.86% | 1 | -13720 | -2764 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 15242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27348 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-01-03 | QTR3 | 23/24 |  | 2023-11-06 | QTR2 | 23/24 | 108 | 1943940.24 | B0 | ACC - LUMP SUM
| 01 | E1U62 | 43852825201 | 2022-03-14 | QTR3 | 21/22 | 1 | 2 | 410 | 530 | 528 | 110% | 1 | 2 | 0 | 0 | 120 | 0 | 6357542 | 50000 | 6307542 | 6484969 | 6447894 | 0 | 0 | 0 | 6447894 | 6320466 | 100.2% | 1 | 0 | 127428 | 46 | 31 | 43 | 0 | 12925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 140352 | 0 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2024-02-22 | QTR3 | 23/24 |  | 2023-10-27 | QTR2 | 23/24 | 115 | 4194626.61 | LBDB | LOW BID DESIGN BUILD
| 01 | E1U96 | 44787715201 | 2022-05-02 | QTR4 | 21/22 | 4 | 4 | 450 | 555 | 552 | 104% | 1 | 3 | 0 | 0 | 84 | 21 | 3028512 | 50000 | 2978512 | 3275716 | 3237381 | 0 | 0 | 0 | 3237381 | 3222484 | 108.2% | 1 | -14897 | 247204 | 37 | 47 | 0 | 21 | 110349 | 0 | 0 | 0 | 136854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 258869 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-05-14 | QTR4 | 23/24 |  | 2024-01-21 | QTR3 | 23/24 | 108 | 2974793.54 | LBDB:LBDB::::Y | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| 01 | E1V07 | 44023115201 | 2022-09-15 | QTR1 | 22/23 | 1 | 3 | 75 | 75 | 72 | 96% | 1 | 3 | 0 | 0 | 0 | 0 | 289419 | 14419 | 275000 | 311381 | 315649 | 0 | 0 | 0 | 315649 | 315649 | 114.8% | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 6636 | 0 | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28598 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2023-08-09 | QTR1 | 23/24 |  | 2023-03-29 | QTR3 | 22/23 | 118 | 331704.75
| 01 | E1V14 | 44023715201 | 2023-02-16 | QTR3 | 22/23 | 1 | 1 | 120 | 164 | 164 | 108.3% | 1 | 0 | 0 | 0 | 44 | 0 | 1096407 | 50000 | 1046407 | 1123291 | 1184828 | 0 | 0 | 0 | 1184828 | 1157944 | 110.7% | 0 | 0 | 26884 | 15 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 26884 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-04-30 | QTR4 | 23/24 |  | 2024-01-03 | QTR3 | 23/24 | 115 | 1215794.64
| 01 | E1V17 | 44547515201 | 2023-02-16 | QTR3 | 22/23 | 1 | 2 | 150 | 197 | 183 | 90.67% | 1 | 14 | 0 | 0 | 47 | 0 | 3191521 | 50000 | 3141521 | 3202707 | 3243015 | 0 | 0 | 0 | 3243015 | 3244009 | 103.3% | 1 | 12179 | 11186 | 34 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 14163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25349 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-03-05 | QTR3 | 23/24 |  | 2023-12-22 | QTR2 | 23/24 | 113 | 3232954.27
| 01 | E1V19 | 44620915201 | 2023-02-16 | QTR3 | 22/23 | 1 | 0 | 120 | 146 | 145 | 103.3% | 1 | 1 | 0 | 0 | 21 | 5 | 2718429 | 50000 | 2668429 | 2718429 | 2702583 | 0 | 0 | 0 | 2702583 | 2702583 | 101.3% | 1 | 0 | 0 | 5 | 16 | 0 | 5 | 10433 | 0 | 0 | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 11693 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-04-16 | QTR4 | 23/24 |  | 2024-02-09 | QTR3 | 23/24 | 118 | 2913080.09 | B0 | ACC - LUMP SUM
| 01 | E1V20 | 44620315201 | 2022-11-03 | QTR2 | 22/23 | 1 | 2 | 185 | 216 | 212 | 97.84% | 1 | 4 | 0 | 0 | 31 | 0 | 3919123 | 50000 | 3869123 | 3942427 | 4025522 | 0 | 0 | 0 | 4025522 | 3972960 | 102.7% | 1 | -46071 | 23303 | 22 | 9 | 0 | 0 | 46573 | 0 | 0 | 0 | 16812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69876 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-02-05 | QTR3 | 23/24 |  | 2023-10-26 | QTR2 | 23/24 | 118 | 4631315.91
| 01 | E1V21 | 44782415201 | 2023-03-16 | QTR3 | 22/23 | 1 | 0 | 165 | 187 | 142 | 72.73% | 1 | 45 | 0 | 0 | 22 | 0 | 1465139 | 50000 | 1415139 | 1465139 | 1275611 | 0 | 0 | 0 | 1275611 | 1275611 | 90.14% | 1 | 0 | 0 | 4 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-05-02 | QTR4 | 23/24 |  | 2024-03-19 | QTR3 | 23/24 | 115 | 1729896.93
| 01 | E1V34 | 44972015201 | 2022-05-18 | QTR4 | 21/22 | 1 | 2 | 500 | 577 | 550 | 98.4% | 1 | 27 | 0 | 0 | 77 | 0 | 2335000 | 50000 | 2285000 | 2358883 | 2307883 | 0 | 0 | 0 | 2307883 | 2307883 | 101% | 1 | 0 | 23883 | 19 | 39 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23883 | 15720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 23883 | 15720 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2024-04-11 | QTR4 | 23/24 |  | 2024-02-28 | QTR3 | 23/24 | 106 | 2186687.91 | Y | DESIGN/BUILD PROJECT
| Dist 01 District Let Contracts SubTotal |  |  |  |  | 17 | 30 | 37 | 3967 | 5495 | 5584 | 88.24% | 15 | -89 | 230 | 0 | 1042 | 486 | 54255746 | 856761 | 53398985 | 55622696 | 55044591 | -195268 | 100000 | -95268 | 54949324 | 55403537 | 70.59% | 12 | 948683 | 1366950 | 774 | 376 | 65 | 97 | 563562 | 0 | 24 | 84 | 525641 | 28153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554886 | 15720 | 0 | 0 | 21391 | 0 | 0 | 0 | 0 | 0 | 45 | 245 | 219432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | -260734 | 0 | 134 | 486 | 1624176 | 43873
| District 01 Totals |  |  |  |  | 44 | 77 | 164 | 11831 | 17592 | 18162 | 72.73% | 32 | -570 | 925 | 0 | 4256 | 1505 | 204510921 | 2332799 | 202178122 | 213119989 | 211066578 | -999484 | 100000 | -899484 | 210167094 | 212949157 | 75% | 33 | 5790884 | 8609066 | 3440 | 1116 | 75 | 538 | 3381548 | 334395 | 112 | 195 | 3439294 | 302067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36050 | 0 | 0 | 0 | 675950 | 18860 | 0 | 0 | 535599 | 0 | 0 | 0 | 0 | 0 | 850 | 744 | 1552247 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 72362 | 88730 | 0 | 60 | 0 | 0 | 25 | 0 | -547934 | 0 | 1089 | 1537 | 9145119 | 744053
| 02 | T2703 | 21272425201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 550 | 719 | 968 | 145.3% | 0 | -249 | 249 | 0 | 169 | 0 | 11717625 | 120 | 11717505 | 11666748 | 11573612 | -1206768 | 0 | -1206768 | 10366844 | 10334162 | 88.19% | 1 | -32682 | -50877 | 123 | 46 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68877 | 0 | 0 | 0 | -50877 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 |  | 2021-05-03 | QTR4 | 20/21 | 209 | 12539660.43
| 02 | T2725 | 42307145201 | 2018-12-05 | QTR2 | 18/19 | 1 | 5 | 300 | 737 | 737 | 185.3% | 0 | 0 | 0 | 0 | 181 | 256 | 7294444 | 68754 | 7225690 | 7636147 | 7798283 | 0 | 0 | 0 | 7798283 | 7754246 | 107.3% | 1 | -44037 | 341703 | 85 | 96 | 0 | 27 | 92502 | 0 | 0 | 229 | 220039 | 17548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4989 | 0 | 0 | 0 | 6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 330105 | 23598 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2021-06-17 | QTR4 | 20/21 | 214 | 7079691.78
| 02 | T2749 | 43946715201 | 2019-09-25 | QTR1 | 19/20 | 3 | 10 | 600 | 1149 | 1149 | 134% | 0 | 0 | 0 | 0 | 265 | 284 | 11950705 | 126323 | 11824382 | 12606239 | 12535468 | 0 | 0 | 0 | 12535468 | 12707911 | 107.5% | 1 | 309266 | 655533 | 237 | 108 | 0 | 39 | 488108 | 0 | 0 | 59 | 227908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 4468 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 726457 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-28 | QTR1 | 23/24 |  | 2023-02-27 | QTR3 | 22/23 | 208 | 11844644.47
| 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 127.2% | 0 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 109.4% | 1 | 329791 | 87098 | 104 | 52 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-11-17 | QTR2 | 23/24 |  | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6
| 02 | T2758 | 43939915201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 280 | 461 | 461 | 123.2% | 0 | 0 | 0 | 0 | 116 | 65 | 6913040 | 75958 | 6837082 | 6913040 | 6429139 | 0 | 0 | 0 | 6429139 | 6454714 | 94.41% | 1 | 25575 | 0 | 81 | 35 | 0 | 0 | 2836 | 0 | 0 | 1 | 16654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 19491 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-05 | QTR3 | 23/24 |  | 2021-08-16 | QTR1 | 21/22 | 214 | 7673392.05
| 02 | T2772 | 43404115201 | 2020-05-20 | QTR4 | 19/20 | 4 | 3 | 850 | 1193 | 1193 | 110.8% | 1 | 0 | 0 | 0 | 334 | 9 | 10836000 | 86543 | 10749457 | 11135538 | 11386435 | 0 | 0 | 0 | 11386435 | 11424606 | 106.3% | 1 | 521916 | 299538 | 143 | 108 | 0 | 0 | 0 | 0 | 8 | 0 | 130911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 168628 | 57676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 0 | 299538 | 57676 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-04-03 | QTR4 | 23/24 |  | 2023-12-06 | QTR2 | 23/24 | 208 | 8768180.16
| 02 | T2787 | 44105915201 | 2020-07-29 | QTR1 | 20/21 | 1 | 2 | 250 | 376 | 373 | 116.8% | 1 | 3 | 0 | 0 | 81 | 45 | 13904803 | 145464 | 13759339 | 14427901 | 14501738 | 0 | 0 | 0 | 14501738 | 14430355 | 104.9% | 1 | -71383 | 523099 | 59 | 22 | 0 | 45 | 523099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 523099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-16 | QTR2 | 23/24 |  | 2021-09-15 | QTR1 | 21/22 | 209 | 14722615.57
| 02 | T2788 | 44258115201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 240 | 516 | 513 | 122.1% | 0 | 3 | 0 | 0 | 220 | 56 | 7945667 | 68632 | 7877035 | 7945667 | 8114839 | 0 | 0 | 0 | 8114839 | 8571019 | 108.8% | 1 | 459557 | 0 | 196 | 24 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-16 | QTR2 | 23/24 |  | 2022-07-07 | QTR1 | 22/23 | 209 | 6919711.56
| 02 | T2796 | 44119415201 | 2021-03-31 | QTR3 | 20/21 | 2 | 2 | 200 | 703 | 703 | 253.5% | 0 | 0 | 0 | 0 | 67 | 436 | 1882079 | 50000 | 1832079 | 1993425 | 1914819 | 0 | 0 | 0 | 1914819 | 1920086 | 104.8% | 1 | 5267 | 111345 | 142 | 54 | 0 | 265 | 118838 | 51945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 118838 | 51945 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-02-21 | QTR3 | 23/24 |  | 2023-12-06 | QTR2 | 23/24 | 208 | 1441903.37
| 02 | T2802 | 43575715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 180 | 523 | 523 | 220% | 0 | 0 | 0 | 0 | 29 | 314 | 1262262 | 50000 | 1212262 | 1262262 | 1249368 | 0 | 0 | 0 | 1249368 | 1249498 | 103.1% | 1 | 130 | 0 | 103 | 24 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2022-12-23 | QTR2 | 22/23 | 208 | 1338362.89
| 02 | T2803 | 44126115201 | 2021-05-26 | QTR4 | 20/21 | 2 | 3 | 325 | 487 | 487 | 124.6% | 0 | 0 | 0 | 0 | 162 | 0 | 4633748 | 75000 | 4558748 | 3852057 | 3929376 | 0 | 0 | 0 | 3929376 | 4154909 | 91.14% | 1 | 225533 | -781691 | 40 | 42 | 30 | 0 | -739805 | 0 | 0 | 0 | 7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -732738 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2023-01-06 | QTR3 | 22/23 | 208 | 4540382.58
| 02 | T2821 | 44327315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 150 | 289 | 271 | 122.7% | 0 | 18 | 0 | 0 | 118 | 21 | 4876894 | 52518 | 4824376 | 4984966 | 5022406 | 0 | 0 | 0 | 5022406 | 5415141 | 112.2% | 0 | 392735 | 108073 | 77 | 10 | 0 | 21 | 141356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 21 | 141356 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 |  | 2022-10-13 | QTR2 | 22/23 | 216 | 5483810.94
| 02 | T2822 | 44331315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 250 | 488 | 483 | 98.8% | 1 | 5 | 0 | 0 | 236 | 2 | 9173879 | 91638 | 9082241 | 9173879 | 9342688 | 0 | 0 | 0 | 9342688 | 9910699 | 109.1% | 1 | 568010 | 0 | 205 | 31 | 28 | 0 | 0 | 0 | 0 | 0 | 12476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 2 | 12476 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-03 | QTR2 | 23/24 |  | 2023-06-29 | QTR4 | 22/23 | 209 | 9935885.58
| 02 | T2824 | 44327415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 2 | 250 | 455 | 453 | 105.2% | 1 | 2 | 0 | 0 | 190 | 15 | 3471681 | 50000 | 3421681 | 3603585 | 3475517 | 0 | 0 | 0 | 3475517 | 3614982 | 105.6% | 1 | 141674 | 131904 | 166 | 24 | 0 | 0 | 34801 | 0 | 0 | 15 | 132601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 15 | 169611 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-05-04 | QTR4 | 22/23 | 216 | 3836185.04
| 02 | T2825 | 44328215201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 75 | 125 | 124 | 152% | 0 | 1 | 0 | 0 | 10 | 40 | 698919 | 27456 | 671464 | 698919 | 656099 | 0 | 0 | 0 | 656099 | 656099 | 97.71% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-14 | QTR1 | 23/24 |  | 2022-06-28 | QTR4 | 21/22 | 209 | 629198.54
| 02 | T2826 | 44331115201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 220 | 264 | 264 | 100% | 1 | 0 | 0 | 0 | 44 | 0 | 8657266 | 87492 | 8569774 | 8657266 | 8107793 | 0 | 0 | 0 | 8107793 | 8099899 | 94.52% | 1 | -7895 | 0 | 23 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-29 | QTR1 | 23/24 |  | 2023-05-05 | QTR4 | 22/23 | 209 | 10016766.94
| 02 | T2827 | 43935715201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 300 | 388 | 388 | 107.7% | 1 | 0 | 0 | 0 | 65 | 23 | 6658470 | 60239 | 6598231 | 6939208 | 6857539 | 0 | 0 | 0 | 6857539 | 7130536 | 108.1% | 1 | 272997 | 280738 | 40 | 25 | 0 | 0 | 1266 | 0 | 0 | 20 | 304513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 305779 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-05 | QTR3 | 23/24 |  | 2023-06-28 | QTR4 | 22/23 | 214 | 7633373.36
| 02 | T2829 | 44120815201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 150 | 227 | 224 | 117.3% | 1 | 3 | 0 | 0 | 48 | 29 | 1047740 | 50000 | 997740 | 1047740 | 1004140 | 0 | 0 | 0 | 1004140 | 1004137 | 100.6% | 1 | -3 | 0 | 28 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-10-03 | QTR2 | 23/24 |  | 2023-06-01 | QTR4 | 22/23 | 208 | 1984965.49
| 02 | T2833 | 44325815201 | 2022-01-12 | QTR3 | 21/22 | 1 | 0 | 210 | 235 | 235 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 6173212 | 71171 | 6102041 | 6173212 | 6149692 | 0 | 0 | 0 | 6149692 | 6808147 | 111.6% | 0 | 658455 | 0 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 37498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41624 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2022-11-23 | QTR2 | 22/23 | 214 | 7484487.76
| 02 | T2835 | 44327215201 | 2022-01-26 | QTR3 | 21/22 | 1 | 2 | 250 | 442 | 442 | 100% | 1 | 0 | 0 | 0 | 192 | 0 | 9730642 | 103892 | 9626750 | 9751076 | 10241376 | 0 | 0 | 0 | 10241376 | 10650890 | 110.6% | 0 | 409515 | 20434 | 166 | 26 | 0 | 0 | 116950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | -27382 | 0 | 120 | 0 | 89568 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-02-20 | QTR3 | 23/24 |  | 2023-08-28 | QTR1 | 23/24 | 216 | 11590621.81
| 02 | T2836 | 44325915201 | 2022-02-23 | QTR3 | 21/22 | 2 | 2 | 210 | 287 | 287 | 118.6% | 1 | 0 | 0 | 0 | 72 | 5 | 4069827 | 50000 | 4019827 | 4084043 | 4107794 | 0 | 0 | 0 | 4107794 | 4236681 | 105.4% | 1 | 130239 | 14216 | 19 | 19 | 0 | 0 | 0 | 0 | 34 | 0 | 12864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 14216 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-02 | QTR2 | 23/24 |  | 2023-04-17 | QTR4 | 22/23 | 208 | 5072861.67
| 02 | T2837 | 44329415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 0 | 180 | 262 | 260 | 113.9% | 1 | 2 | 0 | 0 | 55 | 27 | 1371850 | 50000 | 1321850 | 1371850 | 1320562 | 0 | 0 | 0 | 1320562 | 1320562 | 99.9% | 1 | 0 | 0 | 29 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 |  | 2023-01-19 | QTR3 | 22/23 | 208 | 1352767.24
| 02 | T2845 | 44119425201 | 2022-05-25 | QTR4 | 21/22 | 1 | 1 | 100 | 303 | 303 | 255% | 0 | 0 | 0 | 0 | 67 | 136 | 917218 | 36854 | 880364 | 984061 | 1118191 | 0 | 0 | 0 | 1118191 | 1118191 | 127% | 0 | 0 | 66843 | 22 | 26 | 0 | 30 | 23646 | 0 | 0 | 50 | 66843 | 66843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 90489 | 66843 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 |  | 2024-01-11 | QTR3 | 23/24 | 208 | 862998.91
| 02 | T2846 | 44126015201 | 2022-01-12 | QTR3 | 21/22 | 2 | 1 | 300 | 413 | 418 | 101.7% | 1 | -5 | 5 | 0 | 113 | 0 | 9551621 | 106078 | 9445543 | 9552942 | 9869457 | -18930 | 0 | -18930 | 9850527 | 10484168 | 111% | 0 | 634962 | 1321 | 83 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2504 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-11-02 | QTR2 | 23/24 |  | 2023-05-25 | QTR4 | 22/23 | 208 | 11919284.18
| 02 | T2847 | 44328315201 | 2022-03-30 | QTR3 | 21/22 | 2 | 0 | 197 | 390 | 390 | 107.6% | 1 | 0 | 0 | 0 | 178 | 15 | 8536881 | 91154 | 8445727 | 8536881 | 9157134 | 0 | 0 | 0 | 9157134 | 9260550 | 109.6% | 1 | 103416 | 0 | 156 | 22 | 0 | 1 | 23794 | 0 | 0 | 14 | 12482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 15 | 36276 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-12 | QTR3 | 23/24 |  | 2023-08-31 | QTR1 | 23/24 | 209 | 10386871.81
| 02 | T2848 | 44330515201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 360 | 392 | 383 | 97.5% | 1 | 9 | 0 | 0 | 32 | 0 | 13369606 | 130623 | 13238982 | 13375355 | 13678461 | 0 | 0 | 0 | 13678461 | 14086129 | 106.4% | 1 | 413419 | 5750 | 13 | 19 | 0 | 0 | 3089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15345 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-22 | QTR3 | 23/24 |  | 2023-08-03 | QTR1 | 23/24 | 214 | 15619864.41
| 02 | T2855 | 43935815201 | 2021-06-09 | QTR4 | 20/21 | 2 | 0 | 350 | 464 | 459 | 106.6% | 1 | 5 | 0 | 0 | 86 | 28 | 7918962 | 100000 | 7818962 | 7918962 | 7962203 | 0 | 0 | 0 | 7962203 | 8267055 | 105.7% | 1 | 304853 | 0 | 42 | 44 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 |  | 2023-02-23 | QTR3 | 22/23 | 209 | 7233767.77
| 02 | T2856 | 42983025201 | 2021-11-17 | QTR2 | 21/22 | 1 | 2 | 85 | 354 | 373 | 302.4% | 0 | -19 | 19 | 0 | 108 | 161 | 997892 | 42783 | 955110 | 1048834 | 1111095 | -32186 | 0 | -32186 | 1078909 | 1111095 | 116.3% | 0 | 32186 | 50942 | 46 | 70 | 0 | 0 | 0 | 0 | 22 | 121 | 80716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 151 | 80716 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-02-14 | QTR3 | 23/24 |  | 2023-06-08 | QTR4 | 22/23 | 214 | 943264.64
| 02 | T2857 | 44721115201 | 2022-01-26 | QTR3 | 21/22 | 1 | 0 | 120 | 193 | 185 | 131.7% | 0 | 8 | 0 | 0 | 27 | 46 | 1077522 | 44955 | 1032567 | 1077522 | 1075156 | 0 | 0 | 0 | 1075156 | 1075156 | 104.1% | 1 | 0 | 0 | 16 | 11 | 0 | 30 | 18350 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 18350 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2022-10-14 | QTR2 | 22/23 | 208 | 1339271.36
| 02 | T2869 | 43567925201 | 2022-06-08 | QTR4 | 21/22 | 2 | 0 | 180 | 199 | 178 | 88.33% | 1 | 21 | 0 | 0 | 19 | 0 | 1298306 | 50000 | 1248306 | 1298306 | 1209436 | 0 | 0 | 0 | 1209436 | 1209097 | 96.86% | 1 | -339 | 0 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 |  | 2023-04-19 | QTR4 | 22/23 | 209 | 1554775.94
| 02 | T2872 | 44534115201 | 2022-06-08 | QTR4 | 21/22 | 1 | 0 | 300 | 355 | 351 | 98.67% | 1 | 4 | 0 | 0 | 55 | 0 | 13193368 | 109807 | 13083561 | 13193368 | 13034580 | 0 | 0 | 0 | 13034580 | 12703529 | 97.1% | 1 | -331050 | 0 | 29 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-02-20 | QTR3 | 23/24 |  | 2023-08-23 | QTR1 | 23/24 | 208 | 10896297.69
| 02 | T2873 | 44557615201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 90 | 90 | 19 | 21.11% | 1 | 71 | 0 | 0 | 0 | 0 | 240110 | 17791 | 222319 | 240110 | 185940 | 0 | 0 | 0 | 185940 | 185940 | 83.64% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-03-31 | QTR3 | 22/23 | 208 | 402519.71
| 02 | T2875 | 44912925201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 60 | 160 | 160 | 151.7% | 0 | 0 | 0 | 0 | 69 | 31 | 1386562 | 50000 | 1336562 | 1386562 | 1349510 | 0 | 0 | 0 | 1349510 | 1349510 | 101% | 1 | 0 | 0 | 53 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-30 | QTR2 | 23/24 |  | 2023-03-14 | QTR3 | 22/23 | 208 | 1705476.65
| 02 | T2877 | 20954355201 | 2022-06-15 | QTR4 | 21/22 | 2 | 3 | 90 | 144 | 140 | 118.9% | 1 | 4 | 0 | 0 | 47 | 7 | 744369 | 43296 | 701073 | 788349 | 712669 | 0 | 0 | 0 | 712669 | 709731 | 101.2% | 1 | 0 | 43980 | 10 | 23 | 0 | 0 | 0 | 0 | 0 | 7 | 41042 | 41042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7 | 43980 | 41042 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-07 | QTR2 | 23/24 |  | 2023-01-24 | QTR3 | 22/23 | 208 | 931264.85
| 02 | T2879 | 44535315201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 150 | 259 | 259 | 100% | 1 | 0 | 0 | 0 | 109 | 0 | 5044796 | 61908 | 4982887 | 5044796 | 5157015 | 0 | 0 | 0 | 5157015 | 5122877 | 102.8% | 1 | -34138 | 0 | 82 | 27 | 0 | 0 | 1064 | 0 | 0 | 0 | 6899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 8983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 17882 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-06-10 | QTR4 | 23/24 |  | 2024-01-24 | QTR3 | 23/24 | 216 | 5802841.18
| 02 | T2880 | 21293465201 | 2022-08-31 | QTR1 | 22/23 | 2 | 1 | 150 | 265 | 265 | 129.3% | 0 | 0 | 0 | 0 | 71 | 44 | 621970 | 20266 | 601704 | 626401 | 439109 | 0 | 0 | 0 | 439109 | 439109 | 72.98% | 1 | 0 | 4431 | 52 | 19 | 0 | 44 | 18107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 18107 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-02-20 | QTR3 | 23/24 |  | 2023-11-09 | QTR2 | 23/24 | 214 | 485437.68
| 02 | T2881 | 44554015201 | 2022-11-16 | QTR2 | 22/23 | 1 | 0 | 150 | 293 | 293 | 116% | 1 | 0 | 0 | 0 | 112 | 31 | 1959156 | 50000 | 1909156 | 1959156 | 1946528 | 0 | 0 | 0 | 1946528 | 1943700 | 101.8% | 1 | -2828 | 0 | 103 | 16 | 0 | 0 | 0 | 0 | 7 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 17 | 0 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 |  | 2023-12-04 | QTR2 | 23/24 | 208 | 1697524.17
| 02 | T2883 | 44912955201 | 2022-10-26 | QTR2 | 22/23 | 1 | 1 | 80 | 188 | 188 | 100% | 1 | 0 | 0 | 0 | 108 | 0 | 2185964 | 50000 | 2135964 | 2192335 | 1926696 | 0 | 0 | 0 | 1926696 | 1926696 | 90.2% | 1 | 0 | 6371 | 99 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 6371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6371 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-11 | QTR3 | 23/24 |  | 2023-09-29 | QTR1 | 23/24 | 208 | 2721077.2
| 02 | T2887 | 44729015201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 119 | 132 | 126 | 94.96% | 1 | 6 | 0 | 0 | 13 | 0 | 782704 | 28281 | 754423 | 782704 | 743960 | 0 | 0 | 0 | 743960 | 743960 | 98.61% | 1 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2024-02-13 | QTR3 | 23/24 |  | 2023-06-05 | QTR4 | 22/23 | 208 | 659451.55
| 02 | T2888 | 40392055201 | 2022-05-25 | QTR4 | 21/22 | 2 | 0 | 119 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 30 | 97 | 928540 | 44276 | 884264 | 928540 | 970153 | 0 | 0 | 0 | 970153 | 970153 | 109.7% | 1 | 0 | 0 | 118 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-03-04 | QTR3 | 23/24 |  | 2023-10-11 | QTR2 | 23/24 | 208 | 881584.15
| 02 | T2892 | 21071935201 | 2022-10-05 | QTR2 | 22/23 | 2 | 1 | 180 | 315 | 291 | 138.3% | 0 | 24 | 0 | 0 | 135 | 0 | 9775622 | 97298 | 9678325 | 9736781 | 9879780 | 0 | 0 | 0 | 9879780 | 9713317 | 100.4% | 1 | -166463 | -38842 | 25 | 17 | 30 | 0 | -38842 | 0 | 0 | 0 | 10688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | -23365 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-05-13 | QTR4 | 23/24 |  | 2023-12-05 | QTR2 | 23/24 | 209 | 10476736.76
| 02 | T2895 | 44125915201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 200 | 327 | 326 | 99.5% | 1 | 1 | 0 | 0 | 82 | 45 | 6674091 | 68301 | 6605790 | 6674091 | 6876375 | 0 | 0 | 0 | 6876375 | 6832975 | 103.4% | 1 | -43400 | 0 | 99 | 28 | 0 | 0 | 11618 | 0 | 0 | 0 | 12175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 23793 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2024-06-26 | QTR4 | 23/24 |  | 2024-03-14 | QTR3 | 23/24 | 214 | 6898412.52
| 02 | T2899 | 20761175201 | 2022-06-15 | QTR4 | 21/22 | 1 | 1 | 90 | 214 | 214 | 164.4% | 0 | 0 | 0 | 0 | 66 | 58 | 678930 | 39509 | 639421 | 678930 | 558364 | 0 | 0 | 0 | 558364 | 558364 | 87.32% | 1 | 0 | 0 | 44 | 22 | 0 | 8 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2024-02-21 | QTR3 | 23/24 |  | 2023-07-14 | QTR1 | 23/24 | 214 | 998390.21
| 02 | T2902 | 43928015201 | 2022-11-16 | QTR2 | 22/23 | 2 | 2 | 250 | 364 | 331 | 112.8% | 1 | 33 | 0 | 0 | 40 | 74 | 3588897 | 120 | 3588777 | 4279812 | 4203052 | 0 | 0 | 0 | 4203052 | 4179179 | 116.5% | 0 | -4238 | 690915 | 24 | 25 | 0 | 65 | 671280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 19635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 690915 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-06-14 | QTR4 | 23/24 |  | 2024-02-28 | QTR3 | 23/24 | 209 | 4177372.15
| 02 | T2903 | 44556915201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 60 | 109 | 109 | 140% | 0 | 0 | 0 | 0 | 25 | 24 | 203240 | 10914 | 192326 | 203240 | 190113 | 0 | 0 | 0 | 190113 | 190113 | 98.85% | 1 | 0 | 0 | 17 | 8 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-06-06 | QTR4 | 23/24 |  | 2023-12-21 | QTR2 | 23/24 | 214 | 229199.25
| 02 | T2923 | 44542625201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 74 | 101 | 94 | 91.89% | 1 | 7 | 0 | 0 | 26 | 1 | 212969 | 11187 | 201781 | 212969 | 198096 | 0 | 0 | 0 | 198096 | 198096 | 98.17% | 1 | 0 | 0 | 15 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-09-05 | QTR1 | 23/24 |  | 2023-03-01 | QTR3 | 22/23 | 208 | 251711.77
| 02 | T9023 | 44624515223 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 250 | 733 | 730 | 266.8% | 0 | 3 | 0 | 0 | 483 | 0 | 3516622 | 50000 | 3466622 | 3516622 | 3642093 | 0 | 0 | 0 | 3642093 | 3642131 | 105.1% | 1 | 38 | 0 | 14 | 49 | 420 | 0 | 0 | 0 | 0 | 0 | 30591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 41498 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-09-27 | QTR1 | 23/24 |  | 2023-08-03 | QTR1 | 23/24 | 209 | 3117936.11
| Dist 02 Central Let Contract SubTotal |  |  |  |  | 47 | 65 | 50 | 10524 | 17994 | 18034 | 57.45% | 27 | -40 | 273 | 0 | 5045 | 2425 | 238386498 | 2898285 | 235488212 | 240959322 | 242098132 | -1257884 | 0 | -1257884 | 240840248 | 245286682 | 85.11% | 40 | 5201078 | 2572824 | 3268 | 1367 | 528 | 844 | 1564432 | 51945 | 71 | 602 | 1404226 | 138981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788 | 0 | 14 | 0 | 20023 | 0 | 0 | 2 | 109555 | 67137 | 0 | 0 | 0 | 0 | 535 | 477 | 218457 | 58548 | 0 | 0 | 0 | 0 | 0 | 91 | 6050 | 6050 | 303 | 93 | 0 | 0 | 0 | 0 | -96259 | 0 | 1451 | 2109 | 3231271 | 322660
| 02 | E20H1 | 43737715201 | 2022-04-20 | QTR4 | 21/22 | 1 | 0 | 60 | 84 | 84 | 101.7% | 1 | 0 | 0 | 0 | 23 | 1 | 612540 | 23388 | 589152 | 612540 | 596655 | 0 | 0 | 0 | 596655 | 596655 | 101.3% | 1 | 0 | 0 | 9 | 14 | 0 | 1 | 7085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7085 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2024-02-20 | QTR3 | 23/24 |  | 2023-12-05 | QTR2 | 23/24 | 214 | 703931.46
| 02 | E20I1 | 43317155201 | 2022-05-11 | QTR4 | 21/22 | 1 | 0 | 300 | 480 | 480 | 107% | 1 | 0 | 0 | 0 | 172 | 8 | 5311071 | 50000 | 5261071 | 5311071 | 5141726 | 0 | 0 | 0 | 5141726 | 5104730 | 97.03% | 1 | -36996 | 0 | 127 | 32 | 0 | 8 | 40978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 4915 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 8 | 45894 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-22 | QTR3 | 23/24 |  | 2024-01-03 | QTR3 | 23/24 | 214 | 5008995.7
| 02 | E20T5 | 43044935201 | 2022-07-20 | QTR1 | 22/23 | 1 | 0 | 245 | 273 | 268 | 97.96% | 1 | 5 | 0 | 0 | 28 | 0 | 937789 | 50000 | 887789 | 937789 | 902864 | 0 | 0 | 0 | 902864 | 902864 | 101.7% | 1 | 0 | 0 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-01-08 | QTR3 | 23/24 |  | 2023-10-27 | QTR2 | 23/24 | 216 | 1332805.2
| 02 | E20T7 | 43089715201 | 2022-09-14 | QTR1 | 22/23 | 1 | 1 | 240 | 346 | 341 | 108.7% | 1 | 5 | 0 | 0 | 80 | 26 | 4193000 | 50000 | 4143000 | 4523767 | 4592009 | 0 | 0 | 0 | 4592009 | 4591894 | 110.8% | 0 | -116 | 330767 | 23 | 57 | 0 | 26 | 294029 | 0 | 0 | 0 | 68187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 380767 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-05-08 | QTR4 | 23/24 |  | 2024-03-01 | QTR3 | 23/24 | 216 | 4765385.7
| 02 | E20W3 | 43744215201 | 2022-06-08 | QTR4 | 21/22 | 2 | 3 | 300 | 412 | 411 | 109.3% | 1 | 1 | 0 | 0 | 83 | 29 | 2395648 | 50000 | 2345648 | 2453298 | 2436381 | 0 | 0 | 0 | 2436381 | 2403699 | 102.5% | 1 | -30 | 57650 | 49 | 34 | 0 | 29 | 69836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | 0 | 29 | 102486 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-04-03 | QTR4 | 23/24 |  | 2024-01-26 | QTR3 | 23/24 | 214 | 2554733
| 02 | E20W8 | 44277915201 | 2022-11-30 | QTR2 | 22/23 | 1 | 0 | 120 | 182 | 181 | 100% | 1 | 1 | 0 | 0 | 42 | 20 | 1761000 | 50000 | 1711000 | 1761000 | 1791422 | 0 | 0 | 0 | 1791422 | 1791366 | 104.7% | 1 | -56 | 0 | 50 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 8282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8282 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-01-19 | QTR3 | 23/24 |  | 2023-12-05 | QTR2 | 23/24 | 214 | 909989.25
| 02 | E2V58 | 43303615201 | 2016-12-14 | QTR2 | 16/17 | 4 | 30 | 1200 | 2440 | 2437 | 143% | 0 | 3 | 0 | 0 | 487 | 753 | 116979302 | 166302 | 116813000 | 128380916 | 129172623 | 0 | 0 | 0 | 129172623 | 128727437 | 110.2% | 0 | 1167595 | 11401614 | 472 | 249 | 0 | 293 | 4521354 | 76346 | 0 | 171 | 5769031 | 96498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108900 | 0 | 0 | 0 | 450899 | 18997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 474788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596 | 11324973 | 191841 | F363286318 | ARCHER WESTERN CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2024-04-17 | QTR4 | 23/24 |  | 2023-10-31 | QTR2 | 23/24 | 208 | 119230874.66 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
| 02 | E2Y76 | 20972255201 | 2020-04-15 | QTR4 | 19/20 | 2 | 2 | 400 | 967 | 967 | 177% | 0 | 0 | 0 | 0 | 259 | 308 | 4399943 | 50000 | 4349943 | 4455060 | 4448788 | 0 | 0 | 0 | 4448788 | 4443671 | 102.2% | 1 | 52479 | 55117 | 115 | 144 | 0 | 246 | 22225 | 0 | 0 | 0 | 56531 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 83873 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2023-11-28 | QTR2 | 23/24 |  | 2023-07-24 | QTR1 | 23/24 | 208 | 4855272.24
| 02 | E2Z33 | 43860815201 | 2019-11-26 | QTR2 | 19/20 | 2 | 10 | 600 | 1251 | 1251 | 122.3% | 0 | 0 | 0 | 0 | 517 | 134 | 25732018 | 150000 | 25582018 | 27245810 | 27216314 | 0 | 0 | 0 | 27216314 | 27282752 | 106.6% | 1 | 319145 | 1513792 | 449 | 68 | 0 | 0 | 115570 | 0 | 0 | 134 | 1522405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3543 | 0 | 0 | 0 | 0 | 0 | 403 | 0 | 5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42898 | 0 | 403 | 134 | 1603759 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-10 | QTR4 | 23/24 |  | 2023-10-13 | QTR2 | 23/24 | 209 | 20749475.95 | B8:B8::Y | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
| Dist 02 District Let Contracts SubTotal |  |  |  |  | 9 | 15 | 46 | 3465 | 6435 | 6420 | 66.67% | 6 | 15 | 0 | 0 | 1691 | 1279 | 162322311 | 639690 | 161682621 | 175681251 | 176298782 | 0 | 0 | 0 | 176298782 | 175845068 | 77.78% | 7 | 1502021 | 13358940 | 1302 | 629 | 0 | 603 | 5071077 | 76346 | 0 | 306 | 7424436 | 96498 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108900 | 0 | 13 | 0 | 469450 | 18997 | 0 | 0 | 8458 | 0 | 0 | 0 | 0 | 0 | 464 | 132 | 517696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | -42900 | 0 | 477 | 1122 | 13557119 | 191841
| District 02 Totals |  |  |  |  | 56 | 80 | 96 | 13989 | 24429 | 24454 | 58.93% | 33 | -25 | 273 | 0 | 6736 | 3704 | 400708809 | 3537975 | 397170833 | 416640573 | 418396914 | -1257884 | 0 | -1257884 | 417139030 | 421131750 | 83.93% | 47 | 6703099 | 15931764 | 4570 | 1996 | 528 | 1447 | 6635509 | 128291 | 71 | 908 | 8828662 | 235479 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113688 | 0 | 27 | 0 | 489473 | 18997 | 0 | 2 | 118013 | 67137 | 0 | 0 | 0 | 0 | 999 | 609 | 736153 | 58548 | 0 | 0 | 0 | 0 | 0 | 91 | 6050 | 6050 | 303 | 112 | 0 | 0 | 0 | 0 | -139159 | 0 | 1928 | 3231 | 16788390 | 514501
| 03 | T3579 | 41413245201 | 2016-08-31 | QTR1 | 16/17 | 3 | 19 | 1090 | 1999 | 2171 | 139.2% | 0 | -172 | 172 | 0 | 798 | 111 | 42140000 | 150000 | 41990000 | 43136516 | 44789798 | -789688 | 0 | -789688 | 44000110 | 45150067 | 107.5% | 1 | 1313007 | 996516 | 442 | 212 | 4 | 40 | 380492 | 1569 | 0 | 27 | 349096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 8 | 165208 | 0 | 0 | 0 | 18045 | 18045 | 0 | 0 | 0 | 0 | 0 | 0 | 50586 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -159429 | 0 | 80 | 121 | 898999 | 114614 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 |  | 2022-10-21 | QTR2 | 22/23 | 308 | 37004160.16
| 03 | T3598 | 43357725201 | 2021-12-08 | QTR2 | 21/22 | 2 | 0 | 210 | 314 | 314 | 100% | 1 | 0 | 0 | 0 | 104 | 0 | 1449372 | 9292 | 1440080 | 1449372 | 1245314 | 0 | 0 | 0 | 1245314 | 1245462 | 86.49% | 1 | 147 | 0 | 73 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-01-13 | QTR3 | 22/23 | 308 | 1387512.95
| 03 | T3604 | 43282815201 | 2019-02-27 | QTR3 | 18/19 | 2 | 4 | 925 | 1322 | 1301 | 103.1% | 1 | 21 | 0 | 0 | 397 | 0 | 10228411 | 103267 | 10125144 | 10251581 | 10265075 | 0 | 0 | 0 | 10265075 | 10328004 | 102% | 1 | 62929 | 23170 | 263 | 84 | 0 | 0 | 24478 | 0 | 0 | 0 | 5148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 120 | 68927 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2022-12-06 | QTR2 | 22/23 | 308 | 10230057.88
| 03 | T3664 | 43375115201 | 2021-06-09 | QTR4 | 20/21 | 4 | 1 | 185 | 509 | 509 | 218.4% | 0 | 0 | 0 | 0 | 275 | 49 | 2044978 | 50000 | 1994978 | 2045473 | 1907308 | 0 | 0 | 0 | 1907308 | 1907308 | 95.61% | 1 | 0 | 495 | 40 | 65 | 0 | 0 | 0 | 0 | 80 | 49 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 49 | 495 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-05-16 | QTR4 | 23/24 |  | 2023-03-03 | QTR3 | 22/23 | 313 | 2066195.42
| 03 | T3687 | 44072415201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 135 | 164 | 159 | 96.3% | 1 | 5 | 0 | 0 | 29 | 0 | 889778 | 0 | 889778 | 889778 | 849190 | 0 | 0 | 0 | 849190 | 848671 | 95.38% | 1 | -519 | 0 | 16 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-03-27 | QTR3 | 23/24 |  | 2023-09-22 | QTR1 | 23/24 | 321 | 1417656.86
| 03 | T3691 | 43717815201 | 2020-11-18 | QTR2 | 20/21 | 1 | 2 | 480 | 640 | 661 | 109% | 1 | -21 | 21 | 0 | 160 | 0 | 4269226 | 50000 | 4219226 | 4374816 | 4363593 | -30948 | 0 | -30948 | 4332645 | 4394715 | 104.2% | 1 | 138599 | 105591 | 98 | 40 | 8 | 0 | 95913 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 23399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 149628 | 0 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 |  | 2022-12-04 | QTR2 | 22/23 | 308 | 4154505.73
| 03 | T3702 | 42446455201 | 2018-09-26 | QTR1 | 18/19 | 4 | 17 | 1350 | 1989 | 1807 | 99.85% | 1 | 182 | 0 | 0 | 459 | 180 | 49837733 | 167160 | 49670573 | 55271608 | 58609882 | -12750 | 0 | -12750 | 58597132 | 58735900 | 118.3% | 0 | 554098 | 5433874 | 341 | 118 | 0 | 0 | 560255 | 43662 | 0 | 16 | 2344133 | 32770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 2385777 | 2433684 | 0 | 0 | 7220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108898 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 5461229 | 2510116 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-06-06 | QTR4 | 23/24 |  | 2024-01-29 | QTR3 | 23/24 | 306 | 51655054.35
| 03 | T3703 | 43649925201 | 2019-09-25 | QTR1 | 19/20 | 3 | 0 | 150 | 292 | 262 | 100% | 1 | 30 | 0 | 0 | 112 | 30 | 2458081 | 51140 | 2406941 | 2458081 | 2572160 | 0 | 0 | 0 | 2572160 | 2554701 | 106.1% | 1 | -17459 | 0 | 100 | 12 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2020-10-02 | QTR2 | 20/21 | 314 | 2031385.77
| 03 | T3704 | 43938815201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 150 | 222 | 220 | 106% | 1 | 2 | 0 | 0 | 72 | 0 | 1462111 | 0 | 1462111 | 1462111 | 1360760 | 0 | 0 | 0 | 1360760 | 1370361 | 93.72% | 1 | 9601 | 0 | 49 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 |  | 2022-10-07 | QTR2 | 22/23 | 313 | 1750125.19
| 03 | T3712 | 43937115201 | 2021-11-17 | QTR2 | 21/22 | 1 | 3 | 240 | 280 | 543 | 209.6% | 0 | -263 | 263 | 0 | 40 | 0 | 4199999 | 0 | 4199999 | 4207543 | 4275092 | -681696 | 0 | -681696 | 3593396 | 4275464 | 101.8% | 1 | 682068 | 7544 | 22 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 7544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7544 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-01 | QTR3 | 23/24 |  | 2023-08-31 | QTR1 | 23/24 | 321 | 3898368.97
| 03 | T3720 | 43936615201 | 2021-12-08 | QTR2 | 21/22 | 1 | 3 | 245 | 334 | 575 | 208.6% | 0 | -241 | 241 | 0 | 89 | 0 | 3077146 | 0 | 3077146 | 3077146 | 3008864 | -624672 | 0 | -624672 | 2384192 | 2402816 | 78.09% | 1 | 18624 | 0 | 37 | 27 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-20 | QTR3 | 23/24 |  | 2023-10-30 | QTR2 | 23/24 | 321 | 3261895.89
| 03 | T3728 | 21898425201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 420 | 706 | 706 | 112.6% | 1 | 0 | 0 | 0 | 286 | 0 | 5503848 | 53988 | 5449859 | 5503848 | 5615605 | 0 | 0 | 0 | 5615605 | 5632695 | 103.4% | 1 | 85241 | 0 | 181 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 21870 | 0 | 0 | 0 | 2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24418 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2023-10-30 | QTR2 | 23/24 |  | 2023-07-24 | QTR1 | 23/24 | 314 | 7823905.33
| 03 | T3733 | 43188365201 | 2022-11-16 | QTR2 | 22/23 | 1 | 1 | 140 | 298 | 298 | 110% | 1 | 0 | 0 | 0 | 158 | 0 | 1685940 | 50000 | 1635940 | 1730344 | 1594624 | 0 | 0 | 0 | 1594624 | 1590656 | 97.23% | 1 | -3968 | 44404 | 113 | 31 | 60 | 0 | 10492 | 4432 | 14 | 0 | 44005 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 54496 | 4742 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-06-12 | QTR4 | 23/24 |  | 2024-02-14 | QTR3 | 23/24 | 308 | 1924177.46
| 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 1 | 365 | 689 | 689 | 117.8% | 1 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6166449 | 6679471 | 0 | 0 | 0 | 6679471 | 7791843 | 128.1% | 0 | 1176465 | 0 | 170 | 89 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 21 | 67784 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29
| 03 | T3743 | 44173015201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 45 | 83 | 80 | 93.33% | 1 | 3 | 0 | 0 | 38 | 0 | 187229 | 12274 | 174955 | 187229 | 175598 | 0 | 0 | 0 | 175598 | 166353 | 95.08% | 1 | -9245 | 0 | 35 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2020-08-14 | QTR1 | 20/21 | 314 | 262871.46
| 03 | T3750 | 43811125201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 95 | 131 | 130 | 98.95% | 1 | 1 | 0 | 0 | 36 | 0 | 987732 | 41493 | 946239 | 927591 | 903555 | 0 | 0 | 0 | 903555 | 903555 | 95.49% | 1 | 0 | -60141 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-05-12 | QTR4 | 22/23 | 314 | 912225.16
| 03 | T3759 | 44014915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 11 | 454 | 705 | 664 | 114.8% | 1 | 41 | 0 | 0 | 187 | 64 | 6899119 | 54298 | 6844821 | 7276831 | 6961458 | 0 | 0 | 0 | 6961458 | 7368477 | 107.7% | 1 | 416838 | 377713 | 82 | 61 | 0 | 28 | 290730 | 0 | 4 | 43 | 65880 | 6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 71 | 358010 | 6394 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 |  | 2023-04-26 | QTR4 | 22/23 | 314 | 5086089.54
| 03 | T3773 | 44422025201 | 2023-05-24 | QTR4 | 22/23 | 1 | 0 | 80 | 263 | 237 | 67.5% | 1 | 26 | 0 | 0 | 183 | 0 | 556581 | 0 | 556581 | 556581 | 566850 | 0 | 0 | 0 | 566850 | 566850 | 101.8% | 1 | 0 | 0 | 161 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 |  | 2024-04-03 | QTR4 | 23/24 | 314 | 736778
| 03 | T3775 | 43256315201 | 2022-04-27 | QTR4 | 21/22 | 1 | 2 | 150 | 205 | 205 | 100% | 1 | 0 | 0 | 0 | 55 | 0 | 2579717 | 50000 | 2529717 | 2587262 | 2470218 | 0 | 0 | 0 | 2470218 | 2458123 | 97.17% | 1 | -12095 | 7545 | 47 | 8 | 0 | 0 | 5984 | 0 | 0 | 0 | 1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9474 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 |  | 2023-07-26 | QTR1 | 23/24 | 308 | 2583180.72
| 03 | T3784 | 43938515201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 100 | 119 | 100 | 81% | 1 | 19 | 0 | 0 | 19 | 0 | 830333 | 0 | 830333 | 830333 | 808692 | 0 | 0 | 0 | 808692 | 808692 | 97.39% | 1 | 0 | 0 | 10 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 |  | 2023-08-01 | QTR1 | 23/24 | 313 | 771890.7
| 03 | T3787 | 44158815201 | 2021-04-28 | QTR4 | 20/21 | 2 | 6 | 315 | 828 | 828 | 142.9% | 0 | 0 | 0 | 0 | 427 | 86 | 16418543 | 150000 | 16268543 | 16722911 | 17708583 | -15000 | -192500 | -207500 | 17501083 | 18173399 | 111.7% | 0 | 716852 | 304368 | 296 | 82 | 15 | 27 | 103528 | 3211 | 5 | 27 | 149230 | 80099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 18 | 37573 | 10652 | 7 | 14 | 59047 | 15703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 86 | 349378 | 109665 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-02 | QTR4 | 23/24 |  | 2023-10-31 | QTR2 | 23/24 | 308 | 18163993.95
| 03 | T3793 | 43467715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 3 | 230 | 481 | 480 | 106.1% | 1 | 1 | 0 | 0 | 236 | 15 | 6283852 | 73669 | 6210183 | 6727204 | 6844151 | 0 | 0 | 0 | 6844151 | 7176797 | 115.6% | 0 | 332646 | 443352 | 186 | 50 | 0 | 7 | 378034 | 0 | 0 | 8 | 133625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | -51237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 15 | 460422 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2023-06-28 | QTR4 | 22/23 | 308 | 7460138.28
| 03 | T3794 | 44364415201 | 2022-06-15 | QTR4 | 21/22 | 1 | 1 | 100 | 125 | 92 | 67% | 1 | 33 | 0 | 0 | 25 | 0 | 2537432 | 50000 | 2487432 | 2537432 | 2741257 | 0 | 0 | 0 | 2741257 | 2721406 | 109.4% | 1 | -19851 | 0 | 14 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-03-06 | QTR3 | 22/23 | 313 | 2975156.64
| 03 | T3796 | 44404615201 | 2022-01-26 | QTR3 | 21/22 | 1 | 2 | 105 | 181 | 202 | 152.4% | 0 | -21 | 21 | 0 | 76 | 0 | 1458732 | 50000 | 1408732 | 1483251 | 1401648 | -35574 | 0 | -35574 | 1366074 | 1366074 | 96.97% | 1 | 0 | 24520 | 30 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 24915 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-16 | QTR4 | 23/24 |  | 2022-10-31 | QTR2 | 22/23 | 308 | 2613265.24
| 03 | T3797 | 44365615201 | 2022-02-23 | QTR3 | 21/22 | 4 | 3 | 240 | 525 | 524 | 132.9% | 0 | 1 | 0 | 0 | 225 | 60 | 4361277 | 50000 | 4311277 | 5189354 | 5002338 | 0 | 0 | 0 | 5002338 | 5076487 | 117.7% | 0 | 74149 | 828077 | 144 | 61 | 20 | 30 | 402649 | 0 | 0 | 0 | 6727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 427409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 60 | 846684 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-01-22 | QTR3 | 23/24 |  | 2023-11-05 | QTR2 | 23/24 | 308 | 4172545.34
| 03 | T3800 | 44851815201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 140 | 252 | 239 | 141.4% | 0 | 13 | 0 | 0 | 90 | 22 | 3545980 | 0 | 3545980 | 3707781 | 3707779 | 0 | 0 | 0 | 3707779 | 3707779 | 104.6% | 1 | 0 | 161801 | 35 | 6 | 0 | 22 | 93590 | 0 | 49 | 0 | 68210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 22 | 161801 | 0 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-10-30 | QTR2 | 23/24 |  | 2023-08-28 | QTR1 | 23/24 | 308 | 3713438.76
| 03 | T3802 | 44397315201 | 2022-03-30 | QTR3 | 21/22 | 1 | 0 | 188 | 257 | 266 | 104.8% | 1 | -9 | 9 | 0 | 69 | 0 | 6686744 | 66701 | 6620043 | 6686744 | 6712350 | -34074 | 0 | -34074 | 6678276 | 6731897 | 101.7% | 1 | 53621 | 0 | 56 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-28 | QTR3 | 23/24 |  | 2023-10-26 | QTR2 | 23/24 | 321 | 6875752.18
| 03 | T3810 | 44365015201 | 2022-01-26 | QTR3 | 21/22 | 1 | 1 | 270 | 474 | 472 | 121.1% | 0 | 2 | 0 | 0 | 156 | 48 | 10527718 | 106380 | 10421339 | 10784785 | 11111656 | 0 | 0 | 0 | 11111656 | 11389685 | 109.3% | 1 | 278029 | 257067 | 87 | 58 | 5 | 0 | 0 | 0 | 0 | 48 | 274363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 48 | 276583 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 |  | 2023-08-02 | QTR1 | 23/24 | 313 | 10728439.32
| 03 | T3811 | 22083845201 | 2022-01-26 | QTR3 | 21/22 | 1 | 2 | 245 | 532 | 532 | 112.2% | 1 | 0 | 0 | 0 | 203 | 84 | 1327870 | 50000 | 1277870 | 1607733 | 1467485 | 0 | 0 | 0 | 1467485 | 1187623 | 92.94% | 1 | 0 | 279863 | 210 | 47 | 0 | 84 | 279863 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 84 | 279863 | 10500 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-03-04 | QTR3 | 23/24 |  | 2023-09-22 | QTR1 | 23/24 | 313 | 2903300.5
| 03 | T3812 | 44363915201 | 2022-05-25 | QTR4 | 21/22 | 1 | 1 | 245 | 417 | 416 | 107.3% | 1 | 1 | 0 | 0 | 157 | 15 | 13830550 | 119800 | 13710750 | 13861043 | 13971237 | 0 | 39808 | 39808 | 14011044 | 13698217 | 99.91% | 1 | -312827 | 30493 | 81 | 72 | 0 | 5 | 15466 | 0 | 0 | 10 | 46993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15 | 62459 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 |  | 2023-12-28 | QTR2 | 23/24 | 313 | 14936565.66
| 03 | T3816 | 44563215201 | 2022-10-05 | QTR2 | 22/23 | 1 | 1 | 125 | 260 | 257 | 97.6% | 1 | 3 | 0 | 0 | 135 | 0 | 3430508 | 50000 | 3380508 | 3430508 | 3561896 | 0 | 0 | 0 | 3561896 | 3523880 | 104.2% | 1 | -38015 | 0 | 122 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 |  | 2023-10-09 | QTR2 | 23/24 | 314 | 3265522.73
| 03 | T3817 | 44387515201 | 2022-08-31 | QTR1 | 22/23 | 1 | 2 | 60 | 246 | 246 | 100% | 1 | 0 | 0 | 0 | 156 | 30 | 535084 | 0 | 535084 | 538384 | 583904 | 0 | 0 | 0 | 583904 | 580604 | 108.5% | 1 | 0 | 3300 | 165 | 21 | 0 | 0 | 0 | 0 | 0 | 30 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 30 | 3300 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-10 | QTR3 | 23/24 |  | 2023-08-02 | QTR1 | 23/24 | 313 | 438194
| 03 | T3818 | 44387615201 | 2022-10-05 | QTR2 | 22/23 | 1 | 0 | 75 | 150 | 150 | 140% | 0 | 0 | 0 | 0 | 75 | 0 | 287504 | 20245 | 267260 | 287504 | 255356 | 0 | 0 | 0 | 255356 | 255356 | 95.55% | 1 | 0 | 0 | 27 | 18 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-01-18 | QTR3 | 23/24 |  | 2023-09-07 | QTR1 | 23/24 | 314 | 449141.81
| 03 | T3819 | 44404315201 | 2022-08-31 | QTR1 | 22/23 | 1 | 1 | 110 | 251 | 251 | 118.2% | 1 | 0 | 0 | 0 | 121 | 20 | 2236764 | 50000 | 2186764 | 2317147 | 2391790 | 0 | 0 | 0 | 2391790 | 2391790 | 109.4% | 1 | 0 | 80383 | 90 | 31 | 0 | 0 | 0 | 0 | 0 | 20 | 80383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 80383 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-13 | QTR3 | 23/24 |  | 2023-09-11 | QTR1 | 23/24 | 314 | 1726155.21
| 03 | T3823 | 44565615201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 110 | 120 | 86 | 69.09% | 1 | 34 | 0 | 0 | 10 | 0 | 2199429 | 50000 | 2149429 | 2199429 | 2316440 | 0 | 0 | 0 | 2316440 | 2316440 | 107.8% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 |  | 2023-06-22 | QTR4 | 22/23 | 308 | 2955598
| 03 | T3825 | 44565715201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 89 | 101 | 67 | 61.8% | 1 | 34 | 0 | 0 | 12 | 0 | 1398733 | 50000 | 1348733 | 1398733 | 1268603 | 0 | 0 | 0 | 1268603 | 1268603 | 94.06% | 1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-08-21 | QTR1 | 23/24 | 321 | 2259061
| 03 | T3828 | 44404415201 | 2022-02-23 | QTR3 | 21/22 | 1 | 0 | 90 | 183 | 168 | 114.4% | 1 | 15 | 0 | 0 | 93 | 0 | 1388656 | 50000 | 1338656 | 1388656 | 1401865 | 0 | 0 | 0 | 1401865 | 1401865 | 104.7% | 1 | 0 | 0 | 53 | 12 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F432094655 | H.G. CONSTRUCTION DEVELOPMENT & INVESTM | N/A | N/A | N/A | N/A | 2023-12-21 | QTR2 | 23/24 |  | 2022-10-26 | QTR2 | 22/23 | 313 | 1545933
| 03 | T3830 | 43256615201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 180 | 290 | 288 | 98.89% | 1 | 2 | 0 | 0 | 110 | 0 | 3353932 | 50000 | 3303932 | 3353932 | 3387610 | 0 | 0 | 0 | 3387610 | 3371222 | 102% | 1 | -16388 | 0 | 67 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-10 | QTR3 | 23/24 |  | 2023-07-16 | QTR1 | 23/24 | 308 | 3164048.08
| 03 | T3833 | 44560315201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 44 | 49 | 45 | 90.91% | 1 | 4 | 0 | 0 | 5 | 0 | 192351 | 8394 | 183958 | 192351 | 176477 | 0 | 0 | 0 | 176477 | 176477 | 95.93% | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2022-12-22 | QTR2 | 22/23 | 308 | 173499.64
| 03 | T3836 | 43974415201 | 2022-10-05 | QTR2 | 22/23 | 1 | 0 | 169 | 238 | 238 | 100% | 1 | 0 | 0 | 0 | 69 | 0 | 4469056 | 50000 | 4419056 | 4469056 | 4076218 | 0 | 0 | 0 | 4076218 | 3952664 | 89.45% | 1 | -123554 | 0 | 30 | 39 | 0 | 0 | 3365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3365 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2023-08-21 | QTR1 | 23/24 | 314 | 6832323.6
| 03 | T3848 | 43776215201 | 2022-06-15 | QTR4 | 21/22 | 2 | 1 | 150 | 309 | 309 | 157.3% | 0 | 0 | 0 | 0 | 143 | 16 | 2961906 | 50000 | 2911906 | 2971384 | 2833242 | 0 | 50000 | 50000 | 2883242 | 2818993 | 96.81% | 1 | -64250 | 9478 | 48 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 3118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9478 | 9478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 16 | 12596 | 9478 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-13 | QTR3 | 23/24 |  | 2023-10-04 | QTR2 | 23/24 | 314 | 3042412.27 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 03 | T9024 | 44199335223 | 2021-04-28 | QTR4 | 20/21 | 1 | 2 | 250 | 622 | 620 | 99.2% | 1 | 2 | 0 | 0 | 372 | 0 | 3198515 | 50000 | 3148515 | 3289097 | 3304055 | 0 | 0 | 0 | 3304055 | 3304055 | 104.9% | 1 | 39515 | 90582 | 322 | 50 | 90 | 0 | 6000 | 0 | 90 | 0 | 49780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 58960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 126040 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 |  | 2023-06-08 | QTR4 | 22/23 | 314 | 3552350.22
| 03 | T9027 | 44531315215 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 60 | 71 | 71 | 100% | 1 | 0 | 0 | 0 | 11 | 0 | 564819 | 36905 | 527914 | 564819 | 524793 | 0 | 0 | 0 | 524793 | 524793 | 99.41% | 1 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-01-10 | QTR3 | 23/24 |  | 2022-05-13 | QTR4 | 21/22 | 306 | 932089.13
| 03 | T9029 | 44531325216 | 2022-03-30 | QTR3 | 21/22 | 1 | 0 | 150 | 258 | 258 | 119.3% | 1 | 0 | 0 | 0 | 108 | 0 | 2718412 | 50000 | 2668412 | 2718412 | 2266906 | 0 | 0 | 0 | 2266906 | 2266906 | 84.95% | 1 | 0 | 0 | 68 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 6123 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-01-22 | QTR3 | 23/24 |  | 2023-10-30 | QTR2 | 23/24 | 308 | 2758180.6
| Dist 03 Central Let Contracts SubTotal |  |  |  |  | 41 | 61 | 91 | 10289 | 17533 | 17787 | 73.17% | 30 | -254 | 727 | 0 | 6393 | 851 | 236886404 | 2071741 | 234814665 | 246245815 | 251944992 | -2224402 | -102692 | -2327094 | 249617897 | 253787971 | 87.8% | 36 | 5294743 | 9359413 | 4055 | 1550 | 194 | 243 | 2644839 | 63374 | 177 | 308 | 3587829 | 119573 | 0 | 0 | 2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 220 | 3108535 | 2444336 | 11 | 14 | 84312 | 33748 | 0 | 0 | 0 | 0 | 548 | 155 | 165731 | 0 | 0 | 46 | 95000 | 95000 | 38 | 16 | 9478 | 9478 | 231 | 0 | 108898 | 0 | 0 | 0 | -159429 | 0 | 1349 | 1002 | 9647740 | 2765509
| Dist 03 Central Let Contracts SubTotal Including T9 contracts |  |  |  |  | 44 | 122 | 166 | 19948 | 34018 | 34352 | 75% | 33 | -334 | 1282 | 0 | 12479 | 1591 | 438114554 | 4130387 | 433984171 | 455927442 | 465195940 | -3659116 | -205384 | -3864500 | 461331438 | 468521629 | 88.64% | 39 | 9315994 | 17812892 | 8069 | 2949 | 474 | 446 | 4915186 | 125179 | 444 | 589 | 6876342 | 239146 | 0 | 0 | 5096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 432 | 6069285 | 4888672 | 22 | 28 | 209539 | 49451 | 0 | 0 | 0 | 0 | 1181 | 310 | 280876 | 0 | 0 | 46 | 95000 | 95000 | 38 | 32 | 18956 | 18956 | 582 | 0 | 217796 | 0 | 0 | 0 | -159429 | 0 | 3003 | 1883 | 18528644 | 5416404
| 03 | E3S70 | 43992635201 | 2021-05-13 | QTR4 | 20/21 | 2 | 1 | 395 | 597 | 597 | 112.9% | 1 | 0 | 0 | 0 | 202 | 0 | 8497804 | 70195 | 8427609 | 8518932 | 8878921 | 0 | 0 | 0 | 8878921 | 8997063 | 106.8% | 1 | 136935 | 21128 | 102 | 49 | 0 | 0 | 12464 | 0 | 30 | 0 | 28861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 41325 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 |  | 2023-03-30 | QTR3 | 22/23 | 321 | 7939245.14
| 03 | E3T49 | 44546515201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 90 | 134 | 151 | 128.9% | 0 | -17 | 17 | 0 | 35 | 9 | 1331980 | 50000 | 1281980 | 1331980 | 1360250 | -28730 | 12500 | -16230 | 1344020 | 1331520 | 103.9% | 1 | -12500 | 0 | 19 | 16 | 0 | 0 | 810 | 0 | 0 | 9 | 15261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 16071 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-04-30 | QTR4 | 23/24 |  | 2021-04-13 | QTR4 | 20/21 | 321 | 1383418.94 | B10 | ACC - BONUS/INCENT/DISINCENT
| 03 | E3U04 | 21904225201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 65 | 65 | 45 | 69.23% | 1 | 20 | 0 | 0 | 0 | 0 | 278090 | 21110 | 256980 | 278090 | 249120 | 0 | 0 | 0 | 249120 | 249120 | 96.94% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2023-05-18 | QTR4 | 22/23 | 314 | 454253.61
| 03 | E3U32 | 42187425201 | 2022-01-13 | QTR3 | 21/22 | 1 | 0 | 45 | 55 | 52 | 93.33% | 1 | 3 | 0 | 0 | 10 | 0 | 109495 | 5918 | 103577 | 109495 | 105102 | 0 | 0 | 0 | 105102 | 105102 | 101.5% | 1 | 0 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2022-06-09 | QTR4 | 21/22 | 308 | 135676.68
| 03 | E3U47 | 44158915201 | 2021-11-10 | QTR2 | 21/22 | 2 | 3 | 285 | 527 | 526 | 102.8% | 1 | 1 | 0 | 0 | 242 | 0 | 6190992 | 53456 | 6137537 | 6194018 | 6101074 | -18750 | 0 | -18750 | 6082324 | 6229251 | 101.5% | 1 | 146927 | 3025 | 162 | 71 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 0 | 3025 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 |  | 2023-08-02 | QTR1 | 23/24 | 308 | 5430315.21
| 03 | E3U83 | 41768355201 | 2022-07-14 | QTR1 | 22/23 | 1 | 0 | 200 | 401 | 414 | 124.5% | 0 | -13 | 13 | 0 | 201 | 0 | 2363976 | 50000 | 2313976 | 2363976 | 2188042 | -22022 | 0 | -22022 | 2166020 | 2166020 | 93.61% | 1 | 0 | 0 | 121 | 44 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2024-04-30 | QTR4 | 23/24 |  | 2024-01-29 | QTR3 | 23/24 | 308 | 2795459.35
| 03 | E3U84 | 44365915201 | 2022-02-10 | QTR3 | 21/22 | 2 | 1 | 175 | 266 | 264 | 98.86% | 1 | 2 | 0 | 0 | 91 | 0 | 3254371 | 50000 | 3204371 | 3263484 | 3285954 | 0 | 0 | 0 | 3285954 | 3378196 | 105.4% | 1 | 92242 | 9113 | 66 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 |  | 2023-02-18 | QTR3 | 22/23 | 308 | 3044605.63
| 03 | E3U86 | 22068525201 | 2023-03-09 | QTR3 | 22/23 | 1 | 0 | 45 | 58 | 58 | 100% | 1 | 0 | 0 | 0 | 13 | 0 | 148273 | 10291 | 137982 | 148273 | 131932 | 0 | 0 | 0 | 131932 | 131932 | 95.62% | 1 | 0 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F943481793 | FAITH CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2024-03-04 | QTR3 | 23/24 |  | 2023-09-18 | QTR1 | 23/24 | 313 | 216110.85
| 03 | E3V28 | 44891215201 | 2023-05-11 | QTR4 | 22/23 | 1 | 1 | 85 | 161 | 161 | 116.5% | 1 | 0 | 0 | 0 | 68 | 8 | 586983 | 50000 | 536983 | 689291 | 616073 | 0 | 0 | 0 | 616073 | 616073 | 114.7% | 0 | 0 | 102308 | 42 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 102308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 102308 | 0 | F202058265 | STRUCTURAL PRESERVATION SYSTEMS | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 |  | 2024-03-07 | QTR3 | 23/24 | 308 | 1050080.3
| 03 | E3V33 | 44891315201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 75 | 80 | 53 | 64% | 1 | 27 | 0 | 0 | 5 | 0 | 223976 | 14236 | 209740 | 223976 | 187027 | 0 | 0 | 0 | 187027 | 187027 | 89.17% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-06-01 | QTR4 | 22/23 | 308 | 298951.28
| 03 | E3V50 | 42543655201 | 2022-08-18 | QTR1 | 22/23 | 1 | 0 | 250 | 324 | 218 | 57.6% | 1 | 106 | 0 | 0 | 74 | 0 | 3247610 | 50000 | 3197610 | 3247610 | 2860191 | 0 | 0 | 0 | 2860191 | 2860191 | 89.45% | 1 | 0 | 0 | 32 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2024-01-18 | QTR3 | 23/24 |  | 2023-06-21 | QTR4 | 22/23 | 314 | 6703766.52
| 03 | E3V51 | 44538525201 | 2022-06-09 | QTR4 | 21/22 | 1 | 0 | 90 | 106 | 105 | 98.89% | 1 | 1 | 0 | 0 | 16 | 0 | 396162 | 23977 | 372186 | 396162 | 353103 | 0 | 0 | 0 | 353103 | 353103 | 94.87% | 1 | 0 | 0 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2024-01-18 | QTR3 | 23/24 |  | 2022-12-21 | QTR2 | 22/23 | 314 | 736200.83
| 03 | E3V90 | 44575815201 | 2023-01-12 | QTR3 | 22/23 | 1 | 1 | 70 | 78 | 77 | 98.57% | 1 | 1 | 0 | 0 | 8 | 0 | 1499653 | 50000 | 1449653 | 1499653 | 1534493 | 0 | 0 | 0 | 1534493 | 1534493 | 105.9% | 1 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-10-02 | QTR2 | 23/24 |  | 2023-06-27 | QTR4 | 22/23 | 308 | 1524311.21
| 03 | E3W08 | 22282725201 | 2023-05-11 | QTR4 | 22/23 | 1 | 0 | 90 | 100 | 71 | 67.78% | 1 | 29 | 0 | 0 | 10 | 0 | 553641 | 39372 | 514269 | 553641 | 509921 | 0 | 0 | 0 | 509921 | 509921 | 99.15% | 1 | 0 | 0 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-01-18 | QTR3 | 23/24 |  | 2023-10-30 | QTR2 | 23/24 | 313 | 848184.9
| 03 | E3W56 | 45102915201 | 2023-04-13 | QTR4 | 22/23 | 1 | 0 | 80 | 87 | 79 | 90% | 1 | 8 | 0 | 0 | 7 | 0 | 208278 | 11765 | 196514 | 208278 | 193768 | 0 | 0 | 0 | 193768 | 193768 | 98.6% | 1 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2024-02-01 | QTR3 | 23/24 |  | 2023-11-07 | QTR2 | 23/24 | 308 | 247061.64
| 03 | E3W98 | 45055015201 | 2023-08-10 | QTR1 | 23/24 | 1 | 0 | 60 | 94 | 82 | 80% | 1 | 12 | 0 | 0 | 34 | 0 | 123579 | 5912 | 117667 | 123579 | 121257 | 0 | 0 | 0 | 121257 | 121257 | 103.1% | 1 | 0 | 0 | 18 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3211 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2024-03-20 | QTR3 | 23/24 |  | 2024-02-06 | QTR3 | 23/24 | 321 | 124155.84
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 16 | 19 | 7 | 2100 | 3133 | 2953 | 87.5% | 14 | 180 | 30 | 0 | 1016 | 17 | 29014863 | 556232 | 28458634 | 29150438 | 28676228 | -69502 | 12500 | -57002 | 28619226 | 28964037 | 93.75% | 15 | 363604 | 135574 | 602 | 312 | 9 | 0 | 13274 | 0 | 39 | 9 | 56252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 108544 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 17 | 178070 | 0
| District 03 Totals |  |  |  |  | 57 | 80 | 98 | 12389 | 20666 | 20740 | 77.19% | 44 | -74 | 757 | 0 | 7409 | 868 | 265901267 | 2627973 | 263273299 | 275396253 | 280621220 | -2293904 | -90192 | -2384096 | 278237123 | 282752008 | 89.47% | 51 | 5658347 | 9494987 | 4657 | 1862 | 203 | 243 | 2658113 | 63374 | 216 | 317 | 3644081 | 119573 | 0 | 0 | 2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 228 | 3217079 | 2444336 | 44 | 14 | 84312 | 33748 | 0 | 0 | 0 | 0 | 709 | 155 | 165731 | 0 | 0 | 46 | 95000 | 95000 | 38 | 16 | 9478 | 9478 | 252 | 0 | 108898 | 0 | 0 | 0 | -159429 | 0 | 1612 | 1019 | 9825810 | 2765509
| 04 | T4552 | 43696215201 | 2020-05-20 | QTR4 | 19/20 | 2 | 14 | 642 | 1093 | 1084 | 116.7% | 1 | 9 | 0 | 0 | 445 | 6 | 26406739 | 150000 | 26256739 | 27530140 | 27615738 | 0 | 0 | 0 | 27615738 | 28097247 | 107% | 1 | 1507029 | 1123402 | 284 | 51 | 0 | 0 | 40935 | 0 | 110 | 0 | 428405 | 32084 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223929 | 0 | 0 | 0 | 320493 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 11175 | 0 | 0 | 0 | 308488 | 0 | 0 | 6 | 42593 | 42593 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 6 | 1272542 | 74677 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-09-08 | QTR1 | 23/24 | 412 | 27323787.5 | B10 | ACC - BONUS/INCENT/DISINCENT
| 04 | T4562 | 43177035201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 384 | 492 | 492 | 100% | 1 | 0 | 0 | 0 | 108 | 0 | 3588218 | 50000 | 3538218 | 3660295 | 3546957 | 0 | 0 | 0 | 3546957 | 3613971 | 102.1% | 1 | 67014 | 72077 | 71 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 91148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14596 | 0 | 0 | 0 | -11203 | 0 | 0 | 0 | 94541 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2023-03-31 | QTR3 | 22/23 | 412 | 3732217.16
| 04 | T4563 | 43619615201 | 2021-05-26 | QTR4 | 20/21 | 3 | 3 | 466 | 687 | 687 | 100% | 1 | 0 | 0 | 0 | 221 | 0 | 3377160 | 49980 | 3327180 | 3518499 | 3553166 | 0 | 0 | 0 | 3553166 | 3602214 | 108.3% | 1 | 88570 | 141339 | 173 | 48 | 0 | 0 | 5620 | 0 | 0 | 0 | 112295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2406 | 0 | 0 | 0 | 54041 | 0 | 0 | 0 | 0 | 0 | 76 | 0 | 5325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 0 | 179687 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2024-01-23 | QTR3 | 23/24 |  | 2023-06-23 | QTR4 | 22/23 | 412 | 3569811.06
| 04 | T4567 | 43839415201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 388 | 574 | 574 | 119.1% | 1 | 0 | 0 | 0 | 186 | 0 | 2505478 | 50000 | 2455478 | 2517687 | 2397524 | 0 | 0 | 0 | 2397524 | 2420702 | 98.58% | 1 | 167234 | 12209 | 70 | 42 | 0 | 0 | 10842 | 0 | 0 | 0 | 23398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6534 | 0 | 0 | 0 | 1247 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 8119 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 50141 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-10-03 | QTR2 | 23/24 |  | 2023-06-08 | QTR4 | 22/23 | 409 | 2223138.08
| 04 | T4571 | 43839515201 | 2021-01-27 | QTR3 | 20/21 | 2 | 5 | 575 | 701 | 701 | 100% | 1 | 0 | 0 | 0 | 126 | 0 | 2029422 | 50000 | 1979422 | 2048533 | 1920549 | 0 | 0 | 0 | 1920549 | 1968644 | 99.46% | 1 | 49459 | 19111 | 81 | 45 | 0 | 0 | 1911 | 0 | 0 | 0 | 3545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17675 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-06-16 | QTR4 | 22/23 | 409 | 2213111.22
| 04 | T4572 | 43838415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 454 | 621 | 611 | 97.8% | 1 | 10 | 0 | 0 | 167 | 0 | 2952231 | 50000 | 2902231 | 2953979 | 2876141 | 0 | 0 | 0 | 2876141 | 2874393 | 99.04% | 1 | 28318 | 1748 | 122 | 45 | 0 | 0 | 7776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 9524 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-07-24 | QTR1 | 23/24 | 409 | 3045126.89
| 04 | T4573 | 43206675201 | 2021-07-28 | QTR1 | 21/22 | 2 | 3 | 195 | 470 | 465 | 97.44% | 1 | 5 | 0 | 0 | 275 | 0 | 3496673 | 50000 | 3446673 | 3721036 | 3515537 | 0 | 0 | 0 | 3515537 | 3603841 | 104.6% | 1 | 88304 | 224363 | 249 | 26 | 0 | 0 | -2094 | 0 | 0 | 0 | 267470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 265376 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 |  | 2023-04-19 | QTR4 | 22/23 | 412 | 3657623.88
| 04 | T4579 | 44166815201 | 2021-04-28 | QTR4 | 20/21 | 3 | 6 | 480 | 808 | 805 | 99.38% | 1 | 3 | 0 | 0 | 328 | 0 | 12487000 | 142304 | 12344696 | 12883748 | 12540269 | 0 | 0 | 0 | 12540269 | 13525650 | 109.6% | 1 | 1012442 | 432553 | 276 | 52 | 0 | 0 | 6397 | 0 | 0 | 0 | 164863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168610 | 68909 | 0 | 0 | 87581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454512 | 68909 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-03-08 | QTR3 | 23/24 |  | 2023-09-28 | QTR1 | 23/24 | 412 | 14492192.77
| 04 | T4586 | 42957625201 | 2021-09-29 | QTR1 | 21/22 | 5 | 3 | 351 | 638 | 638 | 108.3% | 1 | 0 | 0 | 0 | 280 | 7 | 4581957 | 50000 | 4531957 | 4683431 | 4520450 | 0 | 0 | 0 | 4520450 | 4522418 | 99.79% | 1 | 5386 | 101474 | 218 | 40 | 0 | 0 | 25903 | 0 | 0 | 11 | 98213 | 2552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11541 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 3418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 11 | 139075 | 2552 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 |  | 2024-01-11 | QTR3 | 23/24 | 412 | 4567139.47
| 04 | T4591 | 43811815201 | 2022-01-26 | QTR3 | 21/22 | 2 | 4 | 269 | 478 | 478 | 118.6% | 1 | 0 | 0 | 0 | 209 | 21 | 2543608 | 50000 | 2493608 | 2702421 | 2682407 | 0 | 0 | 0 | 2682407 | 2681177 | 107.5% | 1 | 5915 | 208813 | 137 | 22 | 50 | 0 | 8822 | 0 | 0 | 0 | 139633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7145 | 0 | 0 | 0 | 21699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 177299 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 |  | 2023-08-17 | QTR1 | 23/24 | 412 | 2499977.01
| 04 | T4592 | 43999415201 | 2021-12-08 | QTR2 | 21/22 | 3 | 2 | 316 | 443 | 442 | 118.7% | 1 | 1 | 0 | 0 | 67 | 60 | 2605697 | 50000 | 2555697 | 2718209 | 2649545 | 0 | 0 | 0 | 2649545 | 2756383 | 107.9% | 1 | 109912 | 112512 | 42 | 25 | 0 | 39 | 109438 | 70107 | 0 | 21 | 5837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 118349 | 70107 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-04-03 | QTR4 | 23/24 |  | 2023-06-27 | QTR4 | 22/23 | 412 | 2812232.39
| 04 | T4594 | 43999015201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 212 | 352 | 351 | 113.7% | 1 | 1 | 0 | 0 | 140 | 0 | 2000000 | 50000 | 1950000 | 2008938 | 1868868 | 0 | 0 | 0 | 1868868 | 1862040 | 95.49% | 1 | 2110 | 8938 | 85 | 25 | 0 | 0 | 11450 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 20388 | 0 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2023-07-24 | QTR1 | 23/24 |  | 2023-05-31 | QTR4 | 22/23 | 412 | 2421037.86
| 04 | T4597 | 44177515201 | 2022-01-26 | QTR3 | 21/22 | 2 | 1 | 178 | 274 | 274 | 100% | 1 | 0 | 0 | 0 | 96 | 0 | 957661 | 40792 | 916869 | 958736 | 900445 | 0 | 0 | 0 | 900445 | 899370 | 98.09% | 1 | 0 | 1075 | 72 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 8111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 9186 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-05-11 | QTR4 | 22/23 | 409 | 927528.71
| 04 | T4601 | 44177115201 | 2022-04-27 | QTR4 | 21/22 | 2 | 0 | 172 | 266 | 266 | 100% | 1 | 0 | 0 | 0 | 94 | 0 | 1248248 | 50000 | 1198248 | 1248248 | 1203185 | 0 | 0 | 0 | 1203185 | 1200343 | 100.2% | 1 | -2841 | 0 | 68 | 26 | 0 | 0 | 1296 | 0 | 0 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18092 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-13 | QTR3 | 23/24 |  | 2024-01-24 | QTR3 | 23/24 | 412 | 1328803.72
| 04 | T4603 | 44157815201 | 2022-03-30 | QTR3 | 21/22 | 3 | 0 | 229 | 338 | 338 | 100% | 1 | 0 | 0 | 0 | 109 | 0 | 2249738 | 50000 | 2199738 | 2249738 | 2253443 | 0 | 0 | 0 | 2253443 | 2251225 | 102.3% | 1 | -2218 | 0 | 87 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-09 | QTR2 | 23/24 |  | 2023-08-09 | QTR1 | 23/24 | 412 | 2503871.57
| 04 | T4607 | 43999315201 | 2022-03-30 | QTR3 | 21/22 | 3 | 1 | 222 | 287 | 287 | 100% | 1 | 0 | 0 | 0 | 65 | 0 | 1967721 | 50000 | 1917721 | 1967721 | 1856962 | 0 | 0 | 0 | 1856962 | 1856374 | 96.8% | 1 | 2046 | 2634 | 47 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-09-18 | QTR1 | 23/24 |  | 2023-04-30 | QTR4 | 22/23 | 412 | 2135578.09
| 04 | T4608 | 44177615201 | 2022-01-26 | QTR3 | 21/22 | 1 | 3 | 374 | 514 | 514 | 104.3% | 1 | 0 | 0 | 0 | 140 | 0 | 3370284 | 50000 | 3320284 | 3030235 | 2923805 | 0 | 0 | 0 | 2923805 | 2936404 | 88.44% | 1 | 12599 | -340049 | 80 | 44 | 0 | 0 | 72006 | 65186 | 0 | 0 | -397641 | 3779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | -325635 | 68965 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 |  | 2024-01-05 | QTR3 | 23/24 | 409 | 2521290.97
| 04 | T4609 | 44384515201 | 2022-04-27 | QTR4 | 21/22 | 3 | 1 | 169 | 353 | 353 | 108.9% | 1 | 0 | 0 | 0 | 184 | 0 | 2057691 | 50000 | 2007691 | 2108795 | 2355080 | 0 | 0 | 0 | 2355080 | 2350900 | 117.1% | 0 | -4180 | 51105 | 143 | 26 | 0 | 0 | 92472 | 0 | 15 | 0 | 8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 100999 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-06-12 | QTR4 | 23/24 |  | 2024-02-23 | QTR3 | 23/24 | 412 | 2121963.38
| 04 | T4614 | 44399415201 | 2022-04-27 | QTR4 | 21/22 | 2 | 3 | 227 | 321 | 321 | 104.8% | 1 | 0 | 0 | 0 | 94 | 0 | 4491996 | 50000 | 4441996 | 4563991 | 4393362 | 0 | 0 | 0 | 4393362 | 4376466 | 98.52% | 1 | -6110 | 71995 | 57 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 86648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51997 | 0 | 0 | 0 | 5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10786 | 0 | 0 | 0 | 33274 | 33274 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 83947 | 33274 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-06-14 | QTR4 | 22/23 | 409 | 4062646.65
| 04 | T4628 | 44061275201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 126 | 160 | 142 | 85.71% | 1 | 18 | 0 | 0 | 34 | 0 | 1125012 | 41897 | 1083114 | 1125012 | 994908 | 0 | 0 | 0 | 994908 | 994009 | 91.77% | 1 | -899 | 0 | 11 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2024-03-29 | QTR3 | 23/24 |  | 2024-01-16 | QTR3 | 23/24 | 409 | 879841.48
| 04 | T4629 | 44562315201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 122 | 127 | 107 | 83.61% | 1 | 20 | 0 | 0 | 5 | 0 | 1050673 | 49045 | 1001629 | 1050673 | 985015 | 0 | 0 | 0 | 985015 | 985015 | 98.34% | 1 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-06 | QTR2 | 23/24 |  | 2023-10-30 | QTR2 | 23/24 | 409 | 1029940.35
| Dist 04 Central Let Contracts SubTotal |  |  |  |  | 21 | 48 | 55 | 6551 | 9997 | 9930 | 100% | 21 | 67 | 0 | 0 | 3373 | 94 | 87093207 | 1224018 | 85869189 | 89250065 | 87553356 | 0 | 0 | 0 | 87553356 | 89378786 | 95.24% | 20 | 3130090 | 2245299 | 2374 | 671 | 50 | 39 | 392774 | 135293 | 155 | 32 | 1064087 | 38415 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361023 | 68909 | 0 | 0 | 476519 | 0 | 22 | 0 | 0 | 0 | 527 | 0 | 99085 | 0 | 0 | 0 | 363461 | 33274 | 90 | 6 | 43588 | 42593 | 34 | 0 | 14596 | 0 | 0 | 0 | -11203 | 0 | 878 | 77 | 2700458 | 318484
| 04 | E4T68 | 44074615201 | 2020-05-06 | QTR4 | 19/20 | 6 | 1 | 730 | 939 | 934 | 99.32% | 1 | 5 | 0 | 0 | 209 | 0 | 17557323 | 125751 | 17431572 | 17588765 | 16726429 | 0 | 0 | 0 | 16726429 | 16980455 | 97.41% | 1 | 254025 | 31442 | 144 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31442 | 0 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37742 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 |  | 2023-02-02 | QTR3 | 22/23 | 412 | 12972092.8
| 04 | E4U99 | 44146215201 | 2021-05-07 | QTR4 | 20/21 | 1 | 8 | 228 | 525 | 518 | 144.7% | 0 | 7 | 0 | 0 | 188 | 109 | 12200214 | 101674 | 12098540 | 13805766 | 14066534 | 0 | 0 | 0 | 14066534 | 14068003 | 116.3% | 0 | 140138 | 1605552 | 165 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 1129185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 448054 | 0 | 0 | 0 | 23731 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 109 | 1600970 | 0 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-06-23 | QTR4 | 22/23 | 412 | 10374505.8 | B10 | ACC - BONUS/INCENT/DISINCENT
| 04 | E4V19 | 43215215201 | 2022-01-07 | QTR3 | 21/22 | 1 | 0 | 307 | 326 | 171 | 49.51% | 1 | 155 | 0 | 0 | 19 | 0 | 2335539 | 50000 | 2285539 | 2335539 | 2159702 | 0 | 0 | 0 | 2159702 | 2159702 | 94.49% | 1 | 0 | 0 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-11-20 | QTR2 | 23/24 |  | 2023-10-25 | QTR2 | 23/24 | 409 | 4011283.36 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 04 | E4V21 | 44399715201 | 2022-02-04 | QTR3 | 21/22 | 1 | 0 | 210 | 248 | 246 | 99.05% | 1 | 2 | 0 | 0 | 38 | 0 | 2500423 | 50000 | 2450423 | 2500423 | 2294866 | 0 | 0 | 0 | 2294866 | 2323183 | 94.81% | 1 | 28317 | 0 | 24 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 5415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5415 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-04-29 | QTR4 | 23/24 |  | 2023-12-18 | QTR2 | 23/24 | 408 | 2332741.9
| 04 | E4V26 | 44172115201 | 2021-12-03 | QTR2 | 21/22 | 2 | 1 | 229 | 349 | 343 | 105.7% | 1 | 6 | 0 | 0 | 120 | 0 | 1821552 | 50000 | 1771552 | 1857400 | 1793427 | 0 | 0 | 0 | 1793427 | 1797474 | 101.5% | 1 | 4047 | 35848 | 62 | 39 | 0 | 0 | 35848 | 3011 | 19 | 0 | 38415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 74263 | 3011 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-01-25 | QTR3 | 23/24 |  | 2023-07-31 | QTR1 | 23/24 | 412 | 1667424.49
| 04 | E4V55 | 44359415201 | 2022-05-06 | QTR4 | 21/22 | 1 | 1 | 127 | 224 | 221 | 113.4% | 1 | 3 | 0 | 0 | 97 | 0 | 895596 | 50000 | 845596 | 965406 | 917671 | 0 | 0 | 0 | 917671 | 917671 | 108.5% | 1 | 0 | 69810 | 62 | 15 | 0 | 0 | 69810 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 69810 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 |  | 2023-07-15 | QTR1 | 23/24 | 412 | 1122910.5
| 04 | E4V59 | 44136015201 | 2022-03-04 | QTR3 | 21/22 | 3 | 5 | 398 | 525 | 522 | 89.7% | 1 | 3 | 0 | 0 | 165 | -38 | 6377644 | 54489 | 6323155 | 6402875 | 6172746 | 0 | 0 | 0 | 6172746 | 6337235 | 100.2% | 1 | 164489 | 25231 | 134 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 218069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38 | -138692 | 0 | 0 | -38 | 79377 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-05-06 | QTR4 | 23/24 |  | 2023-11-20 | QTR2 | 23/24 | 412 | 5443223.47
| 04 | E4V75 | 44172215201 | 2022-02-04 | QTR3 | 21/22 | 2 | 4 | 156 | 248 | 248 | 104.5% | 1 | 0 | 0 | 0 | 92 | 0 | 1455255 | 50000 | 1405255 | 1515282 | 1451281 | 0 | 0 | 0 | 1451281 | 1452112 | 103.3% | 1 | 7917 | 60027 | 72 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 76040 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 85192 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-09-01 | QTR1 | 23/24 |  | 2023-03-28 | QTR3 | 22/23 | 409 | 1403378.89
| 04 | E4V81 | 44610115201 | 2022-10-07 | QTR2 | 22/23 | 4 | 3 | 148 | 247 | 247 | 117.6% | 1 | 0 | 0 | 0 | 99 | 0 | 3843000 | 50000 | 3793000 | 3930369 | 3945848 | 0 | 0 | 0 | 3945848 | 3942412 | 103.9% | 1 | -3437 | 87369 | 57 | 16 | 0 | 0 | 0 | 0 | 26 | 0 | 87369 | 77301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6749 | 0 | 0 | 0 | 4512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 98630 | 77301 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-06-10 | QTR4 | 23/24 |  | 2024-02-05 | QTR3 | 23/24 | 409 | 3910539.99
| 04 | E4V84 | 44609715201 | 2022-09-02 | QTR1 | 22/23 | 1 | 1 | 133 | 180 | 179 | 99.25% | 1 | 1 | 0 | 0 | 47 | 0 | 3147147 | 50000 | 3097147 | 3153188 | 2965886 | 0 | 0 | 0 | 2965886 | 2896248 | 93.51% | 1 | -69638 | 6041 | 43 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-08-03 | QTR1 | 23/24 | 409 | 3652108.96 | B1 | ACC - NO EXCUSE BONUS
| 04 | E4W04 | 45059015201 | 2022-06-14 | QTR4 | 21/22 | 1 | 0 | 182 | 209 | 209 | 100% | 1 | 0 | 0 | 0 | 27 | 0 | 1468626 | 50000 | 1418626 | 1468626 | 1421948 | 0 | 0 | 0 | 1421948 | 1421948 | 100.2% | 1 | 0 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2023-11-20 | QTR2 | 23/24 |  | 2023-10-25 | QTR2 | 23/24 | 408 | 2551166.8
| 04 | E4W14 | 44577015201 | 2023-01-06 | QTR3 | 22/23 | 1 | 0 | 227 | 332 | 330 | 99.12% | 1 | 2 | 0 | 0 | 105 | 0 | 4294622 | 50000 | 4244622 | 4294622 | 4411466 | 0 | 0 | 0 | 4411466 | 4411466 | 103.9% | 1 | 0 | 0 | 72 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 47374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47374 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 |  | 2024-04-16 | QTR4 | 23/24 | 412 | 4978122.09
| 04 | E4W41 | 44576915201 | 2023-01-06 | QTR3 | 22/23 | 1 | 2 | 196 | 235 | 235 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 4444623 | 50000 | 4394623 | 4539611 | 4542613 | 0 | 225000 | 225000 | 4767613 | 4542438 | 103.4% | 1 | -225175 | 94987 | 33 | 6 | 0 | 0 | 20337 | 0 | 0 | 0 | 10823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126147 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2024-02-22 | QTR3 | 23/24 |  | 2023-11-09 | QTR2 | 23/24 | 409 | 4468546.98 | B5 | ACC - INCENTIVE/DISINCENTIVE
| Dist 04 District Let Contracts SubTotal |  |  |  |  | 13 | 25 | 26 | 3271 | 4587 | 4403 | 92.31% | 12 | 184 | 0 | 0 | 1245 | 71 | 62341564 | 781914 | 61559650 | 64357872 | 62870417 | 0 | 225000 | 225000 | 63095417 | 63250347 | 92.31% | 12 | 300683 | 2016307 | 897 | 276 | 0 | 0 | 125995 | 3011 | 65 | 0 | 1544757 | 77301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 486245 | 0 | 7 | 0 | 110583 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 7087 | 0 | 0 | 0 | 94987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38 | -138692 | 0 | 130 | 71 | 2230961 | 80312
| District 04 Totals |  |  |  |  | 34 | 73 | 81 | 9822 | 14584 | 14333 | 97.06% | 33 | 251 | 0 | 0 | 4618 | 165 | 149434771 | 2005932 | 147428839 | 153607937 | 150423773 | 0 | 225000 | 225000 | 150648773 | 152629133 | 94.12% | 32 | 3430773 | 4261606 | 3271 | 947 | 50 | 39 | 518769 | 138304 | 220 | 32 | 2608844 | 115716 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 847268 | 68909 | 7 | 0 | 587102 | 0 | 22 | 0 | 0 | 0 | 585 | 0 | 106172 | 0 | 0 | 0 | 458448 | 33274 | 90 | 6 | 43588 | 42593 | 34 | 0 | 14596 | 0 | 0 | -38 | -149895 | 0 | 1008 | 148 | 4931419 | 398796
| 05 | T5552 | 40714345201 | 2016-06-08 | QTR4 | 15/16 | 21 | 32 | 1050 | 1826 | 1829 | 140% | 0 | -3 | 3 | 0 | 359 | 417 | 75824482 | 160000 | 75664482 | 86884143 | 89837352 | 0 | 0 | 0 | 89837352 | 90458012 | 119.6% | 0 | 815723 | 10910761 | 209 | 150 | 0 | 13 | 563442 | 81716 | 0 | 113 | 3719605 | 1534190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | -46035 | 0 | 0 | 0 | 107943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189623 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 417 | 10835624 | 1823881 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2021-10-13 | QTR2 | 21/22 | 509 | 88197361.71 | B2:B2:B5:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B/BONUS
| 05 | T5626 | 24020025201 | 2017-12-06 | QTR2 | 17/18 | 8 | 23 | 1454 | 2090 | 2089 | 117.8% | 1 | 1 | 0 | 0 | 376 | 260 | 108299973 | 155000 | 108144973 | 115225015 | 116585814 | 0 | 0 | 0 | 116585814 | 117462578 | 108.6% | 1 | 1572381 | 6683848 | 186 | 190 | 0 | 260 | 4333446 | 8284 | 0 | 0 | 1863531 | 48189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 6294756 | 56473 | Z04-1543470 | LIBERTY MUTUAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 |  | 2023-12-19 | QTR2 | 23/24 | 507 | 150691414.85
| 05 | T5705 | 44113615201 | 2021-05-26 | QTR4 | 20/21 | 3 | 10 | 310 | 653 | 651 | 119.4% | 1 | 2 | 0 | 0 | 281 | 62 | 15404884 | 150000 | 15254884 | 16605228 | 17046359 | 0 | 0 | 0 | 17046359 | 17998317 | 118% | 0 | 1051871 | 1200344 | 221 | 60 | 0 | 0 | 619876 | 0 | 0 | 0 | 257299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 420621 | 0 | 0 | 42 | 13057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1321179 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-14 | QTR3 | 23/24 |  | 2023-08-07 | QTR1 | 23/24 | 512 | 17500000.26
| 05 | T5726 | 44354415201 | 2022-03-30 | QTR3 | 21/22 | 2 | 0 | 120 | 347 | 347 | 100% | 1 | 0 | 0 | 0 | 227 | 0 | 1057650 | 26700 | 1030950 | 1057650 | 1051826 | 0 | 0 | 0 | 1051826 | 1051826 | 102% | 1 | 0 | 0 | 157 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 6240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25040 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-02-14 | QTR3 | 23/24 |  | 2024-01-04 | QTR3 | 23/24 | 514 | 838159.94
| 05 | T5733 | 44381515201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 290 | 440 | 439 | 106.6% | 1 | 1 | 0 | 0 | 130 | 20 | 7387943 | 81000 | 7306943 | 7578305 | 6929112 | 0 | 0 | 0 | 6929112 | 7638830 | 104.5% | 1 | 716998 | 190361 | 50 | 80 | 0 | 20 | 183081 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 190361 | 436 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2023-04-17 | QTR4 | 22/23 | 513 | 8754090.28
| 05 | T5737 | 44288115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 140 | 343 | 342 | 99.29% | 1 | 1 | 0 | 0 | 203 | 0 | 1605048 | 49058 | 1555990 | 1606653 | 1573163 | 0 | 0 | 0 | 1573163 | 1576898 | 101.3% | 1 | 3735 | 1605 | 66 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-11-30 | QTR2 | 23/24 |  | 2023-07-21 | QTR1 | 23/24 | 514 | 1288583.85
| 05 | T5738 | 44290915201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 270 | 349 | 349 | 100% | 1 | 0 | 0 | 0 | 79 | 0 | 9861239 | 100000 | 9761239 | 9880239 | 9803603 | 0 | 0 | 0 | 9803603 | 10869062 | 111.3% | 0 | 1065459 | 19000 | 40 | 39 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24350 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-02-28 | QTR3 | 22/23 | 514 | 13653415.96
| 05 | T5742 | 43612515201 | 2022-02-23 | QTR3 | 21/22 | 2 | 4 | 250 | 445 | 445 | 108.4% | 1 | 0 | 0 | 0 | 174 | 21 | 4343701 | 50000 | 4293701 | 4496683 | 4615463 | 0 | 0 | 0 | 4615463 | 4641212 | 108.1% | 1 | 25749 | 152983 | 113 | 61 | 0 | 0 | 29867 | 0 | 0 | 42 | 133723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 172975 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-05-03 | QTR4 | 23/24 |  | 2024-02-01 | QTR3 | 23/24 | 514 | 4840790.03
| 05 | T5746 | 43915715201 | 2022-05-25 | QTR4 | 21/22 | 2 | 1 | 200 | 308 | 308 | 114% | 1 | 0 | 0 | 0 | 83 | 25 | 1480640 | 50000 | 1430640 | 1481349 | 1525188 | 0 | 0 | 0 | 1525188 | 1522820 | 106.4% | 1 | -2368 | 709 | 49 | 31 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-06-28 | QTR4 | 23/24 |  | 2024-02-23 | QTR3 | 23/24 | 514 | 1288917.65
| 05 | T5750 | 44568415201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 130 | 168 | 168 | 118.5% | 1 | 0 | 0 | 0 | 14 | 24 | 966460 | 40500 | 925960 | 966460 | 931181 | 0 | 0 | 0 | 931181 | 930236 | 100.5% | 1 | -945 | 0 | 5 | 9 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-09 | QTR3 | 23/24 |  | 2023-11-03 | QTR2 | 23/24 | 515 | 970160.65
| 05 | T5763 | 44569015201 | 2022-08-31 | QTR1 | 22/23 | 2 | 1 | 139 | 176 | 176 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 1690095 | 50000 | 1640095 | 1690972 | 1630216 | 0 | 0 | 0 | 1630216 | 1601935 | 97.67% | 1 | -27404 | 877 | 28 | 9 | 0 | 0 | 20792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21668 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 |  | 2023-09-11 | QTR1 | 23/24 | 513 | 2378838.75
| 05 | T5765 | 43759625201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 190 | 217 | 198 | 90% | 1 | 19 | 0 | 0 | 27 | 0 | 1068776 | 38700 | 1030076 | 1068776 | 1003835 | 0 | 0 | 0 | 1003835 | 1003807 | 97.45% | 1 | -28 | 0 | 19 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263013168 | MEJIA INTERNATIONAL GROUP CORPORATION | N/A | N/A | N/A | N/A | 2023-10-13 | QTR2 | 23/24 |  | 2023-08-29 | QTR1 | 23/24 | 512 | 1065459.45
| 05 | T5766 | 44569515201 | 2022-10-05 | QTR2 | 22/23 | 1 | 0 | 170 | 190 | 188 | 101.2% | 1 | 2 | 0 | 0 | 16 | 4 | 1397100 | 50000 | 1347100 | 1397100 | 1188314 | 0 | 0 | 0 | 1188314 | 1188314 | 88.21% | 1 | 0 | 0 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 4 | 26312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 26312 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 |  | 2023-10-30 | QTR2 | 23/24 | 509 | 1256129.81
| 05 | T5771 | 44316615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 1 | 190 | 226 | 226 | 100% | 1 | 0 | 0 | 0 | 36 | 0 | 3891608 | 50000 | 3841608 | 3851608 | 3861679 | 0 | 0 | 0 | 3861679 | 3828346 | 99.65% | 1 | -33333 | -40000 | 27 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 19342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19342 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-22 | QTR3 | 23/24 |  | 2023-09-26 | QTR1 | 23/24 | 515 | 5132264.8
| 05 | T5774 | 44568815201 | 2022-12-07 | QTR2 | 22/23 | 2 | 1 | 160 | 193 | 192 | 99.38% | 1 | 1 | 0 | 0 | 33 | 0 | 662662 | 40500 | 622162 | 662941 | 634436 | 0 | 0 | 0 | 634436 | 634157 | 101.9% | 1 | 0 | 279 | 22 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-04-11 | QTR4 | 23/24 |  | 2023-12-17 | QTR2 | 23/24 | 512 | 863381
| 05 | T5780 | 44585815201 | 2023-01-04 | QTR3 | 22/23 | 1 | 0 | 210 | 243 | 240 | 98.57% | 1 | 3 | 0 | 0 | 33 | 0 | 1654943 | 50000 | 1604943 | 1654943 | 1622200 | 0 | 0 | 0 | 1622200 | 1622200 | 101.1% | 1 | 0 | 0 | 16 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-06-14 | QTR4 | 23/24 |  | 2024-05-14 | QTR4 | 23/24 | 514 | 1788242.1
| 05 | T5781 | 43713315201 | 2023-01-25 | QTR3 | 22/23 | 3 | 2 | 180 | 241 | 241 | 100% | 1 | 0 | 0 | 0 | 61 | 0 | 1838831 | 53750 | 1785081 | 1848822 | 1683358 | 0 | 0 | 0 | 1683358 | 1678146 | 94.01% | 1 | -5213 | 9991 | 31 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-24 | QTR4 | 23/24 |  | 2024-02-16 | QTR3 | 23/24 | 513 | 2056817.59
| 05 | T5785 | 44976515201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 150 | 203 | 203 | 100% | 1 | 0 | 0 | 0 | 53 | 0 | 527418 | 32500 | 494918 | 527418 | 510407 | 0 | 0 | 0 | 510407 | 510407 | 103.1% | 1 | 0 | 0 | 3 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 4659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11800 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-05-02 | QTR4 | 23/24 |  | 2024-04-09 | QTR4 | 23/24 | 506 | 916063.6
| 05 | T9028 | 44532115223 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 250 | 437 | 437 | 152.8% | 0 | 0 | 0 | 0 | 55 | 132 | 4468000 | 50000 | 4418000 | 4785216 | 5263219 | 0 | 0 | 0 | 5263219 | 5259180 | 119% | 0 | 0 | 317216 | 21 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 30874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30874 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LL | N/A | N/A | N/A | N/A | 2024-05-03 | QTR4 | 23/24 |  | 2024-02-07 | QTR3 | 23/24 | 512 | 3979533.39
| Dist 05 Central Let Contracts SubTotal |  |  |  |  | 18 | 56 | 81 | 5603 | 8658 | 8631 | 94.44% | 17 | 27 | 3 | 0 | 2222 | 833 | 238963453 | 1227708 | 237735745 | 258484305 | 267296725 | 0 | 0 | 0 | 262033506 | 266217103 | 83.33% | 15 | 5182625 | 19130758 | 1249 | 970 | 0 | 342 | 5755854 | 90436 | 0 | 159 | 6032316 | 1582379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 381727 | 0 | 0 | 42 | 174452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299618 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 875 | 18945012 | 1880790
| Dist 05 Central Let Contracts SubTotal includes T9 contracts |  |  |  |  | 19 | 93 | 132 | 10406 | 15927 | 15870 | 89.47% | 17 | 57 | 3 | 0 | 4140 | 1381 | 406570424 | 2345416 | 404225008 | 434869683 | 444756098 | 0 | 0 | 0 | 439492879 | 447235374 | 78.95% | 15 | 9549527 | 27667971 | 2310 | 1824 | 0 | 671 | 10948266 | 99156 | 0 | 205 | 8375901 | 1630568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337 | 809489 | 0 | 0 | 84 | 240961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409613 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 0 | 1333 | 27085274 | 1937699
| 05 | E50B4 | 44290615201 | 2022-07-06 | QTR1 | 22/23 | 1 | 1 | 200 | 317 | 317 | 107% | 1 | 0 | 0 | 0 | 103 | 14 | 3079406 | 50000 | 3029406 | 3129406 | 3205711 | 0 | 0 | 0 | 3205711 | 3130395 | 103.3% | 1 | -75316 | 50000 | 26 | 77 | 0 | 0 | 3862 | 0 | 0 | 28 | 3528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 54904 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 |  | 2023-08-11 | QTR1 | 23/24 | 513 | 3825881.85
| 05 | E51A0 | 43856235201 | 2021-02-16 | QTR3 | 20/21 | 2 | 2 | 470 | 814 | 814 | 113.2% | 1 | 0 | 0 | 0 | 293 | 51 | 14521514 | 150000 | 14371514 | 14674974 | 14758568 | 0 | 0 | 0 | 14758568 | 14990012 | 104.3% | 1 | 320347 | 153460 | 66 | 216 | 0 | 0 | 124159 | 0 | 11 | 113 | 118697 | 75961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 113 | 284283 | 75961 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 |  | 2023-08-11 | QTR1 | 23/24 | 515 | 15223948.66
| 05 | E51A9 | 44102015201 | 2020-09-01 | QTR1 | 20/21 | 1 | 7 | 280 | 534 | 544 | 113.9% | 1 | -10 | 10 | 0 | 225 | 29 | 7501367 | 72000 | 7429367 | 7798794 | 7531686 | -41316 | 0 | -41316 | 7490370 | 7740983 | 104.2% | 1 | 263750 | 297427 | 61 | 164 | 0 | 0 | 19197 | 0 | 0 | 29 | 278231 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 297427 | 5549 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2022-05-27 | QTR4 | 21/22 | 514 | 7321146.81
| 05 | E53B6 | 43901715201 | 2022-09-07 | QTR1 | 22/23 | 1 | 0 | 220 | 261 | 166 | 56.82% | 1 | 95 | 0 | 0 | 41 | 0 | 1640053 | 50000 | 1590053 | 1640053 | 1539808 | 0 | 0 | 0 | 1539808 | 1539808 | 96.84% | 1 | 0 | 0 | 32 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-11-01 | QTR2 | 23/24 |  | 2023-09-15 | QTR1 | 23/24 | 514 | 2062514.65
| 05 | E54B0 | 43986525201 | 2023-01-04 | QTR3 | 22/23 | 2 | 1 | 230 | 292 | 292 | 100% | 1 | 0 | 0 | 0 | 62 | 0 | 1188917 | 50000 | 1138917 | 1190920 | 1139015 | 0 | 0 | 0 | 1139015 | 1136823 | 99.82% | 1 | -189 | 2003 | 34 | 28 | 0 | 0 | 9833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9833 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 |  | 2024-01-18 | QTR3 | 23/24 | 513 | 1369687.25
| 05 | E55B1 | 43914215201 | 2022-12-06 | QTR2 | 22/23 | 1 | 1 | 280 | 384 | 384 | 110.7% | 1 | 0 | 0 | 0 | 74 | 30 | 6255758 | 68000 | 6187758 | 6282058 | 5782361 | 0 | 0 | 0 | 5782361 | 5745517 | 92.85% | 1 | -36845 | 26300 | 46 | 28 | 0 | 0 | 0 | 0 | 0 | 20 | 45289 | 17874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 57746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 103035 | 17874 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-06-05 | QTR4 | 23/24 |  | 2024-03-26 | QTR3 | 23/24 | 515 | 7312039.9
| 05 | E55B2 | 44417515201 | 2022-09-07 | QTR1 | 22/23 | 2 | 2 | 190 | 227 | 228 | 100.5% | 1 | -1 | 1 | 0 | 37 | 0 | 2868033 | 50000 | 2818033 | 2873478 | 2862070 | 0 | 0 | 0 | 2862070 | 2854258 | 101.3% | 1 | -2367 | 5445 | 14 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5445 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-06-25 | QTR4 | 23/24 |  | 2024-01-25 | QTR3 | 23/24 | 509 | 2740878.55
| 05 | E55B3 | 44942415201 | 2022-12-06 | QTR2 | 22/23 | 1 | 0 | 150 | 187 | 187 | 100% | 1 | 0 | 0 | 0 | 37 | 0 | 950694 | 34728 | 915966 | 950694 | 969481 | 0 | 0 | 0 | 969481 | 969481 | 105.8% | 1 | 0 | 0 | 28 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 |  | 2023-09-14 | QTR1 | 23/24 | 509 | 729303.27
| 05 | E55B4 | 44942515201 | 2022-11-01 | QTR2 | 22/23 | 1 | 0 | 170 | 174 | 149 | 85.29% | 1 | 25 | 0 | 0 | 4 | 0 | 967737 | 42032 | 925705 | 967737 | 851103 | 0 | 0 | 0 | 851103 | 851002 | 91.93% | 1 | -101 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-09-06 | QTR1 | 23/24 |  | 2023-07-10 | QTR1 | 23/24 | 514 | 882686.9
| 05 | E55B9 | 44655815201 | 2022-10-11 | QTR2 | 22/23 | 2 | 1 | 130 | 243 | 243 | 100.8% | 1 | 0 | 0 | 0 | 112 | 1 | 1178485 | 48750 | 1129735 | 1182078 | 1222101 | 0 | 0 | 0 | 1222101 | 1216754 | 107.7% | 1 | -1755 | 3592 | 91 | 21 | 0 | 1 | 4476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4476 | 0 | F770603738 | WRANGLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 |  | 2023-10-18 | QTR2 | 23/24 | 513 | 1289085.95
| 05 | E56B2 | 44381615201 | 2022-11-01 | QTR2 | 22/23 | 1 | 0 | 270 | 321 | 321 | 100% | 1 | 0 | 0 | 0 | 51 | 0 | 3435770 | 50000 | 3385770 | 3435770 | 3371565 | 0 | 0 | 0 | 3371565 | 3338650 | 98.61% | 1 | -32915 | 0 | 19 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2024-05-03 | QTR4 | 23/24 |  | 2024-03-25 | QTR3 | 23/24 | 509 | 4749444.93
| 05 | E56B4 | 44713515201 | 2023-04-04 | QTR4 | 22/23 | 1 | 0 | 170 | 195 | 195 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 939661 | 41955 | 897706 | 939661 | 899114 | 0 | 0 | 0 | 899114 | 899114 | 100.2% | 1 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2024-05-10 | QTR4 | 23/24 |  | 2024-01-22 | QTR3 | 23/24 | 514 | 881063.3
| 05 | E57A1 | 44343315201 | 2021-11-02 | QTR2 | 21/22 | 3 | 1 | 350 | 515 | 515 | 108% | 1 | 0 | 0 | 0 | 137 | 28 | 5312936 | 52636 | 5260300 | 5361981 | 5275495 | 0 | 0 | 0 | 5275495 | 5333592 | 101.4% | 1 | 107142 | 49045 | 81 | 56 | 0 | 0 | 2577 | 0 | 0 | 28 | 12635 | 2522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 81860 | 2522 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-12-22 | QTR2 | 23/24 |  | 2023-08-11 | QTR1 | 23/24 | 513 | 6332507.08
| 05 | E57A4 | 44113215201 | 2021-10-05 | QTR2 | 21/22 | 5 | 2 | 289 | 528 | 527 | 99.65% | 1 | 1 | 0 | 0 | 239 | 0 | 7424369 | 84545 | 7339824 | 7591181 | 7558842 | 0 | 0 | 0 | 7558842 | 7794728 | 106.2% | 1 | 394527 | 166812 | 75 | 164 | 0 | 0 | 15614 | 0 | 0 | 0 | 22253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222204 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 |  | 2023-07-12 | QTR1 | 23/24 | 513 | 9276735.05
| 05 | E58A4 | 44290515201 | 2022-02-01 | QTR3 | 21/22 | 3 | 2 | 260 | 357 | 355 | 106.2% | 1 | 2 | 0 | 0 | 79 | 18 | 3001616 | 50000 | 2951616 | 3060677 | 3027637 | 0 | 0 | 0 | 3027637 | 3063478 | 103.8% | 1 | 44903 | 59061 | 54 | 25 | 0 | 0 | 0 | 0 | 0 | 18 | 39866 | 5874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 48928 | 5874 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 |  | 2023-06-20 | QTR4 | 22/23 | 507 | 2459664.25
| 05 | E58A7 | 44602015201 | 2022-02-01 | QTR3 | 21/22 | 1 | 0 | 170 | 301 | 334 | 119.4% | 1 | -33 | 33 | 0 | 131 | 0 | 1509974 | 48500 | 1461474 | 1509974 | 1539994 | -55902 | 0 | -55902 | 1484092 | 1540522 | 105.4% | 1 | 56430 | 0 | 11 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2024-04-24 | QTR4 | 23/24 |  | 2023-11-06 | QTR2 | 23/24 | 509 | 1275856.02
| 05 | E58B2 | 44529415201 | 2022-11-01 | QTR2 | 22/23 | 2 | 1 | 300 | 354 | 325 | 90.33% | 1 | 29 | 0 | 0 | 54 | 0 | 8096921 | 114500 | 7982421 | 8098655 | 8200608 | 0 | 0 | 0 | 8200608 | 8093983 | 101.4% | 1 | -104891 | 1734 | 26 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 65137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65137 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-03-05 | QTR3 | 23/24 |  | 2023-12-20 | QTR2 | 23/24 | 512 | 11713738.11
| 05 | E59A9 | 43913015201 | 2022-01-04 | QTR3 | 21/22 | 1 | 0 | 140 | 248 | 246 | 116.4% | 1 | 2 | 0 | 0 | 83 | 25 | 679529 | 24250 | 655279 | 679529 | 677096 | 0 | 0 | 0 | 677096 | 677187 | 103.3% | 1 | 92 | 0 | 49 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1848 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 |  | 2023-06-08 | QTR4 | 22/23 | 514 | 681570.8
| Dist 05 District Let Contracts SubTotal |  |  |  |  | 18 | 31 | 21 | 4269 | 6252 | 6142 | 100% | 18 | 110 | 44 | 0 | 1787 | 196 | 70552740 | 1081896 | 69470844 | 71367620 | 70412255 | -97218 | 0 | -97218 | 70315037 | 70916287 | 100% | 18 | 932812 | 814879 | 718 | 1058 | 0 | 1 | 179718 | 0 | 11 | 236 | 589405 | 107780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 177485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 272 | 1191418 | 107780
| District 05 Totals |  |  |  |  | 36 | 87 | 102 | 9872 | 14910 | 14773 | 97.22% | 35 | 137 | 47 | 0 | 4009 | 1029 | 309516193 | 2309604 | 307206589 | 329851925 | 337708980 | -97218 | 0 | -97218 | 332348543 | 337133390 | 91.67% | 33 | 6115437 | 19945637 | 1967 | 2028 | 0 | 343 | 5935572 | 90436 | 11 | 395 | 6621721 | 1690159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331 | 559212 | 0 | 0 | 42 | 174452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 544429 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 0 | -106929 | 0 | 11 | 1147 | 20136430 | 1988570
| 06 | T6505 | 43326435201 | 2020-08-26 | QTR1 | 20/21 | 4 | 2 | 350 | 382 | 376 | 98.29% | 1 | 6 | 0 | 0 | 32 | 0 | 4604161 | 51560 | 4552601 | 4652806 | 4445340 | -1 | 400000 | 399999 | 4845339 | 4484965 | 98.51% | 1 | -360374 | 48646 | 14 | 18 | 0 | 0 | 8472 | 0 | 0 | 0 | 7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9425 | 0 | 0 | 0 | 44090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69565 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-10-27 | QTR2 | 23/24 |  | 2022-02-11 | QTR3 | 21/22 | 636 | 4947288.63 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6508 | 42325125201 | 2021-07-28 | QTR1 | 21/22 | 2 | 5 | 900 | 931 | 597 | 62.89% | 1 | 334 | 0 | 0 | 31 | 0 | 42480180 | 150000 | 42330180 | 43009539 | 42865939 | 0 | 4169010 | 4169010 | 47034949 | 42923362 | 101.4% | 1 | -2863217 | 529359 | 9 | 22 | 0 | 0 | 179323 | 10153 | 0 | 0 | 83681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63554 | 0 | 0 | 0 | 68833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474751 | 10153 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-02-07 | QTR3 | 23/24 |  | 2023-10-17 | QTR2 | 23/24 | 613 | 49760527.32 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6513 | 43998615201 | 2022-03-30 | QTR3 | 21/22 | 3 | 2 | 240 | 265 | 220 | 81.25% | 1 | 45 | 0 | 0 | 25 | 0 | 2569128 | 50000 | 2519128 | 2717271 | 2543862 | 0 | 120000 | 120000 | 2663862 | 2540376 | 100.8% | 1 | -123486 | 148143 | 5 | 20 | 0 | 0 | 60316 | 0 | 0 | 0 | 105162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174351 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-06-14 | QTR4 | 22/23 | 636 | 2452591.81 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6515 | 43274845201 | 2022-03-30 | QTR3 | 21/22 | 3 | 2 | 240 | 257 | 221 | 85% | 1 | 36 | 0 | 0 | 17 | 0 | 2455465 | 50000 | 2405465 | 2510141 | 2443596 | 0 | 72000 | 72000 | 2515596 | 2440177 | 101.4% | 1 | -75419 | 54676 | 4 | 13 | 0 | 0 | 16029 | 0 | 0 | 0 | 11977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84859 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-15 | QTR2 | 23/24 |  | 2023-07-14 | QTR1 | 23/24 | 636 | 2281095.15 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6516 | 43998115201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 360 | 474 | 464 | 97.22% | 1 | 10 | 0 | 0 | 114 | 0 | 4166383 | 50000 | 4116383 | 4219775 | 4110877 | 0 | 0 | 0 | 4110877 | 4270005 | 103.7% | 1 | 159128 | 53392 | 87 | 27 | 0 | 0 | 31602 | 0 | 0 | 0 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80062 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-15 | QTR2 | 23/24 |  | 2023-06-30 | QTR4 | 22/23 | 613 | 4661947.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6518 | 42918635201 | 2021-12-08 | QTR2 | 21/22 | 5 | 2 | 300 | 332 | 272 | 80% | 1 | 60 | 0 | 0 | 32 | 0 | 2919079 | 50000 | 2869079 | 2940250 | 2881342 | 0 | 210000 | 210000 | 3091342 | 2942048 | 102.5% | 1 | -146480 | 21171 | 17 | 15 | 0 | 0 | 18966 | 0 | 0 | 0 | 13370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47690 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 |  | 2023-04-22 | QTR4 | 22/23 | 613 | 3061117.05 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6519 | 43476835201 | 2022-01-26 | QTR3 | 21/22 | 3 | 1 | 300 | 347 | 274 | 75.67% | 1 | 73 | 0 | 0 | 47 | 0 | 3487287 | 50000 | 3437287 | 3497187 | 3509376 | 0 | 180000 | 180000 | 3689376 | 3539751 | 103% | 1 | -149625 | 9900 | 25 | 22 | 0 | 0 | 30134 | 0 | 0 | 0 | 10006 | 7982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17834 | 0 | 0 | 0 | 1911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59885 | 7982 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2023-09-13 | QTR1 | 23/24 |  | 2023-07-05 | QTR1 | 23/24 | 613 | 3568827.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6534 | 44389515201 | 2022-01-26 | QTR3 | 21/22 | 2 | 3 | 360 | 459 | 444 | 100% | 1 | 15 | 0 | 0 | 99 | 0 | 6302707 | 55045 | 6247662 | 6392688 | 6335976 | 0 | 238000 | 238000 | 6573976 | 6471394 | 103.6% | 1 | -102582 | 89980 | 56 | 28 | 15 | 0 | 105515 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 107915 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-02-15 | QTR3 | 23/24 |  | 2023-07-10 | QTR1 | 23/24 | 636 | 5606871.85 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 06 | T6537 | 44391615201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 400 | 457 | 360 | 75.75% | 1 | 97 | 0 | 0 | 57 | 0 | 6069480 | 55928 | 6013552 | 6030999 | 5946111 | 0 | 320000 | 320000 | 6266111 | 5937355 | 98.73% | 1 | -328757 | -38482 | 35 | 22 | 0 | 0 | 1186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35217 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-05-31 | QTR4 | 23/24 |  | 2023-12-01 | QTR2 | 23/24 | 636 | 5885247.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6543 | 44183615201 | 2022-08-31 | QTR1 | 22/23 | 2 | 2 | 250 | 265 | 227 | 84.8% | 1 | 38 | 0 | 0 | 15 | 0 | 2810000 | 50000 | 2760000 | 2808895 | 2824415 | 0 | 140000 | 140000 | 2964415 | 2810967 | 101.8% | 1 | -153448 | -1105 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 69778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -58214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11564 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-01-29 | QTR3 | 23/24 |  | 2023-08-31 | QTR1 | 23/24 | 636 | 2984244.15 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | T6545 | 44574515201 | 2022-10-05 | QTR2 | 22/23 | 2 | 0 | 160 | 220 | 218 | 98.75% | 1 | 2 | 0 | 0 | 60 | 0 | 915762 | 48586 | 867176 | 915762 | 904223 | 0 | 0 | 0 | 904223 | 903865 | 104.2% | 1 | -358 | 0 | 39 | 21 | 0 | 0 | 5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30027 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2024-03-07 | QTR3 | 23/24 |  | 2024-01-08 | QTR3 | 23/24 | 636 | 1027818.5
| 06 | T6546 | 44574715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 140 | 183 | 172 | 92.14% | 1 | 11 | 0 | 0 | 43 | 0 | 636402 | 36841 | 599561 | 636402 | 608049 | 0 | 0 | 0 | 608049 | 607521 | 101.3% | 1 | -527 | 0 | 26 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-06-05 | QTR4 | 23/24 |  | 2024-04-18 | QTR4 | 23/24 | 613 | 753182.75
| 06 | T6561 | 43081325201 | 2022-05-25 | QTR4 | 21/22 | 2 | 0 | 150 | 250 | 250 | 100% | 1 | 0 | 0 | 0 | 100 | 0 | 836079 | 31578 | 804501 | 836079 | 782914 | 0 | 0 | 0 | 782914 | 778816 | 96.81% | 1 | -4099 | 0 | 83 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10994 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-04-09 | QTR4 | 23/24 |  | 2023-12-01 | QTR2 | 23/24 | 613 | 760317.1
| 06 | T6563 | 44882915201 | 2022-12-07 | QTR2 | 22/23 | 1 | 1 | 120 | 159 | 159 | 100% | 1 | 0 | 0 | 0 | 39 | 0 | 565000 | 26990 | 538010 | 591990 | 490972 | 0 | 0 | 0 | 490972 | 490972 | 91.26% | 1 | 0 | 26990 | 21 | 18 | 0 | 0 | 6537 | 0 | 0 | 0 | 17308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23846 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-08 | QTR3 | 23/24 |  | 2024-02-26 | QTR3 | 23/24 | 613 | 566783
| 06 | T6571 | 44390315201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 209 | 260 | 256 | 98.09% | 1 | 4 | 0 | 0 | 51 | 0 | 1857275 | 50000 | 1807275 | 1907275 | 1881049 | 0 | 0 | 0 | 1881049 | 1877156 | 103.9% | 1 | -3893 | 50000 | 31 | 20 | 0 | 0 | 29472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47710 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2024-05-01 | QTR4 | 23/24 |  | 2024-03-08 | QTR3 | 23/24 | 613 | 2156608.65
| Dist 06 Central Let Contracts SubTotal |  |  |  |  | 15 | 36 | 25 | 4479 | 5241 | 4510 | 100% | 15 | 731 | 0 | 0 | 762 | 0 | 82674388 | 806528 | 81867860 | 83667059 | 82574041 | -1 | 5849010 | 5849009 | 88423050 | 83018730 | 100% | 15 | -4153137 | 992670 | 462 | 285 | 15 | 0 | 493365 | 10153 | 0 | 0 | 322005 | 7982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169144 | 0 | 0 | 0 | 114834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 1189567 | 18135
| 06 | E6L44 | 43652515201 | 2020-11-19 | QTR2 | 20/21 | 4 | 11 | 600 | 779 | 779 | 101.7% | 1 | 0 | 0 | 0 | 169 | 10 | 10780329 | 111884 | 10668445 | 10840590 | 11062582 | 0 | 0 | 0 | 11062582 | 11134539 | 104.4% | 1 | 187452 | 60261 | 119 | 50 | 0 | 10 | 13320 | 0 | 0 | 0 | 36314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -272957 | 0 | 0 | 10 | 81774 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-01-10 | QTR3 | 23/24 |  | 2023-09-27 | QTR1 | 23/24 | 613 | 11006397.88 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6M36 | 44343215201 | 2022-08-25 | QTR1 | 22/23 | 1 | 0 | 160 | 303 | 303 | 102.5% | 1 | 0 | 0 | 0 | 143 | 0 | 935010 | 46311 | 888699 | 935010 | 1101336 | 0 | 0 | 0 | 1101336 | 1101281 | 123.9% | 0 | -55 | 0 | 112 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 36709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 36709 | 0 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-06-10 | QTR4 | 23/24 |  | 2024-02-27 | QTR3 | 23/24 | 613 | 1073050.3
| 06 | E6N08 | 44196015201 | 2022-01-27 | QTR3 | 21/22 | 2 | 5 | 450 | 483 | 372 | 75.33% | 1 | 111 | 0 | 0 | 33 | 0 | 2813265 | 50000 | 2763265 | 2921577 | 2938675 | 0 | 0 | 0 | 2938675 | 2927754 | 106% | 1 | 65 | 108312 | 12 | 21 | 0 | 0 | 47426 | 0 | 0 | 0 | 12785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107049 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2023-10-17 | QTR2 | 23/24 |  | 2023-08-21 | QTR1 | 23/24 | 613 | 3044682.74
| 06 | E6N09 | 44480525201 | 2022-07-28 | QTR1 | 22/23 | 1 | 0 | 240 | 260 | 172 | 63.33% | 1 | 88 | 0 | 0 | 20 | 0 | 797552 | 50000 | 747552 | 797552 | 706126 | 0 | 0 | 0 | 706126 | 706126 | 94.46% | 1 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-08-11 | QTR1 | 23/24 |  | 2023-06-29 | QTR4 | 22/23 | 613 | 1509363.9
| 06 | E6N47 | 44445015201 | 2022-05-26 | QTR4 | 21/22 | 1 | 2 | 250 | 272 | 220 | 79.2% | 1 | 52 | 0 | 0 | 22 | 0 | 2697327 | 50000 | 2647327 | 2771657 | 2731695 | 0 | 180000 | 180000 | 2911695 | 2718704 | 102.7% | 1 | -192991 | 74329 | 14 | 8 | 0 | 0 | 3630 | 0 | 0 | 0 | 41276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48138 | 0 | 0 | 0 | 3654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96698 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 |  | 2023-05-24 | QTR4 | 22/23 | 636 | 2883318.39 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 06 | E6N55 | 44196815201 | 2021-08-26 | QTR1 | 21/22 | 1 | 0 | 280 | 460 | 459 | 119.3% | 1 | 1 | 0 | 0 | 180 | 0 | 757063 | 47154 | 709909 | 757063 | 654819 | 0 | 0 | 0 | 654819 | 654819 | 92.24% | 1 | 0 | 0 | 101 | 24 | 0 | 0 | 33282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 33282 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 |  | 2023-04-06 | QTR4 | 22/23 | 636 | 1042435.8
| 06 | E6O02 | 44479915201 | 2022-10-06 | QTR2 | 22/23 | 2 | 0 | 200 | 217 | 206 | 94.5% | 1 | 11 | 0 | 0 | 17 | 0 | 779455 | 29484 | 749971 | 779455 | 733765 | 0 | 0 | 0 | 733765 | 733765 | 97.84% | 1 | 0 | 0 | 8 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14889 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2024-01-09 | QTR3 | 23/24 |  | 2023-12-13 | QTR2 | 23/24 | 613 | 612148
| 06 | E6O04 | 44196515201 | 2022-11-17 | QTR2 | 22/23 | 1 | 0 | 380 | 414 | 307 | 71.84% | 1 | 107 | 0 | 0 | 34 | 0 | 1446162 | 50000 | 1396162 | 1446162 | 1381923 | 0 | 0 | 0 | 1381923 | 1381923 | 98.98% | 1 | 0 | 0 | 9 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41448 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-03-15 | QTR3 | 23/24 |  | 2024-02-08 | QTR3 | 23/24 | 613 | 2588372.8
| Dist 06 District Let Contracts SubTotal |  |  |  |  | 8 | 13 | 18 | 2560 | 3188 | 2818 | 100% | 8 | 370 | 0 | 0 | 618 | 10 | 21006163 | 434833 | 20571330 | 21249066 | 21310921 | 0 | 180000 | 180000 | 21490921 | 21358911 | 87.5% | 7 | -5529 | 242902 | 395 | 164 | 0 | 10 | 97658 | 0 | 0 | 0 | 90375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 468860 | 0 | 55 | 0 | 3654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -272957 | 0 | 59 | 10 | 411849 | 0
| District 06 Totals |  |  |  |  | 23 | 49 | 43 | 7039 | 8429 | 7328 | 100% | 23 | 1101 | 0 | 0 | 1380 | 10 | 103680551 | 1241361 | 102439190 | 104916125 | 103884962 | -1 | 6029010 | 6029009 | 109913971 | 104377641 | 95.65% | 22 | -4158666 | 1235572 | 857 | 449 | 15 | 10 | 591023 | 10153 | 0 | 0 | 412380 | 7982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 638004 | 0 | 55 | 0 | 118488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -272957 | 0 | 74 | 10 | 1601416 | 18135
| 07 | T7383 | 40582225201 | 2016-06-20 | QTR4 | 15/16 | 3 | 23 | 730 | 1366 | 2427 | 301.8% | 0 | -1061 | 1061 | 0 | 224 | 412 | 27868889 | 150000 | 27718889 | 32682171 | 33265156 | -3418119 | 0 | -3418119 | 29847037 | 30298655 | 109.3% | 1 | 563653 | 4813282 | 103 | 121 | 0 | 69 | 1450267 | 210761 | 0 | 101 | 1642245 | 76915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27403 | 25562 | 0 | 0 | 0 | 0 | 0 | 0 | 135727 | 74502 | 0 | 0 | 0 | 0 | 0 | 242 | 1356044 | 1356044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 4611687 | 1743784 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2024-06-03 | QTR4 | 23/24 |  | 2023-06-30 | QTR4 | 22/23 | 714 | 32874961.99 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | T7424 | 25729855201 | 2019-03-27 | QTR3 | 18/19 | 3 | 4 | 860 | 964 | 931 | 96.16% | 1 | 33 | 0 | 0 | 104 | 0 | 20155312 | 406894 | 19748419 | 20804212 | 20013184 | 0 | 0 | 0 | 20013184 | 19790050 | 100.2% | 1 | -223135 | 648900 | 54 | 50 | 0 | 0 | 350213 | 0 | 0 | 0 | 262060 | 6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637979 | 6325 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-11-03 | QTR2 | 23/24 |  | 2022-04-12 | QTR4 | 21/22 | 798 | 29301814.47
| 07 | T7428 | 43258435201 | 2019-02-27 | QTR3 | 18/19 | 3 | 6 | 445 | 671 | 685 | 128.3% | 0 | -14 | 14 | 0 | 114 | 112 | 9277781 | 90000 | 9187781 | 9481539 | 10184938 | -48258 | 300000 | 251742 | 10436680 | 10081240 | 109.7% | 1 | -350246 | 203759 | 58 | 56 | 0 | 21 | 283799 | 0 | 0 | 0 | 16679 | 10786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -96529 | 0 | 0 | 0 | 12534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 216484 | 10786 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 |  | 2021-06-25 | QTR4 | 20/21 | 796 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | T7451 | 43982985201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 170 | 178 | 550 | 318.8% | 0 | -372 | 372 | 0 | 8 | 0 | 698558 | 34000 | 664558 | 698558 | 557380 | -158860 | 0 | -158860 | 398520 | 531562 | 79.99% | 1 | 133042 | 0 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2022-07-07 | QTR1 | 22/23 | 799 | 691075.3
| 07 | T7468 | 44138615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 3 | 498 | 556 | 514 | 87.75% | 1 | 42 | 0 | 0 | 77 | -19 | 9161461 | 85000 | 9076461 | 9416662 | 9386983 | 0 | 0 | 0 | 9386983 | 9736387 | 107.3% | 1 | 388067 | 255200 | 53 | 24 | 0 | 0 | 337633 | 0 | 0 | 0 | 90042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 0 | -19 | 324328 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-13 | QTR1 | 23/24 |  | 2022-12-02 | QTR2 | 22/23 | 798 | 9040000
| 07 | T7473 | 43944815201 | 2021-04-28 | QTR4 | 20/21 | 1 | 3 | 370 | 492 | 492 | 106.5% | 1 | 0 | 0 | 0 | 98 | 24 | 3457631 | 50000 | 3407631 | 3534214 | 3460775 | 0 | 0 | 0 | 3460775 | 3513340 | 103.1% | 1 | 76197 | 76582 | 60 | 38 | 0 | 0 | 21491 | 1858 | 0 | 0 | 31459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76582 | 1858 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-06-25 | QTR4 | 23/24 |  | 2023-03-22 | QTR3 | 22/23 | 798 | 3048700
| 07 | T7480 | 44025315201 | 2021-12-08 | QTR2 | 21/22 | 1 | 2 | 230 | 353 | 352 | 105.7% | 1 | 1 | 0 | 0 | 109 | 14 | 8381553 | 92000 | 8289553 | 8507750 | 8880433 | 0 | 0 | 0 | 8880433 | 9224126 | 111.3% | 0 | 351217 | 126197 | 83 | 26 | 0 | 0 | 20058 | 0 | 0 | 14 | 157861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7524 | 7524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 185444 | 7524 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 |  | 2023-07-21 | QTR1 | 23/24 | 796 | 9618300
| 07 | T7484 | 43780725201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 290 | 341 | 341 | 103.4% | 1 | 0 | 0 | 0 | 51 | 0 | 2689020 | 50000 | 2639020 | 2695490 | 2436483 | 0 | 0 | 0 | 2436483 | 2426876 | 91.96% | 1 | -3137 | 6470 | 18 | 23 | 0 | 0 | 1911 | 0 | 0 | 0 | 45879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6470 | 6470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54260 | 6470 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2024-04-30 | QTR4 | 23/24 |  | 2023-12-15 | QTR2 | 23/24 | 799 | 3008900
| 07 | T7485 | 44109915201 | 2022-03-30 | QTR3 | 21/22 | 1 | 0 | 135 | 251 | 251 | 100% | 1 | 0 | 0 | 0 | 116 | 0 | 2037125 | 50000 | 1987125 | 2037125 | 1982019 | 0 | 0 | 0 | 1982019 | 1983777 | 99.83% | 1 | 1758 | 0 | 102 | 14 | 0 | 0 | 4355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7115 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 |  | 2023-05-30 | QTR4 | 22/23 | 798 | 1568900
| 07 | T7491 | 44358325201 | 2022-02-23 | QTR3 | 21/22 | 1 | 0 | 150 | 193 | 193 | 100% | 1 | 0 | 0 | 0 | 43 | 0 | 1439445 | 44000 | 1395445 | 1439445 | 1363648 | 0 | 0 | 0 | 1363648 | 1363533 | 97.71% | 1 | -115 | 0 | 34 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-12-06 | QTR2 | 23/24 |  | 2023-09-14 | QTR1 | 23/24 | 796 | 1085600
| 07 | T7496 | 43591435201 | 2022-05-25 | QTR4 | 21/22 | 1 | 3 | 175 | 248 | 248 | 110.9% | 1 | 0 | 0 | 0 | 73 | 0 | 2222629 | 50000 | 2172629 | 2357768 | 2205247 | 0 | 0 | 0 | 2205247 | 2190340 | 100.8% | 1 | -14907 | 135139 | 44 | 10 | 0 | 0 | 6498 | 0 | 0 | 0 | 145802 | 52681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 152300 | 52681 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-12-04 | QTR2 | 23/24 |  | 2023-09-07 | QTR1 | 23/24 | 799 | 2009600
| 07 | T7498 | 44332015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 0 | 120 | 127 | 127 | 100% | 1 | 0 | 0 | 0 | 7 | 0 | 1340863 | 50000 | 1290863 | 1340863 | 1268582 | -12000 | 0 | -12000 | 1256582 | 1256582 | 97.34% | 1 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 |  | 2023-05-22 | QTR4 | 22/23 | 796 | 2027300
| 07 | T9026 | 44490215223 | 2021-11-17 | QTR2 | 21/22 | 2 | 4 | 250 | 536 | 530 | 193.6% | 0 | 6 | 0 | 0 | 286 | 0 | 4025439 | 50000 | 3975439 | 4151284 | 4188035 | 0 | 0 | 0 | 4188035 | 4185783 | 105.3% | 1 | 0 | 125844 | 13 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 3758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 147045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 153054 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-16 | QTR3 | 23/24 |  | 2023-11-24 | QTR2 | 23/24 | 706 | 3685201.18
| Dist 07 Central Let Contracts SubTotal |  |  |  |  | 12 | 18 | 46 | 4173 | 5740 | 7111 | 75% | 9 | -1371 | 1447 | 0 | 1024 | 543 | 88730267 | 1151894 | 87578374 | 94995797 | 95004828 | -3637237 | 300000 | -3337237 | 91667591 | 92396468 | 91.67% | 11 | 922394 | 6265529 | 616 | 379 | 0 | 90 | 2476225 | 212619 | 0 | 115 | 2392027 | 146707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 91 | -81137 | 0 | 0 | 0 | 44816 | 25562 | 0 | 0 | 0 | 0 | 25 | 0 | 199059 | 88496 | 0 | 0 | 0 | 0 | 0 | 242 | 1356044 | 1356044 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 44 | 519 | 6281571 | 1829428
| Dist 07 Central Let Contracts SubTotal Includes T9 Contracts |  |  |  |  | 13 | 35 | 73 | 7866 | 10650 | 12325 | 69.23% | 9 | -1675 | 1833 | 0 | 2110 | 674 | 153617084 | 2203788 | 151413298 | 161460707 | 160932535 | -3856355 | 600000 | -3256355 | 157676180 | 158680064 | 92.31% | 12 | 1281135 | 7843620 | 1142 | 670 | 0 | 111 | 3502183 | 214477 | 0 | 129 | 3145567 | 216499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 182 | -15229 | 0 | 0 | 0 | 62229 | 25562 | 0 | 0 | 0 | 0 | 50 | 0 | 264642 | 102490 | 0 | 0 | 0 | 0 | 0 | 242 | 1356044 | 1356044 | 0 | 0 | 0 | 0 | 0 | -38 | -210932 | 0 | 328 | 626 | 8104509 | 1915072
| 07 | E7N76 | 43956515201 | 2021-03-10 | QTR3 | 20/21 | 2 | 3 | 300 | 401 | 401 | 100% | 1 | 0 | 0 | 0 | 101 | 0 | 6600000 | 63000 | 6537000 | 7117569 | 6571044 | 0 | 0 | 0 | 6571044 | 6563814 | 100.4% | 1 | 0 | 517569 | 36 | 65 | 0 | 0 | 126742 | 0 | 0 | 0 | 110994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517569 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-19 | QTR3 | 23/24 |  | 2023-05-24 | QTR4 | 22/23 | 799 | 6998000
| 07 | E7N90 | 44822115201 | 2022-01-12 | QTR3 | 21/22 | 1 | 1 | 120 | 172 | 172 | 117.5% | 1 | 0 | 0 | 0 | 52 | 0 | 679686 | 28000 | 651686 | 695950 | 640611 | 0 | 0 | 0 | 640611 | 640611 | 98.3% | 1 | 0 | 16264 | 8 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 16264 | 16264 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-04-20 | QTR4 | 22/23 | 799 | 644500
| 07 | E7N95 | 44025115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 3 | 240 | 317 | 314 | 98.75% | 1 | 3 | 0 | 0 | 77 | 0 | 6430299 | 84000 | 6346299 | 6566839 | 6774752 | 0 | 0 | 0 | 6774752 | 7323867 | 115.4% | 0 | 551655 | 136540 | 52 | 25 | 0 | 0 | 103103 | 4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68698 | 68698 | 0 | 0 | 0 | 0 | 0 | 0 | 2540 | 2540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174342 | 75334 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-07-08 | QTR1 | 23/24 |  | 2023-02-24 | QTR3 | 22/23 | 796 | 8690700
| 07 | E7O02 | 43724915201 | 2021-10-13 | QTR2 | 21/22 | 1 | 7 | 322 | 429 | 422 | 102.8% | 1 | 7 | 0 | 0 | 91 | 16 | 4833500 | 50000 | 4783500 | 5430418 | 5535682 | 0 | 200000 | 200000 | 5735682 | 5261328 | 110% | 1 | -199047 | 596918 | 31 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 328040 | 122639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 275307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 603347 | 122639 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2024-03-04 | QTR3 | 23/24 |  | 2023-10-16 | QTR2 | 23/24 | 796 | 3694800 | B10 | ACC - BONUS/INCENT/DISINCENT
| 07 | E7O03 | 43050015201 | 2021-07-14 | QTR1 | 21/22 | 1 | 2 | 690 | 753 | 681 | 89.57% | 1 | 72 | 0 | 0 | 63 | 0 | 8992000 | 85000 | 8907000 | 9003651 | 9360484 | 0 | 0 | 0 | 9360484 | 9368249 | 105.2% | 1 | 18403 | 11651 | 31 | 32 | 0 | 0 | 35754 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10639 | 10639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56758 | 10639 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-03-01 | QTR3 | 23/24 |  | 2023-11-21 | QTR2 | 23/24 | 799 | 9455800
| 07 | E7O04 | 43952615201 | 2021-09-08 | QTR1 | 21/22 | 1 | 2 | 210 | 235 | 235 | 100% | 1 | 0 | 0 | 0 | 25 | 0 | 1944266 | 50000 | 1894266 | 2045152 | 1898792 | 0 | 0 | 0 | 1898792 | 1886359 | 99.58% | 1 | 0 | 100885 | 10 | 15 | 0 | 0 | 17204 | 0 | 0 | 0 | 71248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12433 | 12433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100885 | 12433 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2022-12-09 | QTR2 | 22/23 | 799 | 1797400
| 07 | E7O11 | 44166515201 | 2022-02-09 | QTR3 | 21/22 | 2 | 0 | 180 | 220 | 220 | 100% | 1 | 0 | 0 | 0 | 40 | 0 | 3049631 | 50000 | 2999631 | 3049631 | 3013462 | 0 | 0 | 0 | 3013462 | 3013181 | 100.5% | 1 | -281 | 0 | 21 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 |  | 2023-06-14 | QTR4 | 22/23 | 798 | 2409700
| 07 | E7P02 | 44146915201 | 2022-05-11 | QTR4 | 21/22 | 1 | 0 | 200 | 248 | 248 | 100% | 1 | 0 | 0 | 0 | 48 | 0 | 2611346 | 50000 | 2561346 | 2611346 | 2617684 | 0 | 0 | 0 | 2617684 | 2617512 | 102.2% | 1 | -173 | 0 | 17 | 31 | 0 | 0 | 9955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9955 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2024-05-06 | QTR4 | 23/24 |  | 2024-01-09 | QTR3 | 23/24 | 796 | 2320500
| 07 | E7P05 | 44024415201 | 2022-04-13 | QTR4 | 21/22 | 2 | 1 | 200 | 342 | 335 | 107% | 1 | 7 | 0 | 0 | 142 | 0 | 5007203 | 50000 | 4957203 | 5075397 | 4790051 | 0 | 0 | 0 | 4790051 | 4756788 | 95.96% | 1 | -33263 | 68194 | 97 | 24 | 0 | 0 | 10809 | 0 | 0 | 0 | 57384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68194 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-06-19 | QTR4 | 23/24 |  | 2023-09-11 | QTR1 | 23/24 | 799 | 5384600
| 07 | E7P09 | 43763615201 | 2022-03-09 | QTR3 | 21/22 | 1 | 3 | 275 | 406 | 406 | 119.6% | 1 | 0 | 0 | 0 | 118 | 13 | 2593388 | 50000 | 2543388 | 2709838 | 2503891 | 0 | 0 | 0 | 2503891 | 2499570 | 98.28% | 1 | 1497 | 116449 | 50 | 27 | 10 | 0 | 9735 | 0 | 0 | 13 | 20708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 60632 | 60632 | 0 | 0 | 1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6508 | 5818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 13 | 99313 | 66449 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-01-09 | QTR3 | 23/24 |  | 2023-09-13 | QTR1 | 23/24 | 799 | 2305500
| 07 | E7P21 | 44024915201 | 2022-04-13 | QTR4 | 21/22 | 1 | 0 | 250 | 423 | 423 | 119.2% | 1 | 0 | 0 | 0 | 125 | 48 | 7905829 | 62000 | 7843829 | 7905829 | 8077210 | 0 | 0 | 0 | 8077210 | 8034957 | 102.4% | 1 | -42254 | 0 | 83 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 5458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5458 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-06-10 | QTR4 | 23/24 |  | 2024-01-03 | QTR3 | 23/24 | 796 | 6822100
| 07 | E7P30 | 44761415201 | 2022-04-13 | QTR4 | 21/22 | 1 | 1 | 140 | 171 | 171 | 100% | 1 | 0 | 0 | 0 | 31 | 0 | 2231499 | 50000 | 2181499 | 2259063 | 2052581 | 0 | 0 | 0 | 2052581 | 2046856 | 93.83% | 1 | -5724 | 27565 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 27565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27565 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2023-12-08 | QTR2 | 23/24 |  | 2023-09-13 | QTR1 | 23/24 | 714 | 1792600
| 07 | E7P36 | 44978015201 | 2022-06-08 | QTR4 | 21/22 | 3 | 3 | 300 | 361 | 338 | 92.33% | 1 | 23 | 0 | 0 | 61 | 0 | 4664000 | 50000 | 4614000 | 4709230 | 4734993 | 0 | 0 | 0 | 4734993 | 4662735 | 101.1% | 1 | -72258 | 45230 | 37 | 24 | 0 | 0 | 25230 | 0 | 0 | 0 | 42961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76416 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-10-26 | QTR2 | 23/24 |  | 2023-08-01 | QTR1 | 23/24 | 799 | 5588200 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
| 07 | E7P61 | 44383615201 | 2023-01-11 | QTR3 | 22/23 | 1 | 1 | 140 | 165 | 161 | 97.14% | 1 | 4 | 0 | 0 | 10 | 15 | 506794 | 19000 | 487794 | 527638 | 475289 | 0 | 0 | 0 | 475289 | 475289 | 97.44% | 1 | 0 | 20844 | 16 | 9 | 0 | 0 | 20844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20844 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-11-17 | QTR2 | 23/24 |  | 2023-10-16 | QTR2 | 23/24 | 799 | 441600
| 07 | E7P63 | 44774815201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 120 | 130 | 71 | 50.83% | 1 | 59 | 0 | 0 | 10 | 0 | 619151 | 50000 | 569151 | 619151 | 571177 | 0 | 0 | 0 | 571177 | 571177 | 100.4% | 1 | 0 | 0 | 7 | 3 | 0 | 0 | 7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7087 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 |  | 2023-07-24 | QTR1 | 23/24 | 799 | 1320700
| 07 | E7P82 | 43782315201 | 2023-03-08 | QTR3 | 22/23 | 2 | 0 | 70 | 103 | 103 | 100% | 1 | 0 | 0 | 0 | 33 | 0 | 341000 | 16000 | 325000 | 341000 | 292314 | 0 | 0 | 0 | 292314 | 292314 | 89.94% | 1 | 0 | 0 | 17 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2024-06-05 | QTR4 | 23/24 |  | 2024-02-16 | QTR3 | 23/24 | 796 | 350800.01
| 07 | E7P89 | 44598115201 | 2023-11-08 | QTR2 | 23/24 | 1 | 0 | 60 | 63 | 54 | 85% | 1 | 9 | 0 | 0 | 3 | 0 | 746261 | 43000 | 703261 | 746261 | 629640 | 0 | 0 | 0 | 629640 | 629640 | 89.53% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2024-05-01 | QTR4 | 23/24 |  | 2024-03-29 | QTR3 | 23/24 | 799 | 927702
| 07 | E7P97 | 45217915201 | 2023-02-10 | QTR3 | 22/23 | 1 | 2 | 30 | 31 | 29 | 93.33% | 1 | 2 | 0 | 0 | 1 | 0 | 338100 | 15000 | 323100 | 327764 | 312738 | 0 | 0 | 0 | 312738 | 312738 | 96.79% | 1 | 0 | -10336 | 1 | 0 | 0 | 0 | 8474 | 0 | 0 | 0 | 29697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10336 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-06-25 | QTR4 | 23/24 |  | 2023-10-10 | QTR2 | 23/24 | 799 | 342400 | B0 | ACC - LUMP SUM
| 07 | E7Q34 | 44583115201 | 2023-11-08 | QTR2 | 23/24 | 1 | 0 | 60 | 60 | 53 | 88.33% | 1 | 7 | 0 | 0 | 0 | 0 | 268116 | 17000 | 251116 | 268116 | 251692 | 0 | 0 | 0 | 251692 | 251692 | 100.2% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-06-18 | QTR4 | 23/24 |  | 2024-05-17 | QTR4 | 23/24 | 798 | 436100
| 07 | E7R18 | 43273425202 | 2020-05-12 | QTR4 | 19/20 | 3 | 15 | 815 | 1016 | 1016 | 112.3% | 1 | 0 | 0 | 0 | 101 | 100 | 63996999 | 150000 | 63846999 | 65132965 | 65090666 | 0 | 0 | 0 | 65090666 | 65542493 | 102.7% | 1 | 2125319 | 1135966 | 50 | 51 | 0 | 0 | 540370 | 0 | 0 | 0 | 120716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332845 | 0 | 0 | 79 | 68593 | 68593 | 0 | 0 | 0 | 0 | 0 | 0 | 206020 | 126890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 1268544 | 195483 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2024-04-26 | QTR4 | 23/24 |  | 2023-05-15 | QTR4 | 22/23 | 714 | 55949573 | B8 | ACC - DESIGN/BUILD - MAJOR
| Dist 07 District Let Contracts SubTotal |  |  |  |  | 20 | 28 | 44 | 4722 | 6046 | 5853 | 100% | 20 | 193 | 0 | 0 | 1132 | 192 | 124359068 | 1032000 | 123327068 | 127142808 | 126194753 | 0 | 200000 | 200000 | 126394753 | 126751170 | 95% | 19 | 2343874 | 2783739 | 588 | 476 | 10 | 0 | 915307 | 4096 | 0 | 13 | 833400 | 138903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 625573 | 60632 | 0 | 79 | 147247 | 137291 | 0 | 0 | 0 | 0 | 0 | 31 | 520677 | 158320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 123 | 3042205 | 499241
| District 07 Totals |  |  |  |  | 32 | 46 | 90 | 8895 | 11786 | 12964 | 90.62% | 29 | -1178 | 1447 | 0 | 2156 | 735 | 213089335 | 2183894 | 210905442 | 222138605 | 221199581 | -3637237 | 500000 | -3137237 | 218062344 | 219147638 | 93.75% | 30 | 3266268 | 9049268 | 1204 | 855 | 10 | 90 | 3391532 | 216715 | 0 | 128 | 3225427 | 285610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 91 | 544436 | 60632 | 0 | 79 | 192063 | 162853 | 0 | 0 | 0 | 0 | 25 | 31 | 719736 | 246816 | 0 | 0 | 0 | 0 | 0 | 242 | 1356044 | 1356044 | 0 | 0 | 0 | 0 | 0 | -19 | -105466 | 0 | 106 | 642 | 9323776 | 2328669
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08 | E8Q78 | 43554615201 | 2018-06-15 | QTR4 | 17/18 | 2 | 27 | 1430 | 1594 | 1265 | 76.99% | 1 | 329 | 0 | 0 | 164 | 0 | 143269821 | 150000 | 143119821 | 145759356 | 145166429 | 0 | 5000000 | 5000000 | 150166429 | 144192875 | 100.7% | 1 | -5873129 | 2489535 | 81 | 83 | 0 | 0 | 398577 | 0 | 0 | 0 | 1404790 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131931 | 0 | 0 | 0 | 551048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140484 | 0 | 0 | 0 | 2379872 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 |  | 2022-03-01 | QTR3 | 21/22 | 854 | 156867749.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
| 08 | E8R75 | 42933945201 | 2019-05-21 | QTR4 | 18/19 | 1 | 5 | 565 | 771 | 769 | 99.65% | 1 | 2 | 0 | 0 | 206 | 0 | 19557418 | 150000 | 19407418 | 20031429 | 19576305 | 0 | 0 | 0 | 19576305 | 19542086 | 100.7% | 1 | -34220 | 474011 | 114 | 92 | 0 | 0 | 558466 | 0 | 0 | 0 | 379263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18588 | 0 | 0 | 0 | 31372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -384455 | 0 | 0 | 0 | 606328 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-04-04 | QTR4 | 23/24 |  | 2022-01-04 | QTR3 | 21/22 | 854 | 16516025.03
| 08 | E8R77 | 43798615201 | 2019-05-14 | QTR4 | 18/19 | 3 | 5 | 738 | 1039 | 1039 | 103.8% | 1 | 0 | 0 | 0 | 301 | 0 | 31832323 | 150000 | 31682323 | 32865375 | 32938830 | 0 | 0 | 0 | 32938830 | 32271398 | 101.9% | 1 | -667433 | 1033052 | 175 | 98 | 0 | 0 | 62194 | 0 | 0 | 0 | 38182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 960260 | 0 | 0 | 0 | 77444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1138080 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2023-08-10 | QTR1 | 23/24 |  | 2022-08-17 | QTR1 | 22/23 | 854 | 33799887.12
| 08 | E8R97 | 43730045201 | 2019-09-17 | QTR1 | 19/20 | 1 | 35 | 939 | 1012 | 938 | 92.12% | 1 | 74 | 0 | 0 | 73 | 0 | 139979406 | 150000 | 139829406 | 145733672 | 144403400 | 0 | 6000000 | 6000000 | 150403400 | 143485400 | 102.6% | 1 | -5542884 | 5754265 | 38 | 35 | 0 | 0 | 48807 | 0 | 0 | 0 | 4196617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94312 | 0 | 0 | 0 | 564973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 983554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5902105 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SO | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 |  | 2022-07-31 | QTR1 | 22/23 | 854 | 118749145.78 | B10 | ACC - BONUS/INCENT/DISINCENT
| 08 | E8S19 | 44387815201 | 2020-04-14 | QTR4 | 19/20 | 2 | 0 | 290 | 387 | 387 | 108.3% | 1 | 0 | 0 | 0 | 73 | 24 | 3263898 | 50000 | 3213898 | 3263898 | 3283729 | 0 | 0 | 0 | 3283729 | 3283729 | 102.2% | 1 | 0 | 0 | 41 | 32 | 0 | 0 | 5725 | 0 | 0 | 6 | 18681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 43358 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-02-13 | QTR3 | 23/24 |  | 2021-11-10 | QTR2 | 21/22 | 854 | 3999932.48
| 08 | E8S55 | 44070015201 | 2020-08-31 | QTR1 | 20/21 | 2 | 7 | 515 | 718 | 716 | 94.17% | 1 | 2 | 0 | 0 | 231 | -28 | 16707654 | 150000 | 16557654 | 17277221 | 16377036 | 0 | 0 | 0 | 16377036 | 16720673 | 101% | 1 | 485146 | 569567 | 175 | 56 | 0 | 0 | 18542 | 0 | 0 | 0 | 58747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469864 | 0 | 0 | 0 | 80825 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -28 | -50316 | 0 | 45 | -28 | 616415 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 |  | 2022-12-20 | QTR2 | 22/23 | 854 | 20328685.57
| 08 | E8S64 | 44388015201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 139 | 169 | 162 | 94.96% | 1 | 7 | 0 | 0 | 30 | 0 | 650221 | 50000 | 600221 | 650221 | 606614 | 0 | 0 | 0 | 606614 | 606614 | 101.1% | 1 | 0 | 0 | 21 | 9 | 0 | 0 | 7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9376 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2024-01-16 | QTR3 | 23/24 |  | 2021-09-07 | QTR1 | 21/22 | 854 | 1256846.42
| 08 | E8S95 | 43496825201 | 2021-07-16 | QTR1 | 21/22 | 1 | 0 | 551 | 887 | 877 | 104.5% | 1 | 10 | 0 | 0 | 301 | 35 | 5495495 | 61300 | 5434195 | 5495495 | 5449321 | 0 | 0 | 0 | 5449321 | 5449321 | 100.3% | 1 | 0 | 0 | 214 | 87 | 0 | 35 | 3783 | 0 | 0 | 0 | 20320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 33126 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-03-15 | QTR3 | 23/24 |  | 2024-02-07 | QTR3 | 23/24 | 854 | 6335420.35 | A3 | ICC - DESIGN/BUILD - MINOR
| 08 | E8T03 | 44262715201 | 2021-05-11 | QTR4 | 20/21 | 1 | 1 | 461 | 714 | 714 | 118% | 1 | 0 | 0 | 0 | 245 | 8 | 3696363 | 50000 | 3646363 | 3796363 | 3750537 | 0 | 0 | 0 | 3750537 | 3751060 | 102.9% | 1 | 46856 | 100000 | 101 | 69 | 0 | 0 | 39569 | 0 | 54 | 8 | 54437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 17353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 8 | 111359 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-01-19 | QTR3 | 23/24 |  | 2023-10-24 | QTR2 | 23/24 | 854 | 3759343.91
| 08 | E8T12 | 44028915201 | 2021-10-19 | QTR2 | 21/22 | 4 | 14 | 384 | 571 | 571 | 102.3% | 1 | 0 | 0 | 0 | 118 | 69 | 18831743 | 150000 | 18681743 | 19112673 | 19162598 | 0 | 0 | 0 | 19162598 | 19631006 | 105.1% | 1 | 476842 | 280930 | 120 | 58 | 0 | 0 | 120163 | 0 | 0 | 4 | 3548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9643 | 0 | 0 | 4 | 133722 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 54673 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 317940 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-05-02 | QTR4 | 23/24 |  | 2023-06-28 | QTR4 | 22/23 | 854 | 18566304.65
| 08 | E8T21 | 44029215201 | 2021-09-14 | QTR1 | 21/22 | 2 | 6 | 350 | 617 | 614 | 110.6% | 1 | 3 | 0 | 0 | 208 | 59 | 13350942 | 121421 | 13229522 | 13774510 | 13575224 | 0 | 0 | 0 | 13575224 | 13523826 | 102.2% | 1 | 353962 | 423568 | 176 | 51 | 0 | 0 | 5500 | 0 | 0 | 0 | 24055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 97132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 405361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 532048 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 |  | 2023-09-08 | QTR1 | 23/24 | 854 | 12351694.57
| 08 | E8T38 | 43730095201 | 2022-02-08 | QTR3 | 21/22 | 1 | 0 | 192 | 242 | 235 | 96.35% | 1 | 7 | 0 | 0 | 50 | 0 | 5115331 | 50000 | 5065331 | 5115331 | 5070631 | 0 | 0 | 0 | 5070631 | 5070631 | 100.1% | 1 | 0 | 0 | 26 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-06-15 | QTR4 | 22/23 | 854 | 5087753.85
| 08 | E8T39 | 44430115201 | 2021-12-14 | QTR2 | 21/22 | 1 | 3 | 234 | 278 | 253 | 89.32% | 1 | 25 | 0 | 0 | 44 | 0 | 1975221 | 50000 | 1925221 | 2101149 | 2102097 | 0 | 0 | 0 | 2102097 | 2083906 | 108.2% | 1 | 7736 | 125928 | 25 | 19 | 0 | 0 | 102641 | 0 | 0 | 0 | 36105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174272 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 |  | 2023-03-08 | QTR3 | 22/23 | 854 | 1709882.3
| 08 | E8T42 | 43799015201 | 2022-03-08 | QTR3 | 21/22 | 2 | 3 | 321 | 359 | 286 | 72.27% | 1 | 73 | 0 | 0 | 54 | -16 | 4166000 | 50000 | 4116000 | 4217668 | 4164480 | 0 | 138823 | 138823 | 4303303 | 4215075 | 102.4% | 1 | -86560 | 51668 | 31 | 23 | 0 | 0 | 44026 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 0 | 0 | 0 | -16 | 98536 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 |  | 2023-05-22 | QTR4 | 22/23 | 854 | 3910716.97 | B5 | ACC - INCENTIVE/DISINCENTIVE
| 08 | E8T68 | 44448615201 | 2022-04-12 | QTR4 | 21/22 | 1 | 2 | 329 | 389 | 389 | 100% | 1 | 0 | 0 | 0 | 60 | 0 | 6695054 | 50000 | 6645054 | 6727768 | 6880189 | 0 | 0 | 0 | 6880189 | 6860508 | 103.2% | 1 | -11968 | 32714 | 26 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 74099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81813 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-11-28 | QTR2 | 23/24 |  | 2023-10-05 | QTR2 | 23/24 | 854 | 6191721.36
| 08 | E8T76 | 44206115201 | 2022-08-16 | QTR1 | 22/23 | 2 | 3 | 342 | 413 | 410 | 99.12% | 1 | 3 | 0 | 0 | 71 | 0 | 15249859 | 70079 | 15179780 | 15714097 | 13670638 | 0 | 0 | 0 | 13670638 | 13262271 | 87.37% | 1 | -408367 | 464238 | 37 | 34 | 0 | 0 | 288708 | 0 | 0 | 0 | 28136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500363 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-06-07 | QTR4 | 23/24 |  | 2024-04-04 | QTR4 | 23/24 | 854 | 16808898.8
| 08 | E8T86 | 43855115201 | 2022-08-16 | QTR1 | 22/23 | 1 | 1 | 136 | 169 | 142 | 97.79% | 1 | 27 | 0 | 0 | 9 | 24 | 597627 | 35230 | 562397 | 652711 | 607225 | 0 | 0 | 0 | 607225 | 607225 | 108% | 1 | 0 | 55083 | 6 | 3 | 0 | 24 | 55083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 55083 | 0 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 |  | 2023-06-23 | QTR4 | 22/23 | 854 | 898718.41
| 08 | E8T87 | 43855015201 | 2022-08-16 | QTR1 | 22/23 | 1 | 0 | 199 | 202 | 84 | 40.7% | 1 | 118 | 0 | 0 | 3 | 0 | 767354 | 50000 | 717354 | 767354 | 705154 | 0 | 0 | 0 | 705154 | 705154 | 98.3% | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 |  | 2023-05-11 | QTR4 | 22/23 | 854 | 1243902.61
| 08 | E8T93 | 44029515201 | 2022-06-14 | QTR4 | 21/22 | 2 | 1 | 250 | 302 | 291 | 95.6% | 1 | 11 | 0 | 0 | 52 | 0 | 8768395 | 92871 | 8675524 | 8771000 | 8359690 | 0 | 0 | 0 | 8359690 | 8174501 | 94.22% | 1 | -182584 | 2605 | 33 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2605 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-14 | QTR4 | 23/24 |  | 2023-11-02 | QTR2 | 23/24 | 854 | 9428515.36
| 08 | E8U17 | 44934015201 | 2023-03-14 | QTR3 | 22/23 | 1 | 3 | 181 | 233 | 232 | 100% | 1 | 1 | 0 | 0 | 51 | 1 | 5184770 | 50000 | 5134770 | 5358078 | 5154131 | 0 | 0 | 0 | 5154131 | 5152940 | 100.4% | 1 | -396 | 173308 | 16 | 35 | 0 | 1 | 34193 | 0 | 0 | 0 | 167821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 204130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-03-21 | QTR3 | 23/24 |  | 2024-01-16 | QTR3 | 23/24 | 854 | 4352337.6
| 08 | E8U24 | 44122465201 | 2023-02-14 | QTR3 | 22/23 | 1 | 1 | 94 | 108 | 107 | 98.94% | 1 | 1 | 0 | 0 | 14 | 0 | 855737 | 38426 | 817311 | 857248 | 864748 | 0 | 0 | 0 | 864748 | 863238 | 105.6% | 1 | 0 | 1510 | 12 | 2 | 0 | 0 | 2884 | 0 | 0 | 0 | 30181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37651 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-01 | QTR2 | 23/24 |  | 2023-09-25 | QTR1 | 23/24 | 854 | 859411.5
| 08 | E8U28 | 44261825201 | 2023-05-09 | QTR4 | 22/23 | 1 | 0 | 86 | 90 | 27 | 26.74% | 1 | 63 | 0 | 0 | 4 | 0 | 491221 | 32753 | 458468 | 491221 | 344856 | 0 | 0 | 0 | 344856 | 344856 | 75.22% | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F721180277 | JACK B. HARPER CONTRACTOR L.L.C. | N/A | N/A | N/A | N/A | 2023-11-27 | QTR2 | 23/24 |  | 2023-09-15 | QTR1 | 23/24 | 854 | 690819.2
| Dist 08 District Let Contracts SubTotal |  |  |  |  | 22 | 34 | 117 | 8726 | 11264 | 10508 | 100% | 22 | 756 | 0 | 0 | 2362 | 176 | 446501853 | 1802080 | 444699774 | 458533838 | 452213862 | 0 | 11138823 | 11138823 | 463352685 | 449798293 | 100% | 22 | -11436999 | 12031982 | 1468 | 870 | 0 | 60 | 1796169 | 0 | 54 | 18 | 6538249 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 28 | 40 | 1773365 | 0 | 0 | 22 | 1705595 | 0 | 0 | 0 | 0 | 0 | 130 | 79 | 1563563 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15477 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | -575255 | 0 | 212 | 176 | 12844460 | 0
| District 08 Totals |  |  |  |  | 22 | 34 | 117 | 8726 | 11264 | 10508 | 100% | 22 | 756 | 0 | 0 | 2362 | 176 | 446501853 | 1802080 | 444699774 | 458533838 | 452213862 | 0 | 11138823 | 11138823 | 463352685 | 449798293 | 100% | 22 | -11436999 | 12031982 | 1468 | 870 | 0 | 60 | 1796169 | 0 | 54 | 18 | 6538249 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 28 | 40 | 1773365 | 0 | 0 | 22 | 1705595 | 0 | 0 | 0 | 0 | 0 | 130 | 79 | 1563563 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15477 | 0 | 0 | 0 | 0 | 0 | 0 | -44 | -575255 | 0 | 212 | 176 | 12844460 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 186 | 446 | 628 | 49483 | 105924 | 78581 | 74.73% | 139 | -1675 | 4086 | 0 | 31123 | 7184 | 1556711330 | 15084460 | 1541626875 | 1623631571 | 1639132089 | -9577572 | 6243626 | -3333946 | 1630534921 | 1649666885 | 87.1% | 162 | 29166888 | 66377392 | 20291 | 8506 | 1077 | 2552 | 16145475 | 970598 | 758 | 1668 | 24101781 | 2545505 | 0 | 0 | 5096 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 40838 | 0 | 554 | 951 | 7534799 | 4960721 | 22 | 114 | 1727845 | 142150 | 22 | 0 | 0 | 0 | 3098 | 1286 | 2695706 | 161038 | 0 | 46 | 6658461 | 128274 | 155 | 407 | 1704976 | 1720349 | 919 | 93 | 232392 | 0 | 25 | -38 | -871952 | 0 | 6630 | 7079 | 68360666 | 10628634
| Statewide District Let Contracts SubTotal |  |  |  |  | 123 | 195 | 316 | 33080 | 46400 | 44681 | 93.5% | 115 | 1719 | 304 | 0 | 10893 | 2427 | 970354308 | 7185406 | 963168906 | 1003105589 | 993021809 | -361988 | 11856323 | 11494335 | 1004516145 | 992287650 | 91.06% | 112 | -5050851 | 32751273 | 6744 | 4161 | 84 | 771 | 8762760 | 83453 | 193 | 666 | 17602515 | 448635 | 0 | 62 | 13454 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 108900 | 0 | 97 | 192 | 4664408 | 95349 | 95 | 101 | 1996928 | 137291 | 0 | 0 | 0 | 0 | 858 | 487 | 3097524 | 158320 | 0 | 0 | 94987 | 0 | 0 | 1 | 15477 | 0 | 21 | 79 | 0 | 0 | 0 | -82 | -1290538 | 0 | 1348 | 2277 | 35080258 | 923047
| Statewide Totals |  |  |  |  | 309 | 641 | 944 | 82563 | 152324 | 123262 | 82.2% | 254 | 44 | 4390 | 0 | 42016 | 9611 | 2527065638 | 22269866 | 2504795781 | 2626737160 | 2632153898 | -9939560 | 18099949 | 8160389 | 2635051066 | 2641954535 | 88.67% | 274 | 24116037 | 99128665 | 27035 | 12667 | 1161 | 3323 | 24908235 | 1054051 | 951 | 2334 | 41704296 | 2994140 | 0 | 62 | 18550 | 0 | 0 | 0 | -89635 | 0 | 0 | 0 | 149738 | 0 | 651 | 1143 | 12199207 | 5056070 | 117 | 215 | 3724773 | 279441 | 22 | 0 | 0 | 0 | 3956 | 1773 | 5793230 | 319358 | 0 | 46 | 6753448 | 128274 | 155 | 408 | 1720453 | 1720349 | 940 | 172 | 232392 | 0 | 25 | -120 | -2162490 | 0 | 7978 | 9356 | 103440924 | 11551681

## Innovative Contract Info
District | Contract Number | Financial Project ID | Contractor Vendor ID | Contract Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Letting Date | Original Contract Amount | Present Contract Amount | Regular Work To Date (From CRS) | Total CRS SA Allocated Amount | Total CRS Contract Adjustments | Actual Expenditure (From FM System) | Contract Adjustments | [5 empty] | Total Contract Adjustments | Innovative Contracting Adjustments | [5 empty] | Total Innovative Contracting Adjustments |  |  |  |  | DOT Original Estimate | Innovative Contract Type
[16 empty] | Liquidated Damages | Freight Adjustments | Court Orders | Arbitration Orders | Other Adjustments | Damage Recovery |  | Incentives | Liquidated Savings | No Excuse Bonuses | Escalating Incentive / Disincentive | A + B Disincentive | Lane Rental |  | Total Adjustments | Regular Work + Total Adjustments | Actual Expenditures | Actual Expenditures - CRS Amounts Paid |  | Code | Description
1 | E1S66 | 43813715201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2020-12-03 | 8623489 | 9397066 | 9569047 | 773577.77 | 0 | 9781152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9569047 | 9781152 | 212105 | 7399516 | B10:B2:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE
1 | E1S92 | 44153415201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-11-04 | 5052712 | 4990876 | 4942213 | -61835.5 | 0 | 5001843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4942213 | 5001843 | 59630 | 4924225
1 | E1U10 | 44592715201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-10-21 | 1030376 | 1035071 | 1194101 | 4694.69 | 0 | 1194101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1194101 | 1194101 | 0 | 838447
1 | E1U11 | 43503825201 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2021-09-16 | 2146553 | 2448898 | 2092854 | 302345.24 | -195268 | 1897587 | -195268 | 0 | 0 | 0 | 0 | 0 | -195268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -195268 | 1897587 | 1897587 | 0 | 1604001
1 | E1U12 | 44155315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-09-16 | 6272386 | 6303322 | 6506395 | 30935.13 | 0 | 6933886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6506395 | 6933886 | 427490 | 6222847
1 | E1U14 | 44477715201 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2021-12-02 | 3819554 | 3657701 | 3521817 | -161853.09 | 0 | 3658011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3521817 | 3658011 | 136195 | 3928133 | B0 | ACC - LUMP SUM
1 | E1U17 | 44594115201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-02-17 | 722056 | 722056 | 642082 | 0 | 100000 | 642815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000 | 100000 | 742082 | 642815 | -99267 | 1070561 | B1 | ACC - NO EXCUSE BONUS
1 | E1U22 | 44198315201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-07-21 | 2187528 | 2184764 | 2110755 | -2764.07 | 0 | 2097036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2110755 | 2097036 | -13720 | 1943940 | B0 | ACC - LUMP SUM
1 | E1U62 | 43852825201 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2022-03-14 | 6357542 | 6484969 | 6447894 | 127427.58 | 0 | 6447894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6447894 | 6447894 | 0 | 4194627 | LBDB | LOW BID DESIGN BUILD
1 | E1U96 | 44787715201 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-05-02 | 3028512 | 3275716 | 3237381 | 247203.68 | 0 | 3222484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3237381 | 3222484 | -14897 | 2974794 | LBDB:LBDB::::Y | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
1 | E1V07 | 44023115201 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2022-09-15 | 289419 | 311381 | 315649 | 21962 | 0 | 315649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315649 | 315649 | 0 | 331705
1 | E1V14 | 44023715201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2023-02-16 | 1096407 | 1123291 | 1184828 | 26884.12 | 0 | 1184828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1184828 | 1184828 | 0 | 1215795
1 | E1V17 | 44547515201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-02-16 | 3191521 | 3202707 | 3243015 | 11185.6 | 0 | 3255194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3243015 | 3255194 | 12179 | 3232954
1 | E1V19 | 44620915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-02-16 | 2718429 | 2718429 | 2702583 | 0 | 0 | 2702583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2702583 | 2702583 | 0 | 2913080 | B0 | ACC - LUMP SUM
1 | E1V20 | 44620315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-11-03 | 3919123 | 3942427 | 4025522 | 23303.46 | 0 | 3979452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4025522 | 3979452 | -46071 | 4631316
1 | E1V21 | 44782415201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-03-16 | 1465139 | 1465139 | 1275611 | 0 | 0 | 1275611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275611 | 1275611 | 0 | 1729897
1 | E1V34 | 44972015201 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2022-05-18 | 2335000 | 2358883 | 2307883 | 23883.24 | 0 | 2307883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2307883 | 2307883 | 0 | 2186688 | Y | DESIGN/BUILD PROJECT
1 | T1191 | 43355045201 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 6386200 | 6748926 | 6715738 | 362725.1 | 0 | 6808172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6715738 | 6808172 | 92434 | 5529850
1 | T1676 | 43131315201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2018-06-13 | 20052828 | 22892173 | 22098737 | 2839344.43 | 0 | 22211208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22098737 | 22211208 | 112471 | 16688857
1 | T1751 | 41066635201 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2020-04-29 | 43563143 | 43826539 | 44814363 | 263396.26 | 0 | 46184516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44814363 | 46184516 | 1370154 | 44746155
1 | T1761 | 42982315201 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 4097408 | 4902150 | 4899132 | 804741.84 | 0 | 4933511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4899132 | 4933511 | 34379 | 4251830
1 | T1762 | 43943415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 10278123 | 10447272 | 10732729 | 169148.9 | -421368 | 11033438 | -421368 | 0 | 0 | 0 | 0 | 0 | -421368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -421368 | 10311361 | 11033438 | 722077 | 10803857
1 | T1770 | 44068615201 | F204003511 | E&M EQUIPMENT | N/A | N/A | N/A | N/A | 2021-03-31 | 2574061 | 2608561 | 2449563 | 34500.18 | -275991 | 2224392 | -275991 | 0 | 0 | 0 | 0 | 0 | -275991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -275991 | 2173572 | 2224392 | 50820 | 2478689
1 | T1772 | 44211515201 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2020-09-30 | 668342 | 668342 | 641177 | 0 | 0 | 631148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641177 | 631148 | -10029 | 802466
1 | T1777 | 43943015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-09-30 | 7973682 | 8225110 | 8476176 | 251427.57 | -106857 | 9010027 | -106857 | 0 | 0 | 0 | 0 | 0 | -106857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -106857 | 8369319 | 9010027 | 640708 | 9500361
1 | T1781 | 44151815201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2021-01-27 | 4960436 | 5450251 | 5315172 | 489814.72 | 0 | 5587423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5315172 | 5587423 | 272251 | 5666706
1 | T1790 | 44240115201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2020-08-26 | 697485 | 700625 | 698869 | 3140.32 | 0 | 698869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698869 | 698869 | 0 | 802616 | B0 | ACC - LUMP SUM
1 | T1797 | 44013415201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 1568347 | 1712719 | 1717066 | 144371.66 | 0 | 1717066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1717066 | 1717066 | 0 | 1575092
1 | T1799 | 44421315201 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-07-28 | 1799984 | 1831736 | 1823093 | 31752.02 | 0 | 1836082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1823093 | 1836082 | 12989 | 1712726
1 | T1803 | 44485625201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-02-23 | 3990760 | 3990760 | 3720606 | 0 | 0 | 3720606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3720606 | 3720606 | 0 | 4528913
1 | T1806 | 44155915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 7108184 | 8445969 | 8418621 | 1337785.07 | 0 | 8684123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8418621 | 8684123 | 265502 | 6181054
1 | T1808 | 44233315201 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2021-10-27 | 1139701 | 1148801 | 1029185 | 9099.67 | 0 | 1030981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1029185 | 1030981 | 1796 | 1098276
1 | T1811 | 44033915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 2754382 | 2849902 | 2874882 | 95519.17 | 0 | 2877458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2874882 | 2877458 | 2576 | 2214963
1 | T1817 | 44068815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 650650 | 655279 | 608957 | 4628.74 | 0 | 609408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608957 | 609408 | 451 | 447610
1 | T1826 | 44421215201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-08-25 | 1045874 | 1076047 | 1015157 | 30173.84 | 0 | 1015157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015157 | 1015157 | 0 | 898648
1 | T1828 | 44033715201 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-02-23 | 560933 | 623460 | 604533 | 62526.98 | 0 | 604533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604533 | 604533 | 0 | 517232 | B0 | ACC - LUMP SUM
1 | T1829 | 44514215201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-03-30 | 5872391 | 5912809 | 6112682 | 40418.35 | 0 | 6163500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6112682 | 6163500 | 50818 | 6322956
1 | T1831 | 43708815201 | F814212997 | NATIONAL TRAFFIC SOLUTION INC | N/A | N/A | N/A | N/A | 2022-03-30 | 1393708 | 1475766 | 1415171 | 82057.69 | 0 | 1415090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415171 | 1415090 | -81 | 1903170
1 | T1832 | 44880215201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-03-30 | 1651156 | 1659184 | 1593043 | 8028.48 | 0 | 1593043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1593043 | 1593043 | 0 | 2046037
1 | T1834 | 44632015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 4197476 | 4197476 | 3945832 | 0 | 0 | 3902393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3945832 | 3902393 | -43439 | 4322111
1 | T1836 | 44155835201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-03-30 | 3587382 | 3716421 | 3659641 | 129038.93 | 0 | 3667717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3659641 | 3667717 | 8077 | 2875280
1 | T1839 | 44012715201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 461461 | 461461 | 428726 | 0 | 0 | 428726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428726 | 428726 | 0 | 438393
1 | T1842 | 44404915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 1796523 | 1801104 | 1763228 | 4580.68 | 0 | 1764750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1763228 | 1764750 | 1522 | 1217942
1 | T1844 | 43982615201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-02-23 | 9424555 | 9468450 | 9631445 | 43894.65 | 0 | 9723448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9631445 | 9723448 | 92003 | 9297483
2 | E20H1 | 43737715201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-04-20 | 612540 | 612540 | 596655 | 0 | 0 | 596655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596655 | 596655 | 0 | 703931
2 | E20I1 | 43317155201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-05-11 | 5311071 | 5311071 | 5141726 | 0 | 0 | 5104730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5141726 | 5104730 | -36996 | 5008996
2 | E20T5 | 43044935201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-07-20 | 937789 | 937789 | 902864 | 0 | 0 | 902864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902864 | 902864 | 0 | 1332805
2 | E20T7 | 43089715201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-09-14 | 4193000 | 4523767 | 4592009 | 330766.78 | 0 | 4591894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4592009 | 4591894 | -116 | 4765386
2 | E20W3 | 43744215201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-06-08 | 2395648 | 2453298 | 2436381 | 57650.16 | 0 | 2436351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2436381 | 2436351 | -30 | 2554733
2 | E20W8 | 44277915201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2022-11-30 | 1761000 | 1761000 | 1791422 | 0 | 0 | 1791366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791422 | 1791366 | -56 | 909989
2 | E2V58 | 43303615201 | F363286318 | ARCHER WESTERN CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2016-12-14 | 116979302 | 128380916 | 130241787 | 11401614.39 | 0 | 130340218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130241787 | 130340218 | 98430 | 119230875 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR
2 | E2Y76 | 20972255201 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2020-04-15 | 4399943 | 4455060 | 4501267 | 55116.96 | 0 | 4501267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4501267 | 4501267 | 0 | 4855272
2 | E2Z33 | 43860815201 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2019-11-26 | 25732018 | 27245810 | 27469022 | 1513792.32 | 0 | 27535459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27469022 | 27535459 | 66438 | 20749476 | B8:B8::Y | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT
2 | T2703 | 21272425201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2018-05-23 | 11717625 | 11666748 | 11573612 | -50877.32 | -1206768 | 10334162 | -1206768 | 0 | 0 | 0 | 0 | 0 | -1206768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1206768 | 10366844 | 10334162 | -32682 | 12539660
2 | T2725 | 42307145201 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2018-12-05 | 7294444 | 7636147 | 7798283 | 341702.82 | 0 | 7754246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7798283 | 7754246 | -44037 | 7079692
2 | T2749 | 43946715201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 11950705 | 12606239 | 12671373 | 655533.43 | 0 | 12844734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12671373 | 12844734 | 173361 | 11844644
2 | T2757 | 43761115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2020-05-20 | 8709827 | 8796925 | 9281776 | 87098.27 | 0 | 9514074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9281776 | 9514074 | 232299 | 10240285
2 | T2758 | 43939915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-02-26 | 6913040 | 6913040 | 6429139 | 0 | 0 | 6454714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6429139 | 6454714 | 25575 | 7673392
2 | T2772 | 43404115201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2020-05-20 | 10836000 | 11135538 | 11823711 | 299538.44 | 0 | 11908350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11823711 | 11908350 | 84639 | 8768180
2 | T2787 | 44105915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-29 | 13904803 | 14427901 | 14501738 | 523098.66 | 0 | 14430355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14501738 | 14430355 | -71383 | 14722616
2 | T2788 | 44258115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 7945667 | 7945667 | 8118217 | 0 | 0 | 8574396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8118217 | 8574396 | 456179 | 6919712
2 | T2796 | 44119415201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-03-31 | 1882079 | 1993425 | 1914819 | 111345.32 | 0 | 1920086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1914819 | 1920086 | 5267 | 1441903
2 | T2802 | 43575715201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 1262262 | 1262262 | 1249368 | 0 | 0 | 1249498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249368 | 1249498 | 130 | 1338363
2 | T2803 | 44126115201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 4633748 | 3852057 | 3929376 | -781690.82 | 0 | 4154909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3929376 | 4154909 | 225533 | 4540383
2 | T2821 | 44327315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 4876894 | 4984966 | 5022406 | 108072.68 | 0 | 5415141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5022406 | 5415141 | 392735 | 5483811
2 | T2822 | 44331315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 9173879 | 9173879 | 9342688 | 0 | 0 | 9910699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9342688 | 9910699 | 568010 | 9935886
2 | T2824 | 44327415201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 3471681 | 3603585 | 3475517 | 131903.51 | 0 | 3617192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3475517 | 3617192 | 141674 | 3836185
2 | T2825 | 44328215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 698919 | 698919 | 656099 | 0 | 0 | 656099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656099 | 656099 | 0 | 629199
2 | T2826 | 44331115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 8657266 | 8657266 | 8107793 | 0 | 0 | 8099899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8107793 | 8099899 | -7895 | 10016767
2 | T2827 | 43935715201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 6658470 | 6939208 | 6857539 | 280737.94 | 0 | 7132056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6857539 | 7132056 | 274517 | 7633373
2 | T2829 | 44120815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-04-27 | 1047740 | 1047740 | 1004140 | 0 | 0 | 1004137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1004140 | 1004137 | -3 | 1984965
2 | T2833 | 44325815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-01-12 | 6173212 | 6173212 | 6149692 | 0 | 0 | 6808147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6149692 | 6808147 | 658455 | 7484488
2 | T2835 | 44327215201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 9730642 | 9751076 | 10241376 | 20434.13 | 0 | 10650890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10241376 | 10650890 | 409515 | 11590622
2 | T2836 | 44325915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-02-23 | 4069827 | 4084043 | 4107794 | 14216.4 | 0 | 4238033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4107794 | 4238033 | 130239 | 5072862
2 | T2837 | 44329415201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 1371850 | 1371850 | 1320562 | 0 | 0 | 1327034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320562 | 1327034 | 6472 | 1352767
2 | T2845 | 44119425201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 917218 | 984061 | 1118191 | 66842.95 | 0 | 1118191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118191 | 1118191 | 0 | 862999
2 | T2846 | 44126015201 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2022-01-12 | 9551621 | 9552942 | 9869457 | 1320.8 | -18930 | 10485489 | -18930 | 0 | 0 | 0 | 0 | 0 | -18930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18930 | 9850527 | 10485489 | 634962 | 11919284
2 | T2847 | 44328315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 8536881 | 8536881 | 9157134 | 0 | 0 | 9260550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9157134 | 9260550 | 103416 | 10386872
2 | T2848 | 44330515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 13369606 | 13375355 | 13678461 | 5749.66 | 0 | 14091879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13678461 | 14091879 | 413419 | 15619864
2 | T2855 | 43935815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 7918962 | 7918962 | 7962203 | 0 | 0 | 8267055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7962203 | 8267055 | 304853 | 7233768
2 | T2856 | 42983025201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-11-17 | 997892 | 1048834 | 1111095 | 50941.53 | -32186 | 1111095 | -32186 | 0 | 0 | 0 | 0 | 0 | -32186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32186 | 1078909 | 1111095 | 32186 | 943265
2 | T2857 | 44721115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 1077522 | 1077522 | 1075156 | 0 | 0 | 1075156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075156 | 1075156 | 0 | 1339271
2 | T2869 | 43567925201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-08 | 1298306 | 1298306 | 1209436 | 0 | 0 | 1209097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209436 | 1209097 | -339 | 1554776
2 | T2872 | 44534115201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-06-08 | 13193368 | 13193368 | 13034580 | 0 | 0 | 12710549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13034580 | 12710549 | -324030 | 10896298
2 | T2873 | 44557615201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 240110 | 240110 | 185940 | 0 | 0 | 185940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185940 | 185940 | 0 | 402520
2 | T2875 | 44912925201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 1386562 | 1386562 | 1349510 | 0 | 0 | 1349510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349510 | 1349510 | 0 | 1705477
2 | T2877 | 20954355201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 744369 | 788349 | 712669 | 43979.98 | 0 | 717926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712669 | 717926 | 5257 | 931265
2 | T2879 | 44535315201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 5044796 | 5044796 | 5157015 | 0 | 0 | 5122877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5157015 | 5122877 | -34138 | 5802841
2 | T2880 | 21293465201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-08-31 | 621970 | 626401 | 439109 | 4431.34 | 0 | 439109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439109 | 439109 | 0 | 485438
2 | T2881 | 44554015201 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-11-16 | 1959156 | 1959156 | 1946528 | 0 | 0 | 1943700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1946528 | 1943700 | -2828 | 1697524
2 | T2883 | 44912955201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 2185964 | 2192335 | 1926696 | 6371.04 | 0 | 1926696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1926696 | 1926696 | 0 | 2721077
2 | T2887 | 44729015201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 782704 | 782704 | 743960 | 0 | 0 | 743960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743960 | 743960 | 0 | 659452
2 | T2888 | 40392055201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 928540 | 928540 | 970153 | 0 | 0 | 970153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 970153 | 970153 | 0 | 881584
2 | T2892 | 21071935201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 9775622 | 9736781 | 9879780 | -38841.66 | 0 | 9713317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9879780 | 9713317 | -166463 | 10476737
2 | T2895 | 44125915201 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 6674091 | 6674091 | 6876375 | 0 | 0 | 6832975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6876375 | 6832975 | -43400 | 6898413
2 | T2899 | 20761175201 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2022-06-15 | 678930 | 678930 | 558364 | 0 | 0 | 558364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558364 | 558364 | 0 | 998390
2 | T2902 | 43928015201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-11-16 | 3588897 | 4279812 | 4203052 | 690915.3 | 0 | 4198814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4203052 | 4198814 | -4238 | 4177372
2 | T2903 | 44556915201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2023-01-25 | 203240 | 203240 | 190113 | 0 | 0 | 190113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190113 | 190113 | 0 | 229199
2 | T2923 | 44542625201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 212969 | 212969 | 198096 | 0 | 0 | 198096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198096 | 198096 | 0 | 251712
2 | T9023 | 44624515223 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2021-02-17 | 3516622 | 3516622 | 3642093 | 0 | 0 | 3642131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3642093 | 3642131 | 38 | 3117936
3 | E3S70 | 43992635201 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-05-13 | 8497804 | 8518932 | 8897714 | 21128.25 | 0 | 9015856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8897714 | 9015856 | 118142 | 7939245
3 | E3T49 | 44546515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-07-09 | 1331980 | 1331980 | 1360250 | 0 | -16230 | 1331520 | -28730 | 0 | 0 | 0 | 0 | 0 | -28730 | 12500 | 0 | 0 | 0 | 0 | 0 | 12500 | -16230 | 1344020 | 1331520 | -12500 | 1383419 | B10 | ACC - BONUS/INCENT/DISINCENT
3 | E3U04 | 21904225201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-01-12 | 278090 | 278090 | 249120 | 0 | 0 | 249120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249120 | 249120 | 0 | 454254
3 | E3U32 | 42187425201 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2022-01-13 | 109495 | 109495 | 105102 | 0 | 0 | 105102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105102 | 105102 | 0 | 135677
3 | E3U47 | 44158915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-11-10 | 6190992 | 6194018 | 6101074 | 3025.35 | -18750 | 6229251 | 0 | 0 | 0 | 0 | 0 | -18750 | -18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18750 | 6082324 | 6229251 | 146927 | 5430315
3 | E3U83 | 41768355201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2022-07-14 | 2363976 | 2363976 | 2188042 | 0 | -22022 | 2166020 | -22022 | 0 | 0 | 0 | 0 | 0 | -22022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22022 | 2166020 | 2166020 | 0 | 2795459
3 | E3U84 | 44365915201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-02-10 | 3254371 | 3263484 | 3285954 | 9112.73 | 0 | 3378196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3285954 | 3378196 | 92242 | 3044606
3 | E3U86 | 22068525201 | F943481793 | FAITH CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2023-03-09 | 148273 | 148273 | 131932 | 0 | 0 | 131932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131932 | 131932 | 0 | 216111
3 | E3V28 | 44891215201 | F202058265 | STRUCTURAL PRESERVATION SYSTEMS | N/A | N/A | N/A | N/A | 2023-05-11 | 586983 | 689291 | 616073 | 102308 | 0 | 616073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616073 | 616073 | 0 | 1050080
3 | E3V33 | 44891315201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2023-01-12 | 223976 | 223976 | 187027 | 0 | 0 | 187027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187027 | 187027 | 0 | 298951
3 | E3V50 | 42543655201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-08-18 | 3247610 | 3247610 | 2860191 | 0 | 0 | 2860191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2860191 | 2860191 | 0 | 6703767
3 | E3V51 | 44538525201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2022-06-09 | 396162 | 396162 | 353103 | 0 | 0 | 353103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353103 | 353103 | 0 | 736201
3 | E3V90 | 44575815201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-01-12 | 1499653 | 1499653 | 1534493 | 0 | 0 | 1534493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534493 | 1534493 | 0 | 1524311
3 | E3W08 | 22282725201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-05-11 | 553641 | 553641 | 509921 | 0 | 0 | 509921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509921 | 509921 | 0 | 848185
3 | E3W56 | 45102915201 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2023-04-13 | 208278 | 208278 | 193768 | 0 | 0 | 193768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193768 | 193768 | 0 | 247062
3 | E3W98 | 45055015201 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2023-08-10 | 123579 | 123579 | 121257 | 0 | 0 | 121257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121257 | 121257 | 0 | 124156
3 | T3579 | 41413245201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-08-31 | 42140000 | 43136516 | 44812912 | 996516.18 | -789688 | 45313117 | -739708 | 0 | 0 | 0 | 0 | -49980 | -789688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -789688 | 44023224 | 45313117 | 1289893 | 37004160
3 | T3598 | 43357725201 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2021-12-08 | 1449372 | 1449372 | 1245314 | 0 | 0 | 1245462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245314 | 1245462 | 147 | 1387513
3 | T3604 | 43282815201 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 10228411 | 10251581 | 10265075 | 23170.26 | 0 | 10328004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10265075 | 10328004 | 62929 | 10230058
3 | T3664 | 43375115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-06-09 | 2044978 | 2045473 | 1907308 | 495 | 0 | 1907308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1907308 | 1907308 | 0 | 2066195
3 | T3687 | 44072415201 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 889778 | 889778 | 849190 | 0 | 0 | 848671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849190 | 848671 | -519 | 1417657
3 | T3691 | 43717815201 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2020-11-18 | 4269226 | 4374816 | 4440122 | 105590.54 | -30948 | 4471244 | -30948 | 0 | 0 | 0 | 0 | 0 | -30948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30948 | 4409174 | 4471244 | 62070 | 4154506
3 | T3702 | 42446455201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2018-09-26 | 49837733 | 55271608 | 58974974 | 5433874.1 | -12750 | 59151230 | 0 | 0 | 0 | 0 | 0 | -12750 | -12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12750 | 58962224 | 59151230 | 189005 | 51655054
3 | T3703 | 43649925201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2019-09-25 | 2458081 | 2458081 | 2572160 | 0 | 0 | 2554701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2572160 | 2554701 | -17459 | 2031386
3 | T3704 | 43938815201 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 1462111 | 1462111 | 1360760 | 0 | 0 | 1370361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360760 | 1370361 | 9601 | 1750125
3 | T3712 | 43937115201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-11-17 | 4199999 | 4207543 | 4275092 | 7543.56 | -681696 | 4275464 | -681696 | 0 | 0 | 0 | 0 | 0 | -681696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -681696 | 3593396 | 4275464 | 682068 | 3898369
3 | T3720 | 43936615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 3077146 | 3077146 | 3008864 | 0 | -624672 | 2402816 | -624672 | 0 | 0 | 0 | 0 | 0 | -624672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -624672 | 2384192 | 2402816 | 18624 | 3261896
3 | T3728 | 21898425201 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2021-06-09 | 5503848 | 5503848 | 5683756 | 0 | 0 | 5700846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5683756 | 5700846 | 17090 | 7823905
3 | T3733 | 43188365201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-11-16 | 1685940 | 1730344 | 1594624 | 44404.28 | 0 | 1590656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1594624 | 1590656 | -3968 | 1924177
3 | T3740 | 43626615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2020-11-18 | 6166449 | 6166449 | 6743565 | 0 | 0 | 7855936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6743565 | 7855936 | 1112372 | 7986598
3 | T3743 | 44173015201 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2020-02-26 | 187229 | 187229 | 175598 | 0 | 0 | 166353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175598 | 166353 | -9245 | 262871
3 | T3750 | 43811125201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2022-07-27 | 987732 | 927591 | 903555 | -60141.3 | 0 | 903555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903555 | 903555 | 0 | 912225
3 | T3759 | 44014915201 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2021-03-31 | 6899119 | 7276831 | 6971277 | 377712.53 | 0 | 7378296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6971277 | 7378296 | 407019 | 5086090
3 | T3773 | 44422025201 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2023-05-24 | 556581 | 556581 | 566850 | 0 | 0 | 566850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566850 | 566850 | 0 | 736778
3 | T3775 | 43256315201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-04-27 | 2579717 | 2587262 | 2470218 | 7545 | 0 | 2458123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2470218 | 2458123 | -12095 | 2583181
3 | T3784 | 43938515201 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-02-22 | 830333 | 830333 | 808692 | 0 | 0 | 808692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808692 | 808692 | 0 | 771891
3 | T3787 | 44158815201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 16418543 | 16722911 | 17753119 | 304367.73 | -207500 | 18217935 | 0 | 0 | 0 | 0 | 0 | -15000 | -15000 | 0 | 0 | 0 | 0 | 0 | -192500 | -192500 | -207500 | 17545619 | 18217935 | 672316 | 18163994
3 | T3793 | 43467715201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2021-10-27 | 6283852 | 6727204 | 6844151 | 443352.47 | 0 | 7176797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6844151 | 7176797 | 332646 | 7460138
3 | T3794 | 44364415201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 2537432 | 2537432 | 2741257 | 0 | 0 | 2721406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2741257 | 2721406 | -19851 | 2975157
3 | T3796 | 44404615201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 1458732 | 1483251 | 1401648 | 24519.52 | -35574 | 1366074 | -35574 | 0 | 0 | 0 | 0 | 0 | -35574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35574 | 1366074 | 1366074 | 0 | 2613265
3 | T3797 | 44365615201 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2022-02-23 | 4361277 | 5189354 | 5002338 | 828077.01 | 0 | 5076487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5002338 | 5076487 | 74149 | 4172545
3 | T3800 | 44851815201 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 3545980 | 3707781 | 3707779 | 161800.68 | 0 | 3707779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3707779 | 3707779 | 0 | 3713439
3 | T3802 | 44397315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 6686744 | 6686744 | 6712350 | 0 | -34074 | 6731897 | -34074 | 0 | 0 | 0 | 0 | 0 | -34074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34074 | 6678276 | 6731897 | 53621 | 6875752
3 | T3810 | 44365015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 10527718 | 10784785 | 11111656 | 257066.75 | 0 | 11389685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11111656 | 11389685 | 278029 | 10728439
3 | T3811 | 22083845201 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2022-01-26 | 1327870 | 1607733 | 1467485 | 279862.54 | 0 | 1467485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1467485 | 1467485 | 0 | 2903301
3 | T3812 | 44363915201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 13830550 | 13861043 | 13971237 | 30492.89 | 39808 | 13698217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39808 | 0 | 0 | 0 | 0 | 0 | 39808 | 39808 | 14011044 | 13698217 | -312827 | 14936566
3 | T3816 | 44563215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 3430508 | 3430508 | 3561896 | 0 | 0 | 3523880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3561896 | 3523880 | -38015 | 3265523
3 | T3817 | 44387515201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 535084 | 538384 | 583904 | 3300 | 0 | 583904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583904 | 583904 | 0 | 438194
3 | T3818 | 44387615201 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 287504 | 287504 | 255356 | 0 | 0 | 255356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255356 | 255356 | 0 | 449142
3 | T3819 | 44404315201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 2236764 | 2317147 | 2391790 | 80383.18 | 0 | 2391790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2391790 | 2391790 | 0 | 1726155
3 | T3823 | 44565615201 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-01-25 | 2199429 | 2199429 | 2316440 | 0 | 0 | 2316440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2316440 | 2316440 | 0 | 2955598
3 | T3825 | 44565715201 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-03-29 | 1398733 | 1398733 | 1268603 | 0 | 0 | 1268603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268603 | 1268603 | 0 | 2259061
3 | T3828 | 44404415201 | F432094655 | H.G. CONSTRUCTION DEVELOPMENT & INVESTM | N/A | N/A | N/A | N/A | 2022-02-23 | 1388656 | 1388656 | 1401865 | 0 | 0 | 1401865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401865 | 1401865 | 0 | 1545933
3 | T3830 | 43256615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 3353932 | 3353932 | 3387610 | 0 | 0 | 3371222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3387610 | 3371222 | -16388 | 3164048
3 | T3833 | 44560315201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 192351 | 192351 | 176477 | 0 | 0 | 176477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176477 | 176477 | 0 | 173500
3 | T3836 | 43974415201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 4469056 | 4469056 | 4076218 | 0 | 0 | 3952664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4076218 | 3952664 | -123554 | 6832324
3 | T3848 | 43776215201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-06-15 | 2961906 | 2971384 | 2833242 | 9478.1 | 50000 | 2818993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 2883242 | 2818993 | -64250 | 3042412 | B5 | ACC - INCENTIVE/DISINCENTIVE
3 | T9024 | 44199335223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 3198515 | 3289097 | 3343570 | 90581.99 | 0 | 3343570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3343570 | 3343570 | 0 | 3552350
3 | T9027 | 44531315215 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2021-10-27 | 564819 | 564819 | 524793 | 0 | 0 | 524793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524793 | 524793 | 0 | 932089
3 | T9029 | 44531325216 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 2718412 | 2718412 | 2266906 | 0 | 0 | 2266906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2266906 | 2266906 | 0 | 2758181
4 | E4T68 | 44074615201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-05-06 | 17557323 | 17588765 | 16726429 | 31442 | 0 | 16980455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16726429 | 16980455 | 254025 | 12972093
4 | E4U99 | 44146215201 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-05-07 | 12200214 | 13805766 | 14205204 | 1605551.79 | 0 | 14206673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14205204 | 14206673 | 1469 | 10374506 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | E4V19 | 43215215201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-01-07 | 2335539 | 2335539 | 2159702 | 0 | 0 | 2159702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159702 | 2159702 | 0 | 4011283 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | E4V21 | 44399715201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-02-04 | 2500423 | 2500423 | 2294866 | 0 | 0 | 2323183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2294866 | 2323183 | 28317 | 2332742
4 | E4V26 | 44172115201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-03 | 1821552 | 1857400 | 1793427 | 35848.19 | 0 | 1797474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1793427 | 1797474 | 4047 | 1667424
4 | E4V55 | 44359415201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2022-05-06 | 895596 | 965406 | 917671 | 69809.69 | 0 | 917671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917671 | 917671 | 0 | 1122911
4 | E4V59 | 44136015201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-03-04 | 6377644 | 6402875 | 6172746 | 25230.68 | 0 | 6337235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6172746 | 6337235 | 164489 | 5443223
4 | E4V75 | 44172215201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-02-04 | 1455255 | 1515282 | 1451281 | 60027.27 | 0 | 1459199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1451281 | 1459199 | 7917 | 1403379
4 | E4V81 | 44610115201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-10-07 | 3843000 | 3930369 | 3945848 | 87368.83 | 0 | 3942412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3945848 | 3942412 | -3437 | 3910540
4 | E4V84 | 44609715201 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2022-09-02 | 3147147 | 3153188 | 2965886 | 6040.86 | 0 | 2896248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2965886 | 2896248 | -69638 | 3652109 | B1 | ACC - NO EXCUSE BONUS
4 | E4W04 | 45059015201 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2022-06-14 | 1468626 | 1468626 | 1421948 | 0 | 0 | 1421948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1421948 | 1421948 | 0 | 2551167
4 | E4W14 | 44577015201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2023-01-06 | 4294622 | 4294622 | 4411466 | 0 | 0 | 4411466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4411466 | 4411466 | 0 | 4978122
4 | E4W41 | 44576915201 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2023-01-06 | 4444623 | 4539611 | 4542613 | 94987.29 | 225000 | 4542438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 225000 | 225000 | 4767613 | 4542438 | -225175 | 4468547 | B5 | ACC - INCENTIVE/DISINCENTIVE
4 | T4552 | 43696215201 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2020-05-20 | 26406739 | 27530140 | 28635441 | 1123401.87 | 0 | 29122767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28635441 | 29122767 | 487326 | 27323788 | B10 | ACC - BONUS/INCENT/DISINCENT
4 | T4562 | 43177035201 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 3588218 | 3660295 | 3546957 | 72077.49 | 0 | 3613971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3546957 | 3613971 | 67014 | 3732217
4 | T4563 | 43619615201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2021-05-26 | 3377160 | 3518499 | 3592688 | 141338.65 | 0 | 3641736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3592688 | 3641736 | 49048 | 3569811
4 | T4567 | 43839415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 2505478 | 2517687 | 2533462 | 12209.09 | 0 | 2567224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533462 | 2567224 | 33762 | 2223138
4 | T4571 | 43839515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-01-27 | 2029422 | 2048533 | 1920549 | 19111.21 | 0 | 1970008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920549 | 1970008 | 49459 | 2213111
4 | T4572 | 43838415201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2021-01-27 | 2952231 | 2953979 | 2904459 | 1747.99 | 0 | 2904459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2904459 | 2904459 | 0 | 3045127
4 | T4573 | 43206675201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-07-28 | 3496673 | 3721036 | 3515537 | 224363.43 | 0 | 3603841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3515537 | 3603841 | 88304 | 3657624
4 | T4579 | 44166815201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-04-28 | 12487000 | 12883748 | 12540269 | 396747.96 | 0 | 13552710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12540269 | 13552710 | 1012442 | 14492193
4 | T4586 | 42957625201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-09-29 | 4581957 | 4683431 | 4520450 | 101473.92 | 0 | 4525836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520450 | 4525836 | 5386 | 4567139
4 | T4591 | 43811815201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 2543608 | 2702421 | 2682407 | 158812.75 | 0 | 2688322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2682407 | 2688322 | 5915 | 2499977
4 | T4592 | 43999415201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-12-08 | 2605697 | 2718209 | 2649545 | 112511.82 | 0 | 2759456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2649545 | 2759456 | 109912 | 2812232
4 | T4594 | 43999015201 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2021-12-08 | 2000000 | 2008938 | 1868868 | 8938.46 | 0 | 1870979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1868868 | 1870979 | 2110 | 2421038
4 | T4597 | 44177515201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2022-01-26 | 957661 | 958736 | 900445 | 1074.85 | 0 | 900445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900445 | 900445 | 0 | 927529
4 | T4601 | 44177115201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 1248248 | 1248248 | 1203185 | 0 | 0 | 1200343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203185 | 1200343 | -2841 | 1328804
4 | T4603 | 44157815201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 2249738 | 2249738 | 2253443 | 0 | 0 | 2251225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253443 | 2251225 | -2218 | 2503872
4 | T4607 | 43999315201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2022-03-30 | 1967721 | 1967721 | 1856962 | 0 | 0 | 1859008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1856962 | 1859008 | 2046 | 2135578
4 | T4608 | 44177615201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-01-26 | 3370284 | 3030235 | 2923805 | -340048.97 | 0 | 2936404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2923805 | 2936404 | 12599 | 2521291
4 | T4609 | 44384515201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 2057691 | 2108795 | 2355080 | 51104.56 | 0 | 2350900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355080 | 2350900 | -4180 | 2121963
4 | T4614 | 44399415201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-04-27 | 4491996 | 4563991 | 4393362 | 71995.43 | 0 | 4387252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4393362 | 4387252 | -6110 | 4062647
4 | T4628 | 44061275201 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2023-02-22 | 1125012 | 1125012 | 994908 | 0 | 0 | 994009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994908 | 994009 | -899 | 879841
4 | T4629 | 44562315201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-12-07 | 1050673 | 1050673 | 985015 | 0 | 0 | 985015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985015 | 985015 | 0 | 1029940
5 | E50B4 | 44290615201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-07-06 | 3079406 | 3129406 | 3205711 | 50000 | 0 | 3130395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3205711 | 3130395 | -75316 | 3825882
5 | E51A0 | 43856235201 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2021-02-16 | 14521514 | 14674974 | 14844010 | 153460.05 | 0 | 15078914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14844010 | 15078914 | 234904 | 15223949
5 | E51A9 | 44102015201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2020-09-01 | 7501367 | 7798794 | 7544823 | 297427.05 | -41316 | 7754120 | -41316 | 0 | 0 | 0 | 0 | 0 | -41316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41316 | 7503507 | 7754120 | 250613 | 7321147
5 | E53B6 | 43901715201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-09-07 | 1640053 | 1640053 | 1539808 | 0 | 0 | 1539808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1539808 | 1539808 | 0 | 2062515
5 | E54B0 | 43986525201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-01-04 | 1188917 | 1190920 | 1139015 | 2002.86 | 0 | 1138826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139015 | 1138826 | -189 | 1369687
5 | E55B1 | 43914215201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-12-06 | 6255758 | 6282058 | 5782361 | 26300.22 | 0 | 5745517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5782361 | 5745517 | -36845 | 7312040
5 | E55B2 | 44417515201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-09-07 | 2868033 | 2873478 | 2862070 | 5444.77 | 0 | 2859702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862070 | 2859702 | -2367 | 2740879
5 | E55B3 | 44942415201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2022-12-06 | 950694 | 950694 | 969481 | 0 | 0 | 969481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 969481 | 969481 | 0 | 729303
5 | E55B4 | 44942515201 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-11-01 | 967737 | 967737 | 851103 | 0 | 0 | 851002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851103 | 851002 | -101 | 882687
5 | E55B9 | 44655815201 | F770603738 | WRANGLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-10-11 | 1178485 | 1182078 | 1222101 | 3592.47 | 0 | 1220346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222101 | 1220346 | -1755 | 1289086
5 | E56B2 | 44381615201 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2022-11-01 | 3435770 | 3435770 | 3371565 | 0 | 0 | 3338650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3371565 | 3338650 | -32915 | 4749445
5 | E56B4 | 44713515201 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2023-04-04 | 939661 | 939661 | 899114 | 0 | 0 | 899114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899114 | 899114 | 0 | 881063
5 | E57A1 | 44343315201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-11-02 | 5312936 | 5361981 | 5275495 | 49044.96 | 0 | 5382637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5275495 | 5382637 | 107142 | 6332507
5 | E57A4 | 44113215201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2021-10-05 | 7424369 | 7591181 | 7558842 | 166811.87 | 0 | 7953369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7558842 | 7953369 | 394527 | 9276735
5 | E58A4 | 44290515201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-02-01 | 3001616 | 3060677 | 3027637 | 59061.42 | 0 | 3072540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3027637 | 3072540 | 44903 | 2459664
5 | E58A7 | 44602015201 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2022-02-01 | 1509974 | 1509974 | 1539994 | 0 | -55902 | 1540522 | -55902 | 0 | 0 | 0 | 0 | 0 | -55902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -55902 | 1484092 | 1540522 | 56430 | 1275856
5 | E58B2 | 44529415201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2022-11-01 | 8096921 | 8098655 | 8200608 | 1734.18 | 0 | 8095717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8200608 | 8095717 | -104891 | 11713738
5 | E59A9 | 43913015201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-01-04 | 679529 | 679529 | 677096 | 0 | 0 | 677187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677096 | 677187 | 92 | 681571
5 | T5552 | 40714345201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2016-06-08 | 75824482 | 86884143 | 89837352 | 10910760.93 | 0 | 90653074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89837352 | 90653074 | 815723 | 88197362 | B2:B2:B5:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B/BONUS
5 | T5626 | 24020025201 | Z04-1543470 | LIBERTY MUTUAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2017-12-06 | 108299973 | 115225015 | 117199660 | 6683847.75 | 0 | 118158195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117199660 | 118158195 | 958535 | 150691415
5 | T5705 | 44113615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2021-05-26 | 15404884 | 16605228 | 17135945 | 1200343.68 | 0 | 18098230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17135945 | 18098230 | 962285 | 17500000
5 | T5726 | 44354415201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-03-30 | 1057650 | 1057650 | 1051826 | 0 | 0 | 1051826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051826 | 1051826 | 0 | 838160
5 | T5733 | 44381515201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2021-10-27 | 7387943 | 7578305 | 6929112 | 190361.43 | 0 | 7646110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6929112 | 7646110 | 716998 | 8754090
5 | T5737 | 44288115201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2021-12-08 | 1605048 | 1606653 | 1573163 | 1605 | 0 | 1576898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573163 | 1576898 | 3735 | 1288584
5 | T5738 | 44290915201 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 9861239 | 9880239 | 9803603 | 18999.77 | 0 | 10869062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9803603 | 10869062 | 1065459 | 13653416
5 | T5742 | 43612515201 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2022-02-23 | 4343701 | 4496683 | 4615463 | 152982.64 | 0 | 4641212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4615463 | 4641212 | 25749 | 4840790
5 | T5746 | 43915715201 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-05-25 | 1480640 | 1481349 | 1525188 | 709.28 | 0 | 1522820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525188 | 1522820 | -2368 | 1288918
5 | T5750 | 44568415201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2022-07-27 | 966460 | 966460 | 931181 | 0 | 0 | 930236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931181 | 930236 | -945 | 970161
5 | T5763 | 44569015201 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2022-08-31 | 1690095 | 1690972 | 1630216 | 876.83 | 0 | 1602812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630216 | 1602812 | -27404 | 2378839
5 | T5765 | 43759625201 | F263013168 | MEJIA INTERNATIONAL GROUP CORPORATION | N/A | N/A | N/A | N/A | 2022-10-26 | 1068776 | 1068776 | 1003835 | 0 | 0 | 1003807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1003835 | 1003807 | -28 | 1065459
5 | T5766 | 44569515201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-10-05 | 1397100 | 1397100 | 1188314 | 0 | 0 | 1188314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188314 | 1188314 | 0 | 1256130
5 | T5771 | 44316615201 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2022-10-26 | 3891608 | 3851608 | 3861679 | -40000 | 0 | 3868346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3861679 | 3868346 | 6667 | 5132265
5 | T5774 | 44568815201 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2022-12-07 | 662662 | 662941 | 634436 | 279.3 | 0 | 634436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634436 | 634436 | 0 | 863381
5 | T5780 | 44585815201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-01-04 | 1654943 | 1654943 | 1622200 | 0 | 0 | 1622200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1622200 | 1622200 | 0 | 1788242
5 | T5781 | 43713315201 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-01-25 | 1838831 | 1848822 | 1683358 | 9990.61 | 0 | 1678146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683358 | 1678146 | -5213 | 2056818
5 | T5785 | 44976515201 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-03-29 | 527418 | 527418 | 510407 | 0 | 0 | 510407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510407 | 510407 | 0 | 916064
5 | T9028 | 44532115223 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LL | N/A | N/A | N/A | N/A | 2022-01-26 | 4468000 | 4785216 | 5263219 | 317216.11 | 0 | 5263219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5263219 | 5263219 | 0 | 3979533
6 | E6L44 | 43652515201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2020-11-19 | 10780329 | 10840590 | 11164804 | 60261.3 | 0 | 11250033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11164804 | 11250033 | 85230 | 11006398 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6M36 | 44343215201 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2022-08-25 | 935010 | 935010 | 1101336 | 0 | 0 | 1101281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101336 | 1101281 | -55 | 1073050
6 | E6N08 | 44196015201 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2022-01-27 | 2813265 | 2921577 | 2938675 | 108311.92 | 0 | 2938740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938675 | 2938740 | 65 | 3044683
6 | E6N09 | 44480525201 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2022-07-28 | 797552 | 797552 | 706126 | 0 | 0 | 706126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706126 | 706126 | 0 | 1509364
6 | E6N47 | 44445015201 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2022-05-26 | 2697327 | 2771657 | 2731695 | 74329.48 | 180000 | 2718704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 2911695 | 2718704 | -192991 | 2883318 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | E6N55 | 44196815201 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2021-08-26 | 757063 | 757063 | 654819 | 0 | 0 | 654819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654819 | 654819 | 0 | 1042436
6 | E6O02 | 44479915201 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2022-10-06 | 779455 | 779455 | 733765 | 0 | 0 | 733765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733765 | 733765 | 0 | 612148
6 | E6O04 | 44196515201 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2022-11-17 | 1446162 | 1446162 | 1381923 | 0 | 0 | 1381923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381923 | 1381923 | 0 | 2588373
6 | T6505 | 43326435201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2020-08-26 | 4604161 | 4652806 | 4445340 | 48645.61 | 399999 | 4484965 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000 | 399999 | 4845339 | 4484965 | -360374 | 4947289 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6508 | 42325125201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-07-28 | 42480180 | 43009539 | 42865939 | 529358.98 | 4169010 | 44171731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 1169010 | 0 | 4169010 | 4169010 | 47034949 | 44171731 | -2863217 | 49760527 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6513 | 43998615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-03-30 | 2569128 | 2717271 | 2543862 | 148143.16 | 120000 | 2540376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 120000 | 2663862 | 2540376 | -123486 | 2452592 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6515 | 43274845201 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2022-03-30 | 2455465 | 2510141 | 2443596 | 54676.34 | 72000 | 2440177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 72000 | 72000 | 2515596 | 2440177 | -75419 | 2281095 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6516 | 43998115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2021-10-27 | 4166383 | 4219775 | 4110877 | 53391.64 | 0 | 4270005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4110877 | 4270005 | 159128 | 4661947 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6518 | 42918635201 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 2919079 | 2940250 | 2881342 | 21170.5 | 210000 | 2944862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 210000 | 210000 | 3091342 | 2944862 | -146480 | 3061117 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6519 | 43476835201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2022-01-26 | 3487287 | 3497187 | 3509376 | 9900 | 180000 | 3539751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 180000 | 3689376 | 3539751 | -149625 | 3568828 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6534 | 44389515201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-01-26 | 6302707 | 6392688 | 6335976 | 89980.23 | 238000 | 6471394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238000 | 0 | 0 | 0 | 0 | 0 | 238000 | 238000 | 6573976 | 6471394 | -102582 | 5606872 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
6 | T6537 | 44391615201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-04-27 | 6069480 | 6030999 | 5946111 | -38481.6 | 320000 | 5937355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 6266111 | 5937355 | -328757 | 5885247 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6543 | 44183615201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2022-08-31 | 2810000 | 2808895 | 2824415 | -1104.66 | 140000 | 2810967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 140000 | 140000 | 2964415 | 2810967 | -153448 | 2984244 | B5 | ACC - INCENTIVE/DISINCENTIVE
6 | T6545 | 44574515201 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2022-10-05 | 915762 | 915762 | 904223 | 0 | 0 | 903865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 904223 | 903865 | -358 | 1027819
6 | T6546 | 44574715201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2022-10-26 | 636402 | 636402 | 608049 | 0 | 0 | 607521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608049 | 607521 | -527 | 753183
6 | T6561 | 43081325201 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2022-05-25 | 836079 | 836079 | 782914 | 0 | 0 | 778816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782914 | 778816 | -4099 | 760317
6 | T6563 | 44882915201 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2022-12-07 | 565000 | 591990 | 490972 | 26990 | 0 | 490972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490972 | 490972 | 0 | 566783
6 | T6571 | 44390315201 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2023-01-25 | 1857275 | 1907275 | 1881049 | 50000 | 0 | 1877156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1881049 | 1877156 | -3893 | 2156609
7 | E7N76 | 43956515201 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-03-10 | 6600000 | 7117569 | 6571044 | 517568.76 | 0 | 6571044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6571044 | 6571044 | 0 | 6998000
7 | E7N90 | 44822115201 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2022-01-12 | 679686 | 695950 | 640611 | 16263.93 | 0 | 640611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640611 | 640611 | 0 | 644500
7 | E7N95 | 44025115201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 6430299 | 6566839 | 6774752 | 136540.44 | 0 | 7326407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6774752 | 7326407 | 551655 | 8690700
7 | E7O02 | 43724915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2021-10-13 | 4833500 | 5430418 | 5535682 | 596918.24 | 200000 | 5536636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 5735682 | 5536636 | -199047 | 3694800 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | E7O03 | 43050015201 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2021-07-14 | 8992000 | 9003651 | 9360484 | 11651.02 | 0 | 9378888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9360484 | 9378888 | 18403 | 9455800
7 | E7O04 | 43952615201 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2021-09-08 | 1944266 | 2045152 | 1898792 | 100885.18 | 0 | 1898792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1898792 | 1898792 | 0 | 1797400
7 | E7O11 | 44166515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-02-09 | 3049631 | 3049631 | 3013462 | 0 | 0 | 3013181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3013462 | 3013181 | -281 | 2409700
7 | E7P02 | 44146915201 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2022-05-11 | 2611346 | 2611346 | 2617684 | 0 | 0 | 2617512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2617684 | 2617512 | -173 | 2320500
7 | E7P05 | 44024415201 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2022-04-13 | 5007203 | 5075397 | 4790051 | 68193.86 | 0 | 4756788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4790051 | 4756788 | -33263 | 5384600
7 | E7P09 | 43763615201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2022-03-09 | 2593388 | 2709838 | 2503891 | 116449.49 | 0 | 2505388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2503891 | 2505388 | 1497 | 2305500
7 | E7P21 | 44024915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-04-13 | 7905829 | 7905829 | 8077210 | 0 | 0 | 8034957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8077210 | 8034957 | -42254 | 6822100
7 | E7P30 | 44761415201 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2022-04-13 | 2231499 | 2259063 | 2052581 | 27564.52 | 0 | 2046856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052581 | 2046856 | -5724 | 1792600
7 | E7P36 | 44978015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2022-06-08 | 4664000 | 4709230 | 4734993 | 45229.8 | 0 | 4662735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4734993 | 4662735 | -72258 | 5588200 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM
7 | E7P61 | 44383615201 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-01-11 | 506794 | 527638 | 475289 | 20844.36 | 0 | 475289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475289 | 475289 | 0 | 441600
7 | E7P63 | 44774815201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-01-11 | 619151 | 619151 | 571177 | 0 | 0 | 571177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571177 | 571177 | 0 | 1320700
7 | E7P82 | 43782315201 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2023-03-08 | 341000 | 341000 | 292314 | 0 | 0 | 292314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292314 | 292314 | 0 | 350800
7 | E7P89 | 44598115201 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-11-08 | 746261 | 746261 | 629640 | 0 | 0 | 629640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629640 | 629640 | 0 | 927702
7 | E7P97 | 45217915201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-02-10 | 338100 | 327764 | 312738 | -10335.63 | 0 | 312738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312738 | 312738 | 0 | 342400 | B0 | ACC - LUMP SUM
7 | E7Q34 | 44583115201 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-11-08 | 268116 | 268116 | 251692 | 0 | 0 | 251692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251692 | 251692 | 0 | 436100
7 | E7R18 | 43273425202 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2020-05-12 | 63996999 | 65132965 | 66612296 | 1135966.2 | 0 | 67215985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66612296 | 67215985 | 603689 | 55949573 | B8 | ACC - DESIGN/BUILD - MAJOR
7 | T7383 | 40582225201 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2016-06-20 | 27868889 | 32682171 | 33265156 | 4813282.11 | -3418119 | 30410690 | -3403119 | 0 | 0 | 0 | 0 | -15000 | -3418119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3418119 | 29847037 | 30410690 | 563653 | 32874962 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | T7424 | 25729855201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2019-03-27 | 20155312 | 20804212 | 20013184 | 648899.65 | 0 | 19790050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20013184 | 19790050 | -223135 | 29301814
7 | T7428 | 43258435201 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2019-02-27 | 9277781 | 9481539 | 10184938 | 203758.52 | 251742 | 10145611 | -48258 | 0 | 0 | 0 | 0 | 0 | -48258 | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 251742 | 10436680 | 10145611 | -291069 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT
7 | T7451 | 43982985201 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2020-04-29 | 698558 | 698558 | 557380 | 0 | -158860 | 531562 | -158860 | 0 | 0 | 0 | 0 | 0 | -158860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -158860 | 398520 | 531562 | 133042 | 691075
7 | T7468 | 44138615201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2021-01-27 | 9161461 | 9416662 | 9425645 | 255200.4 | 0 | 9775049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9425645 | 9775049 | 349405 | 9040000
7 | T7473 | 43944815201 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2021-04-28 | 3457631 | 3534214 | 3460775 | 76582.42 | 0 | 3536972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460775 | 3536972 | 76197 | 3048700
7 | T7480 | 44025315201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-12-08 | 8381553 | 8507750 | 8880433 | 126196.94 | 0 | 9233589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8880433 | 9233589 | 353156 | 9618300
7 | T7484 | 43780725201 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2022-07-27 | 2689020 | 2695490 | 2436483 | 6469.96 | 0 | 2433346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2436483 | 2433346 | -3137 | 3008900
7 | T7485 | 44109915201 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2022-03-30 | 2037125 | 2037125 | 1982019 | 0 | 0 | 1983777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1982019 | 1983777 | 1758 | 1568900
7 | T7491 | 44358325201 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2022-02-23 | 1439445 | 1439445 | 1363648 | 0 | 0 | 1363533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1363648 | 1363533 | -115 | 1085600
7 | T7496 | 43591435201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 2222629 | 2357768 | 2205247 | 135139.13 | 0 | 2190340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2205247 | 2190340 | -14907 | 2009600
7 | T7498 | 44332015201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-05-25 | 1340863 | 1340863 | 1268582 | 0 | -12000 | 1256582 | 0 | 0 | 0 | 0 | 0 | -12000 | -12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12000 | 1256582 | 1256582 | 0 | 2027300
7 | T9026 | 44490215223 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-11-17 | 4025439 | 4151284 | 4188035 | 125844.34 | 0 | 4188035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4188035 | 4188035 | 0 | 3685201
8 | E8Q78 | 43554615201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2018-06-15 | 143269821 | 145759356 | 145166429 | 2489534.99 | 5000000 | 144293300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 150166429 | 144293300 | -5873129 | 156867750 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE
8 | E8R75 | 42933945201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2019-05-21 | 19557418 | 20031429 | 19576305 | 474010.91 | 0 | 19542086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19576305 | 19542086 | -34220 | 16516025
8 | E8R77 | 43798615201 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2019-05-14 | 31832323 | 32865375 | 32938830 | 1033051.69 | 0 | 32271398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32938830 | 32271398 | -667433 | 33799887
8 | E8R97 | 43730045201 | F800866395 | JOHNSON BROS. CORPORATION A SO | N/A | N/A | N/A | N/A | 2019-09-17 | 139979406 | 145733672 | 144794963 | 5754265.13 | 6000000 | 144860516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000 | 150794963 | 144860516 | -5934447 | 118749146 | B10 | ACC - BONUS/INCENT/DISINCENT
8 | E8S19 | 44387815201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2020-04-14 | 3263898 | 3263898 | 3283729 | 0 | 0 | 3283729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3283729 | 3283729 | 0 | 3999932
8 | E8S55 | 44070015201 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2020-08-31 | 16707654 | 17277221 | 16518546 | 569566.94 | 0 | 16862183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16518546 | 16862183 | 343637 | 20328686
8 | E8S64 | 44388015201 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2020-09-15 | 650221 | 650221 | 606614 | 0 | 0 | 606614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606614 | 606614 | 0 | 1256846
8 | E8S95 | 43496825201 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2021-07-16 | 5495495 | 5495495 | 5449321 | 0 | 0 | 5449321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5449321 | 5449321 | 0 | 6335420 | A3 | ICC - DESIGN/BUILD - MINOR
8 | E8T03 | 44262715201 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2021-05-11 | 3696363 | 3796363 | 3796871 | 100000 | 0 | 3797393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3796871 | 3797393 | 522 | 3759344
8 | E8T12 | 44028915201 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2021-10-19 | 18831743 | 19112673 | 19162598 | 280930.44 | 0 | 19639440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19162598 | 19639440 | 476842 | 18566305
8 | E8T21 | 44029215201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2021-09-14 | 13350942 | 13774510 | 13575224 | 423567.64 | 0 | 13929187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13575224 | 13929187 | 353962 | 12351695
8 | E8T38 | 43730095201 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2022-02-08 | 5115331 | 5115331 | 5070631 | 0 | 0 | 5070631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5070631 | 5070631 | 0 | 5087754
8 | E8T39 | 44430115201 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2021-12-14 | 1975221 | 2101149 | 2102097 | 125927.59 | 0 | 2109833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2102097 | 2109833 | 7736 | 1709882
8 | E8T42 | 43799015201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2022-03-08 | 4166000 | 4217668 | 4164480 | 51668.12 | 138823 | 4216743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138823 | 0 | 0 | 0 | 0 | 0 | 138823 | 138823 | 4303303 | 4216743 | -86560 | 3910717 | B5 | ACC - INCENTIVE/DISINCENTIVE
8 | E8T68 | 44448615201 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2022-04-12 | 6695054 | 6727768 | 6880189 | 32713.79 | 0 | 6868222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6880189 | 6868222 | -11968 | 6191721
8 | E8T76 | 44206115201 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2022-08-16 | 15249859 | 15714097 | 13670638 | 464238.2 | 0 | 13262271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13670638 | 13262271 | -408367 | 16808899
8 | E8T86 | 43855115201 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2022-08-16 | 597627 | 652711 | 607225 | 55083.3 | 0 | 607225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607225 | 607225 | 0 | 898718
8 | E8T87 | 43855015201 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2022-08-16 | 767354 | 767354 | 705154 | 0 | 0 | 705154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705154 | 705154 | 0 | 1243903
8 | E8T93 | 44029515201 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2022-06-14 | 8768395 | 8771000 | 8359690 | 2605.28 | 0 | 8252206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8359690 | 8252206 | -107484 | 9428515
8 | E8U17 | 44934015201 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-03-14 | 5184770 | 5358078 | 5154131 | 173307.59 | 0 | 5153734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5154131 | 5153734 | -396 | 4352338
8 | E8U24 | 44122465201 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-02-14 | 855737 | 857248 | 864748 | 1510.44 | 0 | 864748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864748 | 864748 | 0 | 859412
8 | E8U28 | 44261825201 | F721180277 | JACK B. HARPER CONTRACTOR L.L.C. | N/A | N/A | N/A | N/A | 2023-05-09 | 491221 | 491221 | 344856 | 0 | 0 | 344856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344856 | 344856 | 0 | 690819

## Detailed Data - PPP (hidden)
Contract Let | District | Contract Number | Financial Project ID | Let Date | Quarter Let | Year Let/ Num of Contracts | Number Projects | Number of SAs | Original Contract Days | Present Contract Days | Days Used | % Days Used of Orig Days | Num Contracts<= 1.2% Increase in Time | Unused Days | Delinquent Days | Days Suspended | Time Extension | SA Days | CRS Original Contract Amount | Amount Included in Original for Contingency Pay Item | Adjusted Original Amount | CRS Present Contract Amount | Regular Work To Date (From CRS) | Total CRS Contract Adjustments | CRS Innovative Contract Adjustments | Total CRS Adjustments | Total CRS Amount Paid to Contractor | Actual Expenditure (Does Not Include Innovative Contract Adjustment Payments) | % Expend. of Adj Orig Amt | Num Contracts<= 1.1% Increase in Cost | Amount Paid After CRS | SA Allocated Amount (From CRS) | Weather Days | Holiday Time Extension Days | Changed Conditions Work Orders |  |  |  | Plans Modifications Work Orders |  |  |  | Specification Modification Work Orders |  |  |  | Value Engineering Work Orders |  |  |  | Partnering Work Orders |  |  |  | CEI Action/InAction Work Orders |  |  |  | Minor Changes Work Orders |  |  |  | Defective Materials Work Orders |  |  |  | Weather Related Damage Work Orders |  |  |  | Claims Work Orders |  |  |  | Utility Delays Work Orders |  |  |  | Material Shortage Work Orders |  |  |  | Cost Savings Initiative |  |  |  | Totals Work Orders |  |  |  | Contractor Vendor ID | Contractor Name | Designer Vendor ID | Designer Name | CEI Vendor ID | CEI Name | Passed Date | Quarter Passed | Fiscal Year Passed | Conditional Acceptance Date | Final Acceptance Date | Quarter Accepted | Year Accepted | Managing Cost Center | DOT Original Estimate | Innovative Contract Type
[35 empty] | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | Time Ext Days | SA Days | SA Amount | Premium Cost | [15 empty] | Code | Description
[29 empty] | 0% | 1
| Dist 01 - Central Let Contrats SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 01 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 01 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 02 Central Let Contract SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 02 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 02 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 03 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03 | E3K68 | 22077395201 | 2012-09-18 | QTR1 | 12/13 | 10 | 10 | 1565 | 1565 | 3290 | 210.2% | 0 | -1725 | 1725 | 0 | 0 | -100 | 98502934 | 150000 | 98352934 | 101997749 | 101979312 | 0 | 7900000 | 7900000 | 109879312 | 3307126 | 3.363% | 1 | -106503708 | 3494815 | 0 | 0 | 0 | 0 | 2529474 | 732 | 0 | 0 | 710246 | 1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158121 | 0 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38535 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35024 | 0 | 0 | -100 | 3403092 | 2088 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-05-09 | QTR4 | 23/24 |  | 2022-10-20 | QTR2 | 22/23 | 306 | 98502934 | B1:B5:B8:DB:P3 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP
[29 empty] | 0% | 1
| Dist 03 District Let Contracts SubTotal |  |  |  |  | 1 | 10 | 10 | 1565 | 1565 | 3290 | 0% | 0 | -1725 | 1725 | 0 | 0 | -100 | 98502934 | 150000 | 98352934 | 101997749 | 101979312 | 0 | 7900000 | 7900000 | 109879312 | 3307126 | 200% | 2 | -106503708 | 3494815 | 0 | 0 | 0 | 0 | 2529474 | 732 | 0 | 0 | 710246 | 1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158121 | 0 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38535 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35024 | 0 | 0 | -100 | 3403092 | 2088
| District 03 Totals |  |  |  |  | 1 | 10 | 10 | 1565 | 1565 | 3290 | 0% | 0 | -1725 | 1725 | 0 | 0 | -100 | 98502934 | 150000 | 98352934 | 101997749 | 101979312 | 0 | 7900000 | 7900000 | 109879312 | 3307126 | 300% | 3 | -106503708 | 3494815 | 0 | 0 | 0 | 0 | 2529474 | 732 | 0 | 0 | 710246 | 1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158121 | 0 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38535 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35024 | 0 | 0 | -100 | 3403092 | 2088
[29 empty] | 0% | 1
| Dist 04 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 04 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 04 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 05 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 05 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 06 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 06 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 06 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | 0% | 1
| Dist 07 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 07 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 Central Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dist 08 District Let Contracts SubTotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| District 08 Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide Central Let Contracts SubTotal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Statewide District Let Contracts SubTotal |  |  |  |  | 1 | 10 | 10 | 1565 | 1565 | 3290 | 0% | 0 | -1725 | 1725 | 0 | 0 | -100 | 98502934 | 150000 | 98352934 | 101997749 | 101979312 | 0 | 7900000 | 7900000 | 109879312 | 3307126 | 800% | 8 | -106503708 | 3494815 | 0 | 0 | 0 | 0 | 2529474 | 732 | 0 | 0 | 710246 | 1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158121 | 0 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38535 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35024 | 0 | 0 | -100 | 3403092 | 2088
| Statewide Totals |  |  |  |  | 1 | 10 | 10 | 1565 | 1565 | 3290 | 0% | 0 | -1725 | 1725 | 0 | 0 | -100 | 98502934 | 150000 | 98352934 | 101997749 | 101979312 | 0 | 7900000 | 7900000 | 109879312 | 3307126 | 1500% | 15 | -106503708 | 3494815 | 0 | 0 | 0 | 0 | 2529474 | 732 | 0 | 0 | 710246 | 1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158121 | 0 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38535 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35024 | 0 | 0 | -100 | 3403092 | 2088

## Sheet1 (hidden)
01CO | 01 | T1191 | 43355045201 | 2021-06-09 | QTR4 | 20/21 | 2 | 6 | 320 | 579 | 579 | 0 | 0 | 0 | 207 | 52 | 6386200 | 56445 | 6329755 | 6748926 | 6664293 | 0 | 0 | 0 | 6664293 | 6748506 | 143879 | 362725 | 149 | 7 | 20 | 118601 | 0 | 0 | 32 | 264904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 8221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 52 | 391726 | 0 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2024-01-23 | QTR3 | 23/24 | 2023-08-04 | QTR1 | 23/24 | 115 | 5529849.57 |  |  | 5 | 26 | 25 | 0 | 0 | 0 |  | CO | 27 | 01co | 1 | 27
01CO | 01 | T1676 | 43131315201 | 2018-06-13 | QTR4 | 17/18 | 3 | 32 | 1200 | 1846 | 1845 | 1 | 0 | 0 | 357 | 289 | 20052828 | 150000 | 19902828 | 22892173 | 22098737 | 0 | 0 | 0 | 22098737 | 22107645 | 112471 | 2839344 | 254 | 0 | 275 | 1504569 | 159745 | 0 | 0 | 752980 | 13922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470970 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 103564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 2840833 | 173668 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-05-10 | QTR4 | 23/24 | 2023-12-29 | QTR2 | 23/24 | 113 | 16688857.48 |  |  | 24 | 117 | 0 | 0 | 0 | 0 |  | CO | 17 | 01do | 28 | 44
01CO | 01 | T1751 | 41066635201 | 2020-04-29 | QTR4 | 19/20 | 4 | 15 | 875 | 1016 | 963 | 53 | 0 | 0 | 127 | 14 | 43563143 | 150000 | 43413143 | 43826539 | 44268970 | 0 | 0 | 0 | 44268970 | 45616616 | 1915546 | 263396 | 80 | 0 | 0 | 351912 | 3918 | 7 | 0 | 219896 | 30715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17978 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 22507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18317 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 343410 | 34633 | F592571763 | JR. DAVIS CONSTRUCTION CO. INC. | N/A | N/A | N/A | N/A | 2023-09-11 | QTR1 | 23/24 | 2023-04-28 | QTR4 | 22/23 | 108 | 44746155.07 |  |  | 0 | 54 | 0 | 0 | -287200 | 0 |  | CO | 47 | 02co | 45 | 91
01CO | 01 | T1761 | 42982315201 | 2021-06-09 | QTR4 | 20/21 | 2 | 18 | 275 | 545 | 530 | 15 | 0 | 0 | 223 | 47 | 4097408 | 50000 | 4047408 | 4902150 | 4899132 | 0 | 0 | 0 | 4899132 | 4822749 | 34379 | 804742 | 131 | 0 | 42 | 118523 | 55203 | 51 | 5 | 478225 | 97145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42992 | 42992 | 0 | 0 | 0 | 0 | 51 | 47 | 830672 | 195339 | F474451572 | V & H CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2023-02-24 | QTR3 | 22/23 | 113 | 4251830.23 |  |  | 0 | 41 | 0 | 0 | 0 | 0 |  | CO | 9 | 02do | 92 | 100
01CO | 01 | T1762 | 43943415201 | 2020-09-30 | QTR1 | 20/21 | 2 | 2 | 350 | 634 | 731 | -97 | 97 | 0 | 263 | 21 | 10278123 | 111374 | 10166749 | 10447272 | 10596778 | -421368 | 0 | -421368 | 10175410 | 10869033 | 858028 | 169149 | 239 | 0 | 0 | 0 | 0 | 0 | 10 | 155202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24064 | 0 | 0 | 0 | 0 | 0 | 189 | 11 | 28454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 21 | 207720 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-06-04 | QTR4 | 23/24 | 2023-03-09 | QTR3 | 22/23 | 118 | 10803856.75 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO | 44 | 03co | 101 | 144
01CO | 01 | T1770 | 44068615201 | 2021-03-31 | QTR3 | 20/21 | 1 | 5 | 400 | 597 | 734 | -137 | 137 | 0 | 156 | 41 | 2574061 | 50000 | 2524061 | 2608561 | 2446996 | -275991 | 0 | -275991 | 2171004 | 2221824 | 53387 | 34500 | 101 | 3 | 0 | 0 | 0 | 7 | 5 | 18309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27300 | 0 | 0 | 0 | -5115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 40 | 41 | 43394 | 0 | F204003511 | E&M EQUIPMENT | N/A | N/A | N/A | N/A | 2024-05-03 | QTR4 | 23/24 | 2023-07-15 | QTR1 | 23/24 | 115 | 2478688.72 |  |  | 1 | 45 | 0 | 0 | 0 | 0 |  | CO | 16 | 03do | 145 | 160
01CO | 01 | T1772 | 44211515201 | 2020-09-30 | QTR1 | 20/21 | 3 | 1 | 150 | 177 | 607 | -430 | 430 | 0 | 11 | 16 | 668342 | 41495 | 626847 | 668342 | 605783 | 0 | 0 | 0 | 605783 | 595755 | 25365 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 6341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 6341 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 | 2022-12-05 | QTR2 | 22/23 | 108 | 802465.89 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO | 21 | 04co | 161 | 181
01CO | 01 | T1777 | 43943015201 | 2020-09-30 | QTR1 | 20/21 | 4 | 3 | 325 | 607 | 638 | -31 | 31 | 0 | 216 | 66 | 7973682 | 92806 | 7880876 | 8225110 | 8195027 | -106857 | 0 | -106857 | 8088170 | 8717413 | 921857 | 251428 | 207 | 0 | 0 | 126514 | 115529 | 0 | 52 | 124433 | 124433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 14 | 11465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 66 | 262412 | 239963 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 | 2022-10-18 | QTR2 | 22/23 | 118 | 9500361.49 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO | 13 | 04do | 182 | 194
01CO | 01 | T1781 | 44151815201 | 2021-01-27 | QTR3 | 20/21 | 2 | 4 | 285 | 400 | 400 | 0 | 0 | 0 | 41 | 74 | 4960436 | 59129 | 4901307 | 5450251 | 5304714 | 0 | 0 | 0 | 5304714 | 5560151 | 265895 | 489815 | 14 | 0 | 74 | 470632 | 0 | 0 | 0 | 17986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 489815 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2022-06-30 | QTR4 | 21/22 | 118 | 5666706.37 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO | 19 | 05co | 195 | 213
01CO | 01 | T1790 | 44240115201 | 2020-08-26 | QTR1 | 20/21 | 1 | 1 | 110 | 145 | 141 | 4 | 0 | 0 | 26 | 9 | 697485 | 0 | 697485 | 700625 | 698869 | 0 | 0 | 0 | 698869 | 698869 | 0 | 3140 | 21 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140 | 3140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3140 | 3140 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-24 | QTR2 | 23/24 | 2021-07-09 | QTR1 | 21/22 | 108 | 802615.61 | B0 | ACC - LUMP SUM | 9 | 5 | 0 | 0 | 0 | 0 | T | CO | 18 | 05do | 214 | 231
01CO | 01 | T1797 | 44013415201 | 2021-04-28 | QTR4 | 20/21 | 1 | 3 | 250 | 536 | 536 | 0 | 0 | 0 | 286 | 0 | 1568347 | 50000 | 1518347 | 1712719 | 1597886 | 0 | 0 | 0 | 1597886 | 1566868 | 119180 | 144372 | 249 | 0 | 0 | 85263 | 0 | 0 | 0 | 28090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144372 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-14 | QTR3 | 23/24 | 2023-12-08 | QTR2 | 23/24 | 113 | 1575091.8 |  |  | 0 | 37 | 0 | 0 | 0 | 0 |  | CO | 15 | 06co | 232 | 246
01CO | 01 | T1799 | 44421315201 | 2021-07-28 | QTR1 | 21/22 | 2 | 4 | 150 | 427 | 427 | 0 | 0 | 0 | 277 | 0 | 1799984 | 50000 | 1749984 | 1831736 | 1823093 | 0 | 0 | 0 | 1823093 | 1813838 | 12989 | 31752 | 189 | 0 | 0 | 5503 | 0 | 0 | 0 | 8913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 22244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 42196 | 0 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2024-03-15 | QTR3 | 23/24 | 2023-08-31 | QTR1 | 23/24 | 118 | 1712726.18 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO | 8 | 06do | 247 | 254
01CO | 01 | T1803 | 44485625201 | 2022-02-23 | QTR3 | 21/22 | 1 | 3 | 290 | 335 | 325 | 10 | 0 | 0 | 45 | 0 | 3990760 | 0 | 3990760 | 3990760 | 3720606 | 0 | 0 | 0 | 3720606 | 3720606 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-06-05 | QTR4 | 23/24 | 2024-02-28 | QTR3 | 23/24 | 113 | 4528912.63 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO | 13 | 07co | 255 | 267
01CO | 01 | T1806 | 44155915201 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 250 | 391 | 391 | 0 | 0 | 0 | 134 | 7 | 7108184 | 63330 | 7044854 | 8445969 | 8418621 | 0 | 0 | 0 | 8418621 | 7803372 | 265502 | 1337785 | 92 | 0 | 0 | 0 | 0 | 23 | 7 | 473396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 880751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 39 | 1354148 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 | 2023-05-01 | QTR4 | 22/23 | 115 | 6181054.02 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO | 20 | 07do | 268 | 287
01CO | 01 | T1808 | 44233315201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 140 | 293 | 293 | 0 | 0 | 0 | 153 | 0 | 1139701 | 50000 | 1089701 | 1148801 | 1029185 | 0 | 0 | 0 | 1029185 | 1021881 | 1796 | 9100 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 9100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 9100 | 0 | F134205756 | COBB SITE DEVELOPMENT INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-03-17 | QTR3 | 22/23 | 108 | 1098275.5 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO | 0 | 08co | 288 | 287
01CO | 01 | T1811 | 44033915201 | 2022-01-26 | QTR3 | 21/22 | 1 | 3 | 200 | 464 | 464 | 0 | 0 | 0 | 84 | 180 | 2754382 | 50000 | 2704382 | 2849902 | 2874882 | 0 | 0 | 0 | 2874882 | 2854767 | 2576 | 95519 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 58096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 22690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 80786 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2024-03-12 | QTR3 | 23/24 | 2023-10-24 | QTR2 | 23/24 | 108 | 2214962.73 |  |  | 180 | 28 | 0 | 0 | 0 | 0 |  | CO | 22 | 08do | 288 | 309
01CO | 01 | T1817 | 44068815201 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 80 | 165 | 165 | 0 | 0 | 0 | 85 | 0 | 650650 | 18505 | 632145 | 655279 | 608957 | 0 | 0 | 0 | 608957 | 609408 | 451 | 4629 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 8153 | 45738 | 0 | 0 | 0 | 0 | 27 | 0 | 15989 | 45738 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-21 | QTR1 | 23/24 | 2022-12-13 | QTR2 | 22/23 | 115 | 447609.94 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1826 | 44421215201 | 2021-08-25 | QTR1 | 21/22 | 1 | 3 | 107 | 259 | 259 | 0 | 0 | 0 | 44 | 108 | 1045874 | 41345 | 1004529 | 1076047 | 1015157 | 0 | 0 | 0 | 1015157 | 994639 | 0 | 30174 | 132 | 0 | 0 | 10825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 20519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 31344 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2023-03-20 | QTR3 | 22/23 | 118 | 898648.05 |  |  | 18 | 20 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1828 | 44033715201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 97 | 129 | 129 | 0 | 0 | 0 | 32 | 0 | 560933 | 21933 | 539000 | 623460 | 604533 | 0 | 0 | 0 | 604533 | 604533 | 0 | 62527 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 62527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65533 | 0 | F823160551 | LEON AMERICA CONSTRUCTION | N/A | N/A | N/A | N/A | 2023-09-25 | QTR1 | 23/24 | 2023-05-15 | QTR4 | 22/23 | 113 | 517232.45 | B0 | ACC - LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0 |  | CO |  | 0
01CO | 01 | T1829 | 44514215201 | 2022-03-30 | QTR3 | 21/22 | 1 | 2 | 250 | 396 | 396 | 0 | 0 | 0 | 72 | 74 | 5872391 | 66763 | 5805628 | 5912809 | 6112682 | 0 | 0 | 0 | 6112682 | 6149957 | 50818 | 40418 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 26875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 13543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 40418 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-02-19 | QTR3 | 23/24 | 2023-10-17 | QTR2 | 23/24 | 108 | 6322955.67 |  |  | 74 | 24 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1831 | 43708815201 | 2022-03-30 | QTR3 | 21/22 | 1 | 3 | 175 | 281 | 281 | 0 | 0 | 0 | 85 | 21 | 1393708 | 50000 | 1343708 | 1475766 | 1415171 | 0 | 0 | 0 | 1415171 | 1415090 | -81 | 82058 | 70 | 0 | 21 | 11441 | 0 | 0 | 0 | 74605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 86046 | 0 | F814212997 | NATIONAL TRAFFIC SOLUTION INC | N/A | N/A | N/A | N/A | 2024-01-11 | QTR3 | 23/24 | 2023-10-04 | QTR2 | 23/24 | 118 | 1903169.56 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1832 | 44880215201 | 2022-03-30 | QTR3 | 21/22 | 1 | 1 | 280 | 310 | 262 | 48 | 0 | 0 | 30 | 0 | 1651156 | 50000 | 1601156 | 1659184 | 1593043 | 0 | 0 | 0 | 1593043 | 1593043 | 0 | 8028 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8028 | 4095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8028 | 4095 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-03-21 | QTR3 | 23/24 | 2023-12-27 | QTR2 | 23/24 | 113 | 2046036.83 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1834 | 44632015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 2 | 215 | 280 | 272 | 8 | 0 | 0 | 65 | 0 | 4197476 | 50000 | 4147476 | 4197476 | 3945832 | 0 | 0 | 0 | 3945832 | 3902393 | -43439 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12995 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 | 2023-06-22 | QTR4 | 22/23 | 113 | 4322110.94 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1836 | 44155835201 | 2022-03-30 | QTR3 | 21/22 | 2 | 5 | 250 | 279 | 279 | 0 | 0 | 0 | 29 | 0 | 3587382 | 0 | 3587382 | 3716421 | 3659641 | 0 | 0 | 0 | 3659641 | 3667717 | 8077 | 129039 | 7 | 0 | 0 | 10283 | 0 | 0 | 0 | 118756 | 3604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129039 | 3604 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-05-21 | QTR4 | 23/24 | 2023-09-08 | QTR1 | 23/24 | 115 | 2875279.8 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1839 | 44012715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 0 | 130 | 175 | 175 | 0 | 0 | 0 | 45 | 0 | 461461 | 21100 | 440361 | 461461 | 428726 | 0 | 0 | 0 | 428726 | 428726 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2023-03-06 | QTR3 | 22/23 | 115 | 438393.45 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1842 | 44404915201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 160 | 206 | 206 | 0 | 0 | 0 | 46 | 0 | 1796523 | 50000 | 1746523 | 1801104 | 1763228 | 0 | 0 | 0 | 1763228 | 1760169 | 1522 | 4581 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4581 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-03-26 | QTR3 | 23/24 | 2023-03-25 | QTR3 | 22/23 | 115 | 1217941.81 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
01CO | 01 | T1844 | 43982615201 | 2022-02-23 | QTR3 | 21/22 | 2 | 5 | 550 | 625 | 550 | 75 | 0 | 0 | 75 | 0 | 9424555 | 81813 | 9342742 | 9468450 | 9631445 | 0 | 0 | 0 | 9631445 | 9680052 | 92003 | 43895 | 40 | 0 | 0 | 3920 | 0 | 0 | 0 | 3096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76905 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2024-05-23 | QTR4 | 23/24 | 2023-12-01 | QTR2 | 23/24 | 108 | 9297482.95 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | CO
01DO | 01 | E1S66 | 43813715201 | 2020-12-03 | QTR2 | 20/21 | 6 | 8 | 450 | 845 | 838 | 7 | 0 | 0 | 132 | 263 | 8623489 | 90613 | 8532876 | 9397066 | 9294008 | 0 | 0 | 0 | 9294008 | 9490393 | 487144 | 773578 | 84 | 0 | 71 | 305583 | 0 | 0 | 84 | 299190 | 27177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 15720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 263 | 815494 | 27177 | F590767981 | RUSSELL ENGINEERING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 | 2023-06-30 | QTR4 | 22/23 | 115 | 7399516.3 | B10:B2:B5 | ACC - BONUS/INCENT/DISINCENT:ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE | 7 | 48 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1S92 | 44153415201 | 2021-11-04 | QTR2 | 21/22 | 3 | 2 | 275 | 390 | 390 | 0 | 0 | 0 | 115 | 0 | 5052712 | 52873 | 4999839 | 4990876 | 4942213 | 0 | 0 | 0 | 4942213 | 5001843 | 59630 | -61836 | 87 | 0 | 0 | 0 | 0 | 5 | 0 | 6022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -55813 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-12-20 | QTR2 | 23/24 | 2023-09-11 | QTR1 | 23/24 | 115 | 4924224.57 |  |  | 0 | 23 | 0 | 0 | -42313 | 0 |  | DO
01DO | 01 | E1U10 | 44592715201 | 2021-10-21 | QTR2 | 21/22 | 1 | 2 | 90 | 345 | 339 | 6 | 0 | 0 | 58 | 197 | 1030376 | 38210 | 992166 | 1035071 | 1194101 | 0 | 0 | 0 | 1194101 | 1189756 | 0 | 4695 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 5244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18641 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 28229 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-10-27 | QTR2 | 23/24 | 2023-07-16 | QTR1 | 23/24 | 108 | 838447.1 |  |  | 197 | 25 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1U11 | 43503825201 | 2021-09-16 | QTR1 | 21/22 | 1 | 1 | 197 | 242 | 472 | -230 | 230 | 0 | 45 | 0 | 2146553 | 50000 | 2096553 | 2448898 | 2092854 | -195268 | 0 | -195268 | 1897587 | 1897587 | 0 | 302345 | 27 | 0 | 0 | 14495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349794 | 0 | F273238420 | OCEANIK.US INC | N/A | N/A | N/A | N/A | 2024-03-27 | QTR3 | 23/24 | 2023-12-20 | QTR2 | 23/24 | 115 | 1604001.39 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1U12 | 44155315201 | 2021-09-16 | QTR1 | 21/22 | 2 | 4 | 300 | 439 | 422 | 17 | 0 | 0 | 139 | 0 | 6272386 | 62629 | 6209757 | 6303322 | 6506395 | 0 | 0 | 0 | 6506395 | 6911842 | 427490 | 30935 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 8892 | 976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 22043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 35473 | 976 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-09-12 | QTR1 | 23/24 | 2023-05-12 | QTR4 | 22/23 | 108 | 6222847.06 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1U14 | 44477715201 | 2021-12-02 | QTR2 | 21/22 | 2 | 2 | 160 | 222 | 222 | 0 | 0 | 0 | 62 | 0 | 3819554 | 50000 | 3769554 | 3657701 | 3521817 | 0 | 0 | 0 | 3521817 | 3658011 | 136195 | -161853 | 29 | 12 | 0 | 56568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | -161853 | 0 | F651115948 | SUPERIOR ASPHALT INC. | N/A | N/A | N/A | N/A | 2023-07-21 | QTR1 | 23/24 | 2023-03-03 | QTR3 | 22/23 | 115 | 3928132.77 | B0 | ACC - LUMP SUM | 0 | 21 | 0 | 0 | -218421 | 0 |  | DO
01DO | 01 | E1U17 | 44594115201 | 2022-02-17 | QTR3 | 21/22 | 1 | 0 | 150 | 171 | 166 | 5 | 0 | 0 | 21 | 0 | 722056 | 48017 | 674039 | 722056 | 642082 | 0 | 100000 | 100000 | 742082 | 642815 | -99267 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-03-17 | QTR3 | 22/23 | 115 | 1070560.76 | B1 | ACC - NO EXCUSE BONUS | 0 | 17 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1U22 | 44198315201 | 2022-07-21 | QTR1 | 22/23 | 2 | 2 | 170 | 194 | 187 | 7 | 0 | 0 | 24 | 0 | 2187528 | 50000 | 2137528 | 2184764 | 2110755 | 0 | 0 | 0 | 2110755 | 2091701 | -13720 | -2764 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 15242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27348 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-01-03 | QTR3 | 23/24 | 2023-11-06 | QTR2 | 23/24 | 108 | 1943940.24 | B0 | ACC - LUMP SUM | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1U62 | 43852825201 | 2022-03-14 | QTR3 | 21/22 | 1 | 2 | 410 | 530 | 528 | 2 | 0 | 0 | 120 | 0 | 6357542 | 50000 | 6307542 | 6484969 | 6447894 | 0 | 0 | 0 | 6447894 | 6320466 | 0 | 127428 | 46 | 43 | 0 | 12925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 140352 | 0 | F550345840 | VECELLIO & GROGAN INC. | N/A | N/A | N/A | N/A | 2024-02-22 | QTR3 | 23/24 | 2023-10-27 | QTR2 | 23/24 | 115 | 4194626.61 | LBDB | LOW BID DESIGN BUILD | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1U96 | 44787715201 | 2022-05-02 | QTR4 | 21/22 | 4 | 4 | 450 | 555 | 552 | 3 | 0 | 0 | 84 | 21 | 3028512 | 50000 | 2978512 | 3275716 | 3237381 | 0 | 0 | 0 | 3237381 | 3222484 | -14897 | 247204 | 37 | 0 | 21 | 110349 | 0 | 0 | 0 | 136854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 258869 | 0 | F591742990 | SOUTHLAND CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-05-14 | QTR4 | 23/24 | 2024-01-21 | QTR3 | 23/24 | 108 | 2974793.54 | LBDB:LBDB::::Y | LOW BID DESIGN BUILD:LOW BID DESIGN BUILD:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 0 | 47 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V07 | 44023115201 | 2022-09-15 | QTR1 | 22/23 | 1 | 3 | 75 | 75 | 72 | 3 | 0 | 0 | 0 | 0 | 289419 | 14419 | 275000 | 311381 | 315649 | 0 | 0 | 0 | 315649 | 315649 | 0 | 21962 | 0 | 0 | 0 | 6636 | 0 | 0 | 0 | 21962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28598 | 0 | F814025800 | ORLANDO R&B LLC | N/A | N/A | N/A | N/A | 2023-08-09 | QTR1 | 23/24 | 2023-03-29 | QTR3 | 22/23 | 118 | 331704.75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V14 | 44023715201 | 2023-02-16 | QTR3 | 22/23 | 1 | 1 | 120 | 164 | 164 | 0 | 0 | 0 | 44 | 0 | 1096407 | 50000 | 1046407 | 1123291 | 1184828 | 0 | 0 | 0 | 1184828 | 1157944 | 0 | 26884 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 26884 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-04-30 | QTR4 | 23/24 | 2024-01-03 | QTR3 | 23/24 | 115 | 1215794.64 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V17 | 44547515201 | 2023-02-16 | QTR3 | 22/23 | 1 | 2 | 150 | 197 | 183 | 14 | 0 | 0 | 47 | 0 | 3191521 | 50000 | 3141521 | 3202707 | 3243015 | 0 | 0 | 0 | 3243015 | 3244009 | 12179 | 11186 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 14163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25349 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-03-05 | QTR3 | 23/24 | 2023-12-22 | QTR2 | 23/24 | 113 | 3232954.27 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V19 | 44620915201 | 2023-02-16 | QTR3 | 22/23 | 1 | 0 | 120 | 146 | 145 | 1 | 0 | 0 | 21 | 5 | 2718429 | 50000 | 2668429 | 2718429 | 2702583 | 0 | 0 | 0 | 2702583 | 2702583 | 0 | 0 | 5 | 0 | 5 | 10433 | 0 | 0 | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 11693 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-04-16 | QTR4 | 23/24 | 2024-02-09 | QTR3 | 23/24 | 118 | 2913080.09 | B0 | ACC - LUMP SUM | 5 | 16 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V20 | 44620315201 | 2022-11-03 | QTR2 | 22/23 | 1 | 2 | 185 | 216 | 212 | 4 | 0 | 0 | 31 | 0 | 3919123 | 50000 | 3869123 | 3942427 | 4025522 | 0 | 0 | 0 | 4025522 | 3972960 | -46071 | 23303 | 22 | 0 | 0 | 46573 | 0 | 0 | 0 | 16812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69876 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-02-05 | QTR3 | 23/24 | 2023-10-26 | QTR2 | 23/24 | 118 | 4631315.91 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V21 | 44782415201 | 2023-03-16 | QTR3 | 22/23 | 1 | 0 | 165 | 187 | 142 | 45 | 0 | 0 | 22 | 0 | 1465139 | 50000 | 1415139 | 1465139 | 1275611 | 0 | 0 | 0 | 1275611 | 1275611 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-05-02 | QTR4 | 23/24 | 2024-03-19 | QTR3 | 23/24 | 115 | 1729896.93 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | DO
01DO | 01 | E1V34 | 44972015201 | 2022-05-18 | QTR4 | 21/22 | 1 | 2 | 500 | 577 | 550 | 27 | 0 | 0 | 77 | 0 | 2335000 | 50000 | 2285000 | 2358883 | 2307883 | 0 | 0 | 0 | 2307883 | 2307883 | 0 | 23883 | 19 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23883 | 15720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 23883 | 15720 | F592934582 | HIGHWAY SAFETY DEVICES INC. | N/A | N/A | N/A | N/A | 2024-04-11 | QTR4 | 23/24 | 2024-02-28 | QTR3 | 23/24 | 106 | 2186687.91 | Y | DESIGN/BUILD PROJECT | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
02CO | 02 | T2703 | 21272425201 | 2018-05-23 | QTR4 | 17/18 | 1 | 2 | 550 | 719 | 968 | -249 | 249 | 0 | 169 | 0 | 11717625 | 120 | 11717505 | 11666748 | 11573612 | -1206768 | 0 | -1206768 | 10366844 | 10334162 | -32682 | -50877 | 123 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50877 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 | 2021-05-03 | QTR4 | 20/21 | 209 | 12539660.43 |  |  | 0 | 46 | 0 | 0 | -68877 | 0 |  | CO
02CO | 02 | T2725 | 42307145201 | 2018-12-05 | QTR2 | 18/19 | 1 | 5 | 300 | 737 | 737 | 0 | 0 | 0 | 181 | 256 | 7294444 | 68754 | 7225690 | 7636147 | 7798283 | 0 | 0 | 0 | 7798283 | 7754246 | -44037 | 341703 | 85 | 0 | 27 | 92502 | 0 | 0 | 229 | 220039 | 17548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4989 | 0 | 0 | 0 | 6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 256 | 330105 | 23598 | F650026542 | D.A.B. CONSTRUCTORS INC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2021-06-17 | QTR4 | 20/21 | 214 | 7079691.78 |  |  | 244 | 96 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2749 | 43946715201 | 2019-09-25 | QTR1 | 19/20 | 3 | 10 | 600 | 1149 | 1149 | 0 | 0 | 0 | 265 | 284 | 11950705 | 126323 | 11824382 | 12606239 | 12535468 | 0 | 0 | 0 | 12535468 | 12707911 | 309266 | 655533 | 237 | 0 | 39 | 488108 | 0 | 0 | 59 | 227908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 4468 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 726457 | 0 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-28 | QTR1 | 23/24 | 2023-02-27 | QTR3 | 22/23 | 208 | 11844644.47 |  |  | 166 | 108 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2757 | 43761115201 | 2020-05-20 | QTR4 | 19/20 | 1 | 1 | 400 | 665 | 665 | 0 | 0 | 0 | 265 | 0 | 8709827 | 101684 | 8608142 | 8796925 | 9184283 | 0 | 0 | 0 | 9184283 | 9416582 | 329791 | 87098 | 104 | 20 | 0 | 34375 | 0 | 0 | 0 | 29391 | 13548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89615 | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 109 | 0 | 156554 | 81556 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-11-17 | QTR2 | 23/24 | 2022-08-14 | QTR1 | 22/23 | 208 | 10240284.6 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2758 | 43939915201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 280 | 461 | 461 | 0 | 0 | 0 | 116 | 65 | 6913040 | 75958 | 6837082 | 6913040 | 6429139 | 0 | 0 | 0 | 6429139 | 6454714 | 25575 | 0 | 81 | 0 | 0 | 2836 | 0 | 0 | 1 | 16654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 19491 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-05 | QTR3 | 23/24 | 2021-08-16 | QTR1 | 21/22 | 214 | 7673392.05 |  |  | 65 | 35 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2772 | 43404115201 | 2020-05-20 | QTR4 | 19/20 | 4 | 3 | 850 | 1193 | 1193 | 0 | 0 | 0 | 334 | 9 | 10836000 | 86543 | 10749457 | 11135538 | 11386435 | 0 | 0 | 0 | 11386435 | 11424606 | 521916 | 299538 | 143 | 0 | 0 | 0 | 0 | 8 | 0 | 130911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 168628 | 57676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 0 | 299538 | 57676 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-04-03 | QTR4 | 23/24 | 2023-12-06 | QTR2 | 23/24 | 208 | 8768180.16 |  |  | 0 | 108 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2787 | 44105915201 | 2020-07-29 | QTR1 | 20/21 | 1 | 2 | 250 | 376 | 373 | 3 | 0 | 0 | 81 | 45 | 13904803 | 145464 | 13759339 | 14427901 | 14501738 | 0 | 0 | 0 | 14501738 | 14430355 | -71383 | 523099 | 59 | 0 | 45 | 523099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 523099 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-16 | QTR2 | 23/24 | 2021-09-15 | QTR1 | 21/22 | 209 | 14722615.57 |  |  | 15 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2788 | 44258115201 | 2020-11-18 | QTR2 | 20/21 | 1 | 0 | 240 | 516 | 513 | 3 | 0 | 0 | 220 | 56 | 7945667 | 68632 | 7877035 | 7945667 | 8114839 | 0 | 0 | 0 | 8114839 | 8571019 | 459557 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 56 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-16 | QTR2 | 23/24 | 2022-07-07 | QTR1 | 22/23 | 209 | 6919711.56 |  |  | 56 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2796 | 44119415201 | 2021-03-31 | QTR3 | 20/21 | 2 | 2 | 200 | 703 | 703 | 0 | 0 | 0 | 67 | 436 | 1882079 | 50000 | 1832079 | 1993425 | 1914819 | 0 | 0 | 0 | 1914819 | 1920086 | 5267 | 111345 | 142 | 0 | 265 | 118838 | 51945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 118838 | 51945 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-02-21 | QTR3 | 23/24 | 2023-12-06 | QTR2 | 23/24 | 208 | 1441903.37 |  |  | 285 | 54 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2802 | 43575715201 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 180 | 523 | 523 | 0 | 0 | 0 | 29 | 314 | 1262262 | 50000 | 1212262 | 1262262 | 1249368 | 0 | 0 | 0 | 1249368 | 1249498 | 130 | 0 | 103 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2022-12-23 | QTR2 | 22/23 | 208 | 1338362.89 |  |  | 314 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2803 | 44126115201 | 2021-05-26 | QTR4 | 20/21 | 2 | 3 | 325 | 487 | 487 | 0 | 0 | 0 | 162 | 0 | 4633748 | 75000 | 4558748 | 3852057 | 3929376 | 0 | 0 | 0 | 3929376 | 4154909 | 225533 | -781691 | 40 | 30 | 0 | -739805 | 0 | 0 | 0 | 7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | -732738 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2023-01-06 | QTR3 | 22/23 | 208 | 4540382.58 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2821 | 44327315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 1 | 150 | 289 | 271 | 18 | 0 | 0 | 118 | 21 | 4876894 | 52518 | 4824376 | 4984966 | 5022406 | 0 | 0 | 0 | 5022406 | 5415141 | 392735 | 108073 | 77 | 0 | 21 | 141356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31 | 21 | 141356 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 | 2022-10-13 | QTR2 | 22/23 | 216 | 5483810.94 |  |  | 6 | 10 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2822 | 44331315201 | 2021-09-29 | QTR1 | 21/22 | 1 | 0 | 250 | 488 | 483 | 5 | 0 | 0 | 236 | 2 | 9173879 | 91638 | 9082241 | 9173879 | 9342688 | 0 | 0 | 0 | 9342688 | 9910699 | 568010 | 0 | 205 | 28 | 0 | 0 | 0 | 0 | 0 | 12476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 2 | 12476 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-03 | QTR2 | 23/24 | 2023-06-29 | QTR4 | 22/23 | 209 | 9935885.58 |  |  | 2 | 31 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2824 | 44327415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 2 | 250 | 455 | 453 | 2 | 0 | 0 | 190 | 15 | 3471681 | 50000 | 3421681 | 3603585 | 3475517 | 0 | 0 | 0 | 3475517 | 3614982 | 141674 | 131904 | 166 | 0 | 0 | 34801 | 0 | 0 | 15 | 132601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 15 | 169611 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-05-04 | QTR4 | 22/23 | 216 | 3836185.04 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2825 | 44328215201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 75 | 125 | 124 | 1 | 0 | 0 | 10 | 40 | 698919 | 27456 | 671464 | 698919 | 656099 | 0 | 0 | 0 | 656099 | 656099 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-14 | QTR1 | 23/24 | 2022-06-28 | QTR4 | 21/22 | 209 | 629198.54 |  |  | 40 | 3 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2826 | 44331115201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 220 | 264 | 264 | 0 | 0 | 0 | 44 | 0 | 8657266 | 87492 | 8569774 | 8657266 | 8107793 | 0 | 0 | 0 | 8107793 | 8099899 | -7895 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-29 | QTR1 | 23/24 | 2023-05-05 | QTR4 | 22/23 | 209 | 10016766.94 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2827 | 43935715201 | 2022-02-23 | QTR3 | 21/22 | 1 | 1 | 300 | 388 | 388 | 0 | 0 | 0 | 65 | 23 | 6658470 | 60239 | 6598231 | 6939208 | 6857539 | 0 | 0 | 0 | 6857539 | 7130536 | 272997 | 280738 | 40 | 0 | 0 | 1266 | 0 | 0 | 20 | 304513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 305779 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-05 | QTR3 | 23/24 | 2023-06-28 | QTR4 | 22/23 | 214 | 7633373.36 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2829 | 44120815201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 150 | 227 | 224 | 3 | 0 | 0 | 48 | 29 | 1047740 | 50000 | 997740 | 1047740 | 1004140 | 0 | 0 | 0 | 1004140 | 1004137 | -3 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-10-03 | QTR2 | 23/24 | 2023-06-01 | QTR4 | 22/23 | 208 | 1984965.49 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2833 | 44325815201 | 2022-01-12 | QTR3 | 21/22 | 1 | 0 | 210 | 235 | 235 | 0 | 0 | 0 | 25 | 0 | 6173212 | 71171 | 6102041 | 6173212 | 6149692 | 0 | 0 | 0 | 6149692 | 6808147 | 658455 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 37498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41624 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2022-11-23 | QTR2 | 22/23 | 214 | 7484487.76 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2835 | 44327215201 | 2022-01-26 | QTR3 | 21/22 | 1 | 2 | 250 | 442 | 442 | 0 | 0 | 0 | 192 | 0 | 9730642 | 103892 | 9626750 | 9751076 | 10241376 | 0 | 0 | 0 | 10241376 | 10650890 | 409515 | 20434 | 166 | 0 | 0 | 116950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 120 | 0 | 89568 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2024-02-20 | QTR3 | 23/24 | 2023-08-28 | QTR1 | 23/24 | 216 | 11590621.81 |  |  | 0 | 26 | 0 | 0 | -27382 | 0 |  | CO
02CO | 02 | T2836 | 44325915201 | 2022-02-23 | QTR3 | 21/22 | 2 | 2 | 210 | 287 | 287 | 0 | 0 | 0 | 72 | 5 | 4069827 | 50000 | 4019827 | 4084043 | 4107794 | 0 | 0 | 0 | 4107794 | 4236681 | 130239 | 14216 | 19 | 0 | 0 | 0 | 0 | 34 | 0 | 12864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 14216 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-10-02 | QTR2 | 23/24 | 2023-04-17 | QTR4 | 22/23 | 208 | 5072861.67 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2837 | 44329415201 | 2021-10-27 | QTR2 | 21/22 | 1 | 0 | 180 | 262 | 260 | 2 | 0 | 0 | 55 | 27 | 1371850 | 50000 | 1321850 | 1371850 | 1320562 | 0 | 0 | 0 | 1320562 | 1320562 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 | 2023-01-19 | QTR3 | 22/23 | 208 | 1352767.24 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2845 | 44119425201 | 2022-05-25 | QTR4 | 21/22 | 1 | 1 | 100 | 303 | 303 | 0 | 0 | 0 | 67 | 136 | 917218 | 36854 | 880364 | 984061 | 1118191 | 0 | 0 | 0 | 1118191 | 1118191 | 0 | 66843 | 22 | 0 | 30 | 23646 | 0 | 0 | 50 | 66843 | 66843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 90489 | 66843 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 | 2024-01-11 | QTR3 | 23/24 | 208 | 862998.91 |  |  | 30 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2846 | 44126015201 | 2022-01-12 | QTR3 | 21/22 | 2 | 1 | 300 | 413 | 418 | -5 | 5 | 0 | 113 | 0 | 9551621 | 106078 | 9445543 | 9552942 | 9869457 | -18930 | 0 | -18930 | 9850527 | 10484168 | 634962 | 1321 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 1184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2504 | 0 | F592397581 | DUVAL ASPHALT PRODUCTS INC. | N/A | N/A | N/A | N/A | 2023-11-02 | QTR2 | 23/24 | 2023-05-25 | QTR4 | 22/23 | 208 | 11919284.18 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2847 | 44328315201 | 2022-03-30 | QTR3 | 21/22 | 2 | 0 | 197 | 390 | 390 | 0 | 0 | 0 | 178 | 15 | 8536881 | 91154 | 8445727 | 8536881 | 9157134 | 0 | 0 | 0 | 9157134 | 9260550 | 103416 | 0 | 156 | 0 | 1 | 23794 | 0 | 0 | 14 | 12482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 15 | 36276 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-12 | QTR3 | 23/24 | 2023-08-31 | QTR1 | 23/24 | 209 | 10386871.81 |  |  | 15 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2848 | 44330515201 | 2022-03-30 | QTR3 | 21/22 | 2 | 1 | 360 | 392 | 383 | 9 | 0 | 0 | 32 | 0 | 13369606 | 130623 | 13238982 | 13375355 | 13678461 | 0 | 0 | 0 | 13678461 | 14086129 | 413419 | 5750 | 13 | 0 | 0 | 3089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15345 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-22 | QTR3 | 23/24 | 2023-08-03 | QTR1 | 23/24 | 214 | 15619864.41 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2855 | 43935815201 | 2021-06-09 | QTR4 | 20/21 | 2 | 0 | 350 | 464 | 459 | 5 | 0 | 0 | 86 | 28 | 7918962 | 100000 | 7818962 | 7918962 | 7962203 | 0 | 0 | 0 | 7962203 | 8267055 | 304853 | 0 | 42 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-09-07 | QTR1 | 23/24 | 2023-02-23 | QTR3 | 22/23 | 209 | 7233767.77 |  |  | 28 | 44 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2856 | 42983025201 | 2021-11-17 | QTR2 | 21/22 | 1 | 2 | 85 | 354 | 373 | -19 | 19 | 0 | 108 | 161 | 997892 | 42783 | 955110 | 1048834 | 1111095 | -32186 | 0 | -32186 | 1078909 | 1111095 | 32186 | 50942 | 46 | 0 | 0 | 0 | 0 | 22 | 121 | 80716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 151 | 80716 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-02-14 | QTR3 | 23/24 | 2023-06-08 | QTR4 | 22/23 | 214 | 943264.64 |  |  | 151 | 70 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2857 | 44721115201 | 2022-01-26 | QTR3 | 21/22 | 1 | 0 | 120 | 193 | 185 | 8 | 0 | 0 | 27 | 46 | 1077522 | 44955 | 1032567 | 1077522 | 1075156 | 0 | 0 | 0 | 1075156 | 1075156 | 0 | 0 | 16 | 0 | 30 | 18350 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 18350 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2022-10-14 | QTR2 | 22/23 | 208 | 1339271.36 |  |  | 46 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2869 | 43567925201 | 2022-06-08 | QTR4 | 21/22 | 2 | 0 | 180 | 199 | 178 | 21 | 0 | 0 | 19 | 0 | 1298306 | 50000 | 1248306 | 1298306 | 1209436 | 0 | 0 | 0 | 1209436 | 1209097 | -339 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-08-31 | QTR1 | 23/24 | 2023-04-19 | QTR4 | 22/23 | 209 | 1554775.94 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2872 | 44534115201 | 2022-06-08 | QTR4 | 21/22 | 1 | 0 | 300 | 355 | 351 | 4 | 0 | 0 | 55 | 0 | 13193368 | 109807 | 13083561 | 13193368 | 13034580 | 0 | 0 | 0 | 13034580 | 12703529 | -331050 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-02-20 | QTR3 | 23/24 | 2023-08-23 | QTR1 | 23/24 | 208 | 10896297.69 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2873 | 44557615201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 90 | 90 | 19 | 71 | 0 | 0 | 0 | 0 | 240110 | 17791 | 222319 | 240110 | 185940 | 0 | 0 | 0 | 185940 | 185940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-03-31 | QTR3 | 22/23 | 208 | 402519.71 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2875 | 44912925201 | 2022-06-15 | QTR4 | 21/22 | 1 | 0 | 60 | 160 | 160 | 0 | 0 | 0 | 69 | 31 | 1386562 | 50000 | 1336562 | 1386562 | 1349510 | 0 | 0 | 0 | 1349510 | 1349510 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-11-30 | QTR2 | 23/24 | 2023-03-14 | QTR3 | 22/23 | 208 | 1705476.65 |  |  | 31 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2877 | 20954355201 | 2022-06-15 | QTR4 | 21/22 | 2 | 3 | 90 | 144 | 140 | 4 | 0 | 0 | 47 | 7 | 744369 | 43296 | 701073 | 788349 | 712669 | 0 | 0 | 0 | 712669 | 709731 | 0 | 43980 | 10 | 0 | 0 | 0 | 0 | 0 | 7 | 41042 | 41042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7 | 43980 | 41042 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-07 | QTR2 | 23/24 | 2023-01-24 | QTR3 | 22/23 | 208 | 931264.85 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2879 | 44535315201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 150 | 259 | 259 | 0 | 0 | 0 | 109 | 0 | 5044796 | 61908 | 4982887 | 5044796 | 5157015 | 0 | 0 | 0 | 5157015 | 5122877 | -34138 | 0 | 82 | 0 | 0 | 1064 | 0 | 0 | 0 | 6899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 8983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 17882 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-06-10 | QTR4 | 23/24 | 2024-01-24 | QTR3 | 23/24 | 216 | 5802841.18 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2880 | 21293465201 | 2022-08-31 | QTR1 | 22/23 | 2 | 1 | 150 | 265 | 265 | 0 | 0 | 0 | 71 | 44 | 621970 | 20266 | 601704 | 626401 | 439109 | 0 | 0 | 0 | 439109 | 439109 | 0 | 4431 | 52 | 0 | 44 | 18107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 18107 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-02-20 | QTR3 | 23/24 | 2023-11-09 | QTR2 | 23/24 | 214 | 485437.68 |  |  | 39 | 19 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2881 | 44554015201 | 2022-11-16 | QTR2 | 22/23 | 1 | 0 | 150 | 293 | 293 | 0 | 0 | 0 | 112 | 31 | 1959156 | 50000 | 1909156 | 1959156 | 1946528 | 0 | 0 | 0 | 1946528 | 1943700 | -2828 | 0 | 103 | 0 | 0 | 0 | 0 | 7 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 17 | 0 | 0 | F580641369 | REEVES CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 | 2023-12-04 | QTR2 | 23/24 | 208 | 1697524.17 |  |  | 17 | 16 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2883 | 44912955201 | 2022-10-26 | QTR2 | 22/23 | 1 | 1 | 80 | 188 | 188 | 0 | 0 | 0 | 108 | 0 | 2185964 | 50000 | 2135964 | 2192335 | 1926696 | 0 | 0 | 0 | 1926696 | 1926696 | 0 | 6371 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 6371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6371 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-11 | QTR3 | 23/24 | 2023-09-29 | QTR1 | 23/24 | 208 | 2721077.2 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2887 | 44729015201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 119 | 132 | 126 | 6 | 0 | 0 | 13 | 0 | 782704 | 28281 | 754423 | 782704 | 743960 | 0 | 0 | 0 | 743960 | 743960 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2024-02-13 | QTR3 | 23/24 | 2023-06-05 | QTR4 | 22/23 | 208 | 659451.55 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2888 | 40392055201 | 2022-05-25 | QTR4 | 21/22 | 2 | 0 | 119 | 246 | 246 | 0 | 0 | 0 | 30 | 97 | 928540 | 44276 | 884264 | 928540 | 970153 | 0 | 0 | 0 | 970153 | 970153 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2024-03-04 | QTR3 | 23/24 | 2023-10-11 | QTR2 | 23/24 | 208 | 881584.15 |  |  | 85 | 9 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2892 | 21071935201 | 2022-10-05 | QTR2 | 22/23 | 2 | 1 | 180 | 315 | 291 | 24 | 0 | 0 | 135 | 0 | 9775622 | 97298 | 9678325 | 9736781 | 9879780 | 0 | 0 | 0 | 9879780 | 9713317 | -166463 | -38842 | 25 | 30 | 0 | -38842 | 0 | 0 | 0 | 10688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 93 | 0 | -23365 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-05-13 | QTR4 | 23/24 | 2023-12-05 | QTR2 | 23/24 | 209 | 10476736.76 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2895 | 44125915201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 200 | 327 | 326 | 1 | 0 | 0 | 82 | 45 | 6674091 | 68301 | 6605790 | 6674091 | 6876375 | 0 | 0 | 0 | 6876375 | 6832975 | -43400 | 0 | 99 | 0 | 0 | 11618 | 0 | 0 | 0 | 12175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 23793 | 0 | F043619482 | WHITEHURST V. E. & SONS INC. | N/A | N/A | N/A | N/A | 2024-06-26 | QTR4 | 23/24 | 2024-03-14 | QTR3 | 23/24 | 214 | 6898412.52 |  |  | 45 | 28 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2899 | 20761175201 | 2022-06-15 | QTR4 | 21/22 | 1 | 1 | 90 | 214 | 214 | 0 | 0 | 0 | 66 | 58 | 678930 | 39509 | 639421 | 678930 | 558364 | 0 | 0 | 0 | 558364 | 558364 | 0 | 0 | 44 | 0 | 8 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2024-02-21 | QTR3 | 23/24 | 2023-07-14 | QTR1 | 23/24 | 214 | 998390.21 |  |  | 50 | 22 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2902 | 43928015201 | 2022-11-16 | QTR2 | 22/23 | 2 | 2 | 250 | 364 | 331 | 33 | 0 | 0 | 40 | 74 | 3588897 | 120 | 3588777 | 4279812 | 4203052 | 0 | 0 | 0 | 4203052 | 4179179 | -4238 | 690915 | 24 | 0 | 65 | 671280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 19635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 690915 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-06-14 | QTR4 | 23/24 | 2024-02-28 | QTR3 | 23/24 | 209 | 4177372.15 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2903 | 44556915201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 60 | 109 | 109 | 0 | 0 | 0 | 25 | 24 | 203240 | 10914 | 192326 | 203240 | 190113 | 0 | 0 | 0 | 190113 | 190113 | 0 | 0 | 17 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2024-06-06 | QTR4 | 23/24 | 2023-12-21 | QTR2 | 23/24 | 214 | 229199.25 |  |  | 24 | 8 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T2923 | 44542625201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 74 | 101 | 94 | 7 | 0 | 0 | 26 | 1 | 212969 | 11187 | 201781 | 212969 | 198096 | 0 | 0 | 0 | 198096 | 198096 | 0 | 0 | 15 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-09-05 | QTR1 | 23/24 | 2023-03-01 | QTR3 | 22/23 | 208 | 251711.77 |  |  | 1 | 11 | 0 | 0 | 0 | 0 |  | CO
02CO | 02 | T9023 | 44624515223 | 2021-02-17 | QTR3 | 20/21 | 1 | 0 | 250 | 733 | 730 | 3 | 0 | 0 | 483 | 0 | 3516622 | 50000 | 3466622 | 3516622 | 3642093 | 0 | 0 | 0 | 3642093 | 3642131 | 38 | 0 | 14 | 420 | 0 | 0 | 0 | 0 | 0 | 30591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 41498 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-09-27 | QTR1 | 23/24 | 2023-08-03 | QTR1 | 23/24 | 209 | 3117936.11 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | CO
02DO | 02 | E20H1 | 43737715201 | 2022-04-20 | QTR4 | 21/22 | 1 | 0 | 60 | 84 | 84 | 0 | 0 | 0 | 23 | 1 | 612540 | 23388 | 589152 | 612540 | 596655 | 0 | 0 | 0 | 596655 | 596655 | 0 | 0 | 9 | 0 | 1 | 7085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7085 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2024-02-20 | QTR3 | 23/24 | 2023-12-05 | QTR2 | 23/24 | 214 | 703931.46 |  |  | 1 | 14 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20I1 | 43317155201 | 2022-05-11 | QTR4 | 21/22 | 1 | 0 | 300 | 480 | 480 | 0 | 0 | 0 | 172 | 8 | 5311071 | 50000 | 5261071 | 5311071 | 5141726 | 0 | 0 | 0 | 5141726 | 5104730 | -36996 | 0 | 127 | 0 | 8 | 40978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 4915 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 8 | 45894 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-22 | QTR3 | 23/24 | 2024-01-03 | QTR3 | 23/24 | 214 | 5008995.7 |  |  | 8 | 32 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20T5 | 43044935201 | 2022-07-20 | QTR1 | 22/23 | 1 | 0 | 245 | 273 | 268 | 5 | 0 | 0 | 28 | 0 | 937789 | 50000 | 887789 | 937789 | 902864 | 0 | 0 | 0 | 902864 | 902864 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-01-08 | QTR3 | 23/24 | 2023-10-27 | QTR2 | 23/24 | 216 | 1332805.2 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20T7 | 43089715201 | 2022-09-14 | QTR1 | 22/23 | 1 | 1 | 240 | 346 | 341 | 5 | 0 | 0 | 80 | 26 | 4193000 | 50000 | 4143000 | 4523767 | 4592009 | 0 | 0 | 0 | 4592009 | 4591894 | -116 | 330767 | 23 | 0 | 26 | 294029 | 0 | 0 | 0 | 68187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 380767 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-05-08 | QTR4 | 23/24 | 2024-03-01 | QTR3 | 23/24 | 216 | 4765385.7 |  |  | 0 | 57 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E20W3 | 43744215201 | 2022-06-08 | QTR4 | 21/22 | 2 | 3 | 300 | 412 | 411 | 1 | 0 | 0 | 83 | 29 | 2395648 | 50000 | 2345648 | 2453298 | 2436381 | 0 | 0 | 0 | 2436381 | 2403699 | -30 | 57650 | 49 | 0 | 29 | 69836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 102486 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-04-03 | QTR4 | 23/24 | 2024-01-26 | QTR3 | 23/24 | 214 | 2554733 |  |  | 29 | 34 | 0 | 0 | -2 | 0 |  | DO
02DO | 02 | E20W8 | 44277915201 | 2022-11-30 | QTR2 | 22/23 | 1 | 0 | 120 | 182 | 181 | 1 | 0 | 0 | 42 | 20 | 1761000 | 50000 | 1711000 | 1761000 | 1791422 | 0 | 0 | 0 | 1791422 | 1791366 | -56 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1 | 8282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 20 | 8282 | 0 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-01-19 | QTR3 | 23/24 | 2023-12-05 | QTR2 | 23/24 | 214 | 909989.25 |  |  | 20 | 11 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2V58 | 43303615201 | 2016-12-14 | QTR2 | 16/17 | 4 | 30 | 1200 | 2440 | 2437 | 3 | 0 | 0 | 487 | 753 | 116979302 | 166302 | 116813000 | 128380916 | 129172623 | 0 | 0 | 0 | 129172623 | 128727437 | 1167595 | 11401614 | 472 | 0 | 293 | 4521354 | 76346 | 0 | 171 | 5769031 | 96498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108900 | 0 | 0 | 0 | 450899 | 18997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 474788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596 | 11324973 | 191841 | F363286318 | ARCHER WESTERN CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2024-04-17 | QTR4 | 23/24 | 2023-10-31 | QTR2 | 23/24 | 208 | 119230874.66 | B5:B8 | ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR | 211 | 249 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Y76 | 20972255201 | 2020-04-15 | QTR4 | 19/20 | 2 | 2 | 400 | 967 | 967 | 0 | 0 | 0 | 259 | 308 | 4399943 | 50000 | 4349943 | 4455060 | 4448788 | 0 | 0 | 0 | 4448788 | 4443671 | 52479 | 55117 | 115 | 0 | 246 | 22225 | 0 | 0 | 0 | 56531 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 83873 | 0 | F592385218 | HINSON JAMES D. ELECTRICAL CONTRACTING | N/A | N/A | N/A | N/A | 2023-11-28 | QTR2 | 23/24 | 2023-07-24 | QTR1 | 23/24 | 208 | 4855272.24 |  |  | 308 | 144 | 0 | 0 | 0 | 0 |  | DO
02DO | 02 | E2Z33 | 43860815201 | 2019-11-26 | QTR2 | 19/20 | 2 | 10 | 600 | 1251 | 1251 | 0 | 0 | 0 | 517 | 134 | 25732018 | 150000 | 25582018 | 27245810 | 27216314 | 0 | 0 | 0 | 27216314 | 27282752 | 319145 | 1513792 | 449 | 0 | 0 | 115570 | 0 | 0 | 134 | 1522405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3543 | 0 | 0 | 0 | 0 | 0 | 403 | 0 | 5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403 | 134 | 1603759 | 0 | F593666875 | COXWELL J.B. CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-10 | QTR4 | 23/24 | 2023-10-13 | QTR2 | 23/24 | 209 | 20749475.95 | B8:B8::Y | ACC - DESIGN/BUILD - MAJOR:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD PROJECT:DESIGN/BUILD PROJECT | 32 | 68 | 0 | 0 | -42898 | 0 |  | DO
03CO | 03 | T3579 | 41413245201 | 2016-08-31 | QTR1 | 16/17 | 3 | 19 | 1090 | 1999 | 2171 | -172 | 172 | 0 | 798 | 111 | 42140000 | 150000 | 41990000 | 43136516 | 44789798 | -789688 | 0 | -789688 | 44000110 | 45150067 | 1313007 | 996516 | 442 | 4 | 40 | 380492 | 1569 | 0 | 27 | 349096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 8 | 165208 | 0 | 0 | 0 | 18045 | 18045 | 0 | 0 | 0 | 0 | 0 | 0 | 50586 | 0 | 0 | 46 | 95000 | 95000 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 121 | 898999 | 114614 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-18 | QTR1 | 23/24 | 2022-10-21 | QTR2 | 22/23 | 308 | 37004160.16 |  |  | 38 | 212 | 0 | 0 | -159429 | 0 |  | CO
03CO | 03 | T3598 | 43357725201 | 2021-12-08 | QTR2 | 21/22 | 2 | 0 | 210 | 314 | 314 | 0 | 0 | 0 | 104 | 0 | 1449372 | 9292 | 1440080 | 1449372 | 1245314 | 0 | 0 | 0 | 1245314 | 1245462 | 147 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593582039 | CHAVERS CONSTRUCTION INC | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-01-13 | QTR3 | 22/23 | 308 | 1387512.95 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3604 | 43282815201 | 2019-02-27 | QTR3 | 18/19 | 2 | 4 | 925 | 1322 | 1301 | 21 | 0 | 0 | 397 | 0 | 10228411 | 103267 | 10125144 | 10251581 | 10265075 | 0 | 0 | 0 | 10265075 | 10328004 | 62929 | 23170 | 263 | 0 | 0 | 24478 | 0 | 0 | 0 | 5148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 120 | 68927 | 0 | F630500583 | SCOTT BRIDGE COMPANY INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2022-12-06 | QTR2 | 22/23 | 308 | 10230057.88 |  |  | 0 | 84 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3664 | 43375115201 | 2021-06-09 | QTR4 | 20/21 | 4 | 1 | 185 | 509 | 509 | 0 | 0 | 0 | 275 | 49 | 2044978 | 50000 | 1994978 | 2045473 | 1907308 | 0 | 0 | 0 | 1907308 | 1907308 | 0 | 495 | 40 | 0 | 0 | 0 | 0 | 80 | 49 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 170 | 49 | 495 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-05-16 | QTR4 | 23/24 | 2023-03-03 | QTR3 | 22/23 | 313 | 2066195.42 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3687 | 44072415201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 135 | 164 | 159 | 5 | 0 | 0 | 29 | 0 | 889778 | 0 | 889778 | 889778 | 849190 | 0 | 0 | 0 | 849190 | 848671 | -519 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-03-27 | QTR3 | 23/24 | 2023-09-22 | QTR1 | 23/24 | 321 | 1417656.86 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3691 | 43717815201 | 2020-11-18 | QTR2 | 20/21 | 1 | 2 | 480 | 640 | 661 | -21 | 21 | 0 | 160 | 0 | 4269226 | 50000 | 4219226 | 4374816 | 4363593 | -30948 | 0 | -30948 | 4332645 | 4394715 | 138599 | 105591 | 98 | 8 | 0 | 95913 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 23399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 149628 | 0 | F814575837 | GDB-US | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 | 2022-12-04 | QTR2 | 22/23 | 308 | 4154505.73 |  |  | 0 | 40 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3702 | 42446455201 | 2018-09-26 | QTR1 | 18/19 | 4 | 17 | 1350 | 1989 | 1807 | 182 | 0 | 0 | 459 | 180 | 49837733 | 167160 | 49670573 | 55271608 | 58609882 | -12750 | 0 | -12750 | 58597132 | 58735900 | 554098 | 5433874 | 341 | 0 | 0 | 560255 | 43662 | 0 | 16 | 2344133 | 32770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 2385777 | 2433684 | 0 | 0 | 7220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108898 | 0 | 0 | 180 | 5461229 | 2510116 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-06-06 | QTR4 | 23/24 | 2024-01-29 | QTR3 | 23/24 | 306 | 51655054.35 |  |  | 0 | 118 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3703 | 43649925201 | 2019-09-25 | QTR1 | 19/20 | 3 | 0 | 150 | 292 | 262 | 30 | 0 | 0 | 112 | 30 | 2458081 | 51140 | 2406941 | 2458081 | 2572160 | 0 | 0 | 0 | 2572160 | 2554701 | -17459 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 42000 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2020-10-02 | QTR2 | 20/21 | 314 | 2031385.77 |  |  | 30 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3704 | 43938815201 | 2021-12-08 | QTR2 | 21/22 | 1 | 0 | 150 | 222 | 220 | 2 | 0 | 0 | 72 | 0 | 1462111 | 0 | 1462111 | 1462111 | 1360760 | 0 | 0 | 0 | 1360760 | 1370361 | 9601 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | F630702929 | F & W CONSTRUCTION COMPANY INC. | N/A | N/A | N/A | N/A | 2023-07-19 | QTR1 | 23/24 | 2022-10-07 | QTR2 | 22/23 | 313 | 1750125.19 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3712 | 43937115201 | 2021-11-17 | QTR2 | 21/22 | 1 | 3 | 240 | 280 | 543 | -263 | 263 | 0 | 40 | 0 | 4199999 | 0 | 4199999 | 4207543 | 4275092 | -681696 | 0 | -681696 | 3593396 | 4275464 | 682068 | 7544 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 7544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7544 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-01 | QTR3 | 23/24 | 2023-08-31 | QTR1 | 23/24 | 321 | 3898368.97 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3720 | 43936615201 | 2021-12-08 | QTR2 | 21/22 | 1 | 3 | 245 | 334 | 575 | -241 | 241 | 0 | 89 | 0 | 3077146 | 0 | 3077146 | 3077146 | 3008864 | -624672 | 0 | -624672 | 2384192 | 2402816 | 18624 | 0 | 37 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-20 | QTR3 | 23/24 | 2023-10-30 | QTR2 | 23/24 | 321 | 3261895.89 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3728 | 21898425201 | 2021-06-09 | QTR4 | 20/21 | 1 | 0 | 420 | 706 | 706 | 0 | 0 | 0 | 286 | 0 | 5503848 | 53988 | 5449859 | 5503848 | 5615605 | 0 | 0 | 0 | 5615605 | 5632695 | 85241 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 21870 | 0 | 0 | 0 | 2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24418 | 0 | F630368729 | MURPHREE BRIDGE CORPORATION | N/A | N/A | N/A | N/A | 2023-10-30 | QTR2 | 23/24 | 2023-07-24 | QTR1 | 23/24 | 314 | 7823905.33 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3733 | 43188365201 | 2022-11-16 | QTR2 | 22/23 | 1 | 1 | 140 | 298 | 298 | 0 | 0 | 0 | 158 | 0 | 1685940 | 50000 | 1635940 | 1730344 | 1594624 | 0 | 0 | 0 | 1594624 | 1590656 | -3968 | 44404 | 113 | 60 | 0 | 10492 | 4432 | 14 | 0 | 44005 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 54496 | 4742 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-06-12 | QTR4 | 23/24 | 2024-02-14 | QTR3 | 23/24 | 308 | 1924177.46 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3740 | 43626615201 | 2020-11-18 | QTR2 | 20/21 | 2 | 1 | 365 | 689 | 689 | 0 | 0 | 0 | 303 | 21 | 6166449 | 83640 | 6082809 | 6166449 | 6679471 | 0 | 0 | 0 | 6679471 | 7791843 | 1176465 | 0 | 170 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 21 | 67784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 100 | 21 | 67784 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-02-15 | QTR3 | 22/23 | 314 | 7986598.29 |  |  | 21 | 89 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3743 | 44173015201 | 2020-02-26 | QTR3 | 19/20 | 1 | 0 | 45 | 83 | 80 | 3 | 0 | 0 | 38 | 0 | 187229 | 12274 | 174955 | 187229 | 175598 | 0 | 0 | 0 | 175598 | 166353 | -9245 | 0 | 35 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | F208743994 | EMERALD COAST STRIPING LLC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2020-08-14 | QTR1 | 20/21 | 314 | 262871.46 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3750 | 43811125201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 95 | 131 | 130 | 1 | 0 | 0 | 36 | 0 | 987732 | 41493 | 946239 | 927591 | 903555 | 0 | 0 | 0 | 903555 | 903555 | 0 | -60141 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60141 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-05-12 | QTR4 | 22/23 | 314 | 912225.16 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3759 | 44014915201 | 2021-03-31 | QTR3 | 20/21 | 1 | 11 | 454 | 705 | 664 | 41 | 0 | 0 | 187 | 64 | 6899119 | 54298 | 6844821 | 7276831 | 6961458 | 0 | 0 | 0 | 6961458 | 7368477 | 416838 | 377713 | 82 | 0 | 28 | 290730 | 0 | 4 | 43 | 65880 | 6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 44 | 71 | 358010 | 6394 | F592895927 | ROBERTS AND ROBERTS INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 | 2023-04-26 | QTR4 | 22/23 | 314 | 5086089.54 |  |  | 26 | 61 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3773 | 44422025201 | 2023-05-24 | QTR4 | 22/23 | 1 | 0 | 80 | 263 | 237 | 26 | 0 | 0 | 183 | 0 | 556581 | 0 | 556581 | 556581 | 566850 | 0 | 0 | 0 | 566850 | 566850 | 0 | 0 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | F743148751 | ROGAR MANAGEMENT & CONSULTING OF FLORIDA | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 | 2024-04-03 | QTR4 | 23/24 | 314 | 736778 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3775 | 43256315201 | 2022-04-27 | QTR4 | 21/22 | 1 | 2 | 150 | 205 | 205 | 0 | 0 | 0 | 55 | 0 | 2579717 | 50000 | 2529717 | 2587262 | 2470218 | 0 | 0 | 0 | 2470218 | 2458123 | -12095 | 7545 | 47 | 0 | 0 | 5984 | 0 | 0 | 0 | 1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9474 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 | 2023-07-26 | QTR1 | 23/24 | 308 | 2583180.72 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3784 | 43938515201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 100 | 119 | 100 | 19 | 0 | 0 | 19 | 0 | 830333 | 0 | 830333 | 830333 | 808692 | 0 | 0 | 0 | 808692 | 808692 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F261141819 | CDM CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 | 2023-08-01 | QTR1 | 23/24 | 313 | 771890.7 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3787 | 44158815201 | 2021-04-28 | QTR4 | 20/21 | 2 | 6 | 315 | 828 | 828 | 0 | 0 | 0 | 427 | 86 | 16418543 | 150000 | 16268543 | 16722911 | 17708583 | -15000 | -192500 | -207500 | 17501083 | 18173399 | 716852 | 304368 | 296 | 15 | 27 | 103528 | 3211 | 5 | 27 | 149230 | 80099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 18 | 37573 | 10652 | 7 | 14 | 59047 | 15703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 86 | 349378 | 109665 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-02 | QTR4 | 23/24 | 2023-10-31 | QTR2 | 23/24 | 308 | 18163993.95 |  |  | 60 | 82 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3793 | 43467715201 | 2021-10-27 | QTR2 | 21/22 | 2 | 3 | 230 | 481 | 480 | 1 | 0 | 0 | 236 | 15 | 6283852 | 73669 | 6210183 | 6727204 | 6844151 | 0 | 0 | 0 | 6844151 | 7176797 | 332646 | 443352 | 186 | 0 | 7 | 378034 | 0 | 0 | 8 | 133625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | -51237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 15 | 460422 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2023-06-28 | QTR4 | 22/23 | 308 | 7460138.28 |  |  | 1 | 50 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3794 | 44364415201 | 2022-06-15 | QTR4 | 21/22 | 1 | 1 | 100 | 125 | 92 | 33 | 0 | 0 | 25 | 0 | 2537432 | 50000 | 2487432 | 2537432 | 2741257 | 0 | 0 | 0 | 2741257 | 2721406 | -19851 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-03-06 | QTR3 | 22/23 | 313 | 2975156.64 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3796 | 44404615201 | 2022-01-26 | QTR3 | 21/22 | 1 | 2 | 105 | 181 | 202 | -21 | 21 | 0 | 76 | 0 | 1458732 | 50000 | 1408732 | 1483251 | 1401648 | -35574 | 0 | -35574 | 1366074 | 1366074 | 0 | 24520 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 24915 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-16 | QTR4 | 23/24 | 2022-10-31 | QTR2 | 22/23 | 308 | 2613265.24 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3797 | 44365615201 | 2022-02-23 | QTR3 | 21/22 | 4 | 3 | 240 | 525 | 524 | 1 | 0 | 0 | 225 | 60 | 4361277 | 50000 | 4311277 | 5189354 | 5002338 | 0 | 0 | 0 | 5002338 | 5076487 | 74149 | 828077 | 144 | 20 | 30 | 402649 | 0 | 0 | 0 | 6727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 427409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 60 | 846684 | 0 | F593598732 | ROADS INC. OF NWF | N/A | N/A | N/A | N/A | 2024-01-22 | QTR3 | 23/24 | 2023-11-05 | QTR2 | 23/24 | 308 | 4172545.34 |  |  | 0 | 61 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3800 | 44851815201 | 2022-04-27 | QTR4 | 21/22 | 2 | 2 | 140 | 252 | 239 | 13 | 0 | 0 | 90 | 22 | 3545980 | 0 | 3545980 | 3707781 | 3707779 | 0 | 0 | 0 | 3707779 | 3707779 | 0 | 161801 | 35 | 0 | 22 | 93590 | 0 | 49 | 0 | 68210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 22 | 161801 | 0 | F593113094 | C & D CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-10-30 | QTR2 | 23/24 | 2023-08-28 | QTR1 | 23/24 | 308 | 3713438.76 |  |  | 0 | 6 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3802 | 44397315201 | 2022-03-30 | QTR3 | 21/22 | 1 | 0 | 188 | 257 | 266 | -9 | 9 | 0 | 69 | 0 | 6686744 | 66701 | 6620043 | 6686744 | 6712350 | -34074 | 0 | -34074 | 6678276 | 6731897 | 53621 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-28 | QTR3 | 23/24 | 2023-10-26 | QTR2 | 23/24 | 321 | 6875752.18 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3810 | 44365015201 | 2022-01-26 | QTR3 | 21/22 | 1 | 1 | 270 | 474 | 472 | 2 | 0 | 0 | 156 | 48 | 10527718 | 106380 | 10421339 | 10784785 | 11111656 | 0 | 0 | 0 | 11111656 | 11389685 | 278029 | 257067 | 87 | 5 | 0 | 0 | 0 | 0 | 48 | 274363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 48 | 276583 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 | 2023-08-02 | QTR1 | 23/24 | 313 | 10728439.32 |  |  | 0 | 58 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3811 | 22083845201 | 2022-01-26 | QTR3 | 21/22 | 1 | 2 | 245 | 532 | 532 | 0 | 0 | 0 | 203 | 84 | 1327870 | 50000 | 1277870 | 1607733 | 1467485 | 0 | 0 | 0 | 1467485 | 1187623 | 0 | 279863 | 210 | 0 | 84 | 279863 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 84 | 279863 | 10500 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-03-04 | QTR3 | 23/24 | 2023-09-22 | QTR1 | 23/24 | 313 | 2903300.5 |  |  | 0 | 47 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3812 | 44363915201 | 2022-05-25 | QTR4 | 21/22 | 1 | 1 | 245 | 417 | 416 | 1 | 0 | 0 | 157 | 15 | 13830550 | 119800 | 13710750 | 13861043 | 13971237 | 0 | 39808 | 39808 | 14011044 | 13698217 | -312827 | 30493 | 81 | 0 | 5 | 15466 | 0 | 0 | 10 | 46993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15 | 62459 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 | 2023-12-28 | QTR2 | 23/24 | 313 | 14936565.66 |  |  | 9 | 72 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3816 | 44563215201 | 2022-10-05 | QTR2 | 22/23 | 1 | 1 | 125 | 260 | 257 | 3 | 0 | 0 | 135 | 0 | 3430508 | 50000 | 3380508 | 3430508 | 3561896 | 0 | 0 | 0 | 3561896 | 3523880 | -38015 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 | 2023-10-09 | QTR2 | 23/24 | 314 | 3265522.73 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3817 | 44387515201 | 2022-08-31 | QTR1 | 22/23 | 1 | 2 | 60 | 246 | 246 | 0 | 0 | 0 | 156 | 30 | 535084 | 0 | 535084 | 538384 | 583904 | 0 | 0 | 0 | 583904 | 580604 | 0 | 3300 | 165 | 0 | 0 | 0 | 0 | 0 | 30 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 30 | 3300 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-10 | QTR3 | 23/24 | 2023-08-02 | QTR1 | 23/24 | 313 | 438194 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3818 | 44387615201 | 2022-10-05 | QTR2 | 22/23 | 1 | 0 | 75 | 150 | 150 | 0 | 0 | 0 | 75 | 0 | 287504 | 20245 | 267260 | 287504 | 255356 | 0 | 0 | 0 | 255356 | 255356 | 0 | 0 | 27 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-01-18 | QTR3 | 23/24 | 2023-09-07 | QTR1 | 23/24 | 314 | 449141.81 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3819 | 44404315201 | 2022-08-31 | QTR1 | 22/23 | 1 | 1 | 110 | 251 | 251 | 0 | 0 | 0 | 121 | 20 | 2236764 | 50000 | 2186764 | 2317147 | 2391790 | 0 | 0 | 0 | 2391790 | 2391790 | 0 | 80383 | 90 | 0 | 0 | 0 | 0 | 0 | 20 | 80383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 80383 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-13 | QTR3 | 23/24 | 2023-09-11 | QTR1 | 23/24 | 314 | 1726155.21 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3823 | 44565615201 | 2023-01-25 | QTR3 | 22/23 | 1 | 0 | 110 | 120 | 86 | 34 | 0 | 0 | 10 | 0 | 2199429 | 50000 | 2149429 | 2199429 | 2316440 | 0 | 0 | 0 | 2316440 | 2316440 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-08-16 | QTR1 | 23/24 | 2023-06-22 | QTR4 | 22/23 | 308 | 2955598 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3825 | 44565715201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 89 | 101 | 67 | 34 | 0 | 0 | 12 | 0 | 1398733 | 50000 | 1348733 | 1398733 | 1268603 | 0 | 0 | 0 | 1268603 | 1268603 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F824750393 | COLLINS LAND SERVICES INC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-08-21 | QTR1 | 23/24 | 321 | 2259061 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3828 | 44404415201 | 2022-02-23 | QTR3 | 21/22 | 1 | 0 | 90 | 183 | 168 | 15 | 0 | 0 | 93 | 0 | 1388656 | 50000 | 1338656 | 1388656 | 1401865 | 0 | 0 | 0 | 1401865 | 1401865 | 0 | 0 | 53 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | F432094655 | H.G. CONSTRUCTION DEVELOPMENT & INVESTM | N/A | N/A | N/A | N/A | 2023-12-21 | QTR2 | 23/24 | 2022-10-26 | QTR2 | 22/23 | 313 | 1545933 |  |  | 0 | 12 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3830 | 43256615201 | 2022-04-27 | QTR4 | 21/22 | 1 | 0 | 180 | 290 | 288 | 2 | 0 | 0 | 110 | 0 | 3353932 | 50000 | 3303932 | 3353932 | 3387610 | 0 | 0 | 0 | 3387610 | 3371222 | -16388 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-01-10 | QTR3 | 23/24 | 2023-07-16 | QTR1 | 23/24 | 308 | 3164048.08 |  |  | 0 | 43 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3833 | 44560315201 | 2022-08-31 | QTR1 | 22/23 | 1 | 0 | 44 | 49 | 45 | 4 | 0 | 0 | 5 | 0 | 192351 | 8394 | 183958 | 192351 | 176477 | 0 | 0 | 0 | 176477 | 176477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 0 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2022-12-22 | QTR2 | 22/23 | 308 | 173499.64 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3836 | 43974415201 | 2022-10-05 | QTR2 | 22/23 | 1 | 0 | 169 | 238 | 238 | 0 | 0 | 0 | 69 | 0 | 4469056 | 50000 | 4419056 | 4469056 | 4076218 | 0 | 0 | 0 | 4076218 | 3952664 | -123554 | 0 | 30 | 0 | 0 | 3365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3365 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2023-08-21 | QTR1 | 23/24 | 314 | 6832323.6 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T3848 | 43776215201 | 2022-06-15 | QTR4 | 21/22 | 2 | 1 | 150 | 309 | 309 | 0 | 0 | 0 | 143 | 16 | 2961906 | 50000 | 2911906 | 2971384 | 2833242 | 0 | 50000 | 50000 | 2883242 | 2818993 | -64250 | 9478 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 3118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 9478 | 9478 | 0 | 0 | 0 | 0 | 70 | 16 | 12596 | 9478 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-13 | QTR3 | 23/24 | 2023-10-04 | QTR2 | 23/24 | 314 | 3042412.27 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9024 | 44199335223 | 2021-04-28 | QTR4 | 20/21 | 1 | 2 | 250 | 622 | 620 | 2 | 0 | 0 | 372 | 0 | 3198515 | 50000 | 3148515 | 3289097 | 3304055 | 0 | 0 | 0 | 3304055 | 3304055 | 39515 | 90582 | 322 | 90 | 0 | 6000 | 0 | 90 | 0 | 49780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11300 | 0 | 0 | 0 | 58960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 300 | 0 | 126040 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 | 2023-06-08 | QTR4 | 22/23 | 314 | 3552350.22 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9027 | 44531315215 | 2021-10-27 | QTR2 | 21/22 | 1 | 1 | 60 | 71 | 71 | 0 | 0 | 0 | 11 | 0 | 564819 | 36905 | 527914 | 564819 | 524793 | 0 | 0 | 0 | 524793 | 524793 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593541899 | ACME BARRICADES LC | N/A | N/A | N/A | N/A | 2024-01-10 | QTR3 | 23/24 | 2022-05-13 | QTR4 | 21/22 | 306 | 932089.13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | CO
03CO | 03 | T9029 | 44531325216 | 2022-03-30 | QTR3 | 21/22 | 1 | 0 | 150 | 258 | 258 | 0 | 0 | 0 | 108 | 0 | 2718412 | 50000 | 2668412 | 2718412 | 2266906 | 0 | 0 | 0 | 2266906 | 2266906 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 6123 | 0 | F590879719 | INGRAM SIGNALIZATION INC. | N/A | N/A | N/A | N/A | 2024-01-22 | QTR3 | 23/24 | 2023-10-30 | QTR2 | 23/24 | 308 | 2758180.6 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
03DO | 03 | E3S70 | 43992635201 | 2021-05-13 | QTR4 | 20/21 | 2 | 1 | 395 | 597 | 597 | 0 | 0 | 0 | 202 | 0 | 8497804 | 70195 | 8427609 | 8518932 | 8878921 | 0 | 0 | 0 | 8878921 | 8997063 | 136935 | 21128 | 102 | 0 | 0 | 12464 | 0 | 30 | 0 | 28861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 96 | 0 | 41325 | 0 | F593458160 | HALE CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-09-19 | QTR1 | 23/24 | 2023-03-30 | QTR3 | 22/23 | 321 | 7939245.14 |  |  | 0 | 49 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3T49 | 44546515201 | 2020-07-09 | QTR1 | 20/21 | 1 | 0 | 90 | 134 | 151 | -17 | 17 | 0 | 35 | 9 | 1331980 | 50000 | 1281980 | 1331980 | 1360250 | -28730 | 12500 | -16230 | 1344020 | 1331520 | -12500 | 0 | 19 | 0 | 0 | 810 | 0 | 0 | 9 | 15261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 16071 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-04-30 | QTR4 | 23/24 | 2021-04-13 | QTR4 | 20/21 | 321 | 1383418.94 | B10 | ACC - BONUS/INCENT/DISINCENT | 9 | 16 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U04 | 21904225201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 65 | 65 | 45 | 20 | 0 | 0 | 0 | 0 | 278090 | 21110 | 256980 | 278090 | 249120 | 0 | 0 | 0 | 249120 | 249120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2023-05-18 | QTR4 | 22/23 | 314 | 454253.61 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U32 | 42187425201 | 2022-01-13 | QTR3 | 21/22 | 1 | 0 | 45 | 55 | 52 | 3 | 0 | 0 | 10 | 0 | 109495 | 5918 | 103577 | 109495 | 105102 | 0 | 0 | 0 | 105102 | 105102 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2022-06-09 | QTR4 | 21/22 | 308 | 135676.68 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U47 | 44158915201 | 2021-11-10 | QTR2 | 21/22 | 2 | 3 | 285 | 527 | 526 | 1 | 0 | 0 | 242 | 0 | 6190992 | 53456 | 6137537 | 6194018 | 6101074 | -18750 | 0 | -18750 | 6082324 | 6229251 | 146927 | 3025 | 162 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 0 | 3025 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-10-11 | QTR2 | 23/24 | 2023-08-02 | QTR1 | 23/24 | 308 | 5430315.21 |  |  | 0 | 71 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U83 | 41768355201 | 2022-07-14 | QTR1 | 22/23 | 1 | 0 | 200 | 401 | 414 | -13 | 13 | 0 | 201 | 0 | 2363976 | 50000 | 2313976 | 2363976 | 2188042 | -22022 | 0 | -22022 | 2166020 | 2166020 | 0 | 0 | 121 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2024-04-30 | QTR4 | 23/24 | 2024-01-29 | QTR3 | 23/24 | 308 | 2795459.35 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U84 | 44365915201 | 2022-02-10 | QTR3 | 21/22 | 2 | 1 | 175 | 266 | 264 | 2 | 0 | 0 | 91 | 0 | 3254371 | 50000 | 3204371 | 3263484 | 3285954 | 0 | 0 | 0 | 3285954 | 3378196 | 92242 | 9113 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12130 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-07-25 | QTR1 | 23/24 | 2023-02-18 | QTR3 | 22/23 | 308 | 3044605.63 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3U86 | 22068525201 | 2023-03-09 | QTR3 | 22/23 | 1 | 0 | 45 | 58 | 58 | 0 | 0 | 0 | 13 | 0 | 148273 | 10291 | 137982 | 148273 | 131932 | 0 | 0 | 0 | 131932 | 131932 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F943481793 | FAITH CONSTRUCTION GROUP INC. | N/A | N/A | N/A | N/A | 2024-03-04 | QTR3 | 23/24 | 2023-09-18 | QTR1 | 23/24 | 313 | 216110.85 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V28 | 44891215201 | 2023-05-11 | QTR4 | 22/23 | 1 | 1 | 85 | 161 | 161 | 0 | 0 | 0 | 68 | 8 | 586983 | 50000 | 536983 | 689291 | 616073 | 0 | 0 | 0 | 616073 | 616073 | 0 | 102308 | 42 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 102308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 102308 | 0 | F202058265 | STRUCTURAL PRESERVATION SYSTEMS | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 | 2024-03-07 | QTR3 | 23/24 | 308 | 1050080.3 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V33 | 44891315201 | 2023-01-12 | QTR3 | 22/23 | 1 | 0 | 75 | 80 | 53 | 27 | 0 | 0 | 5 | 0 | 223976 | 14236 | 209740 | 223976 | 187027 | 0 | 0 | 0 | 187027 | 187027 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-06-01 | QTR4 | 22/23 | 308 | 298951.28 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V50 | 42543655201 | 2022-08-18 | QTR1 | 22/23 | 1 | 0 | 250 | 324 | 218 | 106 | 0 | 0 | 74 | 0 | 3247610 | 50000 | 3197610 | 3247610 | 2860191 | 0 | 0 | 0 | 2860191 | 2860191 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2024-01-18 | QTR3 | 23/24 | 2023-06-21 | QTR4 | 22/23 | 314 | 6703766.52 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V51 | 44538525201 | 2022-06-09 | QTR4 | 21/22 | 1 | 0 | 90 | 106 | 105 | 1 | 0 | 0 | 16 | 0 | 396162 | 23977 | 372186 | 396162 | 353103 | 0 | 0 | 0 | 353103 | 353103 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2024-01-18 | QTR3 | 23/24 | 2022-12-21 | QTR2 | 22/23 | 314 | 736200.83 |  |  | 0 | 5 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3V90 | 44575815201 | 2023-01-12 | QTR3 | 22/23 | 1 | 1 | 70 | 78 | 77 | 1 | 0 | 0 | 8 | 0 | 1499653 | 50000 | 1449653 | 1499653 | 1534493 | 0 | 0 | 0 | 1534493 | 1534493 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2023-10-02 | QTR2 | 23/24 | 2023-06-27 | QTR4 | 22/23 | 308 | 1524311.21 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W08 | 22282725201 | 2023-05-11 | QTR4 | 22/23 | 1 | 0 | 90 | 100 | 71 | 29 | 0 | 0 | 10 | 0 | 553641 | 39372 | 514269 | 553641 | 509921 | 0 | 0 | 0 | 509921 | 509921 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2024-01-18 | QTR3 | 23/24 | 2023-10-30 | QTR2 | 23/24 | 313 | 848184.9 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W56 | 45102915201 | 2023-04-13 | QTR4 | 22/23 | 1 | 0 | 80 | 87 | 79 | 8 | 0 | 0 | 7 | 0 | 208278 | 11765 | 196514 | 208278 | 193768 | 0 | 0 | 0 | 193768 | 193768 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F742454910 | WEBBER LLC | N/A | N/A | N/A | N/A | 2024-02-01 | QTR3 | 23/24 | 2023-11-07 | QTR2 | 23/24 | 308 | 247061.64 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
03DO | 03 | E3W98 | 45055015201 | 2023-08-10 | QTR1 | 23/24 | 1 | 0 | 60 | 94 | 82 | 12 | 0 | 0 | 34 | 0 | 123579 | 5912 | 117667 | 123579 | 121257 | 0 | 0 | 0 | 121257 | 121257 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3211 | 0 | F842662495 | ALEXANDER DESIGN + BUILD LLC | N/A | N/A | N/A | N/A | 2024-03-20 | QTR3 | 23/24 | 2024-02-06 | QTR3 | 23/24 | 321 | 124155.84 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04CO | 04 | T4552 | 43696215201 | 2020-05-20 | QTR4 | 19/20 | 2 | 14 | 642 | 1093 | 1084 | 9 | 0 | 0 | 445 | 6 | 26406739 | 150000 | 26256739 | 27530140 | 27615738 | 0 | 0 | 0 | 27615738 | 28097247 | 1507029 | 1123402 | 284 | 0 | 0 | 40935 | 0 | 110 | 0 | 428405 | 32084 | 0 | 0 | 0 | 0 | 0 | 0 | -103477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223929 | 0 | 0 | 0 | 320493 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 11175 | 0 | 0 | 0 | 308488 | 0 | 0 | 6 | 42593 | 42593 | 23 | 0 | 0 | 0 | 280 | 6 | 1272542 | 74677 | F812774010 | LEAD ENGINEERING CONTRACTORS LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-09-08 | QTR1 | 23/24 | 412 | 27323787.5 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 51 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4562 | 43177035201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 384 | 492 | 492 | 0 | 0 | 0 | 108 | 0 | 3588218 | 50000 | 3538218 | 3660295 | 3546957 | 0 | 0 | 0 | 3546957 | 3613971 | 67014 | 72077 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 91148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14596 | 0 | 0 | 0 | 94541 | 0 | F650434021 | HORIZON CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2023-03-31 | QTR3 | 22/23 | 412 | 3732217.16 |  |  | 0 | 37 | 0 | 0 | -11203 | 0 |  | CO
04CO | 04 | T4563 | 43619615201 | 2021-05-26 | QTR4 | 20/21 | 3 | 3 | 466 | 687 | 687 | 0 | 0 | 0 | 221 | 0 | 3377160 | 49980 | 3327180 | 3518499 | 3553166 | 0 | 0 | 0 | 3553166 | 3602214 | 88570 | 141339 | 173 | 0 | 0 | 5620 | 0 | 0 | 0 | 112295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2406 | 0 | 0 | 0 | 54041 | 0 | 0 | 0 | 0 | 0 | 76 | 0 | 5325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 0 | 179687 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2024-01-23 | QTR3 | 23/24 | 2023-06-23 | QTR4 | 22/23 | 412 | 3569811.06 |  |  | 0 | 48 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4567 | 43839415201 | 2021-05-26 | QTR4 | 20/21 | 3 | 2 | 388 | 574 | 574 | 0 | 0 | 0 | 186 | 0 | 2505478 | 50000 | 2455478 | 2517687 | 2397524 | 0 | 0 | 0 | 2397524 | 2420702 | 167234 | 12209 | 70 | 0 | 0 | 10842 | 0 | 0 | 0 | 23398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6534 | 0 | 0 | 0 | 1247 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 8119 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 50141 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-10-03 | QTR2 | 23/24 | 2023-06-08 | QTR4 | 22/23 | 409 | 2223138.08 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4571 | 43839515201 | 2021-01-27 | QTR3 | 20/21 | 2 | 5 | 575 | 701 | 701 | 0 | 0 | 0 | 126 | 0 | 2029422 | 50000 | 1979422 | 2048533 | 1920549 | 0 | 0 | 0 | 1920549 | 1968644 | 49459 | 19111 | 81 | 0 | 0 | 1911 | 0 | 0 | 0 | 3545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17675 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-06-16 | QTR4 | 22/23 | 409 | 2213111.22 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4572 | 43838415201 | 2021-01-27 | QTR3 | 20/21 | 1 | 1 | 454 | 621 | 611 | 10 | 0 | 0 | 167 | 0 | 2952231 | 50000 | 2902231 | 2953979 | 2876141 | 0 | 0 | 0 | 2876141 | 2874393 | 28318 | 1748 | 122 | 0 | 0 | 7776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 9524 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-07-24 | QTR1 | 23/24 | 409 | 3045126.89 |  |  | 0 | 45 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4573 | 43206675201 | 2021-07-28 | QTR1 | 21/22 | 2 | 3 | 195 | 470 | 465 | 5 | 0 | 0 | 275 | 0 | 3496673 | 50000 | 3446673 | 3721036 | 3515537 | 0 | 0 | 0 | 3515537 | 3603841 | 88304 | 224363 | 249 | 0 | 0 | -2094 | 0 | 0 | 0 | 267470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 265376 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-08-29 | QTR1 | 23/24 | 2023-04-19 | QTR4 | 22/23 | 412 | 3657623.88 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4579 | 44166815201 | 2021-04-28 | QTR4 | 20/21 | 3 | 6 | 480 | 808 | 805 | 3 | 0 | 0 | 328 | 0 | 12487000 | 142304 | 12344696 | 12883748 | 12540269 | 0 | 0 | 0 | 12540269 | 13525650 | 1012442 | 432553 | 276 | 0 | 0 | 6397 | 0 | 0 | 0 | 164863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168610 | 68909 | 0 | 0 | 87581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454512 | 68909 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-03-08 | QTR3 | 23/24 | 2023-09-28 | QTR1 | 23/24 | 412 | 14492192.77 |  |  | 0 | 52 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4586 | 42957625201 | 2021-09-29 | QTR1 | 21/22 | 5 | 3 | 351 | 638 | 638 | 0 | 0 | 0 | 280 | 7 | 4581957 | 50000 | 4531957 | 4683431 | 4520450 | 0 | 0 | 0 | 4520450 | 4522418 | 5386 | 101474 | 218 | 0 | 0 | 25903 | 0 | 0 | 11 | 98213 | 2552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11541 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 3418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 11 | 139075 | 2552 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 | 2024-01-11 | QTR3 | 23/24 | 412 | 4567139.47 |  |  | 7 | 40 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4591 | 43811815201 | 2022-01-26 | QTR3 | 21/22 | 2 | 4 | 269 | 478 | 478 | 0 | 0 | 0 | 209 | 21 | 2543608 | 50000 | 2493608 | 2702421 | 2682407 | 0 | 0 | 0 | 2682407 | 2681177 | 5915 | 208813 | 137 | 50 | 0 | 8822 | 0 | 0 | 0 | 139633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7145 | 0 | 0 | 0 | 21699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 177299 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 | 2023-08-17 | QTR1 | 23/24 | 412 | 2499977.01 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4592 | 43999415201 | 2021-12-08 | QTR2 | 21/22 | 3 | 2 | 316 | 443 | 442 | 1 | 0 | 0 | 67 | 60 | 2605697 | 50000 | 2555697 | 2718209 | 2649545 | 0 | 0 | 0 | 2649545 | 2756383 | 109912 | 112512 | 42 | 0 | 39 | 109438 | 70107 | 0 | 21 | 5837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 118349 | 70107 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-04-03 | QTR4 | 23/24 | 2023-06-27 | QTR4 | 22/23 | 412 | 2812232.39 |  |  | 21 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4594 | 43999015201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 212 | 352 | 351 | 1 | 0 | 0 | 140 | 0 | 2000000 | 50000 | 1950000 | 2008938 | 1868868 | 0 | 0 | 0 | 1868868 | 1862040 | 2110 | 8938 | 85 | 0 | 0 | 11450 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 20388 | 0 | F650814419 | ZAHLENE ENTERPRISES INC | N/A | N/A | N/A | N/A | 2023-07-24 | QTR1 | 23/24 | 2023-05-31 | QTR4 | 22/23 | 412 | 2421037.86 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4597 | 44177515201 | 2022-01-26 | QTR3 | 21/22 | 2 | 1 | 178 | 274 | 274 | 0 | 0 | 0 | 96 | 0 | 957661 | 40792 | 916869 | 958736 | 900445 | 0 | 0 | 0 | 900445 | 899370 | 0 | 1075 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 8111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 9186 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-05-11 | QTR4 | 22/23 | 409 | 927528.71 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4601 | 44177115201 | 2022-04-27 | QTR4 | 21/22 | 2 | 0 | 172 | 266 | 266 | 0 | 0 | 0 | 94 | 0 | 1248248 | 50000 | 1198248 | 1248248 | 1203185 | 0 | 0 | 0 | 1203185 | 1200343 | -2841 | 0 | 68 | 0 | 0 | 1296 | 0 | 0 | 0 | 16795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18092 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-13 | QTR3 | 23/24 | 2024-01-24 | QTR3 | 23/24 | 412 | 1328803.72 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4603 | 44157815201 | 2022-03-30 | QTR3 | 21/22 | 3 | 0 | 229 | 338 | 338 | 0 | 0 | 0 | 109 | 0 | 2249738 | 50000 | 2199738 | 2249738 | 2253443 | 0 | 0 | 0 | 2253443 | 2251225 | -2218 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-09 | QTR2 | 23/24 | 2023-08-09 | QTR1 | 23/24 | 412 | 2503871.57 |  |  | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4607 | 43999315201 | 2022-03-30 | QTR3 | 21/22 | 3 | 1 | 222 | 287 | 287 | 0 | 0 | 0 | 65 | 0 | 1967721 | 50000 | 1917721 | 1967721 | 1856962 | 0 | 0 | 0 | 1856962 | 1856374 | 2046 | 2634 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6840 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2023-09-18 | QTR1 | 23/24 | 2023-04-30 | QTR4 | 22/23 | 412 | 2135578.09 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4608 | 44177615201 | 2022-01-26 | QTR3 | 21/22 | 1 | 3 | 374 | 514 | 514 | 0 | 0 | 0 | 140 | 0 | 3370284 | 50000 | 3320284 | 3030235 | 2923805 | 0 | 0 | 0 | 2923805 | 2936404 | 12599 | -340049 | 80 | 0 | 0 | 72006 | 65186 | 0 | 0 | -397641 | 3779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | -325635 | 68965 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 | 2024-01-05 | QTR3 | 23/24 | 409 | 2521290.97 |  |  | 0 | 44 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4609 | 44384515201 | 2022-04-27 | QTR4 | 21/22 | 3 | 1 | 169 | 353 | 353 | 0 | 0 | 0 | 184 | 0 | 2057691 | 50000 | 2007691 | 2108795 | 2355080 | 0 | 0 | 0 | 2355080 | 2350900 | -4180 | 51105 | 143 | 0 | 0 | 92472 | 0 | 15 | 0 | 8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 100999 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-06-12 | QTR4 | 23/24 | 2024-02-23 | QTR3 | 23/24 | 412 | 2121963.38 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4614 | 44399415201 | 2022-04-27 | QTR4 | 21/22 | 2 | 3 | 227 | 321 | 321 | 0 | 0 | 0 | 94 | 0 | 4491996 | 50000 | 4441996 | 4563991 | 4393362 | 0 | 0 | 0 | 4393362 | 4376466 | -6110 | 71995 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 86648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51997 | 0 | 0 | 0 | 5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10786 | 0 | 0 | 0 | 33274 | 33274 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 83947 | 33274 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-06-14 | QTR4 | 22/23 | 409 | 4062646.65 |  |  | 0 | 26 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4628 | 44061275201 | 2023-02-22 | QTR3 | 22/23 | 1 | 0 | 126 | 160 | 142 | 18 | 0 | 0 | 34 | 0 | 1125012 | 41897 | 1083114 | 1125012 | 994908 | 0 | 0 | 0 | 994908 | 994009 | -899 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F455312119 | THE STOUT GROUP LLC | N/A | N/A | N/A | N/A | 2024-03-29 | QTR3 | 23/24 | 2024-01-16 | QTR3 | 23/24 | 409 | 879841.48 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
04CO | 04 | T4629 | 44562315201 | 2022-12-07 | QTR2 | 22/23 | 1 | 0 | 122 | 127 | 107 | 20 | 0 | 0 | 5 | 0 | 1050673 | 49045 | 1001629 | 1050673 | 985015 | 0 | 0 | 0 | 985015 | 985015 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-06 | QTR2 | 23/24 | 2023-10-30 | QTR2 | 23/24 | 409 | 1029940.35 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | CO
04DO | 04 | E4T68 | 44074615201 | 2020-05-06 | QTR4 | 19/20 | 6 | 1 | 730 | 939 | 934 | 5 | 0 | 0 | 209 | 0 | 17557323 | 125751 | 17431572 | 17588765 | 16726429 | 0 | 0 | 0 | 16726429 | 16980455 | 254025 | 31442 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31442 | 0 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37742 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-06 | QTR1 | 23/24 | 2023-02-02 | QTR3 | 22/23 | 412 | 12972092.8 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4U99 | 44146215201 | 2021-05-07 | QTR4 | 20/21 | 1 | 8 | 228 | 525 | 518 | 7 | 0 | 0 | 188 | 109 | 12200214 | 101674 | 12098540 | 13805766 | 14066534 | 0 | 0 | 0 | 14066534 | 14068003 | 140138 | 1605552 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 1129185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 448054 | 0 | 0 | 0 | 23731 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 109 | 1600970 | 0 | F203598843 | PCL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-06-23 | QTR4 | 22/23 | 412 | 10374505.8 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V19 | 43215215201 | 2022-01-07 | QTR3 | 21/22 | 1 | 0 | 307 | 326 | 171 | 155 | 0 | 0 | 19 | 0 | 2335539 | 50000 | 2285539 | 2335539 | 2159702 | 0 | 0 | 0 | 2159702 | 2159702 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-11-20 | QTR2 | 23/24 | 2023-10-25 | QTR2 | 23/24 | 409 | 4011283.36 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V21 | 44399715201 | 2022-02-04 | QTR3 | 21/22 | 1 | 0 | 210 | 248 | 246 | 2 | 0 | 0 | 38 | 0 | 2500423 | 50000 | 2450423 | 2500423 | 2294866 | 0 | 0 | 0 | 2294866 | 2323183 | 28317 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 5415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5415 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-04-29 | QTR4 | 23/24 | 2023-12-18 | QTR2 | 23/24 | 408 | 2332741.9 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V26 | 44172115201 | 2021-12-03 | QTR2 | 21/22 | 2 | 1 | 229 | 349 | 343 | 6 | 0 | 0 | 120 | 0 | 1821552 | 50000 | 1771552 | 1857400 | 1793427 | 0 | 0 | 0 | 1793427 | 1797474 | 4047 | 35848 | 62 | 0 | 0 | 35848 | 3011 | 19 | 0 | 38415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 74263 | 3011 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-01-25 | QTR3 | 23/24 | 2023-07-31 | QTR1 | 23/24 | 412 | 1667424.49 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V55 | 44359415201 | 2022-05-06 | QTR4 | 21/22 | 1 | 1 | 127 | 224 | 221 | 3 | 0 | 0 | 97 | 0 | 895596 | 50000 | 845596 | 965406 | 917671 | 0 | 0 | 0 | 917671 | 917671 | 0 | 69810 | 62 | 0 | 0 | 69810 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 69810 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2023-11-15 | QTR2 | 23/24 | 2023-07-15 | QTR1 | 23/24 | 412 | 1122910.5 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V59 | 44136015201 | 2022-03-04 | QTR3 | 21/22 | 3 | 5 | 398 | 525 | 522 | 3 | 0 | 0 | 165 | -38 | 6377644 | 54489 | 6323155 | 6402875 | 6172746 | 0 | 0 | 0 | 6172746 | 6337235 | 164489 | 25231 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 218069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38 | 79377 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2024-05-06 | QTR4 | 23/24 | 2023-11-20 | QTR2 | 23/24 | 412 | 5443223.47 |  |  | 0 | 31 | 0 | -38 | -138692 | 0 |  | DO
04DO | 04 | E4V75 | 44172215201 | 2022-02-04 | QTR3 | 21/22 | 2 | 4 | 156 | 248 | 248 | 0 | 0 | 0 | 92 | 0 | 1455255 | 50000 | 1405255 | 1515282 | 1451281 | 0 | 0 | 0 | 1451281 | 1452112 | 7917 | 60027 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 76040 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 85192 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-09-01 | QTR1 | 23/24 | 2023-03-28 | QTR3 | 22/23 | 409 | 1403378.89 |  |  | 0 | 13 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V81 | 44610115201 | 2022-10-07 | QTR2 | 22/23 | 4 | 3 | 148 | 247 | 247 | 0 | 0 | 0 | 99 | 0 | 3843000 | 50000 | 3793000 | 3930369 | 3945848 | 0 | 0 | 0 | 3945848 | 3942412 | -3437 | 87369 | 57 | 0 | 0 | 0 | 0 | 26 | 0 | 87369 | 77301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6749 | 0 | 0 | 0 | 4512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 98630 | 77301 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-06-10 | QTR4 | 23/24 | 2024-02-05 | QTR3 | 23/24 | 409 | 3910539.99 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4V84 | 44609715201 | 2022-09-02 | QTR1 | 22/23 | 1 | 1 | 133 | 180 | 179 | 1 | 0 | 0 | 47 | 0 | 3147147 | 50000 | 3097147 | 3153188 | 2965886 | 0 | 0 | 0 | 2965886 | 2896248 | -69638 | 6041 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6041 | 0 | F201928479 | J.W. CHEATHAM LLC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-08-03 | QTR1 | 23/24 | 409 | 3652108.96 | B1 | ACC - NO EXCUSE BONUS | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W04 | 45059015201 | 2022-06-14 | QTR4 | 21/22 | 1 | 0 | 182 | 209 | 209 | 0 | 0 | 0 | 27 | 0 | 1468626 | 50000 | 1418626 | 1468626 | 1421948 | 0 | 0 | 0 | 1421948 | 1421948 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F651005943 | LAMBERT BROS. INC. | N/A | N/A | N/A | N/A | 2023-11-20 | QTR2 | 23/24 | 2023-10-25 | QTR2 | 23/24 | 408 | 2551166.8 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W14 | 44577015201 | 2023-01-06 | QTR3 | 22/23 | 1 | 0 | 227 | 332 | 330 | 2 | 0 | 0 | 105 | 0 | 4294622 | 50000 | 4244622 | 4294622 | 4411466 | 0 | 0 | 0 | 4411466 | 4411466 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 47374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47374 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 | 2024-04-16 | QTR4 | 23/24 | 412 | 4978122.09 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | DO
04DO | 04 | E4W41 | 44576915201 | 2023-01-06 | QTR3 | 22/23 | 1 | 2 | 196 | 235 | 235 | 0 | 0 | 0 | 39 | 0 | 4444623 | 50000 | 4394623 | 4539611 | 4542613 | 0 | 225000 | 225000 | 4767613 | 4542438 | -225175 | 94987 | 33 | 0 | 0 | 20337 | 0 | 0 | 0 | 10823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126147 | 0 | F462302687 | JONES BENITEZ CORPORATION | N/A | N/A | N/A | N/A | 2024-02-22 | QTR3 | 23/24 | 2023-11-09 | QTR2 | 23/24 | 409 | 4468546.98 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 6 | 0 | 0 | 0 | 0 |  | DO
05CO | 05 | T5552 | 40714345201 | 2016-06-08 | QTR4 | 15/16 | 21 | 32 | 1050 | 1826 | 1829 | -3 | 3 | 0 | 359 | 417 | 75824482 | 160000 | 75664482 | 86884143 | 89837352 | 0 | 0 | 0 | 89837352 | 90458012 | 815723 | 10910761 | 209 | 0 | 13 | 563442 | 81716 | 0 | 113 | 3719605 | 1534190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | -46035 | 0 | 0 | 0 | 107943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189623 | 0 | 0 | 0 | 6200000 | 0 | 0 | 36 | 207976 | 207976 | 0 | 0 | 0 | 0 | 0 | 417 | 10835624 | 1823881 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2021-10-13 | QTR2 | 21/22 | 509 | 88197361.71 | B2:B2:B5:B:B:B7 | ACC - A+B (COST+TIME BIDDING):ACC - A+B (COST+TIME BIDDING):ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - A+B/BONUS:ACC - A+B/BONUS | 0 | 150 | 0 | 0 | -106929 | 0 |  | CO
05CO | 05 | T5626 | 24020025201 | 2017-12-06 | QTR2 | 17/18 | 8 | 23 | 1454 | 2090 | 2089 | 1 | 0 | 0 | 376 | 260 | 108299973 | 155000 | 108144973 | 115225015 | 116585814 | 0 | 0 | 0 | 116585814 | 117462578 | 1572381 | 6683848 | 186 | 0 | 260 | 4333446 | 8284 | 0 | 0 | 1863531 | 48189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 6294756 | 56473 | Z04-1543470 | LIBERTY MUTUAL INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 | 2023-12-19 | QTR2 | 23/24 | 507 | 150691414.85 |  |  | 0 | 190 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5705 | 44113615201 | 2021-05-26 | QTR4 | 20/21 | 3 | 10 | 310 | 653 | 651 | 2 | 0 | 0 | 281 | 62 | 15404884 | 150000 | 15254884 | 16605228 | 17046359 | 0 | 0 | 0 | 17046359 | 17998317 | 1051871 | 1200344 | 221 | 0 | 0 | 619876 | 0 | 0 | 0 | 257299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 420621 | 0 | 0 | 42 | 13057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1321179 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-14 | QTR3 | 23/24 | 2023-08-07 | QTR1 | 23/24 | 512 | 17500000.26 |  |  | 21 | 60 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5726 | 44354415201 | 2022-03-30 | QTR3 | 21/22 | 2 | 0 | 120 | 347 | 347 | 0 | 0 | 0 | 227 | 0 | 1057650 | 26700 | 1030950 | 1057650 | 1051826 | 0 | 0 | 0 | 1051826 | 1051826 | 0 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 6240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25040 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-02-14 | QTR3 | 23/24 | 2024-01-04 | QTR3 | 23/24 | 514 | 838159.94 |  |  | 0 | 70 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5733 | 44381515201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 290 | 440 | 439 | 1 | 0 | 0 | 130 | 20 | 7387943 | 81000 | 7306943 | 7578305 | 6929112 | 0 | 0 | 0 | 6929112 | 7638830 | 716998 | 190361 | 50 | 0 | 20 | 183081 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 190361 | 436 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2023-04-17 | QTR4 | 22/23 | 513 | 8754090.28 |  |  | 0 | 80 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5737 | 44288115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 140 | 343 | 342 | 1 | 0 | 0 | 203 | 0 | 1605048 | 49058 | 1555990 | 1606653 | 1573163 | 0 | 0 | 0 | 1573163 | 1576898 | 3735 | 1605 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-11-30 | QTR2 | 23/24 | 2023-07-21 | QTR1 | 23/24 | 514 | 1288583.85 |  |  | 0 | 137 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5738 | 44290915201 | 2021-12-08 | QTR2 | 21/22 | 1 | 1 | 270 | 349 | 349 | 0 | 0 | 0 | 79 | 0 | 9861239 | 100000 | 9761239 | 9880239 | 9803603 | 0 | 0 | 0 | 9803603 | 10869062 | 1065459 | 19000 | 40 | 0 | 0 | 5350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24350 | 0 | F592147362 | V.A. PAVING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-02-28 | QTR3 | 22/23 | 514 | 13653415.96 |  |  | 0 | 39 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5742 | 43612515201 | 2022-02-23 | QTR3 | 21/22 | 2 | 4 | 250 | 445 | 445 | 0 | 0 | 0 | 174 | 21 | 4343701 | 50000 | 4293701 | 4496683 | 4615463 | 0 | 0 | 0 | 4615463 | 4641212 | 25749 | 152983 | 113 | 0 | 0 | 29867 | 0 | 0 | 42 | 133723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 172975 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2024-05-03 | QTR4 | 23/24 | 2024-02-01 | QTR3 | 23/24 | 514 | 4840790.03 |  |  | 21 | 61 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5746 | 43915715201 | 2022-05-25 | QTR4 | 21/22 | 2 | 1 | 200 | 308 | 308 | 0 | 0 | 0 | 83 | 25 | 1480640 | 50000 | 1430640 | 1481349 | 1525188 | 0 | 0 | 0 | 1525188 | 1522820 | -2368 | 709 | 49 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-06-28 | QTR4 | 23/24 | 2024-02-23 | QTR3 | 23/24 | 514 | 1288917.65 |  |  | 25 | 31 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5750 | 44568415201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 130 | 168 | 168 | 0 | 0 | 0 | 14 | 24 | 966460 | 40500 | 925960 | 966460 | 931181 | 0 | 0 | 0 | 931181 | 930236 | -945 | 0 | 5 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-09 | QTR3 | 23/24 | 2023-11-03 | QTR2 | 23/24 | 515 | 970160.65 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5763 | 44569015201 | 2022-08-31 | QTR1 | 22/23 | 2 | 1 | 139 | 176 | 176 | 0 | 0 | 0 | 37 | 0 | 1690095 | 50000 | 1640095 | 1690972 | 1630216 | 0 | 0 | 0 | 1630216 | 1601935 | -27404 | 877 | 28 | 0 | 0 | 20792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21668 | 0 | F591233559 | HALIFAX PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 | 2023-09-11 | QTR1 | 23/24 | 513 | 2378838.75 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5765 | 43759625201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 190 | 217 | 198 | 19 | 0 | 0 | 27 | 0 | 1068776 | 38700 | 1030076 | 1068776 | 1003835 | 0 | 0 | 0 | 1003835 | 1003807 | -28 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F263013168 | MEJIA INTERNATIONAL GROUP CORPORATION | N/A | N/A | N/A | N/A | 2023-10-13 | QTR2 | 23/24 | 2023-08-29 | QTR1 | 23/24 | 512 | 1065459.45 |  |  | 0 | 8 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5766 | 44569515201 | 2022-10-05 | QTR2 | 22/23 | 1 | 0 | 170 | 190 | 188 | 2 | 0 | 0 | 16 | 4 | 1397100 | 50000 | 1347100 | 1397100 | 1188314 | 0 | 0 | 0 | 1188314 | 1188314 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 4 | 26312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 26312 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 | 2023-10-30 | QTR2 | 23/24 | 509 | 1256129.81 |  |  | 4 | 9 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5771 | 44316615201 | 2022-10-26 | QTR2 | 22/23 | 1 | 1 | 190 | 226 | 226 | 0 | 0 | 0 | 36 | 0 | 3891608 | 50000 | 3841608 | 3851608 | 3861679 | 0 | 0 | 0 | 3861679 | 3828346 | -33333 | -40000 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 19342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19342 | 0 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-03-22 | QTR3 | 23/24 | 2023-09-26 | QTR1 | 23/24 | 515 | 5132264.8 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5774 | 44568815201 | 2022-12-07 | QTR2 | 22/23 | 2 | 1 | 160 | 193 | 192 | 1 | 0 | 0 | 33 | 0 | 662662 | 40500 | 622162 | 662941 | 634436 | 0 | 0 | 0 | 634436 | 634157 | 0 | 279 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591858994 | TRAFFIC CONTROL DEVICES LLC | N/A | N/A | N/A | N/A | 2024-04-11 | QTR4 | 23/24 | 2023-12-17 | QTR2 | 23/24 | 512 | 863381 |  |  | 0 | 11 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5780 | 44585815201 | 2023-01-04 | QTR3 | 22/23 | 1 | 0 | 210 | 243 | 240 | 3 | 0 | 0 | 33 | 0 | 1654943 | 50000 | 1604943 | 1654943 | 1622200 | 0 | 0 | 0 | 1622200 | 1622200 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-06-14 | QTR4 | 23/24 | 2024-05-14 | QTR4 | 23/24 | 514 | 1788242.1 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5781 | 43713315201 | 2023-01-25 | QTR3 | 22/23 | 3 | 2 | 180 | 241 | 241 | 0 | 0 | 0 | 61 | 0 | 1838831 | 53750 | 1785081 | 1848822 | 1683358 | 0 | 0 | 0 | 1683358 | 1678146 | -5213 | 9991 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-04-24 | QTR4 | 23/24 | 2024-02-16 | QTR3 | 23/24 | 513 | 2056817.59 |  |  | 0 | 30 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T5785 | 44976515201 | 2023-03-29 | QTR3 | 22/23 | 1 | 0 | 150 | 203 | 203 | 0 | 0 | 0 | 53 | 0 | 527418 | 32500 | 494918 | 527418 | 510407 | 0 | 0 | 0 | 510407 | 510407 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11800 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-05-02 | QTR4 | 23/24 | 2024-04-09 | QTR4 | 23/24 | 506 | 916063.6 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
05CO | 05 | T9028 | 44532115223 | 2022-01-26 | QTR3 | 21/22 | 2 | 2 | 250 | 437 | 437 | 0 | 0 | 0 | 55 | 132 | 4468000 | 50000 | 4418000 | 4785216 | 5263219 | 0 | 0 | 0 | 5263219 | 5259180 | 0 | 317216 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 30874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30874 | 0 | F461727342 | TRAFFIC MANAGEMENT SOLUTIONS LL | N/A | N/A | N/A | N/A | 2024-05-03 | QTR4 | 23/24 | 2024-02-07 | QTR3 | 23/24 | 512 | 3979533.39 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | CO
05DO | 05 | E50B4 | 44290615201 | 2022-07-06 | QTR1 | 22/23 | 1 | 1 | 200 | 317 | 317 | 0 | 0 | 0 | 103 | 14 | 3079406 | 50000 | 3029406 | 3129406 | 3205711 | 0 | 0 | 0 | 3205711 | 3130395 | -75316 | 50000 | 26 | 0 | 0 | 3862 | 0 | 0 | 28 | 3528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 54904 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 | 2023-08-11 | QTR1 | 23/24 | 513 | 3825881.85 |  |  | 14 | 77 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51A0 | 43856235201 | 2021-02-16 | QTR3 | 20/21 | 2 | 2 | 470 | 814 | 814 | 0 | 0 | 0 | 293 | 51 | 14521514 | 150000 | 14371514 | 14674974 | 14758568 | 0 | 0 | 0 | 14758568 | 14990012 | 320347 | 153460 | 66 | 0 | 0 | 124159 | 0 | 11 | 113 | 118697 | 75961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 113 | 284283 | 75961 | F591616643 | NELSON DAVID CONSTRUCTION CO. | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 | 2023-08-11 | QTR1 | 23/24 | 515 | 15223948.66 |  |  | 51 | 216 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E51A9 | 44102015201 | 2020-09-01 | QTR1 | 20/21 | 1 | 7 | 280 | 534 | 544 | -10 | 10 | 0 | 225 | 29 | 7501367 | 72000 | 7429367 | 7798794 | 7531686 | -41316 | 0 | -41316 | 7490370 | 7740983 | 263750 | 297427 | 61 | 0 | 0 | 19197 | 0 | 0 | 29 | 278231 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 297427 | 5549 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2022-05-27 | QTR4 | 21/22 | 514 | 7321146.81 |  |  | 5 | 164 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E53B6 | 43901715201 | 2022-09-07 | QTR1 | 22/23 | 1 | 0 | 220 | 261 | 166 | 95 | 0 | 0 | 41 | 0 | 1640053 | 50000 | 1590053 | 1640053 | 1539808 | 0 | 0 | 0 | 1539808 | 1539808 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2023-11-01 | QTR2 | 23/24 | 2023-09-15 | QTR1 | 23/24 | 514 | 2062514.65 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E54B0 | 43986525201 | 2023-01-04 | QTR3 | 22/23 | 2 | 1 | 230 | 292 | 292 | 0 | 0 | 0 | 62 | 0 | 1188917 | 50000 | 1138917 | 1190920 | 1139015 | 0 | 0 | 0 | 1139015 | 1136823 | -189 | 2003 | 34 | 0 | 0 | 9833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9833 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-02-29 | QTR3 | 23/24 | 2024-01-18 | QTR3 | 23/24 | 513 | 1369687.25 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B1 | 43914215201 | 2022-12-06 | QTR2 | 22/23 | 1 | 1 | 280 | 384 | 384 | 0 | 0 | 0 | 74 | 30 | 6255758 | 68000 | 6187758 | 6282058 | 5782361 | 0 | 0 | 0 | 5782361 | 5745517 | -36845 | 26300 | 46 | 0 | 0 | 0 | 0 | 0 | 20 | 45289 | 17874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 57746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 103035 | 17874 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-06-05 | QTR4 | 23/24 | 2024-03-26 | QTR3 | 23/24 | 515 | 7312039.9 |  |  | 30 | 28 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B2 | 44417515201 | 2022-09-07 | QTR1 | 22/23 | 2 | 2 | 190 | 227 | 228 | -1 | 1 | 0 | 37 | 0 | 2868033 | 50000 | 2818033 | 2873478 | 2862070 | 0 | 0 | 0 | 2862070 | 2854258 | -2367 | 5445 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5445 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2024-06-25 | QTR4 | 23/24 | 2024-01-25 | QTR3 | 23/24 | 509 | 2740878.55 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B3 | 44942415201 | 2022-12-06 | QTR2 | 22/23 | 1 | 0 | 150 | 187 | 187 | 0 | 0 | 0 | 37 | 0 | 950694 | 34728 | 915966 | 950694 | 969481 | 0 | 0 | 0 | 969481 | 969481 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 | 2023-09-14 | QTR1 | 23/24 | 509 | 729303.27 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B4 | 44942515201 | 2022-11-01 | QTR2 | 22/23 | 1 | 0 | 170 | 174 | 149 | 25 | 0 | 0 | 4 | 0 | 967737 | 42032 | 925705 | 967737 | 851103 | 0 | 0 | 0 | 851103 | 851002 | -101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F521301361 | COASTAL GUNITE CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-09-06 | QTR1 | 23/24 | 2023-07-10 | QTR1 | 23/24 | 514 | 882686.9 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E55B9 | 44655815201 | 2022-10-11 | QTR2 | 22/23 | 2 | 1 | 130 | 243 | 243 | 0 | 0 | 0 | 112 | 1 | 1178485 | 48750 | 1129735 | 1182078 | 1222101 | 0 | 0 | 0 | 1222101 | 1216754 | -1755 | 3592 | 91 | 0 | 1 | 4476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4476 | 0 | F770603738 | WRANGLER CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-05-20 | QTR4 | 23/24 | 2023-10-18 | QTR2 | 23/24 | 513 | 1289085.95 |  |  | 1 | 21 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B2 | 44381615201 | 2022-11-01 | QTR2 | 22/23 | 1 | 0 | 270 | 321 | 321 | 0 | 0 | 0 | 51 | 0 | 3435770 | 50000 | 3385770 | 3435770 | 3371565 | 0 | 0 | 0 | 3371565 | 3338650 | -32915 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 0 | F731707896 | ATLANTIC CIVIL CONSTRUCTORS CORP | N/A | N/A | N/A | N/A | 2024-05-03 | QTR4 | 23/24 | 2024-03-25 | QTR3 | 23/24 | 509 | 4749444.93 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E56B4 | 44713515201 | 2023-04-04 | QTR4 | 22/23 | 1 | 0 | 170 | 195 | 195 | 0 | 0 | 0 | 25 | 0 | 939661 | 41955 | 897706 | 939661 | 899114 | 0 | 0 | 0 | 899114 | 899114 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F381164400 | RAM CONSTRUCTION SERVICES OF MICHIGAN I | N/A | N/A | N/A | N/A | 2024-05-10 | QTR4 | 23/24 | 2024-01-22 | QTR3 | 23/24 | 514 | 881063.3 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A1 | 44343315201 | 2021-11-02 | QTR2 | 21/22 | 3 | 1 | 350 | 515 | 515 | 0 | 0 | 0 | 137 | 28 | 5312936 | 52636 | 5260300 | 5361981 | 5275495 | 0 | 0 | 0 | 5275495 | 5333592 | 107142 | 49045 | 81 | 0 | 0 | 2577 | 0 | 0 | 28 | 12635 | 2522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 81860 | 2522 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-12-22 | QTR2 | 23/24 | 2023-08-11 | QTR1 | 23/24 | 513 | 6332507.08 |  |  | 28 | 56 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E57A4 | 44113215201 | 2021-10-05 | QTR2 | 21/22 | 5 | 2 | 289 | 528 | 527 | 1 | 0 | 0 | 239 | 0 | 7424369 | 84545 | 7339824 | 7591181 | 7558842 | 0 | 0 | 0 | 7558842 | 7794728 | 394527 | 166812 | 75 | 0 | 0 | 15614 | 0 | 0 | 0 | 22253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222204 | 0 | F202045800 | MASCI GENERAL CONTRACTORS INC | N/A | N/A | N/A | N/A | 2023-09-15 | QTR1 | 23/24 | 2023-07-12 | QTR1 | 23/24 | 513 | 9276735.05 |  |  | 0 | 164 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58A4 | 44290515201 | 2022-02-01 | QTR3 | 21/22 | 3 | 2 | 260 | 357 | 355 | 2 | 0 | 0 | 79 | 18 | 3001616 | 50000 | 2951616 | 3060677 | 3027637 | 0 | 0 | 0 | 3027637 | 3063478 | 44903 | 59061 | 54 | 0 | 0 | 0 | 0 | 0 | 18 | 39866 | 5874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 48928 | 5874 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2023-12-14 | QTR2 | 23/24 | 2023-06-20 | QTR4 | 22/23 | 507 | 2459664.25 |  |  | 18 | 25 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58A7 | 44602015201 | 2022-02-01 | QTR3 | 21/22 | 1 | 0 | 170 | 301 | 334 | -33 | 33 | 0 | 131 | 0 | 1509974 | 48500 | 1461474 | 1509974 | 1539994 | -55902 | 0 | -55902 | 1484092 | 1540522 | 56430 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F453608140 | VALENCIA CONSTRUCTION GROUP | N/A | N/A | N/A | N/A | 2024-04-24 | QTR4 | 23/24 | 2023-11-06 | QTR2 | 23/24 | 509 | 1275856.02 |  |  | 0 | 120 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E58B2 | 44529415201 | 2022-11-01 | QTR2 | 22/23 | 2 | 1 | 300 | 354 | 325 | 29 | 0 | 0 | 54 | 0 | 8096921 | 114500 | 7982421 | 8098655 | 8200608 | 0 | 0 | 0 | 8200608 | 8093983 | -104891 | 1734 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 65137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65137 | 0 | F593155035 | P & S PAVING INC. | N/A | N/A | N/A | N/A | 2024-03-05 | QTR3 | 23/24 | 2023-12-20 | QTR2 | 23/24 | 512 | 11713738.11 |  |  | 0 | 28 | 0 | 0 | 0 | 0 |  | DO
05DO | 05 | E59A9 | 43913015201 | 2022-01-04 | QTR3 | 21/22 | 1 | 0 | 140 | 248 | 246 | 2 | 0 | 0 | 83 | 25 | 679529 | 24250 | 655279 | 679529 | 677096 | 0 | 0 | 0 | 677096 | 677187 | 92 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1848 | 0 | F264318212 | CARR CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-08-18 | QTR1 | 23/24 | 2023-06-08 | QTR4 | 22/23 | 514 | 681570.8 |  |  | 25 | 34 | 0 | 0 | 0 | 0 |  | DO
06CO | 06 | T6505 | 43326435201 | 2020-08-26 | QTR1 | 20/21 | 4 | 2 | 350 | 382 | 376 | 6 | 0 | 0 | 32 | 0 | 4604161 | 51560 | 4552601 | 4652806 | 4445340 | -1 | 400000 | 399999 | 4845339 | 4484965 | -360374 | 48646 | 14 | 0 | 0 | 8472 | 0 | 0 | 0 | 7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9425 | 0 | 0 | 0 | 44090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69565 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-10-27 | QTR2 | 23/24 | 2022-02-11 | QTR3 | 21/22 | 636 | 4947288.63 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6508 | 42325125201 | 2021-07-28 | QTR1 | 21/22 | 2 | 5 | 900 | 931 | 597 | 334 | 0 | 0 | 31 | 0 | 42480180 | 150000 | 42330180 | 43009539 | 42865939 | 0 | 4169010 | 4169010 | 47034949 | 44092372 | -2863217 | 529359 | 9 | 0 | 0 | 179323 | 10153 | 0 | 0 | 83681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63554 | 0 | 0 | 0 | 68833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474751 | 10153 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-02-07 | QTR3 | 23/24 | 2023-10-17 | QTR2 | 23/24 | 613 | 49760527.32 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6513 | 43998615201 | 2022-03-30 | QTR3 | 21/22 | 3 | 2 | 240 | 265 | 220 | 45 | 0 | 0 | 25 | 0 | 2569128 | 50000 | 2519128 | 2717271 | 2543862 | 0 | 120000 | 120000 | 2663862 | 2540376 | -123486 | 148143 | 5 | 0 | 0 | 60316 | 0 | 0 | 0 | 105162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174351 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-06-14 | QTR4 | 22/23 | 636 | 2452591.81 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6515 | 43274845201 | 2022-03-30 | QTR3 | 21/22 | 3 | 2 | 240 | 257 | 221 | 36 | 0 | 0 | 17 | 0 | 2455465 | 50000 | 2405465 | 2510141 | 2443596 | 0 | 72000 | 72000 | 2515596 | 2440177 | -75419 | 54676 | 4 | 0 | 0 | 16029 | 0 | 0 | 0 | 11977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84859 | 0 | F454767314 | ROADWAY CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-12-15 | QTR2 | 23/24 | 2023-07-14 | QTR1 | 23/24 | 636 | 2281095.15 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 13 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6516 | 43998115201 | 2021-10-27 | QTR2 | 21/22 | 3 | 3 | 360 | 474 | 464 | 10 | 0 | 0 | 114 | 0 | 4166383 | 50000 | 4116383 | 4219775 | 4110877 | 0 | 0 | 0 | 4110877 | 4270005 | 159128 | 53392 | 87 | 0 | 0 | 31602 | 0 | 0 | 0 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80062 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2023-12-15 | QTR2 | 23/24 | 2023-06-30 | QTR4 | 22/23 | 613 | 4661947.2 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 27 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6518 | 42918635201 | 2021-12-08 | QTR2 | 21/22 | 5 | 2 | 300 | 332 | 272 | 60 | 0 | 0 | 32 | 0 | 2919079 | 50000 | 2869079 | 2940250 | 2881342 | 0 | 210000 | 210000 | 3091342 | 2942048 | -146480 | 21171 | 17 | 0 | 0 | 18966 | 0 | 0 | 0 | 13370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47690 | 0 | F590753039 | WEEKLEY ASPHALT PAVING INC. | N/A | N/A | N/A | N/A | 2023-08-22 | QTR1 | 23/24 | 2023-04-22 | QTR4 | 22/23 | 613 | 3061117.05 | B5:B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 15 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6519 | 43476835201 | 2022-01-26 | QTR3 | 21/22 | 3 | 1 | 300 | 347 | 274 | 73 | 0 | 0 | 47 | 0 | 3487287 | 50000 | 3437287 | 3497187 | 3509376 | 0 | 180000 | 180000 | 3689376 | 3539751 | -149625 | 9900 | 25 | 0 | 0 | 30134 | 0 | 0 | 0 | 10006 | 7982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17834 | 0 | 0 | 0 | 1911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59885 | 7982 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2023-09-13 | QTR1 | 23/24 | 2023-07-05 | QTR1 | 23/24 | 613 | 3568827.55 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6534 | 44389515201 | 2022-01-26 | QTR3 | 21/22 | 2 | 3 | 360 | 459 | 444 | 15 | 0 | 0 | 99 | 0 | 6302707 | 55045 | 6247662 | 6392688 | 6335976 | 0 | 238000 | 238000 | 6573976 | 6471394 | -102582 | 89980 | 56 | 15 | 0 | 105515 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 107915 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-02-15 | QTR3 | 23/24 | 2023-07-10 | QTR1 | 23/24 | 636 | 5606871.85 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 28 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6537 | 44391615201 | 2022-04-27 | QTR4 | 21/22 | 2 | 1 | 400 | 457 | 360 | 97 | 0 | 0 | 57 | 0 | 6069480 | 55928 | 6013552 | 6030999 | 5946111 | 0 | 320000 | 320000 | 6266111 | 5937355 | -328757 | -38482 | 35 | 0 | 0 | 1186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35217 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-05-31 | QTR4 | 23/24 | 2023-12-01 | QTR2 | 23/24 | 636 | 5885247.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 22 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6543 | 44183615201 | 2022-08-31 | QTR1 | 22/23 | 2 | 2 | 250 | 265 | 227 | 38 | 0 | 0 | 15 | 0 | 2810000 | 50000 | 2760000 | 2808895 | 2824415 | 0 | 140000 | 140000 | 2964415 | 2810967 | -153448 | -1105 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 69778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -58214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11564 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2024-01-29 | QTR3 | 23/24 | 2023-08-31 | QTR1 | 23/24 | 636 | 2984244.15 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 5 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6545 | 44574515201 | 2022-10-05 | QTR2 | 22/23 | 2 | 0 | 160 | 220 | 218 | 2 | 0 | 0 | 60 | 0 | 915762 | 48586 | 867176 | 915762 | 904223 | 0 | 0 | 0 | 904223 | 903865 | -358 | 0 | 39 | 0 | 0 | 5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30027 | 0 | F591690152 | H & R PAVING INC. | N/A | N/A | N/A | N/A | 2024-03-07 | QTR3 | 23/24 | 2024-01-08 | QTR3 | 23/24 | 636 | 1027818.5 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6546 | 44574715201 | 2022-10-26 | QTR2 | 22/23 | 1 | 0 | 140 | 183 | 172 | 11 | 0 | 0 | 43 | 0 | 636402 | 36841 | 599561 | 636402 | 608049 | 0 | 0 | 0 | 608049 | 607521 | -527 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-06-05 | QTR4 | 23/24 | 2024-04-18 | QTR4 | 23/24 | 613 | 753182.75 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6561 | 43081325201 | 2022-05-25 | QTR4 | 21/22 | 2 | 0 | 150 | 250 | 250 | 0 | 0 | 0 | 100 | 0 | 836079 | 31578 | 804501 | 836079 | 782914 | 0 | 0 | 0 | 782914 | 778816 | -4099 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10994 | 0 | F830345690 | FLORIDA ENGINEERING & DEVELOPMENT CORP | N/A | N/A | N/A | N/A | 2024-04-09 | QTR4 | 23/24 | 2023-12-01 | QTR2 | 23/24 | 613 | 760317.1 |  |  | 0 | 17 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6563 | 44882915201 | 2022-12-07 | QTR2 | 22/23 | 1 | 1 | 120 | 159 | 159 | 0 | 0 | 0 | 39 | 0 | 565000 | 26990 | 538010 | 591990 | 490972 | 0 | 0 | 0 | 490972 | 490972 | 0 | 26990 | 21 | 0 | 0 | 6537 | 0 | 0 | 0 | 17308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23846 | 0 | F208608887 | AUM CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-08 | QTR3 | 23/24 | 2024-02-26 | QTR3 | 23/24 | 613 | 566783 |  |  | 0 | 18 | 0 | 0 | 0 | 0 |  | CO
06CO | 06 | T6571 | 44390315201 | 2023-01-25 | QTR3 | 22/23 | 1 | 1 | 209 | 260 | 256 | 4 | 0 | 0 | 51 | 0 | 1857275 | 50000 | 1807275 | 1907275 | 1881049 | 0 | 0 | 0 | 1881049 | 1877156 | -3893 | 50000 | 31 | 0 | 0 | 29472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47710 | 0 | F472761317 | BACALLAO CONSTRUCTION & ENGINEERING DEVE | N/A | N/A | N/A | N/A | 2024-05-01 | QTR4 | 23/24 | 2024-03-08 | QTR3 | 23/24 | 613 | 2156608.65 |  |  | 0 | 20 | 0 | 0 | 0 | 0 |  | CO
06DO | 06 | E6L44 | 43652515201 | 2020-11-19 | QTR2 | 20/21 | 4 | 11 | 600 | 779 | 779 | 0 | 0 | 0 | 169 | 10 | 10780329 | 111884 | 10668445 | 10840590 | 11062582 | 0 | 0 | 0 | 11062582 | 11134539 | 187452 | 60261 | 119 | 0 | 10 | 13320 | 0 | 0 | 0 | 36314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 81774 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-01-10 | QTR3 | 23/24 | 2023-09-27 | QTR1 | 23/24 | 613 | 11006397.88 | B5 | ACC - INCENTIVE/DISINCENTIVE | 10 | 50 | 0 | 0 | -272957 | 0 |  | DO
06DO | 06 | E6M36 | 44343215201 | 2022-08-25 | QTR1 | 22/23 | 1 | 0 | 160 | 303 | 303 | 0 | 0 | 0 | 143 | 0 | 935010 | 46311 | 888699 | 935010 | 1101336 | 0 | 0 | 0 | 1101336 | 1101281 | -55 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 36709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 36709 | 0 | F260713097 | AMERICAN DESIGN ENGINEERING CONSTRUCTION | N/A | N/A | N/A | N/A | 2024-06-10 | QTR4 | 23/24 | 2024-02-27 | QTR3 | 23/24 | 613 | 1073050.3 |  |  | 0 | 27 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N08 | 44196015201 | 2022-01-27 | QTR3 | 21/22 | 2 | 5 | 450 | 483 | 372 | 111 | 0 | 0 | 33 | 0 | 2813265 | 50000 | 2763265 | 2921577 | 2938675 | 0 | 0 | 0 | 2938675 | 2927754 | 65 | 108312 | 12 | 0 | 0 | 47426 | 0 | 0 | 0 | 12785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107049 | 0 | F470530367 | KIEWIT INFRASTRUCTURE SOUTH CO. | N/A | N/A | N/A | N/A | 2023-10-17 | QTR2 | 23/24 | 2023-08-21 | QTR1 | 23/24 | 613 | 3044682.74 |  |  | 0 | 21 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N09 | 44480525201 | 2022-07-28 | QTR1 | 22/23 | 1 | 0 | 240 | 260 | 172 | 88 | 0 | 0 | 20 | 0 | 797552 | 50000 | 747552 | 797552 | 706126 | 0 | 0 | 0 | 706126 | 706126 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F593682914 | SEMINOLE EQUIPMENT INC. | N/A | N/A | N/A | N/A | 2023-08-11 | QTR1 | 23/24 | 2023-06-29 | QTR4 | 22/23 | 613 | 1509363.9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N47 | 44445015201 | 2022-05-26 | QTR4 | 21/22 | 1 | 2 | 250 | 272 | 220 | 52 | 0 | 0 | 22 | 0 | 2697327 | 50000 | 2647327 | 2771657 | 2731695 | 0 | 180000 | 180000 | 2911695 | 2718704 | -192991 | 74329 | 14 | 0 | 0 | 3630 | 0 | 0 | 0 | 41276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48138 | 0 | 0 | 0 | 3654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96698 | 0 | F481277685 | JVA ENGINEERING CONTRACTOR INC | N/A | N/A | N/A | N/A | 2023-08-23 | QTR1 | 23/24 | 2023-05-24 | QTR4 | 22/23 | 636 | 2883318.39 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 8 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6N55 | 44196815201 | 2021-08-26 | QTR1 | 21/22 | 1 | 0 | 280 | 460 | 459 | 1 | 0 | 0 | 180 | 0 | 757063 | 47154 | 709909 | 757063 | 654819 | 0 | 0 | 0 | 654819 | 654819 | 0 | 0 | 101 | 0 | 0 | 33282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 33282 | 0 | F134122485 | FREYSSINET INC. | N/A | N/A | N/A | N/A | 2023-07-14 | QTR1 | 23/24 | 2023-04-06 | QTR4 | 22/23 | 636 | 1042435.8 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O02 | 44479915201 | 2022-10-06 | QTR2 | 22/23 | 2 | 0 | 200 | 217 | 206 | 11 | 0 | 0 | 17 | 0 | 779455 | 29484 | 749971 | 779455 | 733765 | 0 | 0 | 0 | 733765 | 733765 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14889 | 0 | F461187423 | SOUTHERN ROAD & BRIDGE LLC | N/A | N/A | N/A | N/A | 2024-01-09 | QTR3 | 23/24 | 2023-12-13 | QTR2 | 23/24 | 613 | 612148 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
06DO | 06 | E6O04 | 44196515201 | 2022-11-17 | QTR2 | 22/23 | 1 | 0 | 380 | 414 | 307 | 107 | 0 | 0 | 34 | 0 | 1446162 | 50000 | 1396162 | 1446162 | 1381923 | 0 | 0 | 0 | 1381923 | 1381923 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41448 | 0 | F591641879 | SEACOAST INCORPORATED | N/A | N/A | N/A | N/A | 2024-03-15 | QTR3 | 23/24 | 2024-02-08 | QTR3 | 23/24 | 613 | 2588372.8 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07CO | 07 | T7383 | 40582225201 | 2016-06-20 | QTR4 | 15/16 | 3 | 23 | 730 | 1366 | 2427 | -1061 | 1061 | 0 | 224 | 412 | 27868889 | 150000 | 27718889 | 32682171 | 33265156 | -3418119 | 0 | -3418119 | 29847037 | 30298655 | 563653 | 4813282 | 103 | 0 | 69 | 1450267 | 210761 | 0 | 101 | 1642245 | 76915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27403 | 25562 | 0 | 0 | 0 | 0 | 0 | 0 | 135727 | 74502 | 0 | 0 | 0 | 0 | 0 | 242 | 1356044 | 1356044 | 0 | 0 | 0 | 0 | 0 | 412 | 4611687 | 1743784 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2024-06-03 | QTR4 | 23/24 | 2023-06-30 | QTR4 | 22/23 | 714 | 32874961.99 | B10 | ACC - BONUS/INCENT/DISINCENT | 32 | 121 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7424 | 25729855201 | 2019-03-27 | QTR3 | 18/19 | 3 | 4 | 860 | 964 | 931 | 33 | 0 | 0 | 104 | 0 | 20155312 | 406894 | 19748419 | 20804212 | 20013184 | 0 | 0 | 0 | 20013184 | 19790050 | -223135 | 648900 | 54 | 0 | 0 | 350213 | 0 | 0 | 0 | 262060 | 6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637979 | 6325 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2023-11-03 | QTR2 | 23/24 | 2022-04-12 | QTR4 | 21/22 | 798 | 29301814.47 |  |  | 0 | 50 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7428 | 43258435201 | 2019-02-27 | QTR3 | 18/19 | 3 | 6 | 445 | 671 | 685 | -14 | 14 | 0 | 114 | 112 | 9277781 | 90000 | 9187781 | 9481539 | 10184938 | -48258 | 300000 | 251742 | 10436680 | 10081240 | -350246 | 203759 | 58 | 0 | 21 | 283799 | 0 | 0 | 0 | 16679 | 10786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | -96529 | 0 | 0 | 0 | 12534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 216484 | 10786 | F593221511 | PCS CIVIL INC. | N/A | N/A | N/A | N/A | 2023-08-28 | QTR1 | 23/24 | 2021-06-25 | QTR4 | 20/21 | 796 | 9500000 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 56 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7451 | 43982985201 | 2020-04-29 | QTR4 | 19/20 | 1 | 1 | 170 | 178 | 550 | -372 | 372 | 0 | 8 | 0 | 698558 | 34000 | 664558 | 698558 | 557380 | -158860 | 0 | -158860 | 398520 | 531562 | 133042 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | Z43-0990710 | ARCH INSURANCE COMPANY | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2022-07-07 | QTR1 | 22/23 | 799 | 691075.3 |  |  | 0 | 7 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7468 | 44138615201 | 2021-01-27 | QTR3 | 20/21 | 1 | 3 | 498 | 556 | 514 | 42 | 0 | 0 | 77 | -19 | 9161461 | 85000 | 9076461 | 9416662 | 9386983 | 0 | 0 | 0 | 9386983 | 9736387 | 388067 | 255200 | 53 | 0 | 0 | 337633 | 0 | 0 | 0 | 90042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19 | 324328 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-07-13 | QTR1 | 23/24 | 2022-12-02 | QTR2 | 22/23 | 798 | 9040000 |  |  | 0 | 24 | 0 | -19 | -105466 | 0 |  | CO
07CO | 07 | T7473 | 43944815201 | 2021-04-28 | QTR4 | 20/21 | 1 | 3 | 370 | 492 | 492 | 0 | 0 | 0 | 98 | 24 | 3457631 | 50000 | 3407631 | 3534214 | 3460775 | 0 | 0 | 0 | 3460775 | 3513340 | 76197 | 76582 | 60 | 0 | 0 | 21491 | 1858 | 0 | 0 | 31459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76582 | 1858 | F465639198 | WATSON CIVIL CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-06-25 | QTR4 | 23/24 | 2023-03-22 | QTR3 | 22/23 | 798 | 3048700 |  |  | 0 | 38 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7480 | 44025315201 | 2021-12-08 | QTR2 | 21/22 | 1 | 2 | 230 | 353 | 352 | 1 | 0 | 0 | 109 | 14 | 8381553 | 92000 | 8289553 | 8507750 | 8880433 | 0 | 0 | 0 | 8880433 | 9224126 | 351217 | 126197 | 83 | 0 | 0 | 20058 | 0 | 0 | 14 | 157861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7524 | 7524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 185444 | 7524 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-11-07 | QTR2 | 23/24 | 2023-07-21 | QTR1 | 23/24 | 796 | 9618300 |  |  | 14 | 26 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7484 | 43780725201 | 2022-07-27 | QTR1 | 22/23 | 1 | 1 | 290 | 341 | 341 | 0 | 0 | 0 | 51 | 0 | 2689020 | 50000 | 2639020 | 2695490 | 2436483 | 0 | 0 | 0 | 2436483 | 2426876 | -3137 | 6470 | 18 | 0 | 0 | 1911 | 0 | 0 | 0 | 45879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6470 | 6470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54260 | 6470 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2024-04-30 | QTR4 | 23/24 | 2023-12-15 | QTR2 | 23/24 | 799 | 3008900 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7485 | 44109915201 | 2022-03-30 | QTR3 | 21/22 | 1 | 0 | 135 | 251 | 251 | 0 | 0 | 0 | 116 | 0 | 2037125 | 50000 | 1987125 | 2037125 | 1982019 | 0 | 0 | 0 | 1982019 | 1983777 | 1758 | 0 | 102 | 0 | 0 | 4355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7115 | 0 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-05-22 | QTR4 | 23/24 | 2023-05-30 | QTR4 | 22/23 | 798 | 1568900 |  |  | 0 | 14 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7491 | 44358325201 | 2022-02-23 | QTR3 | 21/22 | 1 | 0 | 150 | 193 | 193 | 0 | 0 | 0 | 43 | 0 | 1439445 | 44000 | 1395445 | 1439445 | 1363648 | 0 | 0 | 0 | 1363648 | 1363533 | -115 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | F592554039 | AMERICAN LIGHTING AND SIGNALIZATION LLC | N/A | N/A | N/A | N/A | 2023-12-06 | QTR2 | 23/24 | 2023-09-14 | QTR1 | 23/24 | 796 | 1085600 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7496 | 43591435201 | 2022-05-25 | QTR4 | 21/22 | 1 | 3 | 175 | 248 | 248 | 0 | 0 | 0 | 73 | 0 | 2222629 | 50000 | 2172629 | 2357768 | 2205247 | 0 | 0 | 0 | 2205247 | 2190340 | -14907 | 135139 | 44 | 0 | 0 | 6498 | 0 | 0 | 0 | 145802 | 52681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 152300 | 52681 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-12-04 | QTR2 | 23/24 | 2023-09-07 | QTR1 | 23/24 | 799 | 2009600 |  |  | 0 | 10 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T7498 | 44332015201 | 2022-05-25 | QTR4 | 21/22 | 1 | 0 | 120 | 127 | 127 | 0 | 0 | 0 | 7 | 0 | 1340863 | 50000 | 1290863 | 1340863 | 1268582 | -12000 | 0 | -12000 | 1256582 | 1256582 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-27 | QTR1 | 23/24 | 2023-05-22 | QTR4 | 22/23 | 796 | 2027300 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | CO
07CO | 07 | T9026 | 44490215223 | 2021-11-17 | QTR2 | 21/22 | 2 | 4 | 250 | 536 | 530 | 6 | 0 | 0 | 286 | 0 | 4025439 | 50000 | 3975439 | 4151284 | 4188035 | 0 | 0 | 0 | 4188035 | 4185783 | 0 | 125844 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 3758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 147045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 153054 | 0 | F593044703 | CHINCHOR ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-02-16 | QTR3 | 23/24 | 2023-11-24 | QTR2 | 23/24 | 706 | 3685201.18 |  |  | 0 | 33 | 0 | 0 | 0 | 0 |  | CO
07DO | 07 | E7N76 | 43956515201 | 2021-03-10 | QTR3 | 20/21 | 2 | 3 | 300 | 401 | 401 | 0 | 0 | 0 | 101 | 0 | 6600000 | 63000 | 6537000 | 7117569 | 6571044 | 0 | 0 | 0 | 6571044 | 6563814 | 0 | 517569 | 36 | 0 | 0 | 126742 | 0 | 0 | 0 | 110994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517569 | 0 | F650446255 | QUINN CONSTRUCTION INC. | N/A | N/A | N/A | N/A | 2024-03-19 | QTR3 | 23/24 | 2023-05-24 | QTR4 | 22/23 | 799 | 6998000 |  |  | 0 | 65 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N90 | 44822115201 | 2022-01-12 | QTR3 | 21/22 | 1 | 1 | 120 | 172 | 172 | 0 | 0 | 0 | 52 | 0 | 679686 | 28000 | 651686 | 695950 | 640611 | 0 | 0 | 0 | 640611 | 640611 | 0 | 16264 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16264 | 16264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 16264 | 16264 | F274431832 | BLACKTIP SERVICES INCORPORATED | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-04-20 | QTR4 | 22/23 | 799 | 644500 |  |  | 0 | 23 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7N95 | 44025115201 | 2021-12-08 | QTR2 | 21/22 | 1 | 3 | 240 | 317 | 314 | 3 | 0 | 0 | 77 | 0 | 6430299 | 84000 | 6346299 | 6566839 | 6774752 | 0 | 0 | 0 | 6774752 | 7323867 | 551655 | 136540 | 52 | 0 | 0 | 103103 | 4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68698 | 68698 | 0 | 0 | 0 | 0 | 0 | 0 | 2540 | 2540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174342 | 75334 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2023-07-08 | QTR1 | 23/24 | 2023-02-24 | QTR3 | 22/23 | 796 | 8690700 |  |  | 0 | 25 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O02 | 43724915201 | 2021-10-13 | QTR2 | 21/22 | 1 | 7 | 322 | 429 | 422 | 7 | 0 | 0 | 91 | 16 | 4833500 | 50000 | 4783500 | 5430418 | 5535682 | 0 | 200000 | 200000 | 5735682 | 5261328 | -199047 | 596918 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 328040 | 122639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 275307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 603347 | 122639 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2024-03-04 | QTR3 | 23/24 | 2023-10-16 | QTR2 | 23/24 | 796 | 3694800 | B10 | ACC - BONUS/INCENT/DISINCENT | 16 | 60 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O03 | 43050015201 | 2021-07-14 | QTR1 | 21/22 | 1 | 2 | 690 | 753 | 681 | 72 | 0 | 0 | 63 | 0 | 8992000 | 85000 | 8907000 | 9003651 | 9360484 | 0 | 0 | 0 | 9360484 | 9368249 | 18403 | 11651 | 31 | 0 | 0 | 35754 | 0 | 0 | 0 | 2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10639 | 10639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56758 | 10639 | F263552913 | SUPERIOR CONSTRUCTION COMPANY SOUTHEAST | N/A | N/A | N/A | N/A | 2024-03-01 | QTR3 | 23/24 | 2023-11-21 | QTR2 | 23/24 | 799 | 9455800 |  |  | 0 | 32 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O04 | 43952615201 | 2021-09-08 | QTR1 | 21/22 | 1 | 2 | 210 | 235 | 235 | 0 | 0 | 0 | 25 | 0 | 1944266 | 50000 | 1894266 | 2045152 | 1898792 | 0 | 0 | 0 | 1898792 | 1886359 | 0 | 100885 | 10 | 0 | 0 | 17204 | 0 | 0 | 0 | 71248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12433 | 12433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100885 | 12433 | F820821263 | AJ GENERAL CONSTRUCTION SERVICES INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2022-12-09 | QTR2 | 22/23 | 799 | 1797400 |  |  | 0 | 15 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7O11 | 44166515201 | 2022-02-09 | QTR3 | 21/22 | 2 | 0 | 180 | 220 | 220 | 0 | 0 | 0 | 40 | 0 | 3049631 | 50000 | 2999631 | 3049631 | 3013462 | 0 | 0 | 0 | 3013462 | 3013181 | -281 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2023-07-20 | QTR1 | 23/24 | 2023-06-14 | QTR4 | 22/23 | 798 | 2409700 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P02 | 44146915201 | 2022-05-11 | QTR4 | 21/22 | 1 | 0 | 200 | 248 | 248 | 0 | 0 | 0 | 48 | 0 | 2611346 | 50000 | 2561346 | 2611346 | 2617684 | 0 | 0 | 0 | 2617684 | 2617512 | -173 | 0 | 17 | 0 | 0 | 9955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9955 | 0 | F273534317 | GOSALIA CONCRETE CONSTRUCTORS INC. | N/A | N/A | N/A | N/A | 2024-05-06 | QTR4 | 23/24 | 2024-01-09 | QTR3 | 23/24 | 796 | 2320500 |  |  | 0 | 31 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P05 | 44024415201 | 2022-04-13 | QTR4 | 21/22 | 2 | 1 | 200 | 342 | 335 | 7 | 0 | 0 | 142 | 0 | 5007203 | 50000 | 4957203 | 5075397 | 4790051 | 0 | 0 | 0 | 4790051 | 4756788 | -33263 | 68194 | 97 | 0 | 0 | 10809 | 0 | 0 | 0 | 57384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68194 | 0 | F590594298 | HUBBARD CONSTRUCTION COMPANY | N/A | N/A | N/A | N/A | 2024-06-19 | QTR4 | 23/24 | 2023-09-11 | QTR1 | 23/24 | 799 | 5384600 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P09 | 43763615201 | 2022-03-09 | QTR3 | 21/22 | 1 | 3 | 275 | 406 | 406 | 0 | 0 | 0 | 118 | 13 | 2593388 | 50000 | 2543388 | 2709838 | 2503891 | 0 | 0 | 0 | 2503891 | 2499570 | 1497 | 116449 | 50 | 10 | 0 | 9735 | 0 | 0 | 13 | 20708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 60632 | 60632 | 0 | 0 | 1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6508 | 5818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 13 | 99313 | 66449 | F591925201 | CONE & GRAHAM INC. | N/A | N/A | N/A | N/A | 2024-01-09 | QTR3 | 23/24 | 2023-09-13 | QTR1 | 23/24 | 799 | 2305500 |  |  | 13 | 27 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P21 | 44024915201 | 2022-04-13 | QTR4 | 21/22 | 1 | 0 | 250 | 423 | 423 | 0 | 0 | 0 | 125 | 48 | 7905829 | 62000 | 7843829 | 7905829 | 8077210 | 0 | 0 | 0 | 8077210 | 8034957 | -42254 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 5458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5458 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-06-10 | QTR4 | 23/24 | 2024-01-03 | QTR3 | 23/24 | 796 | 6822100 |  |  | 0 | 42 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P30 | 44761415201 | 2022-04-13 | QTR4 | 21/22 | 1 | 1 | 140 | 171 | 171 | 0 | 0 | 0 | 31 | 0 | 2231499 | 50000 | 2181499 | 2259063 | 2052581 | 0 | 0 | 0 | 2052581 | 2046856 | -5724 | 27565 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 27565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27565 | 0 | F381808100 | KAMMINGA & ROODVOETS INC. | N/A | N/A | N/A | N/A | 2023-12-08 | QTR2 | 23/24 | 2023-09-13 | QTR1 | 23/24 | 714 | 1792600 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P36 | 44978015201 | 2022-06-08 | QTR4 | 21/22 | 3 | 3 | 300 | 361 | 338 | 23 | 0 | 0 | 61 | 0 | 4664000 | 50000 | 4614000 | 4709230 | 4734993 | 0 | 0 | 0 | 4734993 | 4662735 | -72258 | 45230 | 37 | 0 | 0 | 25230 | 0 | 0 | 0 | 42961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76416 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2023-10-26 | QTR2 | 23/24 | 2023-08-01 | QTR1 | 23/24 | 799 | 5588200 | B0:B0:B0 | ACC - LUMP SUM:ACC - LUMP SUM:ACC - LUMP SUM | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P61 | 44383615201 | 2023-01-11 | QTR3 | 22/23 | 1 | 1 | 140 | 165 | 161 | 4 | 0 | 0 | 10 | 15 | 506794 | 19000 | 487794 | 527638 | 475289 | 0 | 0 | 0 | 475289 | 475289 | 0 | 20844 | 16 | 0 | 0 | 20844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20844 | 0 | F592361020 | M & J CONSTRUCTION COMPANY OF PINELLAS C | N/A | N/A | N/A | N/A | 2023-11-17 | QTR2 | 23/24 | 2023-10-16 | QTR2 | 23/24 | 799 | 441600 |  |  | 15 | 9 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P63 | 44774815201 | 2023-01-11 | QTR3 | 22/23 | 1 | 0 | 120 | 130 | 71 | 59 | 0 | 0 | 10 | 0 | 619151 | 50000 | 569151 | 619151 | 571177 | 0 | 0 | 0 | 571177 | 571177 | 0 | 0 | 7 | 0 | 0 | 7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7087 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2023-10-19 | QTR2 | 23/24 | 2023-07-24 | QTR1 | 23/24 | 799 | 1320700 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P82 | 43782315201 | 2023-03-08 | QTR3 | 22/23 | 2 | 0 | 70 | 103 | 103 | 0 | 0 | 0 | 33 | 0 | 341000 | 16000 | 325000 | 341000 | 292314 | 0 | 0 | 0 | 292314 | 292314 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F452997668 | BURGESS CIVIL LLC | N/A | N/A | N/A | N/A | 2024-06-05 | QTR4 | 23/24 | 2024-02-16 | QTR3 | 23/24 | 796 | 350800.01 |  |  | 0 | 16 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P89 | 44598115201 | 2023-11-08 | QTR2 | 23/24 | 1 | 0 | 60 | 63 | 54 | 9 | 0 | 0 | 3 | 0 | 746261 | 43000 | 703261 | 746261 | 629640 | 0 | 0 | 0 | 629640 | 629640 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F592073526 | ENGINEER CONTROL SYSTEMS CORPORATION | N/A | N/A | N/A | N/A | 2024-05-01 | QTR4 | 23/24 | 2024-03-29 | QTR3 | 23/24 | 799 | 927702 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7P97 | 45217915201 | 2023-02-10 | QTR3 | 22/23 | 1 | 2 | 30 | 31 | 29 | 2 | 0 | 0 | 1 | 0 | 338100 | 15000 | 323100 | 327764 | 312738 | 0 | 0 | 0 | 312738 | 312738 | 0 | -10336 | 1 | 0 | 0 | 8474 | 0 | 0 | 0 | 29697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10336 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-06-25 | QTR4 | 23/24 | 2023-10-10 | QTR2 | 23/24 | 799 | 342400 | B0 | ACC - LUMP SUM | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7Q34 | 44583115201 | 2023-11-08 | QTR2 | 23/24 | 1 | 0 | 60 | 60 | 53 | 7 | 0 | 0 | 0 | 0 | 268116 | 17000 | 251116 | 268116 | 251692 | 0 | 0 | 0 | 251692 | 251692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F208163134 | BRIDGE MASTERS CONSTRUCTION LLC | N/A | N/A | N/A | N/A | 2024-06-18 | QTR4 | 23/24 | 2024-05-17 | QTR4 | 23/24 | 798 | 436100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | DO
07DO | 07 | E7R18 | 43273425202 | 2020-05-12 | QTR4 | 19/20 | 3 | 15 | 815 | 1016 | 1016 | 0 | 0 | 0 | 101 | 100 | 63996999 | 150000 | 63846999 | 65132965 | 65090666 | 0 | 0 | 0 | 65090666 | 65542493 | 2125319 | 1135966 | 50 | 0 | 0 | 540370 | 0 | 0 | 0 | 120716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332845 | 0 | 0 | 79 | 68593 | 68593 | 0 | 0 | 0 | 0 | 0 | 0 | 206020 | 126890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 1268544 | 195483 | F042534615 | MIDDLESEX CORPORATION (THE) | N/A | N/A | N/A | N/A | 2024-04-26 | QTR4 | 23/24 | 2023-05-15 | QTR4 | 22/23 | 714 | 55949573 | B8 | ACC - DESIGN/BUILD - MAJOR | 0 | 51 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8Q78 | 43554615201 | 2018-06-15 | QTR4 | 17/18 | 2 | 27 | 1430 | 1594 | 1265 | 329 | 0 | 0 | 164 | 0 | 143269821 | 150000 | 143119821 | 145759356 | 145166429 | 0 | 5000000 | 5000000 | 150166429 | 144192875 | -5873129 | 2489535 | 81 | 0 | 0 | 398577 | 0 | 0 | 0 | 1404790 | 0 | 0 | 0 | 13454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131931 | 0 | 0 | 0 | 551048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2379872 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 | 2022-03-01 | QTR3 | 21/22 | 854 | 156867749.98 | B5:B5 | ACC - INCENTIVE/DISINCENTIVE:ACC - INCENTIVE/DISINCENTIVE | 0 | 83 | 0 | 0 | -140484 | 0 |  | DO
08DO | 08 | E8R75 | 42933945201 | 2019-05-21 | QTR4 | 18/19 | 1 | 5 | 565 | 771 | 769 | 2 | 0 | 0 | 206 | 0 | 19557418 | 150000 | 19407418 | 20031429 | 19576305 | 0 | 0 | 0 | 19576305 | 19542086 | -34220 | 474011 | 114 | 0 | 0 | 558466 | 0 | 0 | 0 | 379263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18588 | 0 | 0 | 0 | 31372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606328 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-04-04 | QTR4 | 23/24 | 2022-01-04 | QTR3 | 21/22 | 854 | 16516025.03 |  |  | 0 | 92 | 0 | 0 | -384455 | 0 |  | DO
08DO | 08 | E8R77 | 43798615201 | 2019-05-14 | QTR4 | 18/19 | 3 | 5 | 738 | 1039 | 1039 | 0 | 0 | 0 | 301 | 0 | 31832323 | 150000 | 31682323 | 32865375 | 32938830 | 0 | 0 | 0 | 32938830 | 32271398 | -667433 | 1033052 | 175 | 0 | 0 | 62194 | 0 | 0 | 0 | 38182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 960260 | 0 | 0 | 0 | 77444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1138080 | 0 | F592023298 | COMMUNITY ASPHALT CORP. | N/A | N/A | N/A | N/A | 2023-08-10 | QTR1 | 23/24 | 2022-08-17 | QTR1 | 22/23 | 854 | 33799887.12 |  |  | 0 | 98 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8R97 | 43730045201 | 2019-09-17 | QTR1 | 19/20 | 1 | 35 | 939 | 1012 | 938 | 74 | 0 | 0 | 73 | 0 | 139979406 | 150000 | 139829406 | 145733672 | 144403400 | 0 | 6000000 | 6000000 | 150403400 | 143485400 | -5542884 | 5754265 | 38 | 0 | 0 | 48807 | 0 | 0 | 0 | 4196617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94312 | 0 | 0 | 0 | 564973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 983554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5902105 | 0 | F800866395 | JOHNSON BROS. CORPORATION A SO | N/A | N/A | N/A | N/A | 2023-07-05 | QTR1 | 23/24 | 2022-07-31 | QTR1 | 22/23 | 854 | 118749145.78 | B10 | ACC - BONUS/INCENT/DISINCENT | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S19 | 44387815201 | 2020-04-14 | QTR4 | 19/20 | 2 | 0 | 290 | 387 | 387 | 0 | 0 | 0 | 73 | 24 | 3263898 | 50000 | 3213898 | 3263898 | 3283729 | 0 | 0 | 0 | 3283729 | 3283729 | 0 | 0 | 41 | 0 | 0 | 5725 | 0 | 0 | 6 | 18681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 43358 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2024-02-13 | QTR3 | 23/24 | 2021-11-10 | QTR2 | 21/22 | 854 | 3999932.48 |  |  | 24 | 32 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S55 | 44070015201 | 2020-08-31 | QTR1 | 20/21 | 2 | 7 | 515 | 718 | 716 | 2 | 0 | 0 | 231 | -28 | 16707654 | 150000 | 16557654 | 17277221 | 16377036 | 0 | 0 | 0 | 16377036 | 16720673 | 485146 | 569567 | 175 | 0 | 0 | 18542 | 0 | 0 | 0 | 58747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469864 | 0 | 0 | 0 | 80825 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 38754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | -28 | 616415 | 0 | F980461222 | OHLA USA INC | N/A | N/A | N/A | N/A | 2023-08-17 | QTR1 | 23/24 | 2022-12-20 | QTR2 | 22/23 | 854 | 20328685.57 |  |  | 0 | 56 | 0 | -28 | -50316 | 0 |  | DO
08DO | 08 | E8S64 | 44388015201 | 2020-09-15 | QTR1 | 20/21 | 1 | 0 | 139 | 169 | 162 | 7 | 0 | 0 | 30 | 0 | 650221 | 50000 | 600221 | 650221 | 606614 | 0 | 0 | 0 | 606614 | 606614 | 0 | 0 | 21 | 0 | 0 | 7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9376 | 0 | F650850057 | SIGNAL TECHNOLOGY AND INSTALLATION CORP. | N/A | N/A | N/A | N/A | 2024-01-16 | QTR3 | 23/24 | 2021-09-07 | QTR1 | 21/22 | 854 | 1256846.42 |  |  | 0 | 9 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8S95 | 43496825201 | 2021-07-16 | QTR1 | 21/22 | 1 | 0 | 551 | 887 | 877 | 10 | 0 | 0 | 301 | 35 | 5495495 | 61300 | 5434195 | 5495495 | 5449321 | 0 | 0 | 0 | 5449321 | 5449321 | 0 | 0 | 214 | 0 | 35 | 3783 | 0 | 0 | 0 | 20320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 33126 | 0 | F592502221 | HORSEPOWER ELECTRIC INC. | N/A | N/A | N/A | N/A | 2024-03-15 | QTR3 | 23/24 | 2024-02-07 | QTR3 | 23/24 | 854 | 6335420.35 | A3 | ICC - DESIGN/BUILD - MINOR | 35 | 87 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T03 | 44262715201 | 2021-05-11 | QTR4 | 20/21 | 1 | 1 | 461 | 714 | 714 | 0 | 0 | 0 | 245 | 8 | 3696363 | 50000 | 3646363 | 3796363 | 3750537 | 0 | 0 | 0 | 3750537 | 3751060 | 46856 | 100000 | 101 | 0 | 0 | 39569 | 0 | 54 | 8 | 54437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 17353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 8 | 111359 | 0 | F208429863 | SICE INC | N/A | N/A | N/A | N/A | 2024-01-19 | QTR3 | 23/24 | 2023-10-24 | QTR2 | 23/24 | 854 | 3759343.91 |  |  | 8 | 69 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T12 | 44028915201 | 2021-10-19 | QTR2 | 21/22 | 4 | 14 | 384 | 571 | 571 | 0 | 0 | 0 | 118 | 69 | 18831743 | 150000 | 18681743 | 19112673 | 19162598 | 0 | 0 | 0 | 19162598 | 19631006 | 476842 | 280930 | 120 | 0 | 0 | 120163 | 0 | 0 | 4 | 3548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9643 | 0 | 0 | 4 | 133722 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 54673 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15477 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 317940 | 0 | F581401468 | PREFERRED MATERIALS INC. | N/A | N/A | N/A | N/A | 2024-05-02 | QTR4 | 23/24 | 2023-06-28 | QTR4 | 22/23 | 854 | 18566304.65 |  |  | 1 | 58 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T21 | 44029215201 | 2021-09-14 | QTR1 | 21/22 | 2 | 6 | 350 | 617 | 614 | 3 | 0 | 0 | 208 | 59 | 13350942 | 121421 | 13229522 | 13774510 | 13575224 | 0 | 0 | 0 | 13575224 | 13523826 | 353962 | 423568 | 176 | 0 | 0 | 5500 | 0 | 0 | 0 | 24055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 97132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 405361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 532048 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-18 | QTR2 | 23/24 | 2023-09-08 | QTR1 | 23/24 | 854 | 12351694.57 |  |  | 40 | 51 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T38 | 43730095201 | 2022-02-08 | QTR3 | 21/22 | 1 | 0 | 192 | 242 | 235 | 7 | 0 | 0 | 50 | 0 | 5115331 | 50000 | 5065331 | 5115331 | 5070631 | 0 | 0 | 0 | 5070631 | 5070631 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F020546095 | EARTHSCAPES UNLIMITED INC. | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-06-15 | QTR4 | 22/23 | 854 | 5087753.85 |  |  | 0 | 24 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T39 | 44430115201 | 2021-12-14 | QTR2 | 21/22 | 1 | 3 | 234 | 278 | 253 | 25 | 0 | 0 | 44 | 0 | 1975221 | 50000 | 1925221 | 2101149 | 2102097 | 0 | 0 | 0 | 2102097 | 2083906 | 7736 | 125928 | 25 | 0 | 0 | 102641 | 0 | 0 | 0 | 36105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174272 | 0 | F204804098 | HALLEY ENGINEERING CONTRACTORS INC. | N/A | N/A | N/A | N/A | 2023-07-28 | QTR1 | 23/24 | 2023-03-08 | QTR3 | 22/23 | 854 | 1709882.3 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T42 | 43799015201 | 2022-03-08 | QTR3 | 21/22 | 2 | 3 | 321 | 359 | 286 | 73 | 0 | 0 | 54 | -16 | 4166000 | 50000 | 4116000 | 4217668 | 4164480 | 0 | 138823 | 138823 | 4303303 | 4215075 | -86560 | 51668 | 31 | 0 | 0 | 44026 | 0 | 0 | 0 | 3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | 98536 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-09-26 | QTR1 | 23/24 | 2023-05-22 | QTR4 | 22/23 | 854 | 3910716.97 | B5 | ACC - INCENTIVE/DISINCENTIVE | 0 | 23 | 0 | -16 | 0 | 0 |  | DO
08DO | 08 | E8T68 | 44448615201 | 2022-04-12 | QTR4 | 21/22 | 1 | 2 | 329 | 389 | 389 | 0 | 0 | 0 | 60 | 0 | 6695054 | 50000 | 6645054 | 6727768 | 6880189 | 0 | 0 | 0 | 6880189 | 6860508 | -11968 | 32714 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 74099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81813 | 0 | F592318360 | PRINCE CONTRACTING LLC. | N/A | N/A | N/A | N/A | 2023-11-28 | QTR2 | 23/24 | 2023-10-05 | QTR2 | 23/24 | 854 | 6191721.36 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T76 | 44206115201 | 2022-08-16 | QTR1 | 22/23 | 2 | 3 | 342 | 413 | 410 | 3 | 0 | 0 | 71 | 0 | 15249859 | 70079 | 15179780 | 15714097 | 13670638 | 0 | 0 | 0 | 13670638 | 13262271 | -408367 | 464238 | 37 | 0 | 0 | 288708 | 0 | 0 | 0 | 28136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500363 | 0 | F591115297 | GENERAL ASPHALT COMPANY LLC | N/A | N/A | N/A | N/A | 2024-06-07 | QTR4 | 23/24 | 2024-04-04 | QTR4 | 23/24 | 854 | 16808898.8 |  |  | 0 | 34 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T86 | 43855115201 | 2022-08-16 | QTR1 | 22/23 | 1 | 1 | 136 | 169 | 142 | 27 | 0 | 0 | 9 | 24 | 597627 | 35230 | 562397 | 652711 | 607225 | 0 | 0 | 0 | 607225 | 607225 | 0 | 55083 | 6 | 0 | 24 | 55083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 55083 | 0 | F900658000 | ELITE INDUSTRIAL PAINTING | N/A | N/A | N/A | N/A | 2023-08-02 | QTR1 | 23/24 | 2023-06-23 | QTR4 | 22/23 | 854 | 898718.41 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T87 | 43855015201 | 2022-08-16 | QTR1 | 22/23 | 1 | 0 | 199 | 202 | 84 | 118 | 0 | 0 | 3 | 0 | 767354 | 50000 | 717354 | 767354 | 705154 | 0 | 0 | 0 | 705154 | 705154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F201424580 | GULF COAST CONTRACTING LLC | N/A | N/A | N/A | N/A | 2023-07-31 | QTR1 | 23/24 | 2023-05-11 | QTR4 | 22/23 | 854 | 1243902.61 |  |  | 0 | 3 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8T93 | 44029515201 | 2022-06-14 | QTR4 | 21/22 | 2 | 1 | 250 | 302 | 291 | 11 | 0 | 0 | 52 | 0 | 8768395 | 92871 | 8675524 | 8771000 | 8359690 | 0 | 0 | 0 | 8359690 | 8174501 | -182584 | 2605 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2605 | 0 | F591683951 | C.W. ROBERTS CONTRACTING INC. | N/A | N/A | N/A | N/A | 2024-05-14 | QTR4 | 23/24 | 2023-11-02 | QTR2 | 23/24 | 854 | 9428515.36 |  |  | 0 | 19 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U17 | 44934015201 | 2023-03-14 | QTR3 | 22/23 | 1 | 3 | 181 | 233 | 232 | 1 | 0 | 0 | 51 | 1 | 5184770 | 50000 | 5134770 | 5358078 | 5154131 | 0 | 0 | 0 | 5154131 | 5152940 | -396 | 173308 | 16 | 0 | 1 | 34193 | 0 | 0 | 0 | 167821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 204130 | 0 | F261871966 | AJAX PAVING INDUSTRIES OF FLORIDA LLC | N/A | N/A | N/A | N/A | 2024-03-21 | QTR3 | 23/24 | 2024-01-16 | QTR3 | 23/24 | 854 | 4352337.6 |  |  | 0 | 35 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U24 | 44122465201 | 2023-02-14 | QTR3 | 22/23 | 1 | 1 | 94 | 108 | 107 | 1 | 0 | 0 | 14 | 0 | 855737 | 38426 | 817311 | 857248 | 864748 | 0 | 0 | 0 | 864748 | 863238 | 0 | 1510 | 12 | 0 | 0 | 2884 | 0 | 0 | 0 | 30181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37651 | 0 | F592098662 | RANGER CONSTRUCTION INDUSTRIES INC. | N/A | N/A | N/A | N/A | 2023-12-01 | QTR2 | 23/24 | 2023-09-25 | QTR1 | 23/24 | 854 | 859411.5 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | DO
08DO | 08 | E8U28 | 44261825201 | 2023-05-09 | QTR4 | 22/23 | 1 | 0 | 86 | 90 | 27 | 63 | 0 | 0 | 4 | 0 | 491221 | 32753 | 458468 | 491221 | 344856 | 0 | 0 | 0 | 344856 | 344856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | F721180277 | JACK B. HARPER CONTRACTOR L.L.C. | N/A | N/A | N/A | N/A | 2023-11-27 | QTR2 | 23/24 | 2023-09-15 | QTR1 | 23/24 | 854 | 690819.2 |  |  | 0 | 4 | 0 | 0 | 0 | 0 |  | DO

## Sheet2 (hidden)
03DO | 03 | E3K68 | 22077395201 | 2012-09-18 | QTR1 | 12/13 | 10 | 10 | 1565 | 1565 | 3290 | -1725 | 1725 | 0 | 0 | -100 | 98502934 | 150000 | 98352934 | 101997749 | 101979312 | 0 | 7900000 | 7900000 | 109879312 | 3307126 | -106503708 | 3494815 | 0 | 0 | 0 | 2529474 | 732 | 0 | 0 | 710246 | 1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158121 | 0 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38535 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100 | 3403092 | 2088 | F592871935 | ANDERSON COLUMBIA CO. INC. | N/A | N/A | N/A | N/A | 2024-05-09 | QTR4 | 23/24 | 2022-10-20 | QTR2 | 22/23 | 306 | 98502934 | B1:B5:B8:DB:P3 | ACC - NO EXCUSE BONUS:ACC - INCENTIVE/DISINCENTIVE:ACC - DESIGN/BUILD - MAJOR:DESIGN/BUILD/FINANCE-BUILD/FIN:PUBLIC PRIVATE PARTNERSHIP | 0 | 0 | 0 | 0 | -35024 | 0 |  | DO | 0 | 01co | 1 | 0
CO | [104 empty] | CO | 0 | 01do | 1 | 0
CO | [104 empty] | CO | 0 | 02co | 1 | 0
CO | [104 empty] | CO | 0 | 02do | 1 | 0
CO | [104 empty] | CO | 0 | 03co | 1 | 0
CO | [104 empty] | CO | 1 | 03do | 1 | 1
CO | [104 empty] | CO | 0 | 04co | 2 | 1
CO | [104 empty] | CO | 0 | 04do | 2 | 1
CO | [104 empty] | CO | 0 | 05co | 2 | 1
CO | [103 empty] | T | CO | 0 | 05do | 2 | 1
CO | [104 empty] | CO | 0 | 06co | 2 | 1
CO | [104 empty] | CO | 0 | 06do | 2 | 1
CO | [104 empty] | CO | 0 | 07co | 2 | 1
CO | [104 empty] | CO | 0 | 07do | 2 | 1
CO | [104 empty] | CO | 0 | 08co | 2 | 1
CO | [104 empty] | CO | 0 | 08do | 2 | 1
CO | [104 empty] | CO
CO | [104 empty] | CO
CO | [104 empty] | CO |  | 0