## FY 2025-2026 CAP PLAN
DRAFT Consultant CEI Acquisition Plan - FY25/26 | [28 empty] | LEGEND:
District One Construction
[29 empty] | CS = | Continuing Services
[29 empty] | DBR = | District Bridge Contract
[29 empty] | DW = | District Wide Contract
[29 empty] | F = | Full CEI Contract
[29 empty] | H = | Hybrid Project
[29 empty] | LOA = | Letter of Authorization
[29 empty] | SA = | Supplemental Amendment
Location | Address | Phone | Fax | [11 empty] | Position | Person | Office Phone | Secondary Phone
District 1 Construction | 801 N. Broadway, Bartow, FL 33830 | (863) 519-2300 | (863) 534-0071 | [11 empty] | District Secretary: | James Drigger Jr. | (863) 519-2201 | (863) 519-1902
Ft. Myers Ops Center | 2981 N.E. Pine Island Rd., Cape Coral, FL 33909 | (239) 985-7800 | (239) 656-7742 | [11 empty] | Operations Director: | Keith Slater | (863) 519-2202 | (863) 534-7265
Manatee Ops Center | 14000 SR 64 East, Bradenton, FL 34212 | (941) 708-4400 | (941) 708-4494 | [11 empty] | District Construction Eng: | Amarilys Alfonso-Perez | (863) 519-2223 | (863) 534-0071
Bartow Ops Center | 2730 S.R. 60 West, Bartow, FL 33830 | (863) 519-4100 | (863) 519-7924 | [11 empty] | Ass't Constr. Engineer: | Brian Blair | (863) 519-2224 | (863) 534-0071
Heartland Ops Center | 4730 Kenilworth Blvd., Sebring, FL 33870 | (863) 471-4848 | (863) 386-6116 | [11 empty] | District CEI Manager: | Anita Michael | (863) 519-2232 | (863) 534-0071
[15 empty] | CEI Contract Administrator: | Jennifer Roberson | (863) 519-2256 | (863) 534-0071
Seq. | Financial Project ID/(Fund) | [7 empty] | Design Project Manager/Phone No./Fax No. | [11 empty] | Event
No. |  | WPI No.(Old)/SPN(Old) | [7 empty] | Resident Construction Office/Resident Engineer | [10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  |  | Federal Project (WP21) | [7 empty] | Construction Project Manager/Phone No./Fax No. | [9 empty] | Event 1: (Note: Scheduled Date-Proposed is subject to change/approval by Professional Services Administrator.)
|  |  |  | Project Name | [7 empty] | Type Project/English-Metric
[5 empty] | Limit-From | [7 empty] | Number of Bridges/Alt. Contract
[6 empty] | Limit -To | [7 empty] | Letting Date (Mo-Year)/Construction Time (Days) | [6 empty] | Event 6: Oral/; Event 9: Scope
[7 empty] | Dist.(Mi.)/Prop. X- Sect. | [7 empty] | Ph 52 Budget $ |  | (% of CEI FY Total Ph 52) |  |  |  | Scope |  | Long | Short | Scope | Written | Consult. | Proposal | Clarif. | Negot. | Agree,
[8 empty] | County | [6 empty] | Ph 62 Budget $ (% of Ph 52) | [5 empty] | Due | Advert | List | List | Meeting | Present. | Select. | Review | Meeting | Meeting | Execution
1Fa | 433183-2-62-08 | [7 empty] | Anita Michael (863) 519-2256 | [9 empty] | Schedule Date-Prop. |  | 2025-02-12 | 2026-01-16 | 2026-02-19 | 2026-02-24 | N/A | N/A | 2026-03-10 | 2026-04-03 | N/A | N/A | 2026-05-30
|  | DS | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | 2025-02-12 | 2026-01-16 | 2026-02-19 | 2026-02-24 | N/A | N/A |  |  | N/A
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: AECOM Technical Services, Inc.; Event 3: CDM Smith, Inc; Event 5: WSB LLC; Event 9: Comments:; Event 11: GF, LP, PH
|  |  |  | CEI (INSPECTION) SAR | [7 empty] | INSPECT CONSTRUCTION PROJS. | [6 empty] | Consultant | Address: | Event 1: 7650 West Courtney Campbell Cswy, Suite 700; Event 3: 401 N Cattleman Road, Suite 110; Event 5: 219 N Mewnan Street, Suite 4; Event 7: report card/ lockdown; Event 9: Project Info:
[5 empty] | ASOTA OPERATIONS CTR-CSC | [15 empty] | Event 1: Tampa, FL 33607; Event 3: Sarasota, Fl 34232; Event 5: Jacksonville, FL 32202; Event 7: date May 2026; Event 9: Funds Encumbered:
[20 empty] | Contact: | Event 1: Crystal Gorman, PE; Event 3: Pinky Pakalapati, PE; Event 5: Rodrick Myrick, PE; Event 9: Funds Encumb. Date:
[7 empty] | 0 | [8 empty] | ( | 0% | ) |  | Phone: | Event 1: (239) 250-6680; Event 3: (941) 391-7290; Event 5: (561) 632-5185; Event 9: Marketing Date:; Event 11: 2025-11-11
|  | JMK-JMS-AM | [5 empty] | DIST/ST-WIDE | [6 empty] | 200000 | ( |  | ) |  | Fax: | Event 1: crystal.goreman@aecom.com; Event 3: pakalapatip@cdmsmith.com; Event 5: rmyrick@wsbeng.com; Event 9: CEI Contract #:; Event 11: 26129
2Fa | 433183-1-62-07 | [7 empty] | Anita Michael (863) 519-2256 | [9 empty] | Schedule Date-Prop. |  | 2025-01-12 | 2025-03-07 | 2025-04-09 | 2025-04-15 | N/A | N/A | 2025-05-06 | 2025-06-02 | N/A | N/A | 2025-07-30
|  | DS | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | 2025-02-12 | 2025-03-07 | 2025-04-09 | 2025-04-15 | N/A | N/A | 2025-05-06 | 2025-06-02 | N/A | N/A | 2025-08-05
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: CTI-Construction Testing & Inspection, INC; Event 3: RS&H, INC.; Event 5: WSB LLC; Event 9: Comments:; Event 11: State DS
|  |  |  | CEI (INSPECTION) BAR | [7 empty] | INSPECT CONSTRUCTION PROJS. | [6 empty] | Consultant | Address: | Event 1: 509 Sawgrass Corporate Parkway; Event 3: 6850 New Tampa Hwy, Suite 300; Event 5: 219 N Newnan ST, Suite 400; Event 9: Project Info:
[5 empty] | TOW OPERATIONS CENTER - C | [15 empty] | Event 1: Cape Coral, FL 33325; Event 3: Lakeland , FL 33815; Event 5: Jacksonville, FL 32202; Event 7: report card/ lockdown; Event 9: Funds Encumbered:; Event 11: 200000
[6 empty] | SC | [13 empty] | Contact: | Event 1: Jorge E Herrera; Event 3: Brent Wilkins, PE; Event 5: Rodrick Myrick, PE; Event 7: date July 2025; Event 9: Funds Encumb. Date:; Event 11: 2025-07-07
[7 empty] | 0 | [8 empty] | ( | 0% | ) |  | Phone: | Event 1: (305) 343-7379; Event 3: (863) 806-5881; Event 5: (561) 632-5185; Event 9: Marketing Date:; Event 11: 2025-02-04
|  | JMK-JMS-AM | [5 empty] | DIST/ST-WIDE | [6 empty] | 200000 | ( |  | ) |  | Fax: | Event 1: jherrera@ctilabs.net; Event 3: Brent.Wilkins@rsandh.com; Event 5: rmyrick@wsbeng.com; Event 9: CEI Contract #:; Event 11: CAX92
3Fa | 433183-3-62-07 | [7 empty] | Anita Michael (863) 519-2256 | [9 empty] | Schedule Date-Prop. |  | 2025-07-12 | 2026-02-13 | 2026-03-18 | 2026-03-24 | N/A | N/A | 2026-04-07 | 2026-04-30 | N/A | N/A | 2026-06-30
|  | DS | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | Event 1: 2025-02-12; Event 2: 2026-02-13; Event 5: N/A; Event 6: N/A; Event 9: N/A; Event 10: N/A
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 9: Comments:; Event 11: CM, MS, GF
|  |  |  | CEI (INSPECTION) FOR | [7 empty] | INSPECT CONSTRUCTION PROJS. | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | T MYERS OP CTR - CSC | [15 empty] | Event 7: report card/ lockdown; Event 9: Funds Encumbered:
[20 empty] | Contact: | Event 7: date June 2026; Event 9: Funds Encumb. Date:
[7 empty] | 0 | [8 empty] | ( | 0% | ) |  | Phone: | Event 9: Marketing Date:; Event 11: 2026-01-07
|  | JMK-JMS-AM | [5 empty] | DIST/ST-WIDE | [6 empty] | 200000 | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: 26117
4Fb | 440272-1-62-01 | [7 empty] | Mark L. Peronto (863) 519-2281 | [9 empty] | Schedule Date-Prop. |  | 2025-06-12 | 2025-08-15 | 2025-09-18 | 2025-09-23 | N/A | N/A | 2025-10-14 | 2025-11-07 | N/A | N/A | 2026-01-30
LS |  | TLWR | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | 2025-02-12 | 2025-08-15 | 2025-09-18 | 2025-09-23 | N/A | N/A | 2025-10-14 | 2025-11-07 | N/A | N/A
Lump Sum |  |  | N/A | [7 empty] | Kirby Radford (863)519-4107 | [7 empty] | Shortlisted | Name: | Event 1: Eisman & Russo Consulting Engineers; Event 3: HighSpans Engineering, Inc.; Event 5: HNTB Corporation; Event 9: Comments:; Event 11: TP, KR, SH
|  |  |  | FORT FRASER TRAIL OV | [7 empty] | BIKE PATH/TRAIL | [6 empty] | Consultant | Address: | Event 1: 6455 Powers Ave; Event 3: 2121 McGregor Blvd Ste.200; Event 5: 555 Morth Broadway Ave; Event 9: Project Info:; Event 11: 26141
[5 empty] | ER SR 60 | [15 empty] | Event 1: Jacksonville, FL 32217; Event 3: Fort Myers, FL 33901; Event 5: Bartow, FL 33830; Event 7: report card/ lockdown; Event 9: Funds Encumbered:; Event 11: 1526985
[14 empty] | January 15, 2026 (375) | [5 empty] | Contact: | Event 1: Dan Foss; Event 3: Vincent Zaliauskas, PE; Event 5: Jaime Deese, PE; Event 7: date January 2026; Event 9: Funds Encumb. Date:; Event 11: 2026-01-23
[7 empty] | 0 | [7 empty] | 9586000 | ( | 1.632% | ) |  | Phone: | Event 1: (813) 205-6135; Event 3: (239) 433-6000; Event 5: (407) 274-0549; Event 9: Marketing Date:; Event 11: 2025-07-23
|  | NEM-KSI-MLP | [5 empty] | POLK | [6 empty] | 1329274 | ( | 13.87% | ) |  | Fax: | Event 1: dfoss@eismanrusso.com; Event 3: VinceZ@HighSpans.com; Event 5: jdeese@hntb.com; Event 9: CEI Contract #:; Event 11: CB051
5Fa | 447287-1-62-01 | [7 empty] | Jeffrey M. Jones (239)-225-1920 | [9 empty] | Schedule Date-Prop. |  | 2025-06-12 | 2026-01-02 | 2026-02-09 | 2026-02-17 | N/A | N/A | 2026-03-03 | 2026-03-26 | N/A | 2026-04-03 | 2026-05-30
LS |  | ACSA | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date |  | 2025-02-12 | 2026-01-02 | 2026-02-09 | 2026-02-17 | N/A | N/A |  |  | N/A
Grouped With 447878-1 grouped with 438067-1 grouped with 447238-1 grouped with 448030-1 ¦¦ Lump Sum |  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: AIM Engineering & Survey; Event 3: Kinard-Stone, Inc; Event 5: Pioneer Engineers, Inc; Event 9: Comments:; Event 11: DD, KH, JT
|  |  |  | SR 25 / SR 80 (US 27 | [7 empty] | RIGID PAVEMENT RECONSTRUCTION | [6 empty] | Consultant | Address: | Event 1: 2161 Fowler Street, Suite 100; Event 3: 12801 Commerce Lake Drive; Event 5: 2005 Vista Parkway, Suite 113; Event 9: Project Info:
[5 empty] | ) FROM INDUSTRIAL CANAL T | [15 empty] | Event 1: Fort Myers, FL 33901; Event 3: Fort Myers, FL 33913; Event 5: West Palm Beach, FL 33411; Event 7: report card/ lockdown; Event 9: Funds Encumbered:
[6 empty] | O W SAGAMORE AVE | [7 empty] | June 10, 2026 (400) | [5 empty] | Contact: | Event 1: Lee Flynn, PE; Event 3: Tom Deer, PE; Event 5: Timir Shah; Event 7: date May 2026 June 2026; Event 9: Funds Encumb. Date:
[7 empty] | 1.354 | [7 empty] | 6294228 | ( | 1.071% | ) |  | Phone: | Event 1: (239) 284-1928; Event 3: (239) 340-3886; Event 5: (414) 687-6670; Event 9: Marketing Date:; Event 11: 2025-08-04
|  | NEM-STP-JMJ | [5 empty] | HENDRY | [6 empty] | 1700497 | ( | 27.02% | ) |  | Fax: | Event 1: lflynn@aimengr.com; Event 3: tom.deer@kinardstone.com; Event 5: timir@pioneercei.com; Event 9: CEI Contract #:; Event 11: 26111
5Fb | 447878-1-62-01 | [7 empty] | David J. Agacinski (239) 225-1924 | [9 empty] | Schedule Date-Prop. |  | 2025-06-12 | 2026-01-02 | 2026-02-09 | 2026-02-17 | N/A | N/A | 2026-03-03 | N/A | N/A | 2026-04-03 | 2026-05-30
LS |  | ACSS | [7 empty] | Sharon Harris, P.E. (863) 471-4854 | [8 empty] | Actual Date |  | 2025-02-12 | 2026-01-02 | 2026-02-09 | 2026-02-17 | N/A | N/A |  | N/A | N/A
Grouped With 447287-1 grouped with 438067-1 grouped with 447238-1 grouped with 448030-1 ¦¦ Lump Sum |  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: AIM Engineering & Survey; Event 3: Kinard-Stone, Inc; Event 5: Pioneer Engineers, Inc; Event 9: Comments:; Event 11: DD, KH, JT
|  |  |  | SR 80 FROM N OF CAPT | [7 empty] | MEDIAN MODIFICATION | [6 empty] | Consultant | Address: | Event 1: 2161 Fowler Street, Suite 100; Event 3: 12801 Commerce Lake Drive; Event 5: 2005 Vista Parkway, Suite 113; Event 9: Project Info:
[5 empty] | AIN HENDRY DR TO W OF FOR | [15 empty] | Event 1: Fort Myers, FL 33901; Event 3: Fort Myers, FL 33913; Event 5: West Palm Beach, FL 33411; Event 7: report card/ lockdown; Event 9: Funds Encumbered:
[6 empty] | REY DR | [7 empty] | May 20, 2026 (200) | [5 empty] | Contact: | Event 1: Lee Flynn, PE; Event 3: Tom Deer, PE; Event 5: Timir Shah; Event 7: date May 2026/ June 2026; Event 9: Funds Encumb. Date:
[7 empty] | 2.117 | [7 empty] | 3355746 | ( | 0.5712% | ) |  | Phone: | Event 1: (239) 284-1928; Event 3: (239) 340-3886; Event 5: (414) 687-6670; Event 9: Marketing Date:; Event 11: 2025-08-04
|  | NEM-STP-DJA | [5 empty] | HENDRY | [6 empty] | 339637 | ( | 10.12% | ) |  | Fax: | Event 1: lflynn@aimengr.com; Event 3: tom.deer@kinardstone.com; Event 5: timir@pioneercei.com; Event 9: CEI Contract #:; Event 11: 26111
6Fa | 447887-1-62-01 | [7 empty] | Mike G. Rud (863) 519-2769 | [9 empty] | Schedule Date-Prop. |  | 2025-07-26 | 2025-09-26 | 2025-10-29 | 2025-11-04 | N/A | N/A | 2025-11-18 | 2025-12-12 | N/A | 2025-12-19 | 2026-02-25
LS |  | ACSS | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | 2025-02-12 | 2025-09-26 | 2025-10-29 | 2025-11-04 | N/A | N/A | 2025-11-18 | 2025-12-12 | N/A | N/A
goes with 449122-1 ¦¦ Lump Sum |  |  | N/A | [7 empty] | Alex Adames (941) 708-4423 | [7 empty] | Shortlisted | Name: | Event 1: E-Plus Engineering and Consulting; Event 3: H.W. Lochner, Inc.; Event 5: Pinnacle Consulting enterprises, Inc.; Event 9: Comments:; Event 11: BW, CM, MS
|  |  |  | SR 72 FROM SWIFT RD | [7 empty] | MEDIAN MODIFICATION | [6 empty] | Consultant | Address: | Event 1: 3845 Beck Blvd, Suite 811; Event 3: 8430 Enterprises Circle, Suite 220; Event 5: 6 Palermo Avenue; Event 9: Project Info:; Event 11: 26121
[5 empty] | TO SAWYER RD | [15 empty] | Event 1: Naples, FL 34114; Event 3: Lakewood Ranch, FL 34202; Event 5: Coral Gables, FL 33134; Event 7: report card/ lockdown; Event 9: Funds Encumbered:; Event 11: 470895
[14 empty] | February 25, 2026 (450) | [5 empty] | Contact: | Event 1: Erik Sibila; Event 3: Gary Downing, PE, MBA; Event 5: Roland A.Rodriguez, PE; Event 7: date February 2026; Event 9: Funds Encumb. Date:; Event 11: 2026-02-18
[7 empty] | 1.506 | [7 empty] | 2931673 | ( | 0.499% | ) |  | Phone: | Event 1: (305) 283-9816; Event 3: (813) 579-9827; Event 5: (305) 345-0696; Event 9: Marketing Date:; Event 11: 2025-08-21
|  | NEM-KSJ-JLF | [5 empty] | SARASOTA | [6 empty] | 470895 | ( | 16.06% | ) |  | Fax: | Event 1: Esibila@epluseng.com; Event 3: gdowning @hwlochner.com; Event 5: rrodriguez@pinnaclecei.com; Event 9: CEI Contract #:; Event 11: CB075
6Fb | 449122-1-62-01 | [7 empty] | Mike G. Rud (863) 519-2769 | [9 empty] | Schedule Date-Prop. |  | 2025-07-26 | 2025-09-26 | 2025-10-29 | 2025-11-04 | N/A | N/A | 2025-11-18 | 2025-12-12 | N/A | 2025-12-19 | 2026-02-25
LS |  | ACSA | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | 2025-02-12 | 2025-09-26 | 2025-10-29 | 2025-11-04 | N/A | N/A | 2025-11-18 | 2025-12-12 | N/A | N/A
goes with 447887-1 ¦¦ Lump Sum |  |  | N/A | [7 empty] | Alex Adames (941) 708-4423 | [7 empty] | Shortlisted | Name: | Event 1: E-Plus Engineering and Consulting; Event 3: H.W. Lochner, Inc.; Event 5: Pinnacle Consulting enterprises, Inc.; Event 9: Comments:; Event 11: BW,CM, MS
|  |  |  | SR 72 FROM US 41 (SR | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 1: 3845 Beck Blvd, Suite 811; Event 3: 8430 Enterprises Circle, Suite 220; Event 5: 6 Palermo Avenue; Event 9: Project Info:; Event 11: 26121
[5 empty] | 45) TO E OF HONORE AVE | [15 empty] | Event 1: Naples, FL 34114; Event 3: Lakewood Ranch, FL 34202; Event 5: Coral Gables, FL 33134; Event 7: report card/ lockdown; Event 9: Funds Encumbered:; Event 11: 1530101
[14 empty] | February 25, 2026 (450) | [5 empty] | Contact: | Event 1: Erik Sibila; Event 3: Gary Downing, PE, MBA; Event 5: Roland A.Rodriguez, PE; Event 7: date February 2026; Event 9: Funds Encumb. Date:; Event 11: 2026-02-18
[7 empty] | 3.829 | [7 empty] | 11796890 | ( | 2.008% | ) |  | Phone: | Event 1: (305) 283-9816; Event 3: (813) 579-9827; Event 5: (305) 345-0696; Event 9: Marketing Date:; Event 11: 2025-08-21
|  | NEM-KSJ-JLF | [5 empty] | SARASOTA | [6 empty] | 1530101 | ( | 12.97% | ) |  | Fax: | Event 1: Esibila@epluseng.com; Event 3: gdowning @hwlochner.com; Event 5: rrodriguez@pinnaclecei.com; Event 9: CEI Contract #:; Event 11: CB078
7Fa | 451734-1-62-01 | [7 empty] | Kimberly D. Abate (863) 519-2745 | [9 empty] | Schedule Date-Prop. |  | 2025-08-31 | 2025-10-31 | 2025-12-10 | 2025-12-16 | N/A | N/A | 2026-01-06 | 2026-01-30 | N/A | 2026-02-03 | 2026-03-25
LS |  | ACNP | [7 empty] | Marlena Gore (941) 749-3500 | [8 empty] | Actual Date |  | 2025-02-12 | 2025-10-31 | 2025-12-10 | 2025-12-16 | N/A | N/A | 2026-01-06 | 2026-01-30 | N/A | 2026-02-03
Lump Sum |  |  | N/A | [7 empty] | Jesten J. Abraham (863) 519-2769 | [7 empty] | Shortlisted | Name: | Event 1: AIM Engineering & Survey; Event 3: E-Plus Engineering and Consulting; Event 5: Kinard -Stone, Inc; Event 9: Comments:; Event 11: AR, MS, WW
|  |  |  | I-75 (SR 93) FROM SR | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 1: 2161 Fowler Street, Ste 100; Event 3: 3845 Beck Blvd, Suite 811; Event 5: 12801 Commerce Lakes Drive, Unit1; Event 9: Project Info:
[5 empty] | 777 TO SR 681 | [15 empty] | Event 1: Fort Myers, Fl 33901; Event 3: Naples, FL 34114; Event 5: Fort Myers, Fl 33913; Event 7: report card/ lockdown; Event 9: Funds Encumbered:
[14 empty] | February 18, 2026 (700) | [5 empty] | Contact: | Event 1: Lee Flynn, PE; Event 3: Erik Sibila; Event 5: Tom Deer, PE; Event 7: date March 2026; Event 9: Funds Encumb. Date:
[7 empty] | 18.175 | [7 empty] | 38010436 | ( | 6.47% | ) |  | Phone: | Event 1: (239) 284-1928; Event 3: (305) 283-9816; Event 5: (239) 340-3886; Event 9: Marketing Date:; Event 11: 2025-08-27
|  | JMK-MCJ-KDA | [5 empty] | SARASOTA | [6 empty] | 3959440 | ( | 10.42% | ) |  | Fax: | Event 1: lflynn@aimengr.com; Event 3: Esibila@epluseng.com; Event 5: tom.deer@kinardstone.com; Event 9: CEI Contract #:; Event 11: 26128
8Fa | 451280-1-62-01 | [7 empty] | Michael Rima L. (813) 612-3374 | [9 empty] | Schedule Date-Prop. |  | 2025-01-21 | 2025-03-21 | 2025-04-23 | 2025-04-29 | N/A | N/A | 2025-04-29 | 2025-06-16 | N/A | 2025-06-23 | 2025-08-29
LS |  | BRRP | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | 2025-02-12 | 2025-03-21 | 2025-04-23 | N/A | N/A | N/A | 2025-04-29 | 2025-06-16 | N/A | 2025-06-23 | 2025-08-07
BDI ¦¦ Lump Sum |  |  | N/A | [7 empty] | Alex Adames (941) 708-4423 | [7 empty] | Shortlisted | Name: | Event 1: HighSpans Engineering, Inc.; Event 9: Comments:; Event 11: BW, CH, CB
|  |  |  | SR 758 OVER SARASOTA | [7 empty] | BRIDGE-REPAIR/REHABILITATION | [6 empty] | Consultant | Address: | Event 1: 2121 McGregor Blvd Ste.200; Event 9: Project Info:; Event 11: 26110
[5 empty] | BAY BRIDGE NO 170061 | [15 empty] | Event 1: Fort Myers, FL 33901; Event 7: report card/ lockdown; Event 9: Funds Encumbered:; Event 11: 645125
[14 empty] | August 21, 2025 (200) | [5 empty] | Contact: | Event 1: Vincent Zaliauskas, PE; Event 7: date August 2025; Event 9: Funds Encumb. Date:; Event 11: 2025-08-06
[7 empty] | 0.241 | [7 empty] | 4311094 | ( | 0.7338% | ) |  | Phone: | Event 1: (239) 433-6000; Event 9: Marketing Date:; Event 11: 2025-02-25
|  | NEM-DBA-MLR | [5 empty] | SARASOTA | [6 empty] | 645125 | ( | 14.96% | ) |  | Fax: | Event 1: VinceZ@HighSpans.com; Event 9: CEI Contract #:; Event 11: CAY48
9Fa | 430204-2-62-01 | [7 empty] | Amy Blair (863) 519-2272 | [9 empty] | Schedule Date-Prop. |  | 2025-07-19 | 2025-09-19 | 2025-10-22 | 2025-10-28 | N/A | N/A | 2025-11-18 | 2025-12-17 | N/A | 2025-12-29 | 2026-03-10
LS |  | ACBR | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | 2025-02-12 | 2025-09-19 | 2025-10-22 | 2025-10-28 | N/A | N/A | 2025-11-18 | 2025-12-17 | N/A | N/A
Lump Sum |  |  | N/A | [7 empty] | Alex Adames (941) 708-4423 | [7 empty] | Shortlisted | Name: | Event 1: Hardesty & Hanover Construction Services, LLC; Event 3: HighSpans Engineering, Inc.; Event 5: KCA & Associates; Event 9: Comments:; Event 11: JC, AA, JB
|  |  |  | SR 684 FROM SR 789 ( | [7 empty] | REPLACE MOVABLE SPAN BRIDGE | [6 empty] | Consultant | Address: | Event 1: 950 Tamiami Trail, Unit 104; Event 3: 2121 McGregor Boulevard Ste 200; Event 5: 201 North Franklin Street, Ste 900; Event 9: Project Info:
[5 empty] | GULF DRIVE) TO 123RD STRE | [15 empty] | Event 1: Port Charlotte, FL 33953; Event 3: Fort Myers, FL 33901; Event 5: Tampa, FL 33602; Event 7: report card/ lockdown; Event 9: Funds Encumbered:
[6 empty] | ET W BRIDGE # 130006 | [7 empty] | March 25, 2026 (1200) | [5 empty] | Contact: | Event 1: Steven Nappi, PE; Event 3: Vince Zaliauskas, PE; Event 5: Kenneth Spillett, PE; Event 7: date March 2026; Event 9: Funds Encumb. Date:
[7 empty] | 0.9 | [7 empty] | 128533728 | ( | 21.88% | ) |  | Phone: | Event 1: (239) 229-5853; Event 3: (239) 433-3000; Event 5: (813) 871-5331; Event 9: Marketing Date:; Event 11: 2025-08-05
|  | NEM-BCC-AEB | [5 empty] | MANATEE | [6 empty] | 10175977 | ( | 7.917% | ) |  | Fax: | Event 1: snappi@hardestyhanover.com; Event 3: VinceZ@HighSpans.com; Event 5: kspillett@kcaeng.com; Event 9: CEI Contract #:; Event 11: 26122
10Fa | 452544-1-62-01 | [7 empty] | Kathern Cothern (863) 519-2637 | [9 empty] | Schedule Date-Prop. |  |  | 2025-12-02 | 2025-01-05 | 2025-01-13 | N/A | N/A | 2026-01-13 | 2026-03-03 | N/A | 2026-03-10 | 2026-04-30
|  | SIWR | [7 empty] | Melissa Slater ( 863) 519-2590 | [8 empty] | Actual Date |  |  | 2025-12-02 | N/A | N/A | N/A | N/A | 2026-01-13 |  | N/A
|  |  | N/A | [7 empty] | Alex Ruiz (941) 465-0840 | [7 empty] | Shortlisted | Name: | Event 1: AECOM Technical Services, Inc.; Event 9: Comments:; Event 11: MS, JC, JH, AR
|  |  |  | I-75 FROM N OF GOLDEN GATE TO | [7 empty] | ADD LANES& RECONSTRUCT | [6 empty] | Consultant | Address: | Event 1: 4415 Metro Parkway, Suite 404; Event 9: Project Info:
[5 empty] | S OF CORKSCREW | [15 empty] | Event 1: Fort Myers, FL 33916; Event 7: report card/ lockdown; Event 9: Funds Encumbered:
[14 empty] | July 1, 2026 (2190) | [5 empty] | Contact: | Event 1: Crystal Gorman, PE; Event 7: date; Event 9: Funds Encumb. Date:
[7 empty] | 17.695 | [7 empty] | 206303414 | ( | 35.11% | ) |  | Phone: | Event 1: (239) 250-6680; Event 9: Marketing Date:; Event 11: 2025-11-21
|  | JMK-MMS-NHB | [5 empty] | DIST-ST-Wide | [6 empty] | 6862779 | ( | 3.327% | ) |  | Fax: | Event 1: crystal.gorman@aecom.com; Event 9: CEI Contract #:; Event 11: 26147
C/S | 196022-9-62-01 | [7 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-10-31
|  | DDR | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | Event 11: 2025-10-01
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 28
|  |  |  | LANDSCAPE ROUNDABOUT | [7 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | SR 64 AT LORRAINE RD | [15 empty] | Event 9: Funds Encumbered:; Event 11: 50698
[14 empty] | October 16, 2025 (60) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-10-01
[7 empty] | 1.918 | [7 empty] | 132001 | ( | 0.02247% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-KSI-DTR | [5 empty] | MANATEE | [6 empty] | 50698 | ( | 38.41% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 201277-8-62-01 | [7 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-02-28
|  | DDR | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | Event 11: 2026-02-05
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAK10; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 21
|  |  |  | I-75 (SR 93) AT CLARK RD (SR 72) INTERCHANGE | [7 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | Event 8: 2026-02-28; Event 9: Project Info:
[29 empty] | Funds Encumbered: |  | 181387
[14 empty] | February 19, 2026 (150) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2026-02-05
[15 empty] | 1894602 | ( | 0.3225% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-KSI-DTR | [5 empty] | SARASOTA | [6 empty] | 181387 | ( | 9.574% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAK10
C/S | 444612-1-62-01 | [7 empty] | Kellie F. Spurgeon (863) 519-2654 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-02-28
|  | ACSA | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | Event 11: 2026-02-05
GW 455769-1 GW 456075-1 |  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 11
|  |  |  | SR 45 (US 41) TO NOR | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 8: 2026-02-26; Event 9: Project Info:
[5 empty] | TH OF EDWARDS DRIVE TO NO | [15 empty] | Event 9: Funds Encumbered:; Event 11: 275148
[6 empty] | RTH OF MAGELLAN DRIVE | [7 empty] | February 25, 2026 (375) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2026-02-05
[7 empty] | 2.088 | [7 empty] | 15660615 | ( | 2.666% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-SEF-KFS | [5 empty] | MANATEE | [6 empty] | 764762 | ( | 4.883% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 444773-2-62-01 | [7 empty] | Ulises Valles (863) 519-2482 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | TALT | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date |  | Event 11: 2025-07-21
|  |  | NA | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAS93; Event 9: Comments:; Event 11: TWO 07 LOA 06
|  |  |  | WEST MAIN STREET FROM HANCHEY | [7 empty] | SIDEWALK | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | ROAD TO W OF FLORIDA AVE | [15 empty] | Event 9: Funds Encumbered:; Event 11: 94174
[14 empty] | July 30, 2025 (100) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-07-21
[7 empty] | 0.389 | [7 empty] | 441486 | ( | 0.07514% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-AEB-UVV | [5 empty] | HARDEE | [6 empty] | 94683 | ( | 21.45% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAS93
C/S | 445044-1-62-01 | [7 empty] | Jennifer S. McKinney (863) 519-2482 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-01-31
|  | ACSA | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | Event 11: 2026-01-28
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 10
|  |  |  | SR 684 (CORTEZ BLVD) | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 8: 2026-01-31; Event 9: Project Info:
[5 empty] | FROM W OF 86TH ST TO W O | [15 empty] | Event 9: Funds Encumbered:; Event 11: 411780
[6 empty] | F 26TH ST | [7 empty] | January 28, 2026 (375) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2026-01-28
[7 empty] | 3.788 | [7 empty] | 12497737 | ( | 2.127% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | MANATEE | [6 empty] | 1575914 | ( | 12.61% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 446535-1-62-01 | [7 empty] | Ahmed Abdellatif (863) 519-2834 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-03-25
|  | ACSU | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAX92; Event 8: Lockdown; Event 9: Comments:
|  |  |  | SR 544 FROM LAKE BLU | [7 empty] | SIDEWALK | [6 empty] | Consultant | Address: | Event 8: 2026-03-31; Event 9: Project Info:
[5 empty] | E DR. TO 26TH ST NW | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | March 25, 2026 (135) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[7 empty] | 0.992 | [7 empty] | 1571238 | ( | 0.2674% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-AEB-AAA | [5 empty] | POLK | [6 empty] | 166574 | ( | 10.6% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAX92
C/S | 447428-1-62-01 | [7 empty] | Jeff L. Mednick (863) 519-2304 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-09-30
|  | DDR | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-09-05
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAX92; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 3
|  |  |  | SR 555 (US 17) FROM | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-09-30; Event 9: Project Info:
[5 empty] | N OF TRANSPORT RD TO AVEN | [15 empty] | Event 9: Funds Encumbered:; Event 11: 676340
[6 empty] | UE G SW | [7 empty] | September 18, 2025 (260) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-09-02
[7 empty] | 6.258 | [7 empty] | 7498840 | ( | 1.276% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-BCC-JLM | [5 empty] | POLK | [6 empty] | 676340 | ( | 9.019% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAX92
C/S | 447882-1-62-01 | [7 empty] | Christopher B. Speese (239) 225-1973 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-10-31
|  | ACSS | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | Event 11: 2025-10-02
goes with 451014-1 |  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 8 LOA 7
|  |  |  | SR 776 FROM CHARLOTT | [7 empty] | MEDIAN MODIFICATION | [6 empty] | Consultant | Address: | Event 8: 2025-10-31; Event 9: Project Info:
[5 empty] | E COUNTY LINE TO TANGERIN | [15 empty] | Event 9: Funds Encumbered:; Event 11: 224608
[6 empty] | E WOODS BLVD | [7 empty] | October 29, 2025 (350) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-10-02
[7 empty] | 2.189 | [7 empty] | 1536192 | ( | 0.2615% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-STP-CBS | [5 empty] | SARASOTA | [6 empty] | 230677 | ( | 15.02% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 447884-2-62-01 | [7 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-02-28
|  | DS | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | Event 11: 2026-02-09
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAH32; Event 8: Lockdown; Event 9: Comments:; Event 11: Two 32 LOA 0.56
|  |  |  | SR 867 MCGREGOR BLVD | [7 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | FROM CYPRESS LAKE TO EDI | [15 empty] | Event 9: Funds Encumbered:; Event 11: 92653
[6 empty] | NBURGH DR | [7 empty] | April 16, 2026 (75) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2026-02-06
[7 empty] | 1.23 | [7 empty] | 382532 | ( | 0.06511% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-KSI-DTR | [5 empty] | LEE | [6 empty] | 94688 | ( | 24.75% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAH32
C/S | 448957-1-62-01 | [7 empty] | Ulises Valles (863) 519-2482 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | DDR | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | Event 11: 2025-07-23
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAH32; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 28 LOA 0.47
|  |  |  | SR 865 FROM E OF SR | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-07-31; Event 9: Project Info:
[5 empty] | 45 (US 41) TO W OF METRO | [15 empty] | Event 9: Funds Encumbered:; Event 11: 268885
[6 empty] | PKWY | [7 empty] | July 17, 2025 (100) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-07-23
[7 empty] | 1.978 | [7 empty] | 2063850 | ( | 0.3513% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-AEB-UVV | [5 empty] | LEE | [6 empty] | 270398 | ( | 13.1% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAH32
C/S | 448971-1-62-01 | [7 empty] | Mike G. Rud (863) 519-2769 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | DDR | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date |  | Event 11: 2025-07-21
|  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAF14; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 25 LOA 41
|  |  |  | SR 70/700 (US 98) FR | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-07-31; Event 9: Project Info:
[5 empty] | OM W OF US 98 TO E OF NW | [15 empty] | Event 9: Funds Encumbered:; Event 11: 203269
[6 empty] | 5TH AVE | [7 empty] | July 17, 2025 (100) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-07-21
[7 empty] | 0.962 | [7 empty] | 1855580 | ( | 0.3158% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JLM-PJM | [5 empty] | OKEECHOBEE | [6 empty] | 281284 | ( | 15.16% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAF14
C/S | 449011-1-62-01 | [7 empty] | Samuel Berkman (863) 519-2317 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-04-29
|  | ACSS | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAN91; Event 8: Lockdown; Event 9: Comments:
|  |  |  | SR 600 (US17/US92) AT ERNIE | [7 empty] | TRAFFIC SIGNALS | [6 empty] | Consultant | Address: | Event 8: 2026-03-01; Event 9: Project Info:
[5 empty] | CALWELL BLVD- INSTALL | [15 empty] | Event 9: Funds Encumbered:
[6 empty] | TRAFFIC SIGNAL | [7 empty] | April 29, 2026 (125) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 0 | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-WHB-SFB | [5 empty] | POLK | [6 empty] | 224556 | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAN91
C/S | 449144-2-62-01 | [7 empty] | Ryan Malloy (863) 519-2839 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-10-31
|  | DEM | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date |  | Event 11: 2025-10-14
|  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAS93; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 09 LOA 09
|  |  |  | SR 25 (US 27) VENUS WILDLIFE CROSSING | [7 empty] | PEDESTRIAN/WILDLIFE UNDERPASS | [6 empty] | Consultant | Address: | Event 8: 2025-10-29; Event 9: Project Info:
[29 empty] | Funds Encumbered: |  | 143796
[14 empty] | May 20, 2026 (250) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-10-14
[7 empty] | 0.378 | [7 empty] | 7293722 | ( | 1.241% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-BJS-RNM | [5 empty] | HIGHLANDS | [6 empty] | 430800 | ( | 5.906% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAS93
C/S | 449177-1-62-01 | [7 empty] | Karina Della-Sera (863) 519-2750 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-10-31
|  | DS | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date |  | Event 11: 2025-10-01
Goes with 451262-1 |  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAS93; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 11 LOA 11
|  |  |  | SR 17 FROM SOUTH OF | [7 empty] | DRAINAGE IMPROVEMENTS | [6 empty] | Consultant | Address: | Event 8: 2025-10-31; Event 9: Project Info:
[5 empty] | LAKE VERONA BLVD TO SOUTH | [15 empty] | Event 9: Funds Encumbered:; Event 11: 635862
[6 empty] | DELANEY AVE | [7 empty] | October 29, 2025 (250) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-10-01
[7 empty] | 0.159 | [7 empty] | 2647966 | ( | 0.4507% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-BJS-KDS | [5 empty] | HIGHLANDS | [6 empty] | 185762 | ( | 7.015% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAS93
C/S | 449231-1-62-01 | [7 empty] | Jennifer S. McKinney (863) 519-2482 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-11-30
|  | DDR | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-11-04
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAX92; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 05 LOA 0.04
|  |  |  | SR 35 (US 17) FROM H | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-11-30; Event 9: Project Info:
[5 empty] | ARDEE COUNTY LINE TO N OF | [15 empty] | Event 9: Funds Encumbered:; Event 11: 320673
[6 empty] | BRIDGE 160079 | [7 empty] | November 6, 2025 (100) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-11-04
[7 empty] | 2.91 | [7 empty] | 4137312 | ( | 0.7042% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-BCC-WDB | [5 empty] | POLK | [6 empty] | 320673 | ( | 7.751% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAX92
C/S | 449654-1-62-01 | [7 empty] | Phil Menke (863) 519-2803 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-09-30
|  | ACSS | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | Event 11: 2025-09-03
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAD91; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 27 LOA 45
|  |  |  | SR 70 (15TH ST E) FR | [7 empty] | SAFETY PROJECT | [6 empty] | Consultant | Address: | Event 8: 2025-09-30; Event 9: Project Info:
[5 empty] | OM 30TH AVE E TO 26TH AVE | [15 empty] | Event 9: Funds Encumbered:; Event 11: 135308
[6 empty] | E | [7 empty] | September 24, 2025 (130) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-09-03
[7 empty] | 0.252 | [7 empty] | 1159236 | ( | 0.1973% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JLM-PJM | [5 empty] | MANATEE | [6 empty] | 139388 | ( | 12.02% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAD91
C/S | 449981-1-62-01 | [7 empty] | Darryl T. Richard (863) 519-2266 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-10-31
|  | DDR | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | Event 11: 2025-10-02
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAH32; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 31 LOA .51
|  |  |  | LANDSCAPE FOWLER ST | [7 empty] | LANDSCAPING | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | AT SR 884 (COLONIAL BLVD) | [15 empty] | Event 9: Funds Encumbered:; Event 11: 42133
[14 empty] | October 16, 2025 (75) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-10-02
[7 empty] | 0.465 | [7 empty] | 250359 | ( | 0.04261% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-KSI-DTR | [5 empty] | LEE | [6 empty] | 42133 | ( | 16.83% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAH32
C/S | 450723-1-62-01 | [7 empty] | David J. Agacinski (239) 225-1924 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-03-25
|  | ACSS | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
Add as SA to CAR41 |  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAR41; Event 8: Lockdown; Event 9: Comments:
|  |  |  | SR 78 FROM W OF SANT | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 8: 2026-03-25; Event 9: Project Info:
[5 empty] | A BARBARA BLVD TO E OF DE | [15 empty] | Event 9: Funds Encumbered:
[6 empty] | L PRADO BLVD | [7 empty] | March 25, 2026 (225) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[7 empty] | 2.708 | [7 empty] | 7878978 | ( | 1.341% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-STP-DJA | [5 empty] | LEE | [6 empty] | 1033566 | ( | 13.12% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAR41
C/S | 450874-1-62-01 | [7 empty] | Phil Menke (863) 519-2803 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-08-31
|  | DDR | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-08-06
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAN91; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 31 LOA .56
|  |  |  | SR 600 (US-92/US-17) | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-08-31; Event 9: Project Info:
[5 empty] | FROM W OF RAMONA AVE TO | [15 empty] | Event 9: Funds Encumbered:; Event 11: 414031
[6 empty] | 3RD ST | [7 empty] | August 21, 2025 (180) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-08-06
[7 empty] | 5.73 | [7 empty] | 7806036 | ( | 1.329% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JLM-PJM | [5 empty] | POLK | [6 empty] | 414192 | ( | 5.306% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAN91
C/S | 450878-1-62-01 | [7 empty] | Marie Carvajal (863) 519-2669 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-09-30
|  | DDR | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-09-15
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAX92; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 2
|  |  |  | SR 33 FROM US 92 TO | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-09-30; Event 9: Project Info:
[5 empty] | PARKVIEW PL | [15 empty] | Event 9: Funds Encumbered:; Event 11: 130646
[14 empty] | September 18, 2025 (80) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-09-05
[7 empty] | 0.522 | [7 empty] | 576122 | ( | 0.09806% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JBH-MMC | [5 empty] | POLK | [6 empty] | 130646 | ( | 22.68% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAX92
C/S | 450882-1-62-01 | [7 empty] | Sam St Hilaire (863) 519-2554 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-10-31
|  | DDR | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-10-02
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAX92; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 4
|  |  |  | SR 17 FROM N OF WAVERLY | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-10-31; Event 9: Project Info:
[5 empty] | RD (CR540) TO S OF LAKE TRASK RD | [15 empty] | Event 9: Funds Encumbered:; Event 11: 214386
[14 empty] | October 16, 2025 (80) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-10-02
[7 empty] | 1.999 | [7 empty] | 1286987 | ( | 0.2191% | ) |  | Phone: | Event 9: Contractor Award Date:
[8 empty] | POLK | [6 empty] | 214386 | ( | 16.66% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAX92
C/S | 450889-1-62-01 | [7 empty] | Mike G. Rud (863) 519-2769 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | DDR | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-07-16
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAN91; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 19 LOA .24
|  |  |  | SR 37 FROM N OF CR 6 | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2026-07-31; Event 9: Project Info:
[5 empty] | 40 TO MOSES ST | [15 empty] | Event 9: Funds Encumbered:; Event 11: 241059
[14 empty] | July 17, 2025 (150) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-07-15
[7 empty] | 2.237 | [7 empty] | 1944982 | ( | 0.331% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JBH-MMC | [5 empty] | POLK | [6 empty] | 257669 | ( | 13.25% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAN91
C/S | 450890-1-62-01 | [7 empty] | C. Scott McCall (863) 519-2277 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-08-31
|  | DS | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-08-06
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAN91; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 32 LOA .57
|  |  |  | SR 37 FROM N OF VIRG | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2026-08-31; Event 9: Project Info:
[5 empty] | INIA ST TO S OF SCHOOLHOU | [15 empty] | Event 9: Funds Encumbered:; Event 11: 342106
[6 empty] | SE RD | [7 empty] | August 21, 2025 (150) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-08-06
[7 empty] | 4.192 | [7 empty] | 5769305 | ( | 0.982% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | POLK | [6 empty] | 1088972 | ( | 18.88% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAN91
C/S | 450892-1-62-01 | [7 empty] | Marie Carvajal (863) 519-2669 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | DDR | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-07-16
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAN91; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 20 LOA .25
|  |  |  | SR 37 FROM N OF SR 6 | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2026-07-31; Event 9: Project Info:
[5 empty] | 74 TO S OF CR 630 | [15 empty] | Event 9: Funds Encumbered:; Event 11: 246869
[14 empty] | July 17, 2025 (150) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-07-15
[7 empty] | 2.737 | [7 empty] | 2111912 | ( | 0.3595% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JBH-MMC | [5 empty] | POLK | [6 empty] | 246869 | ( | 11.69% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAN91
C/S | 451014-1-62-01 | [7 empty] | Ulises Valles (863) 519-2482 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-10-31
|  | DDR | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | Event 11: 2025-10-06
goes with 447882-1 |  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 9
|  |  |  | SR 776 FROM CHARLOTT | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-10-31; Event 9: Project Info:
[5 empty] | E CO LINE TO S OF US 41 | [15 empty] | Event 9: Funds Encumbered:; Event 11: 641653
[14 empty] | October 29, 2025 (350) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-10-06
[7 empty] | 11.806 | [7 empty] | 13090196 | ( | 2.228% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-AEB-UVV | [5 empty] | SARASOTA | [6 empty] | 1542452 | ( | 11.78% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 451017-1-62-01 | [7 empty] | Richard W. "Mose" Howard (863) 519-2374 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-03-31
|  | ACSA | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:
|  |  |  | SR 683 (US 301) FROM | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 8: 2026-03-31; Event 9: Project Info:
[5 empty] | US 41 TO S OF 10TH ST | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | March 25, 2026 (225) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[7 empty] | 1.07 | [7 empty] | 3548973 | ( | 0.6041% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JLM-RWH | [5 empty] | SARASOTA | [6 empty] | 834888 | ( | 23.52% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 451021-1-62-01 | [7 empty] | Mike G. Rud (863) 519-2769 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-08-31
|  | DDR | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date |  | Event 11: 2025-08-06
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAK10; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 20 LOA 20
|  |  |  | SR 789 FROM S OF COQ | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2026-08-31; Event 9: Project Info:
[5 empty] | UINA PARK ENT TO SR 64 | [15 empty] | Event 9: Funds Encumbered:; Event 11: 294724
[14 empty] | August 21, 2025 (125) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-08-06
[7 empty] | 3.738 | [7 empty] | 3359854 | ( | 0.5719% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-SEF-JBH | [5 empty] | MANATEE | [6 empty] | 298526 | ( | 8.885% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAK10
C/S | 451104-1-62-01 | [7 empty] | David J. Agacinski (239) 225-1924 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-03-31
|  | ACSA | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; Event 8: Lockdown; Event 9: Comments:
|  |  |  | SR 35 (US 17) FROM S | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 8: 2026-03-31; Event 9: Project Info:
[5 empty] | OF PINEGROVE CIRCLE TO N | [15 empty] | Event 9: Funds Encumbered:
[6 empty] | OF WASHINGTON LOOP RD | [7 empty] | March 25, 2026 (300) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[7 empty] | 2.397 | [7 empty] | 8766279 | ( | 1.492% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-STP-DJA | [5 empty] | CHARLOTTE | [6 empty] | 709849 | ( | 8.097% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ65
C/S | 451107-1-62-01 | [7 empty] | Phil Menke (863) 519-2803 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-08-31
|  | DDR | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date |  | Event 11: 2025-08-07
|  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAF14; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 26 LOA 46
|  |  |  | SR 710 FROM N OF SE | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2026-08-31; Event 9: Project Info:
[5 empty] | 48TH ST TO SW MARTIN HIGH | [15 empty] | Event 9: Funds Encumbered:; Event 11: 161578
[6 empty] | WAY | [7 empty] | August 21, 2025 (100) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-08-07
[7 empty] | 4.806 | [7 empty] | 4124695 | ( | 0.702% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JLM-PJM | [5 empty] | OKEECHOBEE | [6 empty] | 566090 | ( | 13.72% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAF14
C/S | 451262-1-62-01 | [7 empty] | Richard W. "Mose" Howard (863) 519-2374 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-10-31
|  | ACSA | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date |  | Event 11: 2025-10-01
goes with 449177-1 |  |  | N/A | [7 empty] | Dennis Day (863) 4714865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAS93; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 10
|  |  |  | SR 17 FROM S OF CR 1 | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 8: 2025-10-31; Event 9: Project Info:
[5 empty] | 7 (KENILWORTH BLVD) TO E | [15 empty] | Event 9: Funds Encumbered:; Event 11: 635862
[6 empty] | OF SR 25 (US 98 / US 27) | [7 empty] | October 29, 2025 (250) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-10-01
[7 empty] | 11.603 | [7 empty] | 8079881 | ( | 1.375% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JLM-RWH | [5 empty] | HIGHLANDS | [6 empty] | 708870 | ( | 8.773% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAS93
C/S | 451272-1-62-01 | [7 empty] | C. Scott McCall (863) 519-2277 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-09-30
|  | DDR | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | Event 11: 2025-09-08
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAH32; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 30 LOA .49
|  |  |  | SR 45 (US 41) FROM L | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2025-09-30; Event 9: Project Info:
[5 empty] | EE COUNTY LINE TO N OF OL | [15 empty] | Event 9: Funds Encumbered:; Event 11: 322577
[6 empty] | D US 41 | [7 empty] | September 18, 2025 (100) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-09-03
[7 empty] | 1.181 | [7 empty] | 2448286 | ( | 0.4167% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | COLLIER | [6 empty] | 460695 | ( | 18.82% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAH32
C/S | 451357-1-62-01 | [7 empty] | Michael Rima L. (813) 612-3374 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-08-31
|  | BRRP | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date |  | Event 11: 2025-08-05
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAH32; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 29 LOA .48
|  |  |  | US 41 OVER CALOOSAHA | [7 empty] | BRIDGE-REPAIR/REHABILITATION | [6 empty] | Consultant | Address: | Event 8: 2026-08-31; Event 9: Project Info:
[5 empty] | TCHEE RIVER BRIDGE #12000 | [15 empty] | Event 9: Funds Encumbered:; Event 11: 202809
[6 empty] | 2 | [7 empty] | August 21, 2025 (130) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-08-05
[7 empty] | 0.941 | [7 empty] | 1170166 | ( | 0.1992% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-DBA-MLR | [5 empty] | LEE | [6 empty] | 203098 | ( | 17.36% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAH32
C/S | 451358-1-62-01 | [7 empty] | Jacques J. Louis (239)-225-1914 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-03-31
|  | ACSS | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; Event 8: Lockdown; Event 9: Comments:
|  |  |  | US 41 AT MIDWAY BLVD | [7 empty] | INTERSECTION IMPROVEMENT | [6 empty] | Consultant | Address: | Event 8: 2026-03-30; Event 9: Project Info:
Funds Encumbered:
[14 empty] | March 25, 2026 (120) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[7 empty] | 0.148 | [7 empty] | 1706293 | ( | 0.2904% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-STP-JJL | [5 empty] | CHARLOTTE | [6 empty] | 173594 | ( | 10.17% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ65
C/S | 452617-1-62-01 | [7 empty] | Kellie F. Spurgeon (863) 519-2654 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-08-31
|  | DS | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-08-06
goes with 453810-1-62-01 |  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAN91; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 21 LOA .29
|  |  |  | SR 35 (US 98) FROM N OF SR 60 TO N OF CR 540A | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2026-08-31; Event 9: Project Info:
[29 empty] | Funds Encumbered: |  | 183943
[7 empty] | 3.890 | [6 empty] | August 27, 2025 (400) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-08-05
[15 empty] | 8789898 | ( | 1.496% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-SEF-KFS | [5 empty] | POLK | [6 empty] | 899303 | ( | 10.23% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAN91
C/S | 453401-1-62-01 | [7 empty] | Karina Della-Sera (863) 519-2750 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-09-30
|  | DS | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date |  | Event 11: 2025-09-08
|  |  | N/A | [7 empty] | Dennis Day (863) 4714865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAS93; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 08 LOA 08
|  |  |  | SR 29 FROM OKLAHOMA | [7 empty] | DRAINAGE IMPROVEMENTS | [6 empty] | Consultant | Address: | Event 8: 2025-09-30; Event 9: Project Info:
[5 empty] | AVE TO PARK AVE | [15 empty] | Event 9: Funds Encumbered:; Event 11: 96150
[14 empty] | September 18, 2025 (115) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-09-08
[7 empty] | 0.26 | [7 empty] | 733320 | ( | 0.1248% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-BJS-KDS | [5 empty] | HENDRY | [6 empty] | 96150 | ( | 13.11% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAS93
C/S | 453810-1-62-01 | [7 empty] | Amber Albriton (863) 519-2253 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-08-31
|  | SU | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-08-06
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAN91; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 22 LOA .30
|  |  |  | US 98 AT LYLE PARKWA | [7 empty] | TRAFFIC SIGNALS | [6 empty] | Consultant | Address: | Event 8: 2026-08-31; Event 9: Project Info:
[5 empty] | Y | [15 empty] | Event 9: Funds Encumbered:; Event 11: 183943
[14 empty] | August 27, 2025 (400) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-08-05
[7 empty] | 0.125 | [7 empty] | 1419734 | ( | 0.2416% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JBH-AMA | [5 empty] | POLK | [6 empty] | 187205 | ( | 13.19% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAN91
C/S | 455769-1-62-01 | [7 empty] | Ulises Valles (863) 519-2482 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-02-28
|  | DS | [7 empty] | Trisha Hartzel (941) 708-4401 | [8 empty] | Actual Date
GW 444612-1 GW 456075-1 |  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:
|  |  |  | SR 45 (US41) OVER BOWLESS CREEK | [7 empty] | Bridge-Repair/Rehabilitation | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | BRIDGE #130082 | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | February 25, 2026 (375) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 177650 | ( | 0.03024% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-MLP-UVV | [5 empty] | MANATEE | [6 empty] | 65511 | ( | 36.88% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 455785-1-62-01 | [7 empty] | Samuel Berkman (863) 519-2317 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-03-31
|  | ACSS | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAH32; Event 8: Lockdown; Event 9: Comments:
|  |  |  | SR 82 AT ALABAMA RD NEW SIGNAL | [7 empty] | TRAFFIC SIGNALS | [6 empty] | Consultant | Address: | Event 8: 2026-03-31; Event 9: Project Info:
Funds Encumbered:
[14 empty] | March 25, 2026 (175) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 1909443 | ( | 0.325% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-WHB-SFB | [5 empty] | LEE | [6 empty] | 233817 | ( | 12.25% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAH32
C/S | 455925-1-62-01 | [7 empty] | Belinda Thomas (863) 519-2342 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-05-31
|  | ACSU | [7 empty] | Trisha Hartzel (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:
|  |  |  | SR 684 CORTEZ RD FROM 26TH ST | [7 empty] | ATMS-ARTERIAL TRAFFIC MGMT | [6 empty] | Consultant | Address: | Event 8: 2026-05-31; Event 9: Project Info:
[5 empty] | W TO 301 BLVD E ATSPM/CV UPGRADE | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | May 4, 2026 (135) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 3000000 | ( | 0.5106% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-SAD-BMT | [5 empty] | MANATEE | [6 empty] | 450000 | ( | 15% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 456025-1-62-01 | [7 empty] | Jamie Schley (863) 519-2573 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-06-01
|  | FC5 | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAH32; Event 8: Lockdown; Event 9: Comments:
|  |  |  | I-75 (SR 93) FROM DA | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 8: 2026-06-30; Event 9: Project Info:
[5 empty] | NIELS PARKWAY TO NORTH OF | [15 empty] | Event 9: Funds Encumbered:
[6 empty] | LUCKETT ROAD | [7 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[7 empty] | 8 | [7 empty] | 2098206 | ( | 0.3571% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | LEE | [6 empty] | 157930 | ( | 7.527% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAH32
C/S | 456026-1-62-01 | [7 empty] | Samuel Berkman (863) 519-2317 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ65; Event 9: Comments:
|  |  |  | SR 951 FROM NORTH OF MAINSAIL DR | [7 empty] | TRAFFIC SIGNALS | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | TO SOUTH OF TOWER ROAD | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 261586 | ( | 0.04452% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | LEE | [6 empty] | 21610 | ( | 8.261% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ65
C/S | 456027-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAS93; Event 9: Comments:
|  |  |  | US27 FROM OLD US27 TO NORTH | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | OF RIVER ROAD | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 1503738 | ( | 0.2559% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | GLADES | [6 empty] | 121925 | ( | 8.108% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAS93
C/S | 456029-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; Event 9: Comments:
|  |  |  | US27(SR25) FROM NORTH OF LAKE ISIS | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | AVENUE TO HIGHLANDS COUNTY LINE | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 1085725 | ( | 0.1848% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | HIGHLANDS | [6 empty] | 88572 | ( | 8.158% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: HOC C/S #5
C/S | 456031-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Jessica White, P.E. (239) 985-7852 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Chris Mollitor (239) 985-7883 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAH32; Event 9: Comments:
|  |  |  | SR45 (US 41) FROM NORTH OF ELWOOD ROAD | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | TO USB 41 | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 207254 | ( | 0.03528% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | LEE | [6 empty] | 16805 | ( | 8.108% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAH32
C/S | 456033-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Trisha Hartzel (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 9: Comments:
|  |  |  | US41(SR45) FROM NORTH OF 69TH STREET | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | EAST TO SOUTH OF I-275 | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 338514 | ( | 0.05762% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | MANATEE | [6 empty] | 27448 | ( | 8.108% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 456035-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Trisha Hartzel (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 9: Comments:
|  |  |  | SR64 FROM EAST OF LORRAINE ROAD | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | TO WEST OF 162ND STREET EAST | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 68509 | ( | 0.01166% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | MANATEE | [6 empty] | 5555 | ( | 8.108% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 456037-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Trisha Hartzel (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 9: Comments:
|  |  |  | I-275 BRIDGE 130139 TO SKYWAY BRIDGE | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 105930 | ( | 0.01803% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | MANATEE | [6 empty] | 8589 | ( | 8.108% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 456038-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 9: Comments:
|  |  |  | SR 681 FROM SOUTH OF ISLA PALMA | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | LANE TO SOUTH OF I-75 | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 304548 | ( | 0.05184% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | SARASOTA | [6 empty] | 24694 | ( | 8.108% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 456039-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 9: Comments:
|  |  |  | I-75(SR93) FROM NORTH OF BEE RIDGE ROAD | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | TO SOUTH OF FRUITVILLE ROAD | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 56491 | ( | 0.009615% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | SARASOTA | [6 empty] | 4581 | ( | 8.109% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
C/S | 456040-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; Event 9: Comments:
|  |  |  | US27(SR25) FROM BERNER ROAD TO | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | SOUTH OF SR80 | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 2158888 | ( | 0.3675% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | HENDRY | [6 empty] | 175045 | ( | 8.108% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: HOC C/S #5
C/S | 456075-1-62-01 | [7 empty] | Kellie F. Spurgeon (863) 519-2654 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2026-02-28
|  | DDR | [7 empty] | Trisha Hartzel (941) 708-4401 | [8 empty] | Actual Date
GW 444612-1 GW 455769-1 |  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:; Event 11: TWO 13
|  |  |  | SR 45 (US41) FROM S OF GENERAL SPAATZ | [7 empty] | PAVEMENT ONLY RESURFACE (FLEX) | [6 empty] | Consultant | Address: | Event 8: 2026-02-28; Event 9: Project Info:
[5 empty] | BLVD TO N OF EDWARDS DR | [15 empty] | Event 9: Funds Encumbered:; Event 11: 278580
[14 empty] | February 25, 2026 (375) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 1423785 | ( | 0.2423% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-SEF-KFS | [5 empty] | MANATEE | [6 empty] | 278580 | ( | 19.57% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
LOA | 409988-1-62-05 | [7 empty] | Jon Sands (863) 519-2223 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | DS | [7 empty] | Brian Blair (863) 519-2676 | [8 empty] | Actual Date |  | Event 11: 2025-07-24
(Kayla) |  |  | N/A | [7 empty] | Kayla L. Sapp (863) 519-2227 | [7 empty] | Shortlisted | Name: | Event 1: LOA; Event 8: Lockdown; Event 9: Comments:
|  |  |  | CEI GENERAL CONSULTA | [7 empty] | INSPECT CONSTRUCTION PROJS. | [6 empty] | Consultant | Address: | Event 8: 2025-07-31; Event 9: Project Info:
[5 empty] | NT FOR CONSTRUCTION CEI S | [15 empty] | Event 9: Funds Encumbered:; Event 11: 5000000
[6 empty] | UPPORT - CSC | [13 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-07-24
[7 empty] | $ 4,500,000 | [8 empty] | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-BMB-AMS | [5 empty] | DIST/ST-WIDE | [7 empty] | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAE38
LOA | 409988-1-62-06 | [7 empty] | Jon Sands (863) 519-2223 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | DS | [7 empty] | Brian Blair (863) 519-2676 | [8 empty] | Actual Date |  | Event 11: 2025-07-21
(Kayla) |  |  | N/A | [7 empty] | Anita Michael (863) 519-2256 | [7 empty] | Shortlisted | Name: | Event 1: LOA; Event 8: Lockdown; Event 9: Comments:
|  |  |  | CEI GENERAL CONSULTA | [7 empty] | INSPECT CONSTRUCTION PROJS. | [6 empty] | Consultant | Address: | Event 8: 2025-07-31; Event 9: Project Info:
[5 empty] | NT FOR CONSTRUCTION CEI S | [15 empty] | Event 9: Funds Encumbered:; Event 11: 4100000
[6 empty] | UPPORT - CSC | [13 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-07-22
[7 empty] | $ 4,600,000 | [8 empty] | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-BMB-AMS | [5 empty] | DIST/ST-WIDE | [7 empty] | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAI79
LOA | 433183-1-62-06 | [7 empty] | Anita Michael (863) 519-2256 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | DS | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-07-15
|  |  | N/A | [7 empty] | Brandee Shweil (863) 519-4140 | [7 empty] | Shortlisted | Name: | Event 1: LOA; Event 8: Lockdown; Event 9: Comments:
|  |  |  | CEI (INSPECTION) BAR | [7 empty] | INSPECT CONSTRUCTION PROJS. | [6 empty] | Consultant | Address: | Event 8: 2025-07-31; Event 9: Project Info:
[5 empty] | TOW OPERATIONS CENTER - C | [15 empty] | Event 9: Funds Encumbered:; Event 11: 2173-10-14
[6 empty] | SC | [8 empty] | October 28, 2026 (400) |  |  |  |  | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-07-15
[7 empty] | $ 100,000 | [8 empty] | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-JMS-AM | [5 empty] | DIST/ST-WIDE | [7 empty] | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAN91
SA | 446346-1-62-01 | [7 empty] | C. Scott McCall (863) 519-2277 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2025-07-31
|  | ACNP | [7 empty] | Kevin Morrisey, P.E. (863) 519-4101 | [8 empty] | Actual Date |  | Event 11: 2025-09-10
|  |  | N/A | [7 empty] | Jay Wolf (863) 519-4126 | [7 empty] | Shortlisted | Name: | Event 1: Added as SA to #CAB22; Event 8: Lockdown; Event 9: Comments:; Event 11: AMD 2
|  |  |  | I-4 (SR 400) FROM GA | [7 empty] | RESURFACING | [6 empty] | Consultant | Address: | Event 8: 2025-08-30; Event 9: Project Info:
[5 empty] | LLOWAY RD TO SR 35 | [15 empty] | Event 9: Funds Encumbered:; Event 11: 1098183
[14 empty] | July 30, 2025 (300) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:; Event 11: 2025-08-28
[7 empty] | 8.498 | [7 empty] | 10462065 | ( | 1.781% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JBH-CSM | [5 empty] | POLK | [6 empty] | 1793146 | ( | 17.14% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAB22
C/S | 456028-1-62-01 | [7 empty] | Paul Barnes (863) 519-2680 | [9 empty] | Schedule Date-Prop.
|  | FC5 | [7 empty] | Sharon Harris (863) 471-4854 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Dennis Day (863) 471-4865 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #HOC C/S #5; Event 9: Comments:
|  |  |  | US27 (SR25) FROM HENDRY COUNTY LINE | [7 empty] | ROUTINE MAINTENANCE | [6 empty] | Consultant | Address: | Event 9: Project Info:
[5 empty] | TO RIDGELAWN DRIVE | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | June 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[15 empty] | 263908 | ( | 0.04492% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-AAP-JLS | [5 empty] | HENDRY | [6 empty] | 21938 | ( | 8.313% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: HOC C/S #5
C/S | 444807-6-62-01 | [7 empty] | Richard W. "Mose" Howard (863) 519-2374 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2027-05-26
|  | ACSU | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAK10; Event 8: Lockdown; Event 9: Comments:
|  |  |  | 3RD ST. E. AND 3RD ST. W. ONE-WAY PAIR | [7 empty] | TRAFFIC OPS IMPROVEMENT | [6 empty] | Consultant | Address: | Event 9: Project Info:
Funds Encumbered:
[14 empty] | May 26, 2027 (125) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[7 empty] | 0.038 | [7 empty] | 1945174 | ( | 0.3311% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | NEM-JLM-RWH | [5 empty] | MANATEE | [6 empty] | 252642 | ( | 12.99% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAK10
C/S | 444807-2-62-01 | [7 empty] | Richard W. "Mose" Howard (863) 519-2374 | [9 empty] | Schedule Date-Prop. |  | Event 11: 2027-05-26
|  | ACSU | [7 empty] | Trisha Hartzell, P.E. (941) 708-4401 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Greg Falcone (941) 708-4425 | [7 empty] | Shortlisted | Name: | Event 1: - CONTINUING SERVICES (CS) CONTRACT #CAQ61; Event 8: Lockdown; Event 9: Comments:
|  |  |  | US 41 FROM 10TH AVE | [7 empty] | TRAFFIC OPS IMPROVEMENT | [6 empty] | Consultant | Address: | Event 8: 2026-03-31; Event 9: Project Info:
[5 empty] | TO MANATEE AVE E | [15 empty] | Event 9: Funds Encumbered:
[14 empty] | May 26, 2027 (200) | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[7 empty] | 1.35 | [7 empty] | 3392847 | ( | 0.5775% | ) |  | Phone: | Event 9: Marketing Date:
|  | NEM-JLM-RWH | [5 empty] | MANATEE | [6 empty] | 441071 | ( | 13% | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: CAQ61
Full | 452544-2-62-01 | [7 empty] | NHB | [9 empty] | Schedule Date-Prop. |  | Event 5: N/A; Event 6: N/A; Event 8: N/A; Event 9: N/A
|  | MFF | [7 empty] | Melissa Slater (863( 519-2590 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Marlena Gore (941) 749-7867 | [7 empty] | Shortlisted | Name: | Event 9: Comments:
|  |  |  | I-75 FROM BONITA BEACH TO CORKSCREW | [7 empty] | ADD LANES & RECONSTRUCT | [6 empty] | Consultant | Address: | Event 9: Project Info:
Funds Encumbered:
[20 empty] | Contact: | Event 9: Funds Encumb. Date:
[16 empty] | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-MMS-NHB | [5 empty] | INTERSTATE | [6 empty] | 515000 | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: NEW
Full | 452544-3-62-01 | [7 empty] | NHB | [9 empty] | Schedule Date-Prop. |  | Event 5: N/A; Event 6: N/A; Event 8: N/A; Event 9: N/A
|  | MFF | [7 empty] | Melissa Slater (863( 519-2590 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Marlena Gore (941) 749-7867 | [7 empty] | Shortlisted | Name: | Event 9: Comments:
|  |  |  | I-75 FROM IMMOKALEE TO BONITA BEACH | [7 empty] | ADD LANES & RECONSTRUCT | [6 empty] | Consultant | Address: | Event 9: Project Info:
Funds Encumbered:
[14 empty] | June 1, 2027 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[16 empty] | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-MMS-NHB | [5 empty] | INTERSTATE | [6 empty] | 515000 | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: NEW
Full | 452544-4-62-01 | [7 empty] | NHB | [9 empty] | Schedule Date-Prop. |  | Event 5: N/A; Event 6: N/A; Event 8: N/A; Event 9: N/A
|  | MFF | [7 empty] | Melissa Slater (863( 519-2590 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Marlena Gore (941) 749-7867 | [7 empty] | Shortlisted | Name: | Event 9: Comments:
|  |  |  | IMMOKALEE INTERCHANGE | [7 empty] | ADD LANES & RECONSTRUCT | [6 empty] | Consultant | Address: | Event 9: Project Info:
Funds Encumbered:
[14 empty] | July 1, 2026 | [5 empty] | Contact: | Event 9: Funds Encumb. Date:
[16 empty] | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-MMS-NHB | [5 empty] | INTERSTATE | [6 empty] | 515000 | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: NEW
Full | 452544-5-62-01 | [7 empty] | NHB | [9 empty] | Schedule Date-Prop. |  | Event 5: N/A; Event 6: N/A; Event 8: N/A; Event 9: N/A
|  | MFF | [7 empty] | Melissa Slater (863( 519-2590 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Marlena Gore (941) 749-7867 | [7 empty] | Shortlisted | Name: | Event 9: Comments:
|  |  |  | I-75 FROM IMMOKALEE TO PINE RIDGE | [7 empty] | ADD LANES & RECONSTRUCT | [6 empty] | Consultant | Address: | Event 9: Project Info:
Funds Encumbered:
[20 empty] | Contact: | Event 9: Funds Encumb. Date:
[16 empty] | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-MMS-NHB | [5 empty] | INTERSTATE | [6 empty] | 412000 | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: NEW
Full | 452544-6-62-01 | [7 empty] | NHB | [9 empty] | Schedule Date-Prop. |  | Event 5: N/A; Event 6: N/A; Event 8: N/A; Event 9: N/A
|  | MFF | [7 empty] | Melissa Slater (863( 519-2590 | [8 empty] | Actual Date
|  |  | N/A | [7 empty] | Marlena Gore (941) 749-7867 | [7 empty] | Shortlisted | Name: | Event 9: Comments:
|  |  |  | I-75 FROM PINE RIDGE TO GOLDEN GATE | [7 empty] | ADD LANES & RECONSTRUCT | [6 empty] | Consultant | Address: | Event 9: Project Info:
Funds Encumbered:
[20 empty] | Contact: | Event 9: Funds Encumb. Date:
[16 empty] | ( | 0% | ) |  | Phone: | Event 9: Contractor Award Date:
|  | JMK-MMS-NHB | [5 empty] | INTERSTATE | [6 empty] | 103000 | ( |  | ) |  | Fax: | Event 9: CEI Contract #:; Event 11: NEW
|  | CEI FY 25/26 Total Phase 52 | [12 empty] | 587522635 | ( | 100% | )
|  | CEI FY 25/26 Total Phase 62 | [12 empty] | 49660921 | ( | 8.453% | )