## Slide 1: D4 Production management & scheduling

## Slide 2
Templates
Discoveries
Updating your schedule
Scheduling is here for you!

## Slide 3: TEMPLATES

## Slide 5
PDE Consultant Management
3R Consultant Management
Add Lanes Consultant Management
Templates on the SharePoint Site

## Slide 6
Definitions and activity relationships are available in D4 Schedule Dictionary.
Searchable by:
Activity ID
Activity Name
Results could be in various templates.

## Slide 7: DISCOVERIES
The schedule is a TOOL for Project managers, consultants and Supporting offices.
It must be discovered or customized to your project’s needs PRIOR to your consultant being on board! (You will have the opportunity to further customize the schedule, without a SCR, within 1 month of consultant execution date – as long as commitment years don’t change.) Ensure your schedule is ACHIEVABLE!
Be sure to know your scope (so you’ll know which activities should be removed) and funding (so you’ll know how to adjust durations). Discuss with applicable supporting offices.
It serves as a guide to manage your project’s time.
It can be modified at any time to re-align with your project’s changing needs.
It is logic driven, so duration and logic needs to be considered when discovering – rather than a plan of where each submittal should fall.

## Slide 8: UPDATING YOUR SCHEDULE
Before anyone can do ANY schedule updates in PSEE, they must be trained by Scheduling.
New change in logic? Talk to us so we can make sure your schedule reflects your plan!
PSEE
PSEE update reminder points:
Don’t wait until the last minute to update – we publish weekly.
Select “ALL” rather than the default of 30 day window – there maybe additional activities to update.
DOT PMs - Be sure to review what your consultant is submitting to help alleviate clarifications from us.
Leave comments when requesting activity removal.

## Slide 9: Delegates
DOT PM should have another DOT person as a delegate to approve or update activities in your absence.
Everyone should have all schedulers as a delegate, as well as D4 PSEE Admins, so we can help to troubleshoot any issues. The following list of employees should be included as a delegate for everyone:
Dianne Forte
Zoryana Fedyushko
Lauren Guy
Tzeyu Ng
Miro Poss
Reggie Dugue
Pablo Salazar

## Slide 10: Scheduling is here for you!
Requests should be sent to D4-Scheduling so we can ensure a timely response.
We usually respond within 2 days, but if a more immediate need arises,
be sure to let us know!
Reports/Views – Gantt Chart view, chronological view, 30-day spotlight, specialized reports, etc.

## Slide 11
Questions?
Anything we can do to help???