## Slide 1: FDOT District four consultant forum
FEBRUARY 27, 2018

## Slide 2: WHY ARE WE HERE?
It’s been a while since we all got together
A lot has changed
We need to share ideas, experiences and new ways to get our work done
Presentations will be made available ON THE D-4 KNOWLEDGE BASE after the Forum
http://www.fdot.gov/designsupport/Districts/D4/HomeKB.shtm
http://d4sp.dot.state.fl.us/sites/D4TRANSDEV/KB/SitePages/Home.aspx

## Slide 3: AGENDA FOR TODAY
9:00 Welcome/Introduction of New Staff
9:10 Review of upcoming D-4 Work Program
9:30 LRE Update Reminders
9:40 Scheduling Office
10:00 10 Minute Break
10:15 Typical Section/roundabout/exception/variation Approval Process

## Slide 4: AGENDA FOR TODAY
10:30 UTILITIES
10:45 R/W REQUIREMENTS UPDATE
11:00 10 MINUTE BREAK
11:15 EMO – SWAT/NEPA ASSIGNMENT
11:30 PUBLIC INFORMATION PROCESS FOR PD&E AND DESIGN
11:40 FINAL PLANS ROUND TABLE
11:55 WRAP UP

## Slide 5: D-4 DESIGN OFFICE
CHANGES IN DESIGN OFFICE STAFF
DESIGN ENGINEER
ROADWAY DESIGN ENGINEER
CONSULTANT MANAGEMENT ENGINEER
STRUCTURES DESIGN ENGINEER
UTILITIES ADMINISTRATOR
DRAINAGE ENGINEER
SURVEYOR AND MAPPER
ADMINISTRATOR
STEVE BRAUN
SCOTT PETERSON
JOHN OLSON
JAMES POOLE
EUGENE KHASHPER
RAMON OTERO
JEFF SMITH
MONIFA

## Slide 6: D-4 Consultant Project Management
THREE SECTIONS IN CONSULTANT PROJECT MANAGEMENT
LEADERS OF THE THREE SECTIONS ARE:
JIM HUGHES
ANSON SONNETT
HENRY OAIKHENA

## Slide 7: D-4 Consultant Management - SECTION 4
JIM HUGHES
VANDANA NAGOLE
DONOVAN PESSOA
HAIYAN OU
TBD #1
ROBERT LOPES
VANITA SAINI

## Slide 8: D-4 Consultant Management – SECTION 5
ANSON SONNETT
HUMBERTO ARRIETA
MARIA FORMOSO
RON KAREIVA
TBD #2
HELEN JAMES
FAUSTO GOMEZ
BINOD BASNET

## Slide 9: D-4 Consultant Management – SECTION 6
HENRY OAIKHENA
THUC LE
KENZOT JASMIN
NADIR RODRIGUES
TBD #3
CARL DORVIL
FERNANDO MORALES
BING WANG

## Slide 10: District FOUR ACEC (FICE) Liaison Team
QUARTERLY MEETINGS WITH DISTRICT LEADERSHIP
MEETING MINUTES PUBLISHED
http://www.fdot.gov/procurement/marketingD4/MarketingInformation/FDOT_FICE_Liaison_Committee_Meeting_Minutes.shtm
ACEC REPRESENTATIVES
Bob Behar Rick Chesser
Rudy Gotmare Manny Then
Scott Gombar

## Slide 11: District FOUR ACEC (FICE) Liaison Team
RECENT TOPICS OF DISCUSSION
REVIEW OF STATEWIDE ACEC LIAISON COMMITTEE MEETING ISSUES
JOB CLASSIFICATION TASK TEAM DISCUSSION
NEGOTIATIONS SURVEY – NOT BEING UTILIZED
UNDERUTILIZED WORK TYPES – FACTOR IN SELECTION
SPLIT OF PE V. NON-PE HOURS IN NEGOTIATIONS
READING SCRIPT DURING SELECTION INTERVIEW WILL BE CONSIDERED IN EVALUATION

## Slide 12: DISTRICT FOUR WORK PROGRAM

## Slide 13: DISTRICT FOUR WORK PROGRAM

## Slide 14: DISTRICT FOUR WORK PROGRAM

## Slide 15: DISTRICT FOUR WORK PROGRAM Looking ahead….what’s keeping tim brock awake at night?

## Slide 16: Quality plans – how are we doing?

## Slide 17: Quality plans – how are we doing?
2,364 Supplemental Agreements added 6,120 days during construction

## Slide 18: Quality plans – how are we doing?
$131 million dollars added over the last 10 years during construction

## Slide 19: DISTRICT FOUR – CONSULTANT ACQUISITION PLAN
CONSULTANT PROJECT MANAGEMENT
TOTAL PHASE 22 AND 32 FOR FY 18/19
30 CONTRACTS TO BE ADVERTISED IN PDE AND DESIGN
$49 MILLION CONTRACT DOLLARS IN CONTRACTS
CHANGES OCCUR THROUGHOUT THE YEAR – CHECK REGULARLY

## Slide 20: DISTRICT FOUR – CONSULTANT ACQUISITION PLAN
THE CAP FOR ANY DISTRICT CAN BE FOUND AT:
http://www.fdot.gov/procurement/InternetReports.shtm
PLEASE CONTACT PSU WITH ANY QUESTIONS

## Slide 21: DISTRICT FOUR - CAP
THE CAP FOR DESIGN BUILD PROGRAM FOR ALL DISTRICTS CAN BE FOUND AT:
http://www.fdot.gov/procurement/pdf/DesignBuildAcquisitionPlan.pdf
PLEASE CONTACT PSU WITH ANY QUESTIONS

## Slide 22: DISTRICT FOUR - CAP
UPCOMING DESIGN BUILD PROJECTS IN D-4

## Slide 23: LRE UPDATE CYCLE WHY DO WE DO THIS? PROGRAM MANAGEMENT OFFICE NEEDS TO CONSTRUCT OUR 5 YEAR WORK PROGRAM EVERY YEAR NEED UPDATED ESTIMATES FOR ALL PHASES PLANNING, pde, DESIGN, R/W, CONSTRUCTION, CEI, OPERATIONS, ETC.

## Slide 24: LRE UPDATE CYCLE FY2019 - 66 due to Final Plans by 3/06/2018 – next week!!! FY2023 – 23 by 3/20/2018 FY2022 - 46 by 4/03/2018 FY2021 - 53 by 4/17/2018 FY2020 - 63 by 5/01/2018 Unfunded/others and FY2023 candidates – 80 by 5/15/2018 Plus all new R/W cost estimate requests due in R/W office by 4/30/2018.

## Slide 25: LRE UPDATE CYCLE KICK-OFF MEETING WAS LAST WEEK PRESENTATION IS AVAILABLE IN KNOWLEDGE BASE UNDER ‘PROGRAM MANAGEMENT’ – ‘FINAL PLANS’ remember – the deadline dates are for submittal to final plans there are steps to be performed prior to deadline review by your FDOT PM scope change schedule change

## Slide 26: Scheduling presentation Dianne forte

## Slide 27: 10 minute break

## Slide 28: Typical section, roundabout, exception, variation approval process Monifa godfrey-baker

## Slide 29: Utilities eugene khashper

## Slide 30: RIGHT OF WAY REQUIREMENTS PROJECTS WITH r/W ARE USUALLY DRIVEN BY THE R/W identification and ACQUISITION SCHEDULE CRITICAL THAT THE DESIGN TEAM PROVIDES ACCURATE, COMPLETE AND CONSISTENT INFORMATION TO THE ACQUISITION TEAM d-4 ADDED STEPS TO MINIMIZE CHANGES DURING THE ACQUISITION PHASE

## Slide 31: RIGHT OF WAY REQUIREMENTS MOST r/w PROJECTS HAVE BEEN THROUGH THE pde PROCESS COMING OUT OF PDE: APPROVED ALIGNMENT WITH PRELIMINARY R/W REQUIRMENTS FOR THE CORRIDOR, POTENTIAL POND SITES, OTHER R/W IMPACTS IDENTIFIED DESIGN TEAM FINE TUNES INFORMATION AND PROVIDES FINAL R/W REQUIREMENTS TO THE Mapping office

## Slide 32: RIGHT OF WAY REQUIREMENTS design team: soon after ntp, schedule a r/w kick-off meeting to brief the the r/w office on the project (schedule, degree of impacts, etc.) complete/update design survey finalize geometry, typical section and profile further develop drainage design identify and develop any other elements of project that might impact R/W schedule r/w input meeting

## Slide 33: RIGHT OF WAY REQUIREMENTS goals of r/w input meeting
TARGET 60-90 DAYS PRIOR TO INITIAL ENGINEERING SUBMITTAL
design elements that will impact R/W acquisition (gravity wall or slope)?
What are the “hot” parcels where costs or impacts are severe?
R/W owners who could pose significant challenges for design acquisition
license agreement versus easement
utility challenges

## Slide 34: RIGHT OF WAY REQUIREMENTS
  INVITEES TO R/W INPUT MEETING:
  LEGAL, MAPPING, RIGHT OF WAY, APPROPRIATE DESIGN MANAGER, CONSTRUCTION, APPROPRIATE OPERATIONS ENGINEER
  WHAT TO BRING:
  ROLL PLOT OR GRAPHICS FOR OVERVIEW OF R/W NEEDS
  IDENTIFIED CONTAMINATION SITES
  POTENTIAL TRAFFIC SIGNAL LOCATIONS/CORNER CLIP NEEDS
  DRAINAGE POND LOCATIONS
  TRANSIT LOCATIONS

## Slide 35: RIGHT OF WAY REQUIREMENTS FURTHER REFINE DESIGN ISSUES THAT COULD IMPACT R/W REQUIREMENTS IMPLEMENT COMMENTS FROM R/W INPUT MEETING MAKE INITIAL ENGINEERING SUBMITTAL RECEIVE AND REVIEW ALL COMMENTS RECEIVED FROM Initial engineering submittal schedule r/w requirements meeting

## Slide 36: RIGHT OF WAY REQUIREMENTS goal of r/w requirements meeting: target 15-30 days after initial engineering comments received review design team ‘final’ r/w requirements fee parcels, PERMANENT AND TEMPORARY easements, license agreements, pond locations and sizes, proposed language/usage of proposed easements parcel by parcel review of requirements justification for each parcel discussed

## Slide 37: RIGHT OF WAY REQUIREMENTS
  INVITEES TO R/W INPUT MEETING:
  LEGAL, MAPPING, RIGHT OF WAY, APPROPRIATE DESIGN MANAGER, CONSTRUCTION, APPROPRIATE OPERATIONS ENGINEER
  WHAT TO BRING:
  ROLL PLOT AND PLANS WITH EXISTING AND PROPOSED R/W IDENTIFIED
  IDENTIFIED CONTAMINATION SITES
  FINALIZED TRAFFIC SIGNAL LOCATIONS INCLUDING CORNER CLIPS
  FINALIZED DRAINAGE POND LOCATIONS
  FINALIZED TRANSIT LOCATIONS
  DRIVEWAY PROFILES
  BACK OF SIDEWALK PROFILES
  CROSS SECTIONS

## Slide 38: RIGHT OF WAY REQUIREMENTS address comments received at r/w requirements meeting discuss with r/w office if a follow up r/w requirements meeting IS necessary – frequently two meetings are needed schedule and hold second r/w requirements meeting as necessary respond to comments make final r/w requirements submittal to mapping

## Slide 39: RIGHT OF WAY REQUIREMENTS accommodate these meetings in your project schedule at initial schedule discovery activities need to be advanced in order to make final r/w decisions (drainage design, mast arm locations, driveway profiles, etc.) changes after R/W process has started impact the schedule and may be more costly contact your FDOT PM WITH any questions related to this process

## Slide 40: 10 minute break

## Slide 41: Emo – swat/nepa delegation update georgi celusnek

## Slide 42: Public information process for pd&e and design july jimenez and Jorge padron

## Slide 43: Final plans round table tim brock