## Responsibility Matrix- RACI
Deliverable/Milestone | Project Manager | Business Analyst | Technical Architect | Quality Control Reviewers | Data Analyst | Developer | DBAT | Information Security Manager | Program Manager | Functional Coordinator | Project Sponsor | Portfolio Manager | Executive Sponsor | BSSO App Maintenance Manager
Planning Stage | [14 empty] | Legend
Project Charter - Project > 1000 hrs | R | [7 empty] | A |  | S | S | S
Project Plan - Project > 1000 hrs | R/S | [7 empty] | S | S | I | I | I |  | R | Responsible | Does the work
[15 empty] | A | Accountable | Ensures the deliverables/milestone is completed and acceptable
Project Plan - Project <= 1000 hrs | R/S | [7 empty] | A/S | S | S | S | I | I | C | Consulted | Used in the process of completing the work or must be notified/consulted about the deliverable/milestone
[15 empty] | I | Informed | Informed about the deliverable/milestone
Project Plan Review | C |  |  | R |  |  |  |  | A |  |  | I |  |  | S | Signature Sought | Must sign off on deliverable/milestone
Project Sharepoint Site | R | C | [6 empty] | A | I | I | I | I |  | Deliverable/Milestone Titles
REQUIREMENT PHASE DELIVERABLES | [14 empty] | Left Justified CAPS - PHASE OR MILESTONE
System Requirements | A | R/S |  |  | C |  | I |  | I | S | C | I |  |  | Centered - Deliverable
Software Requirements Specifications | A | R/S |  |  | C |  | I |  | I | S | C | I |  |  | Right Justified - Sub Deliverable
Conceptual Data Model | C | A |  |  | R |  | I |  | I | C |  |  |  |  | *Centered - Milestone
Requirements Traceability Matrix | A | R |  |  | I |  |  |  | I | I
Initial Integration Plan | A | R |  |  | I |  | I |  | C | I
(Requirement Reviews)
Requirements Review | C |  |  | R | I |  |  |  | A | I
Requirements Review Issues Resolved | A | R |  | C |  |  |  |  | C | I
Project Mgmt Deliverables | R | C |  |  | C |  |  |  | A | I | I | I
*Requirements Phase Signoff | R | C |  |  | C |  | I |  | S | S | I | I | I
DESIGN PHASE DELIVERABLES
System Design | A | [7 empty] | I | S | I | I
Data Model | A | C |  |  | R |  | I |  | I | I
Process Model | A | R |  |  | C |  | I |  |  | I
CRUD Matrix (Interaction Analysis) | A | R |  |  | C |  | I |  | I | I
Technical Architecture | A | I | R |  | C | I | C |  |  | I
Detailed Design | A | R | C |  | C |  | I |  | I | I
Security Plan | A | R |  |  |  |  | C | S | C | C | I
Integration Plan | A | R | [6 empty] | C | C | I | I
Conversion Plan | A | R | C |  | C |  | C |  | I
Capacity Plan | A | C | R |  | C |  | C |  | I | I
Training Plan | A | R | [6 empty] | I | S
Test Plan | A | R | I | C |  |  |  |  | I | C
Functional Test Case Matrix | C | R | C | C | I |  |  |  | I | I
Design Reviews
System Design - Technical | A | C | R |  | C |  | C |  | I
System Design - Analyst | A | R | C |  | C |  |  |  | I
Model Review | A | C | C |  | R |  | C |  | I
Security Plan | R | C | C |  | C |  | C | C | A
Resolve Design Review Issues | A | R | R | C | R |  | C |  | I | I
Project Mgmt Deliverables | R | C | C | C | C |  | C |  | A | I | I | I
*Design Phase Signoff | R | C | C | C | C |  | I |  | S | S | I | I | I
CONSTRUCTION PHASE DELIVERABLES
Application System | C | C | A |  |  | R |  |  | I | C | I
Data Structure | C | C | C |  | A | I | R |  | I
Application Environment | A | C | R | C | C | C | C |  | I | I
Functional Test Cases | A | R | C | C | C |  |  |  | I | C | I
Updated Security Plan | A | R | C |  |  |  | I | C | I | I
Updated Training Package | A | R | C | C | I | C |  |  | I | S | I
Implementation Plan | A | C | C |  |  | R | C | C | I | C
Updated Test Plan | A | R | C | C |  | C
Updated Test Case Matrix | C | A | I | R |  | I
Construction Reviews
Construction Reviews | C |  | A | R |  | R |  |  | C | I
Construction Review Issues Resolved | C | C | A | C | C | R | I |  | C | I | I
Project Mgmt Deliverables | R | C | C | C | C | C | C |  | A | I | I | I
*Construction Phase Signoff | R | [5 empty] | I |  | A/S | S | I | I
IMPLEMENTATION PHASE DELIVERABLES
Production Application System | C | C | A |  | C | R | C |  | C | C | I | I | I
Training | C | R |  |  |  | C |  |  |  | A
Conversion | C | C | A |  | C | R | C |  | I | C | I
Project Mgmt Deliverables | R | [7 empty] | A | I | I
*Implementation Phase Signoff | R | C | C |  | C | C | C |  | A/S | S | S | I | I
STABILIZATION PHASE DELIVERABLES
Stable Production Application System | A | C | C |  | C | R | C |  | I | C | I | I
*Stabilization Phase Signoff | R | [7 empty] | A/S | I | I | I | I | S
CLOSURE STAGE DELIVERABLES
Project Closeout Report | R/S | [5 empty] | I |  | A/S | S | C | C | I | C
Post Project Delivery Review Report | R | [7 empty] | A | C | C | I |  | C
Application Maintenance Support Information | A | C | C |  |  | R | I |  | C |  |  |  |  | C
*Closure Stage Signoff | R | [7 empty] | A | C | S | S | I