## OEM PSM Codes - August 2019
Office of Environmental Management PSM Codes
NOTES:
Primavera Activities - for each tracked PSM code below, primavera MUST use EITHER the PSM code followed by all zeros (705000000) or the PSM code followed by 10,000 (705010000)
Reports displaying Projected Finish vs. Actual Finish are always looking at the completion date for the PSM activity or milestone (even if it represents a start date [SEIR START]) - in Primavera, these are Early Finish and Actual Finish for the corresponding primavera activity
Required by COA?
PSM Code | Abbreviated Description | Activity to Track | Description | Duration | CE 2 | EA | EIS | SEIR
PLANNING/PRE-PD&E ACTIVITY CODES
746 | SWAT PLANNING MEETING | SWAT PLANNING MEETING | Date of SWAT Planning Meeting | 1 | Yes | Yes | Yes | Yes
747 | SWAT KICKOFF MEETING | SWAT KICKOFF MEETING | Date of SWAT Kick-Off Meeting | 1 | Yes | Yes | Yes | Yes
770 | SWAT STRATEGY MEETING | SWAT STRATEGY MEETING | Date of SWAT Strategy Meeting | 1 | Yes | Yes | Yes | Yes
700 | ETDM/ETAT PROG. SCREEN START | ETDM/ETAT PROGRAMMING SCREEN START | Enter Date when the Programming Screen is submitted to ETAT for review. Duration = 60 (this includes potential for 15 day extension request) | 45-60 | Yes | Yes | Yes | Yes
701 | ETDM PROG PRELIM SUM REP PUB | ETDM PROGRAMMING PRELIMINARY SUMMARY REPORT PUBLISHED | Enter Date when the Preliminary Programming Summary Report is published and FDOT has addressed all the comments received. Class of Action has not been assigned. | Varies | Yes | Yes | Yes | Yes
702 | ETDM PROG FINAL SUM REP PUB | ETDM PROGRAMMING FINAL SUMMARY REPORT PUBLISHED | Enter Date when the Final Programming Summary Report is published, The Programming Screen Summary is considered Final when Class of Action is assigned and accepted. | Varies | Yes | Yes | Yes | Yes
164 | SCOPE ACTIVITIES | SCOPE ACTIVITIES | Develop State 1, II and III Scope, Prepare Staffhour Estimate |  | Yes | Yes | Yes | Yes | This activity is for PSU PSM CODE
704 | ASSIGN PD&E PROJECT MANAGER | ASSIGN PD&E PROJECT MANAGER | Date PD&E Manager is assigned | 1 | Yes | Yes | Yes | Yes
705 | PD&E ADVERTISEMENT | PD&E ADVERTISEMENT | Date PD&E Project is advertised | 1 | Yes | Yes | Yes | Yes
PD&E PSM CODES
224 | ADVANCE NOTIFICATION | ADVANCE NOTIFICATION | Date AN sent (can be same as Programming Screen Start if AN sent as part of Programming Screen) | 1 | Yes | Yes | Yes | Yes
234 | NOTICE TO PROCEED | NOTICE TO PROCEED | Date Notice to Proceed is given to Consultant | 1 | Yes | Yes | Yes | Yes
706 | TYPE 2 CE START | TYPE 2 CE START | Start Date for Type 2 CE | 1 | Yes
707 | EA START | EA START | Start Date for EA. For EA, use Notice to Proceed Date | 1 |  | Yes
708 | NOI - EIS START | NOI - EIS START | Start of EIS. Date of Notice of Intent Publication in Federal Register. | 1 |  |  | Yes
741 | EIS SCOPING MEETING | EIS Scoping Meeting | Date EIS Scoping Meeting is held | 1 |  |  | Yes
709 | SEIR START | SEIR START | Start Date for SEIR | 1 |  |  |  | Yes
710 | PLANNING CONSISTENCY COMPL | PLANNING CONSISTENCY COMPLETE | Date when Planning Consistency is Complete | Varies | Yes | Yes | Yes
712 | ALTERNATIVES EVALUATION COMPL | ALTERNATIVES EVALUATION COMPLETE | Date Recommended Alternative identified by District (after VE Study) | Varies | Yes | Yes | Yes | Yes
713 | DISTRICT QC OF DRAFT ENV DOC | DISTRICT QC OF DRAFT ENVIRONMENTAL DOCUMENT | End Date when District completes QC of Draft Environmental Documents. The duration of 14 days is suggested but left up to the District to decide. | 14 | Yes | Yes | Yes | Yes
REVIEW CODES
772 | OEM ENGINEERING REVIEW | OEM ENGINEERING REVIEW | Date OEM Review of PTAR and PER is complete | 25 | Yes | Yes | Yes
773 | DISTRICT PREPARES RESPONSES | DISTRICT PREPARES RESPONSES | Date District completes review of comments and provides responses to OEM. The 15-day duration is suggested but left to the District to decide. | 15 | Yes | Yes | Yes
774 | OEM/DISTRICT COMMENT RESOLUTION | OEM/DISTRICT COMMENT RESOLUTION | Date OEM/District resolve issues/comments. A 30 days period allows 15 days for OEM to respond and provides 15 extra days for District to resolve any additional issues. | 30 | Yes | Yes | Yes
722 | TYPE 2 CE TO OEM INITIAL REVIEW | TYPE 2 CE TO OEM INITIAL REVIEW | Date OEM initial review of Type 2 CE is completed by PDC, Engineering Staff | 30 | Yes
726 | TYPE 2 CE TO COOP AGENCY INITIAL REVIEW | TYPE 2 CE TO COOP AGENCY INITIAL REVIEW | Date initial review of Type 2 CE is completed by Cooperating Agency | 30 | Yes
718 | EA TO OEM INITIAL REVIEW | EA TO OEM INITIAL REVIEW | Date OEM initial review of EA is completed by PDC, Engineering Staff | 30 |  | Yes
716 | EA TO COOP AGENCY INITIAL REVIEW | EA TO COOP AGENCY INITIAL REVIEW | Date initial review of EA is completed by Cooperating Agency(s) | 30 |  | Yes
731 | FONSI TO OEM INITIAL REVIEW | FONSI TO OEM INITIAL REVIEW | Date OEM initial review of FONSI is completed by PDC, Engineering Staff | 30 |  | Yes
717 | FONSI TO COOP AGENCY INITIAL REVIEW | FONSI TO COOP AGENCY INITIAL REVIEW | Date initial review of FONSI is completed by Cooperating Agency(s) | 30 |  | Yes
714 | DEIS TO OEM INITIAL REVIEW | DEIS TO OEM INITIAL REIVEW | Date OEM initial review of DEIS is complete by PDC, Engineering Staff | 30 |  |  | Yes
720 | DEIS TO COOP AGENCY INITIAL REVIEW | DEIS TO COOP AGENCY INITIAL REVIEW | Date initial review of DEIS is complete by Cooperating Agency(s) | 30 |  |  | Yes
724 | FEIS TO OEM INITIAL REVIEW | FEIS TO OEM INITIAL REVIEW | Date OEM initial review of FEIS is completed by PDC, Engineering Staff | 30 |  |  | Yes
721 | FEIS TO COOP AGENCY INITIAL REVIEW | FEIS TO COOP AGENCY INITIAL REVIEW | Date initial review of FEIS is completed by Cooperating Agency(s) | 30 |  |  | Yes
729 | ROD TO OEM INITIAL REVIEW | ROD TO OEM INITIAL REVIEW | Date OEM initial review of ROD is completed by PDC, Engineering Staff | 30 |  |  | Yes
733 | TYPE 2 CE OEM APPROVAL FINAL REVIEW | TYPE 2 OEM APPROVAL FINAL REVIEW | Date OEM Final Review is completed in SWEPT. Includes PDC submittal confirmation, EPA recommendation for approval and OEM Director Approval. OEM approves Type 2 CE. | 44 | Yes
719 | EA OEM APPROVAL FINAL REVIEW | EA OEM APPROVAL FINAL REVIEW | Date OEM Final Review is completed in SWEPT. Includes PDC submittal confirmation, EPA and OGC recommendation for approval and OEM Director Approval. OEM approves EA for Public Availability. | 44 |  | Yes
732 | FONSI OEM APPROVAL FINAL REVIEW | FONSI OEM APPROVAL FINAL REVIEW | Date OEM Final Review of FONSI is completed in SWEPT. Includes PDC submittal confirmation, EPA recommendation for approval and OEM Director Approval. OEM approves FONSI. | 44 |  | Yes
723 | OEM NOI APPROVAL FINAL REVIEW | REVIEW of NOI BY OEM | Date OEM/OGC completes Final Review of NOI. | 44 |  |  | Yes
715 | DEIS OEM APPROVAL FINAL REVIEW | DEIS OEM APPROVAL FINAL REVIEW | Date OEM Final Review is completed in SWEPT. Includes PDC submittal confirmation, EPA and OGC recommendation for approval and OEM Director Approval. OEM approves DEIS for Public Availability. | 44 |  |  | Yes
725 | FEIS OEM APPROVAL FINAL REVIEW | FEIS OEM APPROVAL FINAL REVIEW | Date OEM Final Review is completed in SWEPT. Includes PDC submittal confirmation, EPA and OGC recommendation for approval (30 days), and OEM Director Approval. OEM approves FEIS. | 74 |  |  | Yes
730 | ROD OEM APPROVAL FINAL REVIEW | ROD TO OEM APPROVAL FINAL REVIEW | Date OEM Final Review is completed in SWEPT. Includes PDC submittal confirmation, EPA and OGC recommendation for approval and OEM Director Approval. OEM approves ROD. | 44 |  |  | Yes
727 | FEIS/ROD OEM INITIAL REVIEW | FEIS/ROD OEM INITIAL REVIEW | Date OEM initial review of FEIS and ROD is completed by PDC and Engineering Staff | 30 |  |  | Yes
728 | FEIS/ROD OEM APPROVAL FINAL REVIEW | FEIS/ROD OEM APPROVAL FINAL REVIEW | Date OEM Final Review is completed in SWEPT. Includes PDC submittal confirmation, EPA and OGC recommendation for approval (30 days), and OEM Director Approval. OEM approves FEIS and ROD | 74 |  |  | Yes
735 | FEIS/ROD TO COOP AGENCY INITIAL REVIEW | FEIS/ROD TO COOP AGENCY INITIAL REVIEW | Date initial review of FEIS/ROD is complete by Cooperating Agency(s) | 30 |  |  | Yes
APPROVAL CODES
734 | SEIR APPROVED | SEIR APPROVED | Date SEIR is approved | 1 |  |  |  | Yes
263 | LDCA | LDCA | Date of Location Design Concept Approval | 1 | Yes | Yes | Yes | Yes
736 | LDCA PUBLIC NOTICE | LDCA PUBLIC NOTICE | Date of LDCA Public Notice | 1 | Yes | Yes | Yes | Yes
738 | FEDERAL REGISTER NOTICE | FEDERAL REGISTER NOTICE | Date Notice is printed in Federal Register | 1 |  | Yes | Yes
749 | TYPE 1 CE APPROVAL | TYPE 1 CE APPROVAL | Date of Type 1 CE Approval | 1
RE-EVALUATION PSM CODES
737 | REEVALUATION TO OEM INITIAL REVIEW | REEVALUATION TO OEM INITIAL REVIEW | Start Date Re-evaluation is submitted to OEM for initial review by PDC, Engineering Staff. | 30 | Yes | Yes | Yes | Yes
739 | REEVALUATION TO OEM FINAL REVIEW | REEVALUATION TO OEM FINAL REVIEW | Start Date submitted to PDC in SWEPT. Includes End: Date OEM approves Re-evaluation (SWEPT Signature) 44 day duration (includes PDC, EPA and Director review/approval time) | 44 | Yes | Yes | Yes | Yes
PSM CODES WHEN COA IS UNKNOWN OR IF CHANGE IN COA
135 | E.M.O. STUDY | E.M.O. STUDY | General EMO Work. Use T2CE start, EA start, SEIR start, NOI date for EIS. Kept for compatibility with older studies. Do not use code from now on. | Varies | Yes | Yes | Yes | Yes
740 | NEPA COA UNKNOWN | NEPA COA UNKNOWN | Use when COA is unknown. Use NTP date | Varies | Yes | Yes | Yes
742 | COA CHANGE | COA CHANGE | Use when change in COA. Date OEM approved COA change. | 1 | Yes | Yes | Yes
743 | ON HOLD | ON HOLD | Use if the project is stopped. Use date the project was stopped. | 1 | Yes | Yes | Yes | Yes
744 | FEDERAL / STATE CHANGE | FEDERAL / STATE CHANGE | Enter Date when project is changed from Federal to State process or State to Federal process | 1 | Yes | Yes | Yes | Yes
745 | OFF HOLD | OFF HOLD | Date project is taken off hold | 1 | Yes | Yes | Yes | Yes
USE WHEN PART OF YOUR PROJECT
333 | CULTURAL RESOURCES ASSESSMENT SURVEY | CULTURAL RESOURCES ASSESSMENT SURVEY | Date Cultural Resources Assessment Survey is completed | Varies | Yes | Yes | Yes | Yes
335 | PD&E FINAL NOISE STUDY | PD&E FINAL NOISE STUDY | Date Final Noise Study Report is completed | Varies | Yes | Yes | Yes | Yes
339 | VALUE ENGINEERING REVIEW | VALUE ENGINEERING REVIEW | Date Value Engineering Review is completed. This is the date recommendations are accepted or rejected. | 5 | Yes | Yes | Yes | Yes
750 | WETLAND REPORT | WETLAND REPORT | Date Wetland Evaluation Report is complete | Varies | Yes | Yes | Yes | Yes
751 | SECTION 4(F) | SECTION 4(F) | Date Section 4(f) is complete | Varies | Yes | Yes | Yes
752 | INFORMAL USFWS CONSLT COMP | INFORMAL USFWS CONSULTATION COMPLETE | Date Informal USFWS Consultation is complete. Usually date of letter from USFWS. | Varies | Yes | Yes | Yes | Yes
753 | FORMAL USFWS CONSULT COMP | FORMAL USFWS CONSULTATION COMPLETE | Date Formal USFWS Consultation is complete. Allow 135 days to complete. | 135 | Yes | Yes | Yes | Yes
756 | 267 F.S. EFFECTS COMPLET | DHR CONSULTATION, 267 F.S. | Date of DHR Letter concurring with FDOT findings | Varies |  |  |  | Yes
757 | TRAFFIC ANALYSIS/REPORT | TRAFFIC ANALYSIS/REPORT | Date Traffic Analysis/Report is completed | Varies | Yes | Yes | Yes | Yes
758 | CORRIDOR ANALYSIS | CORRIDOR ANALYSIS | Date of Corridor Analysis Report is completed | Varies | Yes | Yes | Yes | Yes
759 | TYPICAL SECTION SELECTION | TYPICAL SECTION SELECTION | Date Typical Section Package is completed and signed. | Varies | Yes | Yes | Yes | Yes
760 | PRELIMINARY ENGINEERING REPORT | PRELIMINARY ENGINEERING REPORT | Date Preliminary Engineering Report is complete, signed and sealed. | Varies | Yes | Yes | Yes | Yes
761 | NATURAL RESOURCE EVALUATION | NATURAL RESOURCE EVALUATION | Date Natural Resource Evaluation Report is finalized | Varies | Yes | Yes | Yes | Yes
762 | SECTION 106 EFFECTS COMPLETE | SHPO CONSULTATION, SECTION 106 CONSULTATION | Date of SHPO Letter concurring with FDOT findings | Varies | Yes | Yes | Yes
763 | INFORMAL NMFS CONSULT COMP | NMFS INFORMAL CONSULTATION COMPLETE | Date of NMFS Letter concurring with FDOT Determination for Informal Consultation | Varies | Yes | Yes | Yes | Yes
764 | FORMAL NMFS CONSULT COMP | NMFS FORMAL CONSULTATION COMPLETE | Date Formal NMFS Consultation is complete. Allow 135 days to complete. | 135 | Yes | Yes | Yes | Yes
765 | INTERCHANGE ACCESS REPORT | INTERCHANGE ACCESS REPORT | Date of Interchange Access Report Approval | Varies | Yes | Yes | Yes | Yes
767 | ACER METHODOLOGY MEMO | ACER METHODOLOGY MEMO | Date MM is approved in ETDM. | Varies | Yes | Yes | Yes | Yes
768 | ACER COMPLETE | ACER COMPLETE | Date District finalized the ACER with recommendation on which alternatives are eliminated. | Varies | Yes | Yes | Yes | Yes
769 | ACER OEM CONCURRENCE | ACER OEM CONCURRENCE | Date OEM concurs with elimination of alternatives and ACER is approved. | Varies | Yes | Yes | Yes | Yes
PUBLIC INVOLVEMENT PSM CODES
365 | PREPARE FOR PUBLIC MEETING | PREPARE FOR PUBLIC MEETING | Date you start Preparing for Public Information/Public Kickoff Meeting. This could include date of site review, newsletter, etc. | Varies | Yes | Yes | Yes | Yes
292 | PUBLIC INFO MEETING | PUBLIC INFORMATION/KICKOFF MEETING | Date of Public Information Meeting/Public Kickoff Meeting | 1 | Yes | Yes | Yes | Yes
711 | ALTERNATIVES WORKSHOP | ALTERNATIVES WORKSHOP | Date of Alternatives/Corridor Workshop | 1 | Yes | Yes | Yes | Yes
366 | PREPARE FOR PUBLIC HEARING | PREPARE FOR PUBLIC HEARING | Date you start Preparing for Public Hearing. This could include date of site review, newsletter, etc. | Varies | Yes | Yes | Yes | Yes
262 | PUBLIC HEARING | PUBLIC HEARING | Date Public Hearing is Held | 1 | Yes | Yes | Yes | Yes
CODES ELIMINATED (May repurpose in future)
703 | INITIAL PD&E SCOPE AND SCHEDULE COMPL | PD&E SCOPE AND SCHEDULE COMPLETE | Date Initial PD&E Scope (Stage 1) and Schedule is completed | [5 empty] | delete in favor of PSM 164
716 | DEIS TO FHWA | DEIS TO FHWA | Date DEIS is submitted to FHWA
717 | DEIS FHWA APPROVAL | DEIS FHWA APPROVAL | Date FHWA Approves DEIS
720 | EA TO FHWA | EA TO FHWA | Date EA is submitted to FHWA
721 | EA APPROVED FHWA | EA APPROVED FHWA | Date FHWA Approves FHWA
726 | FEIS TO FHWA | FEIS TO FHWA | Date FEIS is submitted to FHWA
727 | FEIS FHWA APPROVED | FEIS FHWA APPROVED | Date FHWA approves FEIS
729 | FEIS/ROD TO FHWA APPROVED | FEIS/ROD TO FHWA APPROVED | Date FHWA approves FEIS/ROD
731 | ROD TO FHWA APPROVED | ROD TO FHWA APPROVED | Date FHWA approves ROD
733 | FONSI TO FHWA APPROVED | FONSI TO FHWA APPROVED | Date FONSI is approved by FHWA
735 | CO-LEGAL SUFFICIENCY REVIEW | CO-LEGAL SUFFICIENCY REVIEW | Date Legal Sufficiency Review by FDOT CO Legal Staff is complete
737 | ENV DOC REEVALUATIONS - PE | PREPARE ENVIRONMENTAL DOCUMENT REEVALUATIONS | Date Re-evaluation is completed for Preliminary Engineering
739 | ENV DOC REEVALUATIONS - R/W | PREPARE ENVIRONMENTAL DOCUMENT REEVALUATIONS | Date Re-evaluation is completed for Right-of-Way
741 | ENV DOC REEVAL - DESIGN CHANGE | ENV DOC REEVAL - DESIGN CHANGE | Date Re-evaluation is completed for Design
748 | ENV DOC REEVAL- CONST ADVERTSMT | ENV DOC REEVAL- CONSTRUCTION ADVERTISEMENT | Date Re-evaluation is completed for Construction Advertisement
771 | FINAL PD&E SCOPE | FINAL PD&E SCOPE | Date Final PD&E Scope (Stage 3) | [5 empty] | delete in favor of PSM 164
CODES AVAILABLE
748 | AVAILABLE
754 | AVAILABLE
755 | AVAILABLE
766 | AVAILABLE
775 | AVAILABLE
776 | AVAILABLE
777 | AVAILABLE
778 | AVAILABLE
779 | AVAILABLE
780 | AVAILABLE
781 | AVAILABLE
782 | AVAILABLE
783 | AVAILABLE
784 | AVAILABLE
785 | AVAILABLE
786 | AVAILABLE
787 | AVAILABLE
788 | AVAILABLE
789 | AVAILABLE
790 | AVAILABLE
791 | AVAILABLE
792 | AVAILABLE
793 | AVAILABLE
794 | AVAILABLE
795 | AVAILABLE
796 | AVAILABLE
797 | AVAILABLE
798 | AVAILABLE
799 | AVAILABLE
|  | COA = Class of Action | OGC - Office of General Council
|  | CE 2 = Type 2 Categorical Exclusion | PDC - Project Delivery Coordinator
|  | EA = Environmental Assessment | ACER - Alternative Corridor Evaluation Report
EIS = Environmental Impact Statement
ETDM = Efficient Transportation Decision Making
FHWA = Federal Highway Administration
FONSI = Finding of No Significant Impact
NOI = Notice of Intent
PD&E = Project Development and Environment
ROD = Record of Decision
SEIR = State Environmental Impact Report
OEM = Office of Environmental Management
DHR= Division of Historic Resources