## Project Information
Project Workbook
| Section: | 60GG-1.006 Monitoring & Controlling | Risk & Complexity Category |  |  |  | Project Information
| Documentation or Activity: | [5 empty] | Project
| Monitor & Control Project Risks |  | 4 | 3 | 2 | 1 | Project Manager
| No. | Requirements |  |  |  |  | Risk & Complexity Category
| 006.6.1 | The project is monitoring and controlling project risks as documented in the approved Risk Management Plan. | Required | Required | Required |  | Project Sponsor
| 006.6.2 | The project is performing risk assessments to identify new risks, reassess current risks, escalate risks to issues, and close outdated risks. | Required | Required | Required |  | Last Updated (Date)
| 006.6.3 | The project is maintaining a Risk Tracking Log that includes a description of the project risk. | Required | Required | Required |  | Update Log | Purpose of the update
| 006.6.4 | The project is maintaining a Risk Tracking Log that includes the owner of the project risk. | Required | Required | Required
| 006.6.5 | The project is maintaining a Risk Tracking Log that includes a the risk response / mitigation strategy. | Required | Required | Required
| 006.6.6 | The project is maintaining a Risk Tracking Log that includes risk impact analysis. | Required | Required | Required
| 006.6.7 | The project is maintaining a Risk Tracking Log that includes risk probability. | Required | Required | Required
| 006.6.8 | The project is maintaining a Risk Tracking Log that includes risk priority. | Required | Required | Required
| 006.6.9 | The project is maintaining a Risk Tracking Log that includes risk status. | Required | Required | Required
| 006.6.10 | The project is maintaining a Risk Tracking Log that includes risk open dates. | Required | Required | Required
| 006.6.11 | The project is maintaining a Risk Tracking Log that includes risk close dates. | Required | Required | Required
| 006.6.12 | The project is monitoring, documenting, and addressing project risks. |  |  |  | Required
| Section: | 60GG-1.006 Monitoring & Controlling | Risk & Complexity Category
Documentation or Activity:
| Monitor & Control Project Issues |  | 4 | 3 | 2 | 1
| No. | Requirements
| 006.7.1 | The project is monitoring and controlling project issues as documented in the approved Issue Management Plan. | Required | Required | Required
| 006.7.2 | The project is reviewing all documented issues to identify new issues, reassess current issues, and close resolved issues. | Required | Required | Required
| 006.7.3 | The project is maintaining an Issue Tracking Log that includes the issue description. | Required | Required | Required
| 006.7.4 | The project is maintaining an Issue Tracking Log that includes the issue owner. | Required | Required | Required
| 006.7.5 | The project is maintaining an Issue Tracking Log that includes the issue status. | Required | Required | Required
| 006.7.6 | The project is maintaining an Issue Tracking Log that includes the issue open date. | Required | Required | Required
| 006.7.7 | The project is maintaining an Issue Tracking Log that includes the issue due date. | Required | Required | Required
| 006.7.8 | The project is maintaining an Issue Tracking Log that includes the issue close date. | Required | Required | Required
| 006.7.9 | The project is monitoring, documenting, and addressing project issues. |  |  |  | Required
| Section: | 60GG-1.006 Monitoring & Controlling | Risk & Complexity Category
Documentation or Activity:
| Action Item Tracking |  | 4 | 3 | 2 | 1
| No. | Requirements
| 006.9.1 | The project maintains an action item log that includes the description of the action item. | Required | Required | Recommended | Recommended
| 006.9.2 | The project maintains an action item log that includes the action item owner. | Required | Required | Recommended | Recommended
| 006.9.3 | The project maintains an action item log that includes the action item date assigned. | Required | Required | Recommended | Recommended
| 006.9.4 | The project maintains an action item log that includes the action item date due. | Required | Required | Recommended | Recommended
| 006.9.5 | The project maintains an action item log that includes the action item status. | Required | Required | Recommended | Recommended
| Section: | 60GG-1.006 Monitoring & Controlling | Risk & Complexity Category
Documentation or Activity:
| Decision Tracking |  | 4 | 3 | 2 | 1
| No. | Requirements
| 006.8.1 | The project is maintaining a decision tracking log that includes the project decision description. | Required | Required | Recommended | Recommended
| 006.8.2 | The project is maintaining a decision tracking log that includes the project decision approval authority. | Required | Required | Recommended | Recommended
| 006.8.3 | The project is maintaining a decision tracking log that includes the project decision entry date. | Required | Required | Recommended | Recommended
| 006.8.4 | The project is maintaining a decision tracking log that includes the project decision due date. | Required | Required | Recommended | Recommended
| 006.8.5 | The project is maintaining a decision tracking log that includes the project decision’s actual date of the decision. | Required | Required | Recommended | Recommended
| 006.8.6 | The project is maintaining a decision tracking log that includes the impact to scope, schedule, and cost of the project decision. | Required | Required | Recommended | Recommended
| 006.8.7 | The project is maintaining a decision tracking log that includes the status of the project decision. | Required | Required | Recommended | Recommended
| Section: | 60GG-1.006 Monitoring & Controlling | Risk & Complexity Category
Documentation or Activity:
| Monitor & Control Project Change |  | 4 | 3 | 2 | 1
| No. | Requirements
| 006.1.1 | The project is following the change control process as documented in the Change Management Plan. | Required | Required | Required | Required
| 006.1.2 | An Event-Driven Risk & Complexity (R&C) Assessment is completed for significant change requests. | Required | Required | Required | Required
| 006.1.3 | The project maintains a Change Tracking Log that includes the description of the change. | Required | Required | Required | Required
| 006.1.4 | The project maintains a Change Tracking Log that includes the project impact to scope, schedule, and cost. | Required | Required | Required | Required
| 006.1.5 | The project maintains a Change Tracking Log that includes the change owner. | Required | Required | Required | Required
| 006.1.6 | The project maintains a Change Tracking Log that includes the change status. | Required | Required | Required | Required
| Section: | 60GG-1.006 Monitoring & Controlling | Risk & Complexity Category
Documentation or Activity:
| Lessons Learned |  | 4 | 3 | 2 | 1
| No. | Requirements
| 006.12.1 | The project is documenting the lessons learned from the project team and stakeholders throughout the project. | Required | Required | Required | Required
Instructions
1 | Enter your Project Name on the Header of each tab.
2 | Fill out the Project Information beginning on Row 3 above.
3 | Fill out each tab/log as appropriate. Rule Chapter 60GG-1 required fields are listed above. Other fields are FDOT Recommended.
4 | As updates to any log/tab are made, create a line on the update log beginning on Row 9 above.
5 | Do not make updates to the "Values" tab without approval from the CPM Section Manager. Drop-down lists on other tabs link back to this page.
6 | If this template does not fit the needs of the project, specifically document in the Project Management Plan (PMP) that deviation from this template is necessary. Any altered, added or removed sections to the template must be approved by the signatories listed on the PMP template. Note: Any modifications to the approved template must still meet the requirements of Rule Chapter 60GG-1, Florida Administrative Code (F.A.C.).
Definitions
Risk Log
Risk |  | An uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives
Item # |  | Unique sequence number assigned to each risk identified
Risk Description |  | Narrative of the nature of the risk and potential impacts (positive or negative)
Owner |  | Name of the project team member who is responsible for planning and implementing responses to the risk
Risk Response / Mitigation Plan |  | Narrative of the strategies identified to address the risk
Probability |  | Assessment of the likelihood that the risk will occur
Potential Impact |  | Assessment of the potential effect on a project objective such as schedule, cost, quality, or performance, including both negative effects for threats and positive effects for opportunities; usually reflected using a range
Risk Score |  | A calculated risk exposure created by a multiplying probability times impact
Priority |  | FDOT assigned priority for risk monitoring and mitigation activities
Status |  | An indicator of the state of the risk, e.g., New, Stable, Closed, Increasing
New |  | Risk was identified since the last review period. Will be assigned different status after discussion
Stable |  | No change in the impact or probability factors
Increasing |  | A change in the probability or impact factors changed resulting in an increased risk score
Decreasing |  | A change in the probability or impact factors changed resulting in an decreased risk score
Closed |  | The factors contributing to the risk no longer exist
Date Raised |  | The date the risk is initially identified
Date Closed |  | The date the risk is mitigated, escalated to an issue, or no longer a threat/opportunity to the project
Identified by |  | Name of the project team member who identified the risk
Risk Tolerance |  | The project’s willingness to accept the risk’s impact if it were to occur; rated at low, medium or high
Impacted Area(s) |  | The project aspects that will suffer the negative impacts (or benefit from the opportunity) of the occurrence of the risk, e.g., schedule, cost, quality
Category |  | Categorization of the risk, such as internal vs. external, or confidential vs. non-confidential; provides a way to logically group certain risks
Issues Log
Issue |  | A point or matter in question or in dispute, or a point or matter that is not settled and is under discussion or over which there are opposing views or disagreements
Item # |  | Unique sequence number assigned to each issue identified
Issue Description |  | Brief description of the issue
Owner |  | Name of the project team member who is responsible for resolving the issue
Status |  | An indicator of the state of the issue, e.g., New, Closed, Escalated
New |  | Issue was identified since the last review period. Will be assigned different status after discussion
Pending |  | Issue is open. Activity has been deferred
Open |  | Issue is active, assigned, and actions in progress to close
Closed |  | Appropriate actions or events occurred
Escalated |  | Issues in escalation
Date Opened |  | The date the issue is initially identified
Date Due |  | The date set by the project team or governance body for issue resolution
Date Closed |  | The date the issue is resolved
Priority |  | FDOT assigned priority for resolving the issue
High |  | Project scope, schedule, budget, and/or quality will be significantly impacted if not resolved.
Medium |  | Project scope, schedule, budget, and/or quality will be impacted at a noticeable level if not resolved.
Low |  | No or little impact to project scope, schedule, budget, and/or quality if not resolved
Update / Resolution |  | Description of the actions/activities to resolve issue
Identified by |  | Name of the project team member who identified the issue
Category |  | Identifies extent project affected by the issue
Action Items Log
Action |  | A proactive task identified by the project team to address a known problem or situation. Actions may also come from a risk or issue item
Item # |  | Unique sequence number assigned to each action identified
Action Item Description |  | Brief description of the action item
Owner |  | Name of the project team member who is responsible for completing the action item
Date Assigned |  | The date the action item is initially identified and assigned
Date Due |  | The date set by the project team or governance body for action item completion
Status |  | An indicator of the state of the action item, e.g., New, Completed, Open
New |  | Action item was identified since the last review period. Will be assigned different status after discussion
Pending |  | Action item is open. Activity has been deferred
Open |  | Action item is active and assigned
Completed |  | Action item has been completed
Escalated |  | Action item in escalation
Working |  | Action being worked, in progress
Priority |  | FDOT assigned priority for completing the action item
High |  | Action must be taken immediately (within 3 business days) or project scope, schedule, budget, and/or quality will be impacted
Medium |  | Action must be taken within the next 10 business day or project scope, schedule, budget, and/or quality could be impacted
Low |  | Action must be taken at some point during the project but not within the next 10 business days
Comments |  | Notes or updates for the action item
Assigned by |  | Name of the project team member who assigned the action item
Date Closed |  | The date the action item was completed
Category |  | Identifies extent project affected by the action item
Decision Log
Decision (Item) |  | A formal decision that must be communicated to sponsors and stakeholders
Item # |  | Unique sequence number assigned to each decision identified
Decision/Question Description |  | Brief description of the decision or question
Approval Authority |  | Name of the person who is responsible for making the decision / answering the question
Date of Entry |  | The date the decision or question is initially identified and documented in the Decision Log
Due Date |  | The date set by the project team or governance body for decision to made / question to be answered
Actual Date of Decision |  | The date the decision was made / the question was answered
Project Impact |  | The project aspects that are directly influenced by the decision or question, e.g., schedule, cost, quality
Status |  | An indicator of the state of the decision or question, e.g., New, Closed, Open
New |  | Decision / Question was identified since the last review period. Will be assigned different status after discussion
Pending |  | Decision / Question is open. Activity has been deferred
Open |  | Decision / Question is active and assigned
Closed |  | Decision has been made
Priority |  | FDOT assigned priority for making the decision / answering the question
High |  | Action must be taken immediately (within 3 business days) or project scope, schedule, budget, and/or quality will be impacted
Medium |  | Action must be taken within the next 10 business day or project scope, schedule, budget, and/or quality could be impacted
Low |  | Action must be taken at some point during the project but not within the next 10 business days
Comments |  | Notes or updates for the decision / question
Category |  | Identifies extent project affected by the decision
Change Log
Change Request |  | A formal proposal to modify any document, deliverable, or baseline.
Item # |  | Unique sequence number assigned to each change identified
Change Description |  | Brief description of the change request
Project Impact |  | The project aspects that are directly influenced by the decision or question, e.g., schedule, cost, quality
Owner |  | Name of the project team member who requested the change or should be the contact person for questions regarding the change
Status |  | An indicator of the state of the decision or question, e.g., New, Approved, Rejected, etc.
New |  | Change is identified since the last review period. Will be assigned different status after discussion
Deferred |  | CR is open. Activity has been deferred
Authorized |  | CR is active, assigned
Rejected |  | CR has ben Rejected
Approved |  | CR has been approved
Withdrawn |  | CR has been withdrawn
Approved for later release |  | CR has been approved for later release
Priority |  | FDOT assigned priority for making the decision / answering the question
High |  | Action must be taken immediately (within 3 business days) or project scope, schedule, budget, and/or quality will be impacted
Medium |  | Action must be taken within the next 10 business day or project scope, schedule, budget, and/or quality could be impacted
Low |  | Action must be taken at some point during the project but not within the next 10 business days
Cost Impact |  | If costs are affected, specify the amount of the increase or decrease in costs. If costs are not affected, record a "0".
Schedule Impact |  | If hours are affected, specify the amount of the increase or decrease in hours. If hours are not affected, record a "0".
Justification of the Change |  | Explain why this change is necessary
Impact if the Change is Rejected |  | What is the impact (financially and otherwise) if this change request is rejected?
Date Submitted |  | The date the change request is initially identified and documented in the Change Log
Date Closed |  | The date the change request was resolved (approved, rejected, withdrawn, etc.)
Comments |  | Notes or updates for the change request
Category |  | Identifies extent project affected by the change request
Lessons Learned Log
Lessons Learned |  | A LESSON LEARNED is the knowledge gained during a project which shows how project events were addressed or should be addressed in the future with the purpose of improving future performance. Can be an area of improvement or an area of strength.
Item # |  | Unique sequence number assigned to each lesson identified
Lesson |  | Brief description of the lesson learned
Date Logged |  | Date the Lesson Learned is recorded in the Log
Project Phase |  | Identifies the project phase where the Lesson Learned was identified
Comments |  | Notes or updates for the Lesson
Identified by |  | Name of the project team member who identified the Lesson
Category |  | Identifies an area the Lesson relates to on the project (e.g., Strength, Improvement)
Strength |  | What went right on the project
Improvement |  | Area where the project team saw an opportunity to improve

## Risk Log
Risk Log Definition: An uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives.
Item # | Risk Description | Owner | Risk Response/Mitigation Plan | Probability | Potential Impact | Risk Score (Risk Rating) | Priority | Status | Date Raised | Date Closed | Identified By | Risk Tolerance | Impacted Area(s) | Comments | Category | Probability Value | Impact Value
R001 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R002 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R003 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R004 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R005 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R006 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R007 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R008 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R009 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered
R010 | [6 empty] | FALSE | [8 empty] | Not Entered | Not Entered

## Issues Log
Issue Log Definition: A point or matter in question or in dispute, or a point or matter that is not settled and is under discussion or over which there are opposing views or disagreements.
Item # | Issue Description | Owner | Status | Date Opened | Date Due | Date Closed | Priority | Update/Resolution | Identified by | Category
I001
I002
I003
I004
I005
I006
I007
I008
I009
I010

## Action Item Log
Action Item Log Definition: An ACTION is a proactive task identified by the project team to address a known problem or situation. Actions may also come from a risk or issue item.
Item # | Action Item Description | Owner | Date Assigned | Date Due | Status | Priority | Comments | Assigned by | Date Closed | Category
A001
A002
A003
A004
A005
A006
A007
A008
A009
A010

## Decision Log
Decision Log Definition: A DECISION ITEM is a formal decision that must be communicated to sponsors and stakeholders.
Item # | Decision / Question Description | Approval Authority | Date of Entry | Due Date | Actual Date of Decision | Project Impact | Status | Priority | Comments | Category
D001
D002
D003
D004
D005
D006
D007
D008
D009
D010

## Change Log
Change Log Definition: A CHANGE Request is a formal proposal to modify any document, deliverable, or baseline.
Item # | Change Description | Project Impact | Owner | Status | Priority | Cost Impact | Schedule Impact | Justification of this Change | Impact if the Change is Rejected | Date Submitted | Date Closed | Comments | Category
CR001
CR002
CR003
CR004
CR005
CR006
CR007
CR008
CR009
CR010

## Lessons Learned
Lessons Learned Log Definition: A LESSON LEARNED is the knowledge gained during a project which shows how project events were addressed or should be addressed in the future with the purpose of improving future performance. Can be an area of improvement or an area of strength.
Item # | Lesson | Date Logged | Project Phase | Comments | Identified By | Category
LL001
LL002
LL003
LL004
LL005
LL006
LL007
LL008
LL009
LL010

## Values
Risks
RISKS
Risk Status | Description
New | Risk was identified since the last review period. Will be assigned different status after Risk Management Team discussion.
Stable | No change in the impact or probability factors.
Increasing | A change in the probability or impact factors changed resulting in an increased risk score.
Decreasing | A change in the probability or impact factors changed resulting in an decreased risk score.
Closed | The factors contributing to the risk no longer exist.
Risk Rank | Value |  | Probability | Likelihood of Occurring
Low | 1
Medium | 3 |  | 1- Low | Unlikely
High | 5 |  | 3- Medium | Likely
|  |  | 5- High | Very Likely
Risk Score |  | Probability
|  | 1- Low | 3- Medium | 5- High
Impact | 1- Low | 1 | 3 | 5
| 3- Medium | 3 | 9 | 15
| 5- High | 5 | 15 | 25
Impact | Dimensions to Consider
| Cost | Schedule | Scope | Quality | Numeric Value
1- Low | Impact to project is within the approved budget for the project | No or little impact to project schedule | Minor clarification to existing scope | Project quality is not jeopardized | 1
3- Medium | Impact to project requires a budget amendment of less than $1,000,000 | Schedule impact is possible | Scope change is noticeable, but not deemed significant | Impact to project quality possible | 3
5- High | Impact to project requires a budget amendment of greater than or equal to $1,000,000 | Schedule and deliverable due dates will be impacted | Scope change is deemed significant | Impact to project quality very likely | 5
Issues
ISSUES
Status | Description
New | Issue was identified since the last review period. Will be assigned different status after discussion
Pending | Issue is open. Activity has been deferred
Open | Issue is active, assigned, and actions in progress to close
Closed | Appropriate actions or events occurred
Escalated | Issues in escalation
Priority | Issue Description
High | Project scope, schedule, budget, and/or quality will be significantly impacted if not resolved.
Medium | Project scope, schedule, budget, and/or quality will be impacted at a noticeable level if not resolved.
Low | No or little impact to project scope, schedule, budget, and/or quality if not resolved
Action Items
ACTIONS
Status | Description
New | Action item was identified since the last review period. Will be assigned different status after discussion
Pending | Action item is open. Activity has been deferred
Open | Action item is active and assigned
Completed | Action item has been completed
Escalated | Action item in escalation
Working | Action being worked, in progress
Priority | Action Description
High | Action must be taken immediately (within 3 business days) or project scope, schedule, budget, and/or quality will be impacted.
Medium | Action must be taken within the next 10 business day or project scope, schedule, budget, and/or quality could be impacted.
Low | Action must be taken at some point during the project but not within the next 10 business days.
Decisions
Decisions
Status | Description
New | Decision/Question was identified since the last review period. Will be assigned different status after discussion
Pending | Decision is open. Activity has been deferred
Open | Decision is active and assigned
Closed | Decision has been made
Priority | Action Description
High | Action must be taken immediately (within 3 business days) or project scope, schedule, budget, and/or quality will be impacted.
Medium | Action must be taken within the next 10 business day or project scope, schedule, budget, and/or quality could be impacted.
Low | Action must be taken at some point during the project but not within the next 10 business days.
Change Requests
Change Requests
Status | Description
New | Change is identified since the last review period. Will be assigned different status after discussion
Deferred | CR is open. Activity has been deferred
Authorized | CR is active, assigned
Rejected | CR has ben Rejected
Approved | CR has been approved
Withdrawn | CR has been withdrawn
Approved for later release | CR has been approved for later release
Priority | Action Description
High | Action must be taken immediately (within 3 business days) or project scope, schedule, budget, and/or quality will be impacted.
Medium | Action must be taken within the next 10 business day or project scope, schedule, budget, and/or quality could be impacted.
Low | Action must be taken at some point during the project but not within the next 10 business days.
Lessons Learned
Lessons Learned
Strength | What went right on the project
Improvement | Area where the project team saw an opportunity to improve