## Methodology
*Click on PDF icon to access embedded hyperlinks.

## Curb Ramp Deficiences
Seg ID | Roadway ID | Local Road Name | District | County | Status | Type | DWS Type | Sides | Landing | Curb Extentions | Marked Crossing | Midblock Crossing | Island | Ped Signal | Lat | Long | Milepost (SLD) | FPID # | Fiscal Year (FY) | Letting Date | Project Status on PSEE | Work Mix/Comments
1109 | 26050000 | 331 | 2 | Alachua | Obscured/Needs Field Review | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 29.6528 | -82.3111 | 3.457 | 439489-2 | 2025 | 2024-12-04 | Advertised | 3R/ Will be addressed under this project
5667 | 72050000 | 17 | 2 | Duval | Damaged | Unknown | None | Flared | Yes | No | Faded | No | No | None | 30.3577 | -81.6537 | 10.558 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R/ Will be addressed under this project
63 | 30010000 | 98 | 2 | Dixie | Damaged | One Way Directional | Synthetic Tactile Mats | Returned Curb | No | No | Yes | Yes No Control | No | None | 29.6371 | -83.1343 | 16.05 | 439357-1 | 2022 | 2022-02-23 | Completed | 3R/ Constructed under this project
9500 | 72014000 | 109 | 2 | Duval | Obscured/Needs Field Review | Diagonal | Other | Other | No | No | Yes | No | No | Stand. Ped Signal | 30.2841 | -81.6029 | 3.404 | 209683-1 | 2020 | 2019-11-13 | Completed | Constructed under a Traffic signal update in the corridor
1109 | 26050000 | 331 | 2 | Alachua | Under Construction | One Way Directional | None | Other | No | No | No | No | No | None | 29.6539 | -82.3102 | [5 empty] | In Compliance
14490 | 72291000 | 111 | 2 | Duval | Under Construction | Parallel | Synthetic Tactile Mats | Flared and Returned | Yes | No | Yes | No | No | Stand. Ped Signal | 30.3245 | -81.7305 | [5 empty] | In Compliance
7456 | 35060000 | 53 | 2 | Madison | Under Construction | One Way Directional | Synthetic Tactile Mats | Flared and Returned | No | No | Yes | No | No | None | 30.4677 | -83.41 | [5 empty] | In Compliance

## DWS Deficiences
Seg ID | Roadway ID | Local Road Name | District | County | Status | Type | Dectectable Warning Surface Type | Sides | Landing | Curb Extentions | Marked Crossing | Midblock Crossing | Island | Ped Signal | Lat | Long | Milepost (SLD) | FPID # | Fiscal Year (FY) | Letting Date | Project Status on PSEE | Work Mix/Comments
809 | 26003000 | 120 | 2 | Alachua | Present | Diagonal | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 29.6738 | -82.3307 | 0.502 | 207648-8 | Potential FY 2029 |  | Candidate | 3R
1109 | 26050000 | 331 | 2 | Alachua | Obscured/Needs Field Review | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 29.6528 | -82.3111 | [5 empty] | In Compliance
1109 | 26050000 | 331 | 2 | Alachua | Under Construction | One Way Directional | None | Other | No | No | No | No | No | None | 29.6539 | -82.3102 | [5 empty] | In Compliance
1109 | 26050000 | 331 | 2 | Alachua | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 29.653 | -82.311 | [5 empty] | In Compliance
1109 | 26050000 | 331 | 2 | Alachua | Present | Perpendicular | None | Flared | Yes | No | No | No | No | None | 29.6539 | -82.31 | [5 empty] | In Compliance
1109 | 26050000 | 331 | 2 | Alachua | Present | Perpendicular | None | Flared | Yes | No | No | No | No | None | 29.6538 | -82.3101 | [5 empty] | In Compliance
1982 | 29040000 | 41 | 2 | Columbia | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | None | 30.2029 | -82.643 | [5 empty] | In Compliance
2264 | 27010000 | 90 | 2 | Baker | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.2807 | -82.1334 | [5 empty] | In Compliance
2818 | 26050000 | 331 | 2 | Alachua | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 29.6411 | -82.3117 | [5 empty] | In Compliance
2818 | 26050000 | 331 | 2 | Alachua | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 29.6409 | -82.3118 | [5 empty] | In Compliance
2818 | 26050000 | 331 | 2 | Alachua | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 29.6447 | -82.3117 | [5 empty] | In Compliance
2818 | 26050000 | 331 | 2 | Alachua | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 29.6446 | -82.3117 | [5 empty] | In Compliance
2818 | 26050000 | 331 | 2 | Alachua | Present | Diagonal | Other | Flared | Yes | No | Yes | No | No | None | 29.6409 | -82.3115 | 2.635 | 447962-1 | 2024 | 2024-01-31 | Under Construction | 3R
2818 | 26050000 | 331 | 2 | Alachua | Present | Diagonal | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 29.6458 | -82.3114 | 2.953 | 447962-1 | 2024 | 2024-01-31 | Under Construction | 3R
3428 | 26070000 | 26 | 2 | Alachua | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | None | 29.6522 | -82.3507 | [5 empty] | In Compliance
3428 | 26070000 | 26 | 2 | Alachua | Present | One Way Directional | None | Flared | Yes | No | Yes | No | No | None | 29.6522 | -82.35 | [5 empty] | In Compliance
3428 | 26070000 | 26 | 2 | Alachua | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | None | 29.6522 | -82.3498 | [5 empty] | In Compliance
3428 | 26070000 | 26 | 2 | Alachua | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 29.652 | -82.3496 | [5 empty] | In Compliance
3428 | 26070000 | 26 | 2 | Alachua | Present | Combined Blended Transition | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 29.6522 | -82.3496 | [5 empty] | In Compliance
4021 | 26004000 | 226 | 2 | Alachua | Present | Parallel | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 29.6362 | -82.3297 | [5 empty] | In Compliance
4242 | 28030000 | 301 (SR 16) | 2 | Bradford | Present | Diagonal | Missing or Damaged | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 29.9513 | -82.1089 | 0 | 208020-6 | Potential FY 2029 |  | Candidate | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.3416 | -81.6025 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.3415 | -81.6025 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | No | No | No | None | 30.3416 | -81.6027 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | No | No | No | None | 30.3415 | -81.6027 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Faded | No | No | None | 30.3403 | -81.6025 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Faded | No | No | None | 30.3401 | -81.6025 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Faded | No | No | Standard Pedestrian Signal | 30.3387 | -81.6027 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Faded | No | No | Standard Pedestrian Signal | 30.3387 | -81.6024 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Damaged | No | No | None | 30.3377 | -81.6024 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Faded | No | No | None | 30.3358 | -81.6026 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.3359 | -81.6028 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | Parallel | None | Flared | Yes | No | Yes | No | No | None | 30.3357 | -81.6028 | [5 empty] | In Compliance
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.3398 | -81.6027 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.3397 | -81.6027 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | Perpendicular | Other | Flared | Yes | No | Faded | No | No | Standard Pedestrian Signal | 30.3385 | -81.6025 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | Faded | No | No | Standard Pedestrian Signal | 30.3385 | -81.6027 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | Damaged | No | No | None | 30.3379 | -81.6024 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.3378 | -81.6027 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.3376 | -81.6027 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.3371 | -81.6025 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.3369 | -81.6025 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | Faded | No | No | None | 30.3368 | -81.6027 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | Faded | No | No | None | 30.3367 | -81.6027 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.336 | -81.6025 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.3349 | -81.6029 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5116 | 72110000 | 109 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | No | No | No | None | 30.3348 | -81.6027 | Off SHS | 447124-1 | 2024 |  | PROJECT TO BE DELIVERED VIA JPA UNDER 447124-2 | 3R
5377 | 72220000 | 134 | 2 | Duval | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.2485 | -81.7429 | [5 empty] | In Compliance
5377 | 72220000 | 134 | 2 | Duval | Present | Diagonal | Other | Flared | Yes | No | Faded | No | No | Standard Pedestrian Signal | 30.2485 | -81.7471 | 8.654 | 441261-1 | 2021 | 2021-05-26 | Completed | 3R
5377 | 72220000 | 134 | 2 | Duval | Present | Diagonal | Other | Flared | Yes | No | Faded | No | No | Standard Pedestrian Signal | 30.2485 | -81.7474 | 8.654 | 441261-1 | 2021 | 2021-05-26 | Completed | 3R
5377 | 72220000 | 134 | 2 | Duval | Present | Diagonal | Other | Flared | Yes | No | Faded | No | No | Standard Pedestrian Signal | 30.2482 | -81.7474 | 8.654 | 441261-1 | 2021 | 2021-05-26 | Completed | 3R
5667 | 72050000 | 17 | 2 | Duval | Damaged | Unknown | None | Flared | Yes | No | Faded | No | No | None | 30.3577 | -81.6537 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Returned Curb | No | No | Yes | No | No | None | 30.3557 | -81.654 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared | Yes | No | No | No | No | None | 30.3557 | -81.6538 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared | Yes | No | No | No | No | None | 30.3556 | -81.6537 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared | Yes | No | Yes | No | No | None | 30.3543 | -81.654 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared | Yes | No | Yes | No | No | None | 30.3542 | -81.654 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared | Yes | No | Yes | No | No | None | 30.3536 | -81.654 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared | Yes | No | Yes | No | No | None | 30.3535 | -81.6539 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | None | No | No | Yes | No | No | None | 30.3527 | -81.6539 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | None | Yes | No | Yes | No | No | None | 30.3526 | -81.6539 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | None | No | No | Yes | No | No | None | 30.3549 | -81.6537 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | None | No | No | Yes | No | No | None | 30.3549 | -81.6537 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.3542 | -81.6537 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 30.3541 | -81.6537 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | Combined Blended Transition | None | Flared | Yes | No | Yes | No | No | None | 30.3535 | -81.6537 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | Combined Blended Transition | None | Flared | Yes | No | Yes | No | No | None | 30.3534 | -81.6537 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | Combined Blended Transition | None | Flared and Returned | Yes | No | Yes | No | No | None | 30.3528 | -81.6536 | [5 empty] | In Compliance
5667 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.3527 | -81.6536 | [5 empty] | In Compliance
5844 | 38030000 | 20 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1117 | -83.583 | [5 empty] | In Compliance
5844 | 38030000 | 20 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1115 | -83.583 | [5 empty] | In Compliance
5844 | 38030000 | 20 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1115 | -83.5831 | [5 empty] | In Compliance
6022 | 72050000 | 17 | 2 | Duval | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3754 | -81.6514 | [5 empty] | In Compliance
6022 | 72050000 | 17 | 2 | Duval | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3727 | -81.6515 | [5 empty] | In Compliance
6022 | 72050000 | 17 | 2 | Duval | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3725 | -81.6512 | [5 empty] | In Compliance
6022 | 72050000 | 17 | 2 | Duval | Present | Diagonal | Missing or Damaged | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3808 | -81.6503 | 12.16 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R
6022 | 72050000 | 17 | 2 | Duval | Present | Parallel | Missing or Damaged | Flared | Yes | No | Yes | No | No | None | 30.3784 | -81.6505 | 11.999 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R
6022 | 72050000 | 17 | 2 | Duval | Present | Combined Blended Transition | Missing or Damaged | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3766 | -81.6511 | 11.856 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R
6022 | 72050000 | 17 | 2 | Duval | Present | Parallel | Missing or Damaged | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3763 | -81.651 | 11.856 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R
6022 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | Missing or Damaged | Flared and Returned | No | No | Yes | No | No | None | 30.3734 | -81.6512 | 11.464 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R
6022 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | Missing or Damaged | Flared | Yes | No | Yes | No | No | None | 30.3733 | -81.6512 | 11.464 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R
6022 | 72050000 | 17 | 2 | Duval | Present | Diagonal | Missing or Damaged | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3727 | -81.6512 | 11.596 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R
6022 | 72050000 | 17 | 2 | Duval | Present | One Way Directional | Missing or Damaged | Flared and Returned | No | No | Yes | No | No | None | 30.3687 | -81.652 | 11.325 | 445417-1 | 2023 | 2023-05-17 | Under Construction | 3R
6293 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 30.1655 | -81.7104 | [5 empty] | In Compliance
6400 | 71050000 | 18 | 2 | Clay | Present | One Way Directional | None | Flared and Returned | No | No | Faded | No | No | None | 29.9879 | -81.6912 | [5 empty] | In Compliance
6400 | 71050000 | 18 (SR 16) | 2 | Clay | Present | One Way Directional | Missing or Damaged | Flared and Returned | No | No | Yes | No | No | None | 29.9873 | -81.6922 | 22.752 | 208200-5 | 2026 | 2025-09-24 | In-Design | 3R
6413 | 72050000 | 10 | 2 | Duval | Present | Perpendicular | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3275 | -81.6562 | [5 empty] | In Compliance
6413 | 72050000 | 10 | 2 | Duval | Present | Perpendicular | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3289 | -81.656 | 8.507 | 208957-2 | 2028 | 2027-10-27 | Programmed | 3R
6413 | 72050000 | 10 | 2 | Duval | Present | Perpendicular | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3283 | -81.6562 | 8.455 | 208957-2 | 2028 | 2027-10-27 | Programmed | 3R
6413 | 72050000 | 10 | 2 | Duval | Present | Perpendicular | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3291 | -81.6559 | 8.507 | 208957-2 | 2028 | 2027-10-27 | Programmed | 3R
6413 | 72050000 | 10 | 2 | Duval | Present | Perpendicular | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3276 | -81.6564 | 8.403 | 208957-2 | 2028 | 2027-10-27 | Programmed | 3R
6413 | 72050000 | 10 | 2 | Duval | Present | Perpendicular | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3261 | -81.6568 | 8.294 | 208957-2 | 2028 | 2027-10-27 | Programmed | 3R
6445 | 72015000 | 126 | 2 | Duval | Present | Combined Blended Transition | None | Flared | Yes | No | Faded | No | No | Standard Pedestrian Signal | 30.2895 | -81.6311 | [5 empty] | In Compliance
6456 | 37010000 | 10 | 2 | Suwannee | Present | One Way Directional | Other | Flared and Returned | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.2979 | -82.9886 | 12.652 | 213560-4 | 2026 | 2025-12-10 | In-Design | 3R
6576 | 37040000 | 51 | 2 | Suwannee | Present | One Way Directional | Other | Flared and Returned | No | No | Yes | No | No | None | 30.3017 | -82.9816 | 25.059 | 210750-3 | 2025 | 2025-05-28 | In-Design | 3R
7538 | 71070000 | 21 | 2 | Clay | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.144 | -81.7641 | [5 empty] | In Compliance
7807 | 37040000 | 129 | 2 | Suwannee | Present | Unknown | None | Flared | Yes | No | Faded | No | No | None | 30.296 | -82.9846 | [5 empty] | In Compliance
7807 | 37040000 | 129 | 2 | Suwannee | Present | Unknown | None | Flared | Yes | No | Faded | No | No | None | 30.2958 | -82.9847 | [5 empty] | In Compliance
7888 | 72150000 | 117 | 2 | Duval | Present | Diagonal | Other | Flared | Yes | No | Yes | No | No | None | 30.3752 | -81.6665 | 1.383 | None | None | None | None | Will be be addressed in the next set of Resurfacing Project
7888 | 72150000 | 117 | 2 | Duval | Present | Parallel | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.373 | -81.6651 | 1.553 | None | None | None | None | Will be be addressed in the next set of Resurfacing Project
7888 | 72150000 | 117 | 2 | Duval | Present | Parallel | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3731 | -81.665 | 1.553 | None | None | None | None | Will be be addressed in the next set of Resurfacing Project
8207 | 72050000 | 17 | 2 | Duval | Present | Combined Blended Transition | None | Flared | Yes | No | Yes | No | No | None | 30.3379 | -81.655 | [5 empty] | In Compliance
8280 | 38020000 | 91 | 2 | Taylor | Present | Diagonal | None | Flared | No | No | Yes | No | No | Standard Pedestrian Signal | 30.1115 | -83.589 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | Diagonal | None | Flared | No | No | Yes | No | No | Standard Pedestrian Signal | 30.1115 | -83.5893 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | Combined Blended Transition | None | None | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.1117 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1109 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1107 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1109 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1107 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 30.1101 | -83.589 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.11 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1101 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.11 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 30.1096 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1094 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1096 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1094 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1088 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1087 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1088 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1087 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.108 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1079 | -83.5891 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.108 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1079 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1072 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1071 | -83.5894 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Faded | No | No | None | 30.1054 | -83.589 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | None | 30.1053 | -83.5889 | [5 empty] | In Compliance
8280 | 38020000 | 19 | 2 | Taylor | Present | Diagonal | Other | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.1117 | -83.5891 | 1.029 | 210878-4 | 2028 | 2028-01-26 | Programmed | 3R
8344 | 71010000 | 17 | 2 | Clay | Present | One Way Directional | Other | Flared and Returned | No | No | Yes | No | No | None | 29.9907 | -81.6784 | 11.181 | 208202-5 | 2025 | 2025-03-26 | In-Design | 3R
8344 | 71010000 | 17 | 2 | Clay | Present | One Way Directional | Other | Flared and Returned | No | No | Yes | No | No | None | 29.9906 | -81.6783 | 11.181 | 208202-5 | 2025 | 2025-03-26 | In-Design | 3R
8344 | 71010000 | 17 | 2 | Clay | Present | One Way Directional | Other | Flared and Returned | No | No | Faded | No | No | None | 29.9906 | -81.6786 | 11.181 | 208202-5 | 2025 | 2025-03-26 | In-Design | 3R
8344 | 71010000 | 17 | 2 | Clay | Present | One Way Directional | Other | Flared and Returned | No | No | Faded | No | No | None | 29.9905 | -81.6786 | 11.181 | 208202-5 | 2025 | 2025-03-26 | In-Design | 3R
8344 | 71010000 | 17 | 2 | Clay | Present | One Way Directional | Other | None | No | No | Yes | No | No | None | 29.9893 | -81.6782 | 11.094 | 208202-5 | 2025 | 2025-03-26 | In-Design | 3R
8344 | 71010000 | 17 | 2 | Clay | Present | One Way Directional | Other | Flared and Returned | No | No | Yes | No | No | None | 29.9894 | -81.6782 | 11.094 | 208202-5 | 2025 | 2025-03-26 | In-Design | 3R
8344 | 71010000 | 17 | 2 | Clay | Present | One Way Directional | Other | Flared and Returned | No | No | Yes | No | No | None | 29.9895 | -81.678 | 11.094 | 208202-5 | 2025 | 2025-03-26 | In-Design | 3R
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 30.1652 | -81.7193 | [5 empty] | In Compliance
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 30.1652 | -81.7192 | [5 empty] | In Compliance
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared and Returned | No | No | No | No | No | None | 30.1653 | -81.7173 | [5 empty] | In Compliance
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared and Returned | No | No | No | No | No | None | 30.1653 | -81.7172 | [5 empty] | In Compliance
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 30.1655 | -81.7171 | [5 empty] | In Compliance
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared and Returned | No | No | Faded | No | No | None | 30.1656 | -81.7142 | [5 empty] | In Compliance
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared | Yes | No | Faded | No | No | None | 30.1656 | -81.7141 | [5 empty] | In Compliance
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared and Returned | Yes | No | No | No | No | None | 30.1657 | -81.7131 | [5 empty] | In Compliance
8475 | 71130000 | 224 | 2 | Clay | Present | One Way Directional | None | Flared | No | No | No | No | No | None | 30.1657 | -81.713 | [5 empty] | In Compliance
8736 | 72010000 | 10 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | Yes | No | No | Standard Pedestrian Signal | 30.333 | -81.698 | [5 empty] | In Compliance
8995 | 72120000 | 228 | 2 | Duval | Present | One Way Directional | None | Flared and Returned | No | No | No | No | No | None | 30.302 | -81.7614 | [5 empty] | In Compliance
9223 | 32010000 | 100 | 2 | Hamilton | Present | One Way Directional | Other | None | No | No | Yes | No | No | None | 30.5147 | -82.9462 | 18.617 | 209831-4 | Potential FY 2029 |  | Candidate | 3R
9223 | 32010000 | 100 | 2 | Hamilton | Present | One Way Directional | Other | None | No | No | Yes | No | No | None | 30.5146 | -82.9462 | 18.617 | 209831-4 | Potential FY 2029 |  | Candidate | 3R
9275 | 72014000 | 109 | 2 | Duval | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.2702 | -81.611 | [5 empty] | In Compliance
9275 | 72014000 | 109 | 2 | Duval | Present | Parallel | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.2699 | -81.611 | [5 empty] | In Compliance
9275 | 72014000 | 109 | 2 | Duval | Present | Parallel | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.2699 | -81.6109 | [5 empty] | In Compliance
9275 | 72014000 | 109 | 2 | Duval | Present | Diagonal | Missing or Damaged | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.27 | -81.6108 | 2.253 | 446153-1 | 2029 | 2029-12-05 | Programmed | Add Lanes & Reconstruct
9500 | 72014000 | 109 | 2 | Duval | Present | Parallel | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.2839 | -81.6029 | [5 empty] | In Compliance
9500 | 72014000 | 109 | 2 | Duval | Present | Diagonal | None | Flared and Returned | No | No | Yes | No | No | Standard Pedestrian Signal | 30.2775 | -81.6028 | [5 empty] | In Compliance
9500 | 72014000 | 109 | 2 | Duval | Obscured/Needs Field Review | Diagonal | Other | Other | No | No | Yes | No | No | Standard Pedestrian Signal | 30.2841 | -81.6029 | 3.404 | 209683-1 | 1905-07-12 | 2019-11-13 | Completed | Constructed under a Traffic signal update in the corridor
9636 | 72050000 | 10 | 2 | Duval | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3305 | -81.6553 | [5 empty] | In Compliance
9636 | 72050000 | 1 | 2 | Duval | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | Standard Pedestrian Signal | 30.3304 | -81.6554 | [5 empty] | In Compliance
9802 | 32010000 | 129 | 2 | Hamilton | Present | One Way Directional | Other | Returned Curb | No | No | Yes | No | No | None | 30.5188 | -82.9526 | 19.268 | 209831-4 | Potential FY 2029 |  | Candidate | 3R
9802 | 32010000 | 129 | 2 | Hamilton | Present | One Way Directional | Other | Returned Curb | No | No | Yes | No | No | None | 30.5187 | -82.9524 | 19.268 | 209831-4 | Potential FY 2029 |  | Candidate | 3R
14389 | 76050000 | 20 | 2 | Putnam | Present | One Way Directional | None | Flared | Yes | No | Yes | No | No | None | 29.6442 | -81.6385 | [5 empty] | In Compliance
14389 | 76050000 | 20 | 2 | Putnam | Present | Diagonal | None | Flared | Yes | No | Yes | No | No | None | 29.6441 | -81.6384 | [5 empty] | In Compliance
14389 | 76050000 | 20 | 2 | Putnam | Present | One Way Directional | None | Flared | No | No | Yes | No | No | None | 29.644 | -81.6385 | [5 empty] | In Compliance
14490 | 72291000 | 111 | 2 | Duval | Present | One Way Directional | Other | Flared and Returned | No | No | Yes | No | No | None | 30.3209 | -81.7307 | 3.087 | None | None | None | None | Will be be addressed in the next set of Resurfacing Project